## ALL
ANNEX B
103rd CONTRACTING OFFICE - 3ID, PA- PROJECT MONITORING REPORT - 01 January - 30 June 2023
Code (PAP) | Procurement Project | PMO/ End-User | Is this an Early Procurement Activity? | Mode of Procurement | Schedule for Each Procurement Activity | [12 empty] | Source of Funds | ABC (PhP) |  |  | Contract Cost (PhP) |  |  | List of Invited Observers | Date of Receipt of Invitation | [5 empty] | Remarks (Explaining changes from the APP)
[5 empty] | Pre-Proc Conference | Ads/Post of IAEB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Date of BAC Resolution Recommending Award | Notice of Award | Contract Signing | Notice to Proceed | Delivery/ Completion | Inspection & Acceptance |  | Total | MOOE | CO | Total | MOOE | CO |  | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Delivery/ Completion/ Acceptance (If applicable)
COMPLETED PROCUREMENT ACTIVITIES
5-02-03-010-02 | Office Supplies | H3ID,PA |  | Negotiated 53.9 | [8 empty] | 2023-03-14 | 2023-03-28 | 2023-03-28 | 2023-04-04 | 2023-04-04 | GAA 2023 | 316737 | 316737 |  | 315634 | 315634
5-02-03-990-00 | Other Supplies & | H3ID,PA |  | Negotiated 53.9 | [8 empty] | 2023-03-14 | 2023-03-28 | 2023-03-28 | 2023-04-04 | 2023-04-04 | GAA 2023 | 132840 | 132840 |  | 132546 | 132546
5-02-03-010-01 | Office ICT | H3ID,PA |  | Negotiated 53.9 | [8 empty] | 2023-03-14 | 2023-03-28 | 2023-03-28 | 2023-04-04 | 2023-04-04 | GAA 2023 | 18400 | 18400 |  | 18392 | 18392
5-02-03-010-02 | Office Supplies | CPSH, 3ID, PA |  | Negotiated 53.9 | [8 empty] | 2023-03-10 | 2023-03-28 | 2023-03-28 | 2023-04-04 | 2023-04-04 | GAA 2023 | 54296 | 54296 |  | 54070 | 54070
5-02-13-050-03 | Other Supplies & | 103CO, AFPPS |  | Negotiated 53.9 | [8 empty] | 2023-03-10 | 2023-04-04 | 2023-04-04 | 2023-04-13 | 2023-04-13 | GAA 2023 | 18750 | 18750 |  | 18735 | 18735
5-02-03-010-02 | Office Supplies | 103CO, AFPPS |  | Shopping 52.1b | [8 empty] | 2023-03-10 | 2023-04-04 | 2023-04-04 | 2023-04-13 | 2023-04-13 | GAA 2023 | 16250 | 16250 |  | 16212 | 16212
5-02-05-020-01 | Mobile Exp | 103CO, AFPPS |  | Negotiated 53.9 | [8 empty] | 2023-03-10 | 2023-04-04 | 2023-04-04 | 2023-04-13 | 2023-04-13 | GAA 2023 | 5000 | 5000 |  | 5000 | 5000
5-02-03-010-02 | Office Supplies | 3CMOBN, 3ID, PA |  | Negotiated 53.9 | [8 empty] | 2023-03-14 | 2023-03-30 | 2023-03-30 | 2023-04-04 | 2023-04-04 | GAA 2023 | 6600 | 6600 |  | 6580 | 6580
5-02-02-010-00 | TRNG EXP | 31DRC, 3ID, PA |  | Negotiated 53.9 | [8 empty] | 2023-03-27 | 2023-04-12 | 2023-04-12 | 2023-04-20 | 2023-04-20 | GAA 2023 | 8500 | 8500 |  | 8489 | 8489
5-02-02-010-00 | TRNG EXP | 32DRC, 3ID, PA |  | Negotiated 53.9 | [8 empty] | 2023-03-27 | 2023-04-17 | 2023-04-17 | 2023-04-26 | 2023-04-26 | GAA 2023 | 6992 | 6992 |  | 6984 | 6984
Total Alloted Budget of Procurement Activities | [18 empty] | 584365
Total Contract Price of Procurement Activities Conducted | [18 empty] | 582642
Total Savings (Total Alloted Budget -Total Contract Price) | [18 empty] | 1723
ON-GOING PROCUREMENT ACTIVITIES
5-02-03-990-00 | Other Supplies | 3IMB, IMCOM (P), PA |  | Negotiated 53.9 | [8 empty] | 2023-03-06 | 2023-04-04 | 2023-04-04 | 2023-04-13 | 2023-04-13 | GAA 2023 | 22500 | 22500 |  | 22355 | 22355
5-02-02-010-02 | TRNG EXP | 3IMB, IMCOM (P), PA |  | Negotiated 53.9 | [8 empty] | 2023-03-06 | 2023-04-17 | 2023-04-17 | 2023-04-26 | 2023-04-26 | GAA 2023 | 10000 | 10000 |  | 9940 | 9940
5-02-03-080-00 | Medical & Laboratory Supplies | CPSH, 3ID, PA |  | Negotiated 53.9 | [8 empty] | 2023-03-07 | 2023-03-30 | 2023-03-30 | 2023-04-04 | 2023-04-04 | GAA 2023 | 297475 | 297475 |  | 296295 | 296295
5-02-03-070-00 | Drugs & Med | CPSH, 3ID, PA |  | Negotiated 53.9 | [8 empty] | 2023-03-07 | 2023-05-17 | 2023-05-17 | 2023-05-22 | 2023-05-22 | GAA 2023 | 192000 | 192000 |  | 191558.5 | 191558.5
5-02-030-010-00 | RM of Bldg | CPSH, 3ID, PA |  | Negotiated 53.9 | [8 empty] | 2023-03-07 | 2023-04-25 | 2023-04-25 | 2023-05-05 | 2023-05-05 | GAA 2023 | 8850 | 8850 |  | 8835 | 8835
5-02-13-040-01 | RM of Bldg | SSBN, 3ID, PA |  | Negotiated 53.9 | [8 empty] | 2023-03-07 | 2023-04-17 | 2023-04-17 | 2023-04-26 | 2023-04-26 | GAA 2023 | 40000 | 40000 |  | 39900 | 39900
5-02-13-050-03 | Other Supplies | SSBN, 3ID, PA |  | Negotiated 53.9 | [8 empty] | 2023-03-07 | 2023-04-04 | 2023-04-04 | 2023-04-13 | 2023-04-13 | GAA 2023 | 11852 | 11852 |  | 11380 | 11380
5-02-13-040-01 | RM of Bldg | 3MIBn, 3ID, PA |  | Negotiated 53.9 | [8 empty] | 2023-03-10 | 2023-04-12 | 2023-04-12 | 2023-04-20 | 2023-04-20 | GAA 2023 | 71000 | 71000 |  | 70530 | 70530
5-02-03-010-02 | Office Supplies | 301BDE, 3ID, PA |  | Negotiated 53.9 | [8 empty] | 2023-03-13 | 2023-03-30 | 2023-03-30 | 2023-04-04 | 2023-04-04 | GAA 2023 | 103146 | 103146 |  | 102731 | 102731
5-02-02-010-02 | TRNG EXP | 301BDE, 3ID, PA |  | Negotiated 53.9 | [8 empty] | 2023-03-13 | 2023-04-04 | 2023-04-04 | 2023-04-13 | 2023-04-13 | GAA 2023 | 40000 | 40000 |  | 39850 | 39850
5-02-13-050-03 | RM of ICT | 301BDE, 3ID, PA |  | Negotiated 53.9 | [8 empty] | 2023-03-13 | 2023-04-04 | 2023-04-04 | 2023-04-13 | 2023-04-13 | GAA 2023 | 21750 | 21750 |  | 21700 | 21700
5-02-02-010-00 | TRNG EXP | 82IB, 3ID, PA |  | Negotiated 53.9 | [8 empty] | 2023-03-13 | 2023-03-30 | 2023-03-30 | 2023-04-04 | 2023-04-04 | GAA 2023 | 50000 | 50000 |  | 49814 | 49814
5-02-02-010-00 | TRNG EXP | 3MIBn, 3ID, PA |  | Negotiated 53.9 | [8 empty] | 2023-03-13 | 2023-04-25 | 2023-04-25 | 2023-05-05 | 2023-05-05 | GAA 2023 | 7000 | 7000 |  | 6925 | 6925
5-02-02-010-02 | Office Trng | 3CMOBN, 3ID, PA |  | Negotiated 53.9 | [8 empty] | 2023-03-14 | 2023-04-25 | 2023-04-25 | 2023-05-05 | 2023-05-05 | GAA 2023 | 40000 | 40000 |  | 39840 | 39840
5-02-13-990-00 | RM of PAS | 3CMOBN, 3ID, PA |  | Negotiated 53.9 | [8 empty] | 2023-03-14 | 2023-04-17 | 2023-04-17 | 2023-04-26 | 2023-04-26 | GAA 2023 | 30000 | 30000 |  | 29900 | 29900
5-02-02-010-02 | Office Trng | 94IB, 3ID, PA |  | Negotiated 53.9 | [8 empty] | 2023-03-14 |  |  |  |  | GAA 2023 | 33500 | 33500 |  | 33370 | 33370 | [8 empty] | Findings @ Accounting, Account Code not Alligned based APB
5-02-02-010-02 | Office Trng | 79IB, 3ID, PA |  | Negotiated 53.9 | [8 empty] | 2023-03-20 | 2023-04-12 | 2023-04-12 | 2023-04-20 | 2023-04-20 | GAA 2023 | 18750 | 18750 |  | 18714 | 18714
5-02-02-010-00 | TRNG EXP | 6RCDG, ARESCOM, PA |  | Negotiated 53.9 | [8 empty] | 2023-03-20 | 2023-04-17 | 2023-04-17 | 2023-04-20 | 2023-04-20 | GAA 2023 | 97997 | 97997 |  | 97183 | 97183
5-02-03-990-00 | RM of OffIce Eqpmt | 61IB, 3ID, PA |  | Negotiated 53.9 | [8 empty] | 2023-03-20 | 2023-04-27 | 2023-04-27 | 2023-05-05 | 2023-05-05 | GAA 2023 | 50800 | 50800 |  | 50215 | 50215
5-02-02-010-02 | Office Trng | 61IB, 3ID, PA |  | Negotiated 53.9 | [8 empty] | 2023-03-20 | 2023-04-12 | 2023-04-12 | 2023-04-30 | 2023-04-30 | GAA 2023 | 12000 | 12000 |  | 11950 | 11950
5-02-02-010-02 | Office Trng | 15IB, 3ID, PA |  | Negotiated 53.9 | [8 empty] | 2023-03-22 | 2023-04-12 | 2023-04-12 | 2023-04-20 | 2023-04-20 | GAA 2023 | 9988 | 9988 |  | 9974 | 9974
5-02-03-010-01 | Office ICT | 3DCAU, 3ID, PA |  | Negotiated 53.9 | [8 empty] | 2023-03-22 | 2023-04-12 | 2023-04-12 | 2023-04-20 | 2023-04-20 | GAA 2023 | 12160 | 12160 |  | 12120 | 12120
5-02-02-010-01 | ICT Trng | 3DCAU, 3ID, PA |  | Negotiated 53.9 | [8 empty] | 2023-03-22 | 2023-04-17 | 2023-04-17 | 2023-04-26 | 2023-04-26 | GAA 2023 | 20000 | 20000 |  | 19975 | 19975
5-02-03-010-02 | Office Supplies | 3DCAU, 3ID, PA |  | Negotiated 53.9 | [8 empty] | 2023-03-22 | 2023-04-17 | 2023-04-17 | 2023-04-26 | 2023-04-26 | GAA 2023 | 32838 | 32838 |  | 32730 | 32730
5-02-13-040-01 | RM of Bldg | 79IB, 3ID, PA |  | Negotiated 53.9 | [8 empty] | 2023-03-22 | 2023-05-15 | 2023-05-15 | 2023-05-22 | 2023-05-22 | GAA 2023 | 49500 | 49500 |  | 49221 | 49221
5-02-99-030-00 | Representation Exp | 79IB, 3ID, PA |  | Negotiated 53.9 | [8 empty] | 2023-03-22 | 2023-05-05 | 2023-05-05 | 2023-05-15 | 2023-05-15 | GAA 2023 | 6000 | 6000 |  | 5990 | 5990
5-02-13-040-01 | RM of Bldg | 302BDE, 3ID, PA |  | Negotiated 53.9 | [8 empty] | 2023-03-27 |  |  |  |  | GAA 2023 | 210000 | 210000 |  | 209199 | 209199 | [8 empty] | Findings @ Accounting, Account Code not Alligned based APB
5-02-02-010-02 | Office Trng | 302BDE, 3ID, PA |  | Negotiated 53.9 | [8 empty] | 2023-03-27 | 2023-05-05 | 2023-05-05 | 2023-05-15 | 2023-05-15 | GAA 2023 | 112000 | 112000 |  | 111625 | 111625
5-02-03-010-02 | Office Supplies | 302BDE, 3ID, PA |  | Negotiated 53.9 | [8 empty] | 2023-03-27 | 2023-04-27 | 2023-04-27 | 2023-05-05 | 2023-05-05 | GAA 2023 | 16500 | 16500 |  | 16311 | 16311
5-02-03-070-00 | Drugs & Med | 302BDE, 3ID, PA |  | Negotiated 53.9 | [8 empty] | 2023-03-27 |  |  |  |  | GAA 2023 | 10000 | 10000 |  | 9990 | 9990 | [8 empty] | Findings @ Accounting, Account Code not Alligned based APB
5-02-03-010-02 | Office Supplies | 3FAB, AAR, PA |  | Negotiated 53.9 | [8 empty] | 2023-03-27 | 2023-04-17 | 2023-04-17 | 2023-04-26 | 2023-04-26 | GAA 2023 | 36310 | 36310 |  | 36195 | 36195
5-02-03-010-01 | Office ICT | 3FAB, AAR, PA |  | Negotiated 53.9 | [8 empty] | 2023-03-27 | 2023-04-17 | 2023-04-17 | 2023-04-26 | 2023-04-26 | GAA 2023 | 25200 | 25200 |  | 25200 | 25200
5-02-03-010-02 | Office Supplies | 3SIGBN, ASR, PA |  | Negotiated 53.9 | [8 empty] | 2023-03-27 | 2023-04-17 | 2023-04-17 | 2023-04-26 | 2023-04-26 | GAA 2023 | 32500 | 32500 |  | 32480 | 32480
5-02-13-050-03 | RM of ICT | 3IMB, IMCOM (P), PA |  | Negotiated 53.9 | [8 empty] | 2023-03-27 |  |  |  |  | GAA 2023 | 14950 | 14950 |  | 14940 | 14940 | [8 empty] | Findings @ Accounting, Account Code not Alligned based APB
5-02-13-040-01 | RM of Bldg | 3SIGBN, ASR, PA |  | Negotiated 53.9 | [8 empty] | 2023-04-03 | 2023-05-15 | 2023-05-15 | 2023-05-19 | 2023-05-19 | GAA 2023 | 72500 | 72500 |  | 71730 | 71730
5-02-02-010-02 | Office Trng | 3SIGBN, ASR, PA |  | Negotiated 53.9 | [8 empty] | 2023-04-03 | 2023-05-15 | 2023-05-15 | 2023-05-19 | 2023-05-19 | GAA 2023 | 35000 | 35000 |  | 34793 | 34793
5-02-13-050-02 | RM Office Eqpmt | 3SIGBN, ASR, PA |  | Negotiated 53.9 | [8 empty] | 2023-04-03 | 2023-05-15 | 2023-05-15 | 2023-05-19 | 2023-05-19 | GAA 2023 | 5000 | 5000 |  | 4990 | 4990
5-02-13-050-03 | RM of ICT | 3SIGBN, ASR, PA |  | Negotiated 53.9 | [8 empty] | 2023-04-03 | 2023-04-27 | 2023-04-27 | 2023-05-05 | 2023-05-05 | GAA 2023 | 10000 | 10000 |  | 9995 | 9995
5-02-13-040-01 | RM of Bldg | 303BDE, 3ID, PA |  | Negotiated 53.9 | [8 empty] | 2023-04-11 | 2023-05-16 | 2023-05-16 | 2023-05-30 | 2023-05-30 | GAA 2023 | 60000 | 60000 |  | 59616 | 59616
5-02-03-010-02 | Office Supplies | 303BDE, 3ID, PA |  | Negotiated 53.9 | [8 empty] | 2023-04-11 | 2023-04-27 | 2023-04-27 | 2023-05-05 | 2023-05-05 | GAA 2023 | 59905 | 59905 |  | 59707 | 59707
5-02-02-010-02 | TRNG OFFICE | 303BDE, 3ID, PA |  | Negotiated 53.9 | [8 empty] | 2023-04-11 | 2023-04-27 | 2023-04-27 | 2023-05-05 | 2023-05-05 | GAA 2023 | 49000 | 49000 |  | 48817 | 48817
5-02-03-990-00 | Other Supplies & | 303BDE, 3ID, PA |  | Negotiated 53.9 | [8 empty] | 2023-04-11 | 2023-04-27 | 2023-04-27 | 2023-05-05 | 2023-05-05 | GAA 2023 | 22500 | 22500 |  | 22440 | 22440
5-02-13-040-01 | RM of Bldg | 6FSSU, ASCOM, PA |  | Negotiated 53.9 | [8 empty] | 2023-04-11 | 2023-05-15 | 2023-05-15 | 2023-05-22 | 2023-05-22 | GAA 2023 | 50000 | 50000 |  | 49976 | 49976
5-02-03-010-02 | Office Supplies | 6FSSU, ASCOM, PA |  | Shopping 52.1b | [8 empty] | 2023-04-11 | 2023-05-15 | 2023-05-15 | 2023-05-22 | 2023-05-22 | GAA 2023 | 47000 | 47000 |  | 46982 | 46982
5-02-03-990-00 | Other Supplies & | 6FSSU, ASCOM, PA |  | Negotiated 53.9 | [8 empty] | 2023-04-11 | 2023-05-15 | 2023-05-15 | 2023-05-22 | 2023-05-22 | GAA 2023 | 35995 | 35995 |  | 35950 | 35950
5-02-02-010-02 | Office Trng | 6FSSU, ASCOM, PA |  | Negotiated 53.9 | [8 empty] | 2023-04-11 | 2023-05-15 | 2023-05-15 | 2023-05-22 | 2023-05-22 | GAA 2023 | 20000 | 20000 |  | 19910 | 19910
5-02-03-010-02 | Office Supplies | 6FSSU, ASCOM, PA |  | Shopping 52.1b | [8 empty] | 2023-04-11 | 2023-05-15 | 2023-05-15 | 2023-05-22 | 2023-05-22 | GAA 2023 | 10750 | 10750 |  | 10704 | 10704
5-02-02-010-02 | Office Trng | 12IB, 3ID, PA |  | Negotiated 53.9 | [8 empty] | 2023-04-11 | 2023-05-05 | 2023-05-05 | 2023-05-15 | 2023-05-15 | GAA 2023 | 29994 | 29994 |  | 29916 | 29916
5-02-02-010-02 | TRNG OFFICE | 33DRC, 3ID, PA |  | Negotiated 53.9 | [8 empty] | 2023-04-11 | 2023-05-15 | 2023-05-15 | 2023-05-22 | 2023-05-22 | GAA 2023 | 14997 | 14997 |  | 14965 | 14965
5-02-03-990-00 | Other Supplies & | 3FAB, AAR, PA |  | Negotiated 53.9 | [8 empty] | 2023-04-17 | 2023-05-15 | 2023-05-15 | 2023-05-22 | 2023-05-22 | GAA 2023 | 30988 | 30988 |  | 30918 | 30918
5-02-03-010-02 | Office Supplies | 3HHSC (P), 3ID, PA |  | Negotiated 53.9 | [8 empty] | 2023-04-17 | 2023-05-17 | 2023-05-17 | 2023-05-22 | 2023-05-22 | GAA 2023 | 19992 | 19992 |  | 19962 | 19962
5-02-03-990-00 | Other Supplies & | 3HHSC (P), 3ID, PA |  | Negotiated 53.9 | [8 empty] | 2023-04-17 | 2023-05-17 | 2023-05-17 | 2023-05-22 | 2023-05-22 | GAA 2023 | 3900 | 3900 |  | 3900 | 3900
5-02-03-990-00 | Other Supplies & | 6FSSU, ASCOM, PA |  | Negotiated 53.9 | [8 empty] | 2023-04-20 | 2023-05-17 | 2023-05-17 | 2023-05-24 | 2023-05-24 | GAA 2023 | 4987.5 | 4987.5 |  | 4980 | 4980
5-02-02-010-02 | TRAINING EXP | 3FAB, AAR, PA |  | Negotiated 53.9 | [8 empty] | 2023-04-25 | 2023-05-22 | 2023-05-22 | 2023-05-30 | 2023-05-30 | GAA 2023 | 40000 | 40000 |  | 39863.5 | 39863.5
5-02-03-010-02 | Office Supplies | 3FAB, AAR, PA |  | Negotiated 53.9 | [8 empty] | 2023-04-25 | 2023-05-17 | 2023-05-17 | 2023-05-24 | 2023-05-24 | GAA 2023 | 26230 | 26230 |  | 26190 | 26190
5-02-03-010-01 | Office ICT | 3FAB, AAR, PA |  | Negotiated 53.9 | [8 empty] | 2023-04-25 |  |  |  |  | GAA 2023 | 20520 | 20520 |  | 20520 | 20520 | [8 empty] | Findings @ Accounting, Account Code not Alligned based APB
5-02-03-990-00 | Other Supplies & | 3FAB, AAR, PA |  | Negotiated 53.9 | [8 empty] | 2023-04-25 | 2023-05-17 | 2023-05-17 | 2023-05-24 | 2023-05-24 | GAA 2023 | 15745 | 15745 |  | 15735 | 15735
5-02-13-990-99 | Other Property Plant & Eqpmt | 32DRC, 3ID, PA |  | Negotiated 53.9 | [8 empty] | 2023-04-25 |  |  |  |  | GAA 2023 | 9899 | 9899 |  | 9880 | 9880 | [8 empty] | Findings @ Accounting, Account Code not Alligned based APB
5-02-02-010-02 | TRNG OFFICE | 32DRC, 3ID, PA |  | Negotiated 53.9 | [8 empty] | 2023-04-25 |  |  |  |  | GAA 2023 | 6997 | 6997 |  | 6983 | 6983 | [8 empty] | Findings @ Accounting, Account Code not Alligned based APB
5-02-13-040-01 | RM of Bldg | 32DRC, 3ID, PA |  | Negotiated 53.9 | [8 empty] | 2023-04-25 |  |  |  |  | GAA 2023 | 4936 | 4936 |  | 4920 | 4920 | [8 empty] | Findings @ Accounting, Account Code not Alligned based APB
5-02-03-010-02 | Office Supplies | H3ID, PA |  | Negotiated 53.9 | [8 empty] | 2023-04-28 | 2023-05-17 | 2023-05-17 | 2023-05-24 | 2023-05-24 | GAA 2023 | 801668 | 801668 |  | 800869 | 800869
5-02-03-010-01 | Office ICT | H3ID, PA |  | Negotiated 53.9 | [8 empty] | 2023-04-28 |  |  |  |  | GAA 2023 | 18400 | 18400 |  | 18392 | 18392
5-02-03-010-02 | Office Supplies | 3DTS, 3ID, PA |  | Negotiated 53.9 | [8 empty] | 2023-05-08 |  |  |  |  | GAA 2023 | 55485 | 55485 |  | 55247 | 55247
5-02-03-010-02 | Office Supplies | 3DTS, 3ID, PA |  | Negotiated 53.9 | [8 empty] | 2023-05-08 | 2023-05-15 | 2023-05-15 | 2023-05-22 | 2023-05-22 | GAA 2023 | 55485 | 55485 |  | 55247 | 55247
5-02-13-050-03 | RM of ICT | 3DTS, 3ID, PA |  | Negotiated 53.9 | [8 empty] | 2023-05-08 |  |  |  |  | GAA 2023 | 39985 | 39985 |  | 39920 | 39920
5-02-13-050-03 | RM of ICT | 3DTS, 3ID, PA |  | Negotiated 53.9 | [8 empty] | 2023-05-08 |  |  |  |  | GAA 2023 | 39985 | 39985 |  | 39920 | 39920
5-02-03-010-02 | Office Supplies | 6FAU, ASPA |  | Shopping 52.1b | [8 empty] | 2023-05-08 | 2023-05-30 | 2023-05-30 | 2023-06-05 | 2023-06-05 | GAA 2023 | 17495 | 17495 |  | 17485 | 17485
5-02-03-010-02 | Office Supplies | 3HHSC (P), 3ID, PA |  | Negotiated 53.9 | [8 empty] | 2023-05-08 |  |  |  |  | GAA 2023 | 5997 | 5997 |  | 5985 | 5985
5-02-02-010-02 | TRNG OFFICE | 6FSSU, ASCOM, PA |  | Negotiated 53.9 | [8 empty] | 2023-05-11 | 2023-06-05 | 2023-06-05 |  |  | GAA 2023 | 19975 | 19975 |  | 19814 | 19814
5-02-03-990-00 | Other Supplies & | 6FSSU, ASCOM, PA |  | Negotiated 53.9 | [8 empty] | 2023-05-11 |  |  |  |  | GAA 2023 | 22987.5 | 22987.5 |  | 22940 | 22940
5-02-13-040-01 | RM of Bldg | 31DRC, 3ID, PA |  | Negotiated 53.9 | [8 empty] | 2023-05-11 |  |  |  |  | GAA 2023 | 15000 | 15000 |  | 14979 | 14979
5-02-99-030-00 | Representation Exp | 31DRC, 3ID, PA |  | Negotiated 53.9 | [8 empty] | 2023-05-11 |  |  |  |  | GAA 2023 | 6000 | 6000 |  | 5971 | 5971
5-02-02-010-02 | TRNG OFFICE | 31DRC, 3ID, PA |  | Negotiated 53.9 | [8 empty] | 2023-05-11 |  |  |  |  | GAA 2023 | 5000 | 5000 |  | 4980 | 4980
5-02-03-010-01 | Office ICT | 303BDE, 3ID, PA |  | Negotiated 53.9 | [8 empty] | 2023-05-11 |  |  |  |  | GAA 2023 | 26070 | 26070 |  | 26040 | 26040
5-02-03-010-02 | Office Supplies | 301BDE, 3ID, PA |  | Negotiated 53.9 | [8 empty] | 2023-05-15 |  |  |  |  | GAA 2023 | 103146 | 103146 |  | 102731 | 102731
5-02-03-010-02 | Office Supplies | 3SIGBN, ASR, PA |  | Negotiated 53.9 | [8 empty] | 2023-05-15 |  |  |  |  | GAA 2023 | 32500 | 32500 |  | 32480 | 32480
5-02-02-010-02&01 | TRNG OFFICE/OFFICE ICT | 3SIGBN, ASR, PA |  | Negotiated 53.9 | [8 empty] | 2023-05-15 |  |  |  |  | GAA 2023 | 35000 | 35000 |  | 34883 | 34883
5-02-03-010-02 | Office Supplies | 6FSSU, ASCOM, PA |  | Shopping 52.1b | [8 empty] | 2023-05-15 | 2023-06-05 | 2023-06-05 |  |  | GAA 2023 | 27748 | 27748 |  | 27623 | 27623
5-02-03-990-00 | Other Supplies & | 303BDE, 3ID, PA |  | Negotiated 53.9 | [8 empty] | 2023-05-15 |  |  |  |  | GAA 2023 | 22500 | 22500 |  | 22494 | 22494
5-02-03-010-02 | Office Supplies | 303BDE, 3ID, PA |  | Negotiated 53.9 | [8 empty] | 2023-05-15 |  |  |  |  | GAA 2023 | 46520 | 46520 |  | 46458 | 46458
5-02-02-010-02 | TRNG OFFICE | 12IB, 3ID, PA |  | Negotiated 53.9 | [8 empty] | 2023-05-15 |  |  |  |  | GAA 2023 | 37500 | 37500 |  | 37352 | 37352
5-02-13-050-07 | RM of Communication Eqpmt | 12IB, 3ID, PA |  | Negotiated 53.9 | [8 empty] | 2023-05-15 |  |  |  |  | GAA 2023 | 9988 | 9988 |  | 9980 | 9980
5-02-13-040-01 | RM of Bldg | 82IB, 3ID, PA |  | Negotiated 53.9 | [8 empty] | 2023-05-19 |  |  |  |  | GAA 2023 | 50800 | 50800 |  | 50528 | 50528
5-02-02-010-02&01 | TRNG OFFICE/OFFICE ICT | 61IB, 3ID, PA |  | Negotiated 53.9 | [8 empty] | 2023-05-19 |  |  |  |  | GAA 2023 | 39000 | 39000 |  | 38690 | 38690
5-02-13-050-03 | RM of ICT | 3CMOBN, 3ID, PA |  | Negotiated 53.9 | [8 empty] | 2023-05-29 |  |  |  |  | GAA 2023 | 54000 | 54000 |  | 53850 | 53850
5-02-13-050-07 | RM of Communication Eqpmt | 3CMOBN, 3ID, PA |  | Negotiated 53.9 | [8 empty] | 2023-05-29 |  |  |  |  | GAA 2023 | 30000 | 30000 |  | 29900 | 29900
5-02-03-990-00 | Other Supplies & | 3CMOBN, 3ID, PA |  | Negotiated 53.9 | [8 empty] | 2023-05-29 |  |  |  |  | GAA 2023 | 6600 | 6600 |  | 6580 | 6580
5-02-03-990-00 | Other Supplies & | 103CO, AFPPS |  | Negotiated 53.9 | [8 empty] | 2023-06-05 |  |  |  |  | GAA 2023 | 18750 | 18750 |  | 18735 | 18735
5-02-05-020-01 | Mobile Exp | 103CO, AFPPS |  | Negotiated 53.9 | [8 empty] | 2023-06-05 |  |  |  |  | GAA 2023 | 5000 | 5000 |  | 5000 | 5000
5-02-03-010-02 | Office Supplies | 103CO, AFPPS |  | Shopping 52.1b | [8 empty] | 2023-06-05 |  |  |  |  | GAA 2023 | 16250 | 16250 |  | 16212 | 16212
5-02-030-010-00 | Office Supplies | CPSH, 3ID, PA |  | Negotiated 53.9 | [8 empty] | 2023-06-05 |  |  |  |  | GAA 2023 | 54296 | 54296 |  | 54070 | 54070
Total Alloted Budget of Procurement Activities | [18 empty] | 4172532
Total Contract Price of Procurement Activities Conducted | [18 empty] | 4158633
Total Savings (Total Alloted Budget -Total Contract Price) | [18 empty] | 13899
| Prepared by: | [19 empty] | APPROVED:
Teofisto F Pagayon
TSg (FS) PA
First Sgt/Opn NCO
JONIEFER G DELA TORRE
Lt Colonel (CE) PA
Commanding Officer