## 7ID PMR-1ST SEM 23 (2)
ANNEX B
107H CONTRACTING OFFICE-7ID, PA-PROJECT MONITORING REPORT from 01 January to 30 June 2023
Code (PAP) | Procurement Project | PMO/ End-User | Is this an Early Procurement Activity? | Mode of Procurement | Actual Procurement Activity | [12 empty] | Source of Funds | ABC (PhP) |  |  | Contract Cost (PhP) |  |  | List of Invited Observers | Date of Receipt of Invitation | [5 empty] | Remarks (Explaining changes from the APP)
[5 empty] | Pre-Proc Conference | Ads/Post of IB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Date of BAC Resolution Recommending Award | Notice of Award | Contract Signing | Notice to Proceed | Delivery/ Completion | Inspection & Acceptance |  | Total | MOOE | CO | Total | MOOE | CO |  | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Delivery/ Completion/ Acceptance (If applicable)
COMPLETED PROCUREMENT ACTIVITIES
5-02-03-010-01 | ICT Office Supplies Expense | 7ID, PA | No | Negotiated 53.9 | [8 empty] | 2023-01-25 | 2023-01-25 | 2023-02-15 | 2023-02-23 | 2023-02-23 | GAA CY 2023 | 170290 | 170290 |  | 88829 | 88829 |  | 2
5-02-03-010-02 | Office Supplies Expenses | 7ID, PA | No | Negotiated 53.9 | [8 empty] | 2023-01-25 | 2023-01-25 | 2023-02-15 | 2023-02-23 | 2023-02-23 | GAA CY 2023 | 656182.25 | 656182.25 |  | 144251 | 144251 |  | 2
5-02-03-070-00 | Drugs and Medicines Expenses | 7ID, PA | No | Negotiated 53.9 | [8 empty] | 2023-01-25 | 2023-01-25 | 2023-02-15 | 2023-02-23 | 2023-02-23 | GAA CY 2023 | 429410.5 | 429410.5 |  | 361673.5 | 361673.5 |  | 2
5-02-03-080-00 | Medical, Dental and Laboratory Supplies Expenses | 7ID, PA | No | Negotiated 53.9 | [8 empty] | 2023-01-25 | 2023-01-25 | 2023-02-15 | 2023-02-23 | 2023-02-23 | GAA CY 2023 | 1349590.25 | 1349590.25 |  | 1108427 | 1108427 |  | 2
5-02-03-130-00 | Chemical and Filtering Supplies Expenses | 7ID, PA | No | Negotiated 53.9 | [8 empty] | 2023-01-25 | 2023-01-25 | 2023-02-15 | 2023-02-23 | 2023-02-23 | GAA CY 2023 | 6100 | 6100 |  | 2800 | 2800 |  | 2
5-02-03-210-01 | Semi-Expendable - Machinery | 7ID, PA | No | Negotiated 53.9 | [8 empty] | 2023-01-25 | 2023-01-25 | 2023-02-15 | 2023-02-23 | 2023-02-23 | GAA CY 2023 | 44050 | 44050 |  | 20475 | 20475 |  | 2
5-02-03-210-02 | Semi-Expendable Office Equipment | 7ID, PA | No | Negotiated 53.9 | [8 empty] | 2023-01-25 | 2023-01-25 | 2023-02-15 | 2023-02-23 | 2023-02-23 | GAA CY 2023 | 12000 | 12000 |  | 11800 | 11800 |  | 2
5-02-03-210-03 | Semi Expendable- ICT Equipment | 7ID, PA | No | Negotiated 53.9 | [8 empty] | 2023-01-25 | 2023-01-25 | 2023-02-15 | 2023-02-23 | 2023-02-23 | GAA CY 2023 | 1463874.5 | 1463874.5 |  | 1467350 | 1467350 |  | 2
5-02-03-210-07 | Semi-Expendable C4S Equipment | 7ID, PA | No | Negotiated 53.9 | [8 empty] | 2023-01-25 | 2023-01-25 | 2023-02-15 | 2023-02-23 | 2023-02-23 | GAA CY 2023 | 463700 | 463700 |  | 8450 | 8450 |  | 2
5-02-03-210-10 | Semi-Expandable Medical Equipment | 7ID, PA | No | Negotiated 53.9 | [8 empty] | 2023-01-25 | 2023-01-25 | 2023-02-15 | 2023-02-23 | 2023-02-23 | GAA CY 2023 | 126325 | 126325 |  | 80860 | 80860 |  | 2
5-02-03-210-99 | Semi-Expendable - Other Machinery and Equipment | 7ID, PA | No | Negotiated 53.9 | [8 empty] | 2023-01-25 | 2023-01-25 | 2023-02-15 | 2023-02-23 | 2023-02-23 | GAA CY 2023 | 267575 | 267575 |  | 318650 | 318650 |  | 2
5-02-05-020-01 | Mobile | 7ID, PA | No | Negotiated 53.9 | [8 empty] | 2023-01-25 | 2023-01-25 | 2023-02-15 | 2023-02-23 | 2023-02-23 | GAA CY 2023 | 486570 | 486570 |  | 520230 | 520230 |  | 2
5-02-13-040-01 | Buildings | 7ID, PA | No | Negotiated 53.9 | [8 empty] | 2023-01-25 | 2023-01-25 | 2023-02-15 | 2023-02-23 | 2023-02-23 | GAA CY 2023 | 3699394 | 3699394 |  | 2916480 | 2916480 |  | 2
5-02-13-050-03 | ICT Equipment | 7ID, PA | No | Negotiated 53.9 | [8 empty] | 2023-01-25 | 2023-01-25 | 2023-02-15 | 2023-02-23 | 2023-02-23 | GAA CY 2023 | 158825 | 158825 |  | 98750 | 98750 |  | 2
5-02-13-050-07 | Communication Equipment | 7ID, PA | No | Negotiated 53.9 | [8 empty] | 2023-01-25 | 2023-01-25 | 2023-02-15 | 2023-02-23 | 2023-02-23 | GAA CY 2023 | 45250 | 45250 |  | 38990 | 38990 |  | 2
5-02-13-210-01 | Repairs and Maintenance-Semi-Expendable | 7ID, PA | No | Negotiated 53.9 | [8 empty] | 2023-01-25 | 2023-01-25 | 2023-02-15 | 2023-02-23 | 2023-02-23 | GAA CY 2023 | 115100 | 115100 |  | 22300 | 22300 |  | 2
5-02-13-210-02 | R&M Semi-Expandable Office Equipment | 7ID, PA | No | Negotiated 53.9 | [8 empty] | 2023-01-25 | 2023-01-25 | 2023-02-15 | 2023-02-23 | 2023-02-23 | GAA CY 2023 | 45000 | 45000 |  | 89333 | 89333 |  | 2
5-02-13-210-03 | R&M-Semi-Expendable ICT Equipment | 7ID, PA | No | Negotiated 53.9 | [8 empty] | 2023-01-25 | 2023-01-25 | 2023-02-15 | 2023-02-23 | 2023-02-23 | GAA CY 2023 | 160425 | 160425 |  | 154000 | 154000 |  | 2
5-02-13-210-07 | Repairs and Maintenance Semi-Expendable - Communication Equipment | 7ID, PA | No | Negotiated 53.9 | [8 empty] | 2023-01-25 | 2023-01-25 | 2023-02-15 | 2023-02-23 | 2023-02-23 | GAA CY 2023 | 69200 | 69200 |  | 68900 | 68900 |  | 2
5-02-13-220-01 | Rpr & Maint Semi-Expendable Furniture ans Fixtures | 7ID, PA | No | Negotiated 53.9 | [8 empty] | 2023-01-25 | 2023-01-25 | 2023-02-15 | 2023-02-23 | 2023-02-23 | GAA CY 2023 | 465528 | 465528 |  | 930300 | 930300 |  | 2
5-02-99-070-01 | ICT Software Subscription | 7ID, PA | No | Negotiated 53.9 | [8 empty] | 2023-01-25 | 2023-01-25 | 2023-02-15 | 2023-02-23 | 2023-02-23 | GAA CY 2023 | 171175 | 171175 |  | 151814 | 151814 |  | 2
5-02-03-010-02 | Office Supplies Expenses | 7ID, PA | No | Negotiated 53.9 | [8 empty] | 2023-05-05 | 2023-05-05 | 2023-06-05 | 2023-06-12 | 2023-06-12 | GAA CY 2023 | 691320.865 | 691320.865 |  | 596200 | 596200 |  | 2
5-02-03-080-00 | Medical, Dental and Laboratory Supplies Expenses | 7ID, PA | No | Negotiated 53.9 | [8 empty] | 2023-05-05 | 2023-05-05 | 2023-06-05 | 2023-06-12 | 2023-06-12 | GAA CY 2023 | 3773969.24 | 3773969.24 |  | 702715 | 702715 |  | 2
5-02-03-210-02 | Semi-Expendable Office Equipment | 7ID, PA | No | Negotiated 53.9 | [8 empty] | 2023-05-05 | 2023-05-05 | 2023-06-05 | 2023-06-12 | 2023-06-12 | GAA CY 2023 | 201850 | 201850 |  | 245000 | 245000 |  | 2
5-02-03-210-03 | Semi Expendable- ICT Equipment | 7ID, PA | No | Negotiated 53.9 | [8 empty] | 2023-05-05 | 2023-05-05 | 2023-06-05 | 2023-06-12 | 2023-06-12 | GAA CY 2023 | 1856762.5 | 1856762.5 |  | 149040 | 149040 |  | 2
5-02-03-210-99 | Semi-Expendable - Other Machinery and Equipment | 7ID, PA | No | Negotiated 53.9 | [8 empty] | 2023-05-05 | 2023-05-05 | 2023-06-05 | 2023-06-12 | 2023-06-12 | GAA CY 2023 | 218825.53 | 218825.53 |  | 43400 | 43400 |  | 2
5-02-03-220-01 | Semi-Expendable - Furniture and Fixtures | 7ID, PA | No | Negotiated 53.9 | [8 empty] | 2023-05-05 | 2023-05-05 | 2023-06-05 | 2023-06-12 | 2023-06-12 | GAA CY 2023 | 678176 | 678176 |  | 986830 | 986830 |  | 2
Total Alloted of Budget Procurement Activities | [17 empty] | 17826468.635
Total Contrct PriceOf Procurement Activites Conducted | [20 empty] | 11327847.5
Total Savings (Total Alloted Budget - Total Contract Price) | [17 empty] | 6498621.135
ONGOING PROCUREMENT ACTIVITIES
Total Alloted of Budget Ongoing Procurement Activities | [21 empty] | 0
|  | Prepared by: | [6 empty] | CERTIFIED CORRECT BY: | [11 empty] | NOTED BY:
|  | Mike Louie E Gupit | [6 empty] | ROBERT L VALENZUELA | [11 empty] | LEOTHER S LEVISTE
|  | Sgt (OS) PA | [6 empty] | MAJ (OS) PA | [11 empty] | LTC GSC (QMS) PA
|  | Organizational NCO | [6 empty] | Deputy, G4 | [11 empty] | AC OF S FOR LOGISTICS, G4