## PMR CY 2023
ANNEX A
PHILIPPINE ARMY BIDS AND AWARDS COMMITTEE 2 PROCUREMENT MONITORING REPORT AS OF JUNE 30, 2023
Code (PAP) | Procurement Project | Is this an Early Procurement Activity? | Mode of Procurement | Actual Procurement Activity | [12 empty] | Source of Funds | ABC (PhP) |  |  | Contract Cost (PhP) |  |  | List of Invited Observers | Date of Receipt of Invitation | [5 empty] | Remarks (Explaining changes from the APP)
|  |  |  | Pre-Proc Conference | Ads/Post of IB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Date of BAC Resolution Recommending Award | Notice of Award | Contract Signing | Notice to Proceed | Delivery/ Completion | Inspection & Acceptance |  | Total | MOOE | CO | Total | MOOE | CO |  | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Delivery/ Completion/ Acceptance (If applicable) |  | Remarks
COMPLETED PROCUREMENT ACTIVITIES
1 | Ctg, 105mm: HE | YES | Competitive Bidding | 2022-09-30 | 2022-10-04 | 2022-10-12 | 2022-10-25 | 2022-10-25 | 2022-10-25 | 10 Nov 22 | 2022-11-18 | 12 Jan 23 | 20 Feb 23 | 20 Feb 23 | NA | NA | GoP | 249990000 | 249990000 | NA | 244990200 | 244990200 | NA | COA PCCI ASPA | 2022-10-04 | 2022-10-04 | 2022-10-04 | 2022-10-04 | 07 Nov 22 | NA | NA | COMPLETED
2 | Ctg, 105mm: Smoke HC | YES | Competitive Bidding | 2022-09-30 | 2022-10-04 | 2022-10-12 | 2022-10-25 | 2022-10-25 | 2022-10-25 | 10 Nov 22 | 2022-11-18 | 12 Jan 23 | 20 Feb 23 | 20 Feb 23 | NA | NA | GoP | 249900000 | 249900000 | NA | 244902000 | 244902000 | NA | COA PCCI ASPA | 2022-10-04 | 2022-10-04 | 2022-10-04 | 2022-10-04 | 07 Nov 22 | NA | NA | COMPLETED
3 | Ctg, 60mm: HE | YES | Competitive Bidding | 2022-10-12 | 2022-10-14 | 2022-10-21 | 2022-11-03 | 2022-11-03 | 2022-11-03 | 09 Nov 22 | 2022-11-11 | 10 Jan 23 | 16 Jan 23 | 06 Mar 23 | NA | NA | GoP | 249995200 | 249995200 | NA | 213100687.8 | 213100687.8 | NA | COA PCCI ASPA | 2022-11-14 | 2022-11-14 | 2022-11-14 | 2022-11-14 | 07 Nov 22 | NA | NA | COMPLETED
4 | Ctg, 60mm: Illum | YES | Competitive Bidding | 2022-10-12 | 2022-10-14 | 2022-10-21 | 2022-11-03 | 2022-11-03 | 2022-11-03 | 09 Nov 22 | 2022-11-11 | 10 Jan 23 | 16 Jan 23 | 06 Mar 23 | NA | NA | GoP | 136000000 | 136000000 | NA | 122720800 | 122720800 | NA | COA PCCI ASPA | 2022-11-14 | 2022-11-14 | 2022-11-14 | 2022-11-14 | 07 Nov 22 | NA | NA | COMPLETED
5 | Ctg. 7.62x39mm Ball | YES | Competitive Bidding | 2022-10-14 | 2022-10-19 | 2022-10-28 | 2022-11-10 | 2022-11-10 | 2022-11-10 | 2022-11-16 | 2022-12-05 | 10 Jan 23 | 16 Jan 23 | 06 Mar 23 | NA | NA | GoP | 45741800 | 45741800 | NA | 45676617.94 | 45676617.94 | NA | COA PCCI ASPA | 2022-10-18 | 2022-10-18 | 2022-10-18 | 2022-10-18 | 2022-11-11 | NA | NA | COMPLETED
6 | Ctg. 7.62x51mm: Ball, Long Range (LR) | YES | Competitive Bidding | 2022-10-14 | 2022-10-19 | 2022-10-28 | 2022-11-14 | 2022-11-14 | 2022-11-14 | 21 Nov 22 | 2022-11-28 | 10 Jan 23 | 16 Jan 23 | 20 Feb 23 | NA | NA | GoP | 250000000 | 250000000 | NA | 245000000 | 245000000 | NA | COA PCCI ASPA | 2022-10-18 | 2022-10-18 | 2022-10-18 | 2022-10-18 | 16 Nov 22 | NA | NA | COMPLETED
7 | Ctg, Cal .40 Ball | YES | Competitive Bidding | 2022-10-14 | 2022-10-19 | 2022-10-28 | 2022-11-10 | 2022-11-10 | 2022-11-10 | 2022-11-17 | 2022-11-28 | 10 Jan 23 | 16 Jan 23 | 28 Feb 23 | NA | NA | GoP | 52000000 | 52000000 | NA | 52000000 | 52000000 | NA | COA PCCI ASPA | 2022-10-18 | 2022-10-18 | 2022-10-18 | 2022-10-18 | 2022-11-11 | NA | NA | COMPLETED
8 | Ctg, 155mm: Projectile, HE/ERFBBT | YES | Competitive Bidding | 2022-10-24 | 2022-10-29 | 2022-11-09 | 2022-11-23 | 2022-11-22 | 2022-11-23 | 29 Nov 22 | 2022-12-05 | 12 Jan 23 | 06 Feb 23 | 20 Mar 23 | NA | NA | GoP | 249975000 | 249975000 | NA | 248973989 | 248973989 | NA | COA PCCI ASPA | 2022-11-02 | 2022-11-02 | 2022-11-02 | 2022-11-02 | 24 Nov 22 | NA | NA | COMPLETED
9 | Grenade, Hand, Fragmentation | YES | Competitive Bidding | 2022-10-13 | 2022-10-18 | 2011-11-11 | 2022-11-29 | 2022-11-29 | 2022-11-29 | 07 Dec 22 | 2022-12-12 | 10 Jan 23 | 19 Jan 23 | 06 Mar 23 | NA | NA | GoP | 144000000 | 144000000 | NA | 90585000 | 90585000 | NA | COA PCCI ASPA | 2022-10-18 | 2022-10-18 | 2022-10-18 | 2022-10-18 | 01 Dec 22 | NA | NA | COMPLETED
10 | ICT Equipment | YES | Competitive Bidding | 2022-11-15 | 2022-11-18 | 2022-11-25 | 2022-12-09 | 2022-12-09 | 2022-12-09 | 13 Dec 22 | 2022-12-19 | 27 Mar 23 | 27 Mar 23 | 27 Apr 23 | NA | NA | GoP | 3000000 | 3000000 | NA | 2919000 | 2919000 | NA | COA PCCI ASPA | 2022-11-18 | 2022-11-18 | 2022-11-18 | 2022-11-18 | 2022-11-18 | NA | NA | COMPLETED
11 | Ctg, 81mm: HE | YES | Competitive Bidding | 2022-12-12 | 2022-12-15 | 2023-01-16 | 2023-02-01 | 2023-02-01 | 2023-02-01 | 2023-02-07 | 2023-02-10 | 16 Mar 23 | 26 Apr 23 | 23 Jun 23 | NA | NA | GoP | 95000000 | 95000000 | NA | 84299200 | 84299200 | NA | COA PCCI ASPA | 2022-12-14 | 2022-12-14 | 2022-12-14 | 2022-12-14 | 2022-12-14 | NA | NA | COMPLETED
12 | Ctg, 81mm: Illum | YES | Competitive Bidding | 2022-12-12 | 2022-12-15 | 2023-01-16 | 2023-02-01 | 2023-02-01 | 2023-02-01 | 2023-02-07 | 2023-02-10 | 16 Mar 23 | 26 Apr 23 | 23 Jun 23 | NA | NA | GoP | 208998000 | 208998000 | NA | 185850000 | 185850000 | NA | COA PCCI ASPA | 2022-12-14 | 2022-12-14 | 2022-12-14 | 2022-12-14 | 2022-12-14 | NA | NA | COMPLETED
13 | Combat Reflex Sight (Red Dot) | YES | Competitive Bidding | 2022-10-17 | 2022-10-19 | 2022-10-27 | 2022-11-09 | 2022-11-09 | 2022-11-09 | 2022-11-15 | 2023-03-06 | 2023-03-16 | 31 Mar 23 | 15 May 23 | NA | NA | GoP | 229383000 | 229383000 | NA | 228687900 | 228687900 | NA | COA PCCI ASPA | 2022-10-20 | 2022-10-20 | 2022-10-20 | 2022-10-20 | 2022-11-10 | NA | NA | COMPLETED
14 | Cap, Blasting, Electric | YES | Competitive Bidding | 2023-01-25 | 2023-01-27 | 2023-02-03 | 2023-02-16 | 2023-02-16 | 2023-02-16 | 23 Feb 23 | 2023-03-10 | 28 Mar 23 | 27 Apr 23 | 23 Jun 23 | NA | NA | GoP | 54000000 | 54000000 | NA | 53899650 | 53899650 | NA | COA PCCI ASPA | 2023-01-27 | 2023-01-27 | 2023-01-27 | 2023-01-27 | 2023-02-17 | NA | NA | COMPLETED
15 | Cap, Blasting, Non-Electric (NONEL) | YES | Competitive Bidding | 2023-01-25 | 2023-01-27 | 2023-02-03 | 2023-02-16 | 2023-02-16 | 2023-02-16 | 23 Feb 23 | 2023-03-10 | 28 Mar 23 | 27 Apr 23 | 26 Jun 23 | NA | NA | GoP | 43200000 | 43200000 | NA | 43100000 | 43100000 | NA | COA PCCI ASPA | 2023-01-27 | 2023-01-27 | 2023-01-27 | 2023-01-27 | 2023-02-17 | NA | NA | COMPLETED
16 | Ctg, 9mm Marking | YES | Competitive Bidding | 2022-10-14 | 2022-10-19 | 2022-10-28 | 2022-11-10 | 2022-11-10 | 2022-11-10 | 2022-11-17 | 2023-03-23 | 13 Apr 23 | 27 Apr 23 | 22 Jun 23 | NA | NA | GoP | 50000000 | 50000000 | NA | 49970000 | 49970000 | NA | COA PCCI ASPA | 2022-10-18 | 2022-10-18 | 2022-10-18 | 2022-10-18 | 2022-11-11 | NA | NA | COMPLETED
17 | Enhancement of Night Fighting System (NFS) | YES | Competitive Bidding | 2022-11-15 | 2022-11-18 | 2022-11-25 | 2022-12-09 | 2022-12-09 | 2022-12-09 | 14 Dec 22 | 2022-12-12 | 10 Feb 23 | NA | NA | NA | NA | GoP | 30652115 | 30652115 | NA | 30555000 | 30555000 | NA | COA PCCI ASPA | 2022-11-18 | 2022-11-18 | 2022-11-18 | 2022-11-18 | 2022-11-18 | NA | NA | COMPLETED
18 | KM250 Truck Spares Parts | YES | Competitive Bidding | 2023-02-10 | 2023-02-14 | 2023-02-22 | 03 Apr 23 | 03 Apr 23 | 03 Apr 23 | 22 Mar 23 | 2023-04-26 | 25 May 23 | NA | NA | NA | NA | GoP | 29918870.45 | 29918870.45 | NA | 29915545.68 | 29915545.68 | NA | COA PCCI ASPA | 2023-02-14 | 2023-02-14 | 2023-02-14 | 2023-02-14 | 2023-02-14 | NA | NA | COMPLETED
19 | KM450 and KM451 Truck Spares | YES | Competitive Bidding | 2023-02-10 | 2023-02-14 | 2023-02-22 | 03 Apr 23 | 03 Apr 23 | 03 Apr 23 | 22 Mar 23 | 2023-04-26 | 25 May 23 | NA | NA | NA | NA | GoP | 89490100 | 89490100 | NA | 89472168.5 | 89472168.5 | NA | COA PCCI ASPA | 2023-02-14 | 2023-02-14 | 2023-02-14 | 2023-02-14 | 2023-02-14 | NA | NA | COMPLETED
20 | Fabrication of Trailer, Tank, Water (1,000 L Capacity) | YES | Competitive Bidding | 2023-03-07 | 2023-03-11 | 2023-03-20 | 2023-04-03 | 2023-04-03 | 2023-04-03 | 14 Apr 23 | 2023-05-19 | 23 Jun 23 | NA | NA | NA | NA | GoP | 70920000 | 70920000 | NA | 60000290 | 60000290 | NA | COA PCCI ASPA | 2023-03-13 | 2023-03-13 | 2023-03-13 | 2023-03-13 | 2023-03-13 | NA | NA | COMPLETED
21 | PA Information System Development | NO | Competitive Bidding | 2023-03-30 | 2023-04-01 | 2023-04-13 | 2023-05-09 | 2023-05-09 | 2023-05-09 | 17 May 23 | 2023-06-07 | 23 Jun 23 | NA | NA | NA | NA | GoP | 10672000 | NA | 10672000 | 9430080.68 | NA | 9430080.68 | COA PCCI ASPA | 2023-03-31 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 2023-05-10 | NA | NA | COMPLETED
Total Alloted Budget of Procurement Activities | [17 empty] | 2542836085.45
Total Contract Price of Procurement Actitvites Conducted | [17 empty] | 2376048129.6
Total Savings (Total Alloted Budget - Total Contract Price) | [17 empty] | 166787955.85
0N-GOING PROCUREMENT ACTIVITIES
1 | Fabrication of Ammunition Trailer Storage | NO | Competitive Bidding | 2023-03-30 | 2023-04-01 | 2023-04-13 | 2023-05-09 | 2023-05-09 | 2023-05-09 | 2023-05-16 | 19 Jun 23 | NA | NA | NA | NA | NA | GoP | 8400000 | 8400000 | NA | 7994000 | 7994000 | NA | COA PCCI ASPA | 2023-03-31 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 2023-05-10 | NA | NA | For issuance of NOA
2 | Spare Parts for All Terrain Vehicle (ATV) | YES | Competitive Bidding | 2023-04-20 | 2023-04-21 | 2023-05-02 | 2023-05-16 | 2023-05-16 | 2023-05-16 | 23 May 23 | 2023-06-19 | NA | NA | NA | NA | NA | GoP | 4835362 | 4835362 | NA | 4812920 | 4812920 | NA | COA PCCI ASPA | 2023-04-20 | 2023-04-20 | 2023-04-20 | 2023-04-20 | 2023-04-20 | NA | NA | For issuance of NOA
3 | Office Productivity (280 sets Desktop Computer 140 sets Laptop Computer 190 sets Multi-Function Printer) | NO | Competitive Bidding | 2023-04-20 | 2023-04-21 | 2023-05-09 | 2023-05-26 | 2023-05-26 | 2023-05-26 | 2023-06-01 | 2023-06-19 | NA | NA | NA | NA | NA | GoP | 25810000 | NA | 25810000 | 21999999.08 | NA | 21999999.08 | COA PCCI ASPA | 2023-03-13 | 2023-03-13 | 2023-03-13 | 2023-03-13 | 2023-03-13 | NA | NA | For issuance of NOA
4 | Communication Equipment for RRU-RESCOM | NO | Competitive Bidding | 2023-05-02 | 2023-05-05 | 2023-05-12 | 2023-06-02 | 2023-06-02 | 2023-06-02 | 2023-06-27 | NA | NA | NA | NA | NA | NA | GoP | 5211928 | 5211928 | NA | 4245888 | 4245888 | NA | COA PCCI ASPA | 2023-05-04 | 2023-05-04 | 2023-05-04 | 2023-05-04 | 2023-06-16 | NA | NA | For issuance of NOA
5 | Ctg, Cal. 50 Ball, Linked with Tracer | YES | Competitive Bidding | 2023-02-22 | 2023-02-28 | 2023-03-07 | 2023-03-20 | 2023-03-20 | 2023-03-20 | 2023-03-28 | NA | NA | NA | NA | NA | NA | GoP | 250000000 | 250000000 | NA | 243600000 | 243600000 | NA | COA PCCI ASPA | 2023-02-27 | 2023-02-27 | 2023-02-27 | 2023-02-27 | 2023-03-20 | NA | NA | For Post Qual abroad
6 | Procurement of Grenade, Hand, Smoke and Fuze, Grenade, Practice | YES | Competitive Bidding | 2023-05-10 | 2023-05-12 | 2023-05-22 | 2023-06-19 | 2023-06-19 | 2023-06-19 | NA | NA | NA | NA | NA | NA | NA | GoP | 90000000 | 90000000 | NA | 81750000 | 81750000 | NA | COA PCCI ASPA | 2023-05-12 | 2023-05-12 | 2023-05-12 | 2023-05-12 | 2023-05-12 | NA | NA | For Post Qual abroad
7 | ICT Equipment (Electronic) | YES | Competitive Bidding | 2023-05-02 | 2023-05-05 | 2023-05-12 | 2023-06-02 | 2023-06-02 | 2023-06-02 | NA | NA | NA | NA | NA | NA | NA | GoP | 3500000 | 3500000 | NA | NA | NA | NA | COA PCCI ASPA | 2023-05-04 | 2023-05-04 | 2023-05-04 | 2023-05-04 | NA | NA | NA | For re-bidding
8 | Communication Equipment | YES | Competitive Bidding | 2023-05-02 | 2023-05-05 | 2023-05-12 | 2023-06-02 | 2023-06-02 | 2023-06-02 | NA | NA | NA | NA | NA | NA | NA | GoP | 3000000 | 3000000 | NA | NA | NA | NA | COA PCCI ASPA | 2023-05-04 | 2023-05-04 | 2023-05-04 | 2023-05-04 | NA | NA | NA | For re-bidding
9 | Intrusion and Detection System /Intrusion Prevention System (IDS/IPS), and Complete Accessories | NO | Competitive Bidding | 2023-06-09 | 2023-06-14 | 2023-06-21 | 2023-07-06 | 2023-07-06 | 2023-07-06 | NA | NA | NA | NA | NA | NA | NA | GoP | 40150000 | NA | 40150000 | NA | NA | NA | COA PCCI ASPA | 2023-06-14 | 2023-06-14 | 2023-06-14 | 2023-06-14 | 2023-06-14 | NA | NA | For SOBE
10 | Network Traffic Analyzer and Data Loss Prevention (DLP) Equipment, and Complete Accessories | NO | Competitive Bidding | 2023-06-09 | 2023-06-14 | 2023-06-21 | 2023-07-06 | 2023-07-06 | 2023-07-06 | NA | NA | NA | NA | NA | NA | NA | GoP | 1470000 | NA | 1470000 | NA | NA | NA | COA PCCI ASPA | 2023-06-14 | 2023-06-14 | 2023-06-14 | 2023-06-14 | 2023-06-14 | NA | NA | For SOBE
11 | Next Generation Security Information and Event Management (SIEM) | NO | Competitive Bidding | 2023-06-09 | 2023-06-14 | 2023-06-21 | 2023-07-06 | 2023-07-06 | 2023-07-06 | NA | NA | NA | NA | NA | NA | NA | GoP | 77690000 | NA | 77690000 | NA | NA | NA | COA PCCI ASPA | 2023-06-14 | 2023-06-14 | 2023-06-14 | 2023-06-14 | 2023-06-14 | NA | NA | For SOBE
12 | Forensic Equipment and Complete Accessories | NO | Competitive Bidding | 2023-06-09 | 2023-06-14 | 2023-06-21 | 2023-07-06 | 2023-07-06 | 2023-07-06 | NA | NA | NA | NA | NA | NA | NA | GoP | 1640000 | NA | 1640000 | NA | NA | NA | COA PCCI ASPA | 2023-06-14 | 2023-06-14 | 2023-06-14 | 2023-06-14 | 2023-06-14 | NA | NA | For SOBE
13 | Additional Enhancement of Night Fighting System (NFS) | NO | Competitive Bidding | 2023-06-09 | 2023-06-16 | 2023-06-23 | 2023-07-07 | 2023-07-07 | 2023-07-07 | NA | NA | NA | NA | NA | NA | NA | GoP | 49999999.98 | 49999999.98 | NA | NA | NA | NA | COA PCCI ASPA | 2023-06-15 | 2023-06-15 | 2023-06-15 | 2023-06-15 | 2023-06-15 | NA | NA | For SOBE
14 | Procurement of DART System of TRADOC, PA | NO | Competitive Bidding | [9 empty] | NA | NA | NA | NA | GoP | 95578200 | NA | 95578200 | NA | NA | NA | COA PCCI ASPA | NA | NA | NA | NA | NA | NA | NA | Awaiting for the issuance of order of TWG | bar: 2022-10-17 to 2023-03-16
15 | Procurement of Computer System to Support the Dart System of TRADOC, PA | NO | Competitive Bidding | [9 empty] | NA | NA | NA | NA | GoP | 4573800 | NA | 4573800 | NA | NA | NA | COA PCCI ASPA | NA | NA | NA | NA | NA | NA | NA | Awaiting for the issuance of order of TWG | bar: 2022-10-17 to 2023-03-16
16 | Spare Parts for Howitzers | YES | Competitive Bidding | 2023-01-23 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | GoP | 9726616.08 | 9726616.08 | NA | NA | NA | NA | COA PCCI ASPA | NA | NA | NA | NA | NA | NA | NA | End-user recommended for the change of mode of procurement to Negotiated 53.9
17 | Projectile, 155mm: Smoke HC | YES | Competitive Bidding | 2023-02-06 | 2023-02-08 | 2023-02-16 | 2023-03-01 | 2023-03-01 | 2023-03-01 | NA | NA | NA | NA | NA | NA | NA | GoP | 225000000 | 225000000 | NA | NA | NA | NA | COA PCCI ASPA | 2023-02-08 | 2023-02-08 | 2023-02-08 | 2023-02-08 | NA | NA | NA | Failed bid (For approval of the revised Technical Specifications) | `
18 | M35 Truck Spares Parts | YES | Competitive Bidding | 2022-12-01 | 2022-12-15 | 2023-01-16 | 2023-02-01 | 2023-02-01 | 2023-02-01 | NA | NA | NA | NA | NA | NA | NA | GoP | 19979600 | 19979600 | NA | NA | NA | NA | COA PCCI ASPA | 2022-12-14 | 2022-12-14 | 2022-12-14 | 2022-12-14 | NA | NA | NA | Failed bid (For realignment of fund)
Total Alloted Budget of On-going Procurement Activities | [17 empty] | 916565506.06
| Prepared by: | [14 empty] | Recommended for Approval: | [12 empty] | Approved by:
| DARIO K WAYAGWAG | [14 empty] | ALVIN V FLORES | [12 empty] | ROMEO S BRAWNER JR
| LTC (QMS) PA | [14 empty] | Brigadier General PA | [12 empty] | Lieutenant General PA
| Head Secretariat | [14 empty] | Chairperson | [12 empty] | Head of Procuring Entity

## Sheet1 (hidden)
Competitive Bidding | GoP | YES
Limited Source Bidding | Foreign | NO
Direct Contracting | Special Purpose Fund
Repeat Order | Corporate Budget
Shopping | Income
NP-53.1 Two Failed Biddings | Others
NP-53.2 Emergency Cases
NP-53.3 Take-Over of Contracts
NP-53.4 Adjacent or Contiguous
NP-53.5 Agency-to-Agency
NP-53.6 Scientific, Scholarly, Artistic Work, Exclusive Technology and Media Services
NP-53.7 Highly Technical Consultants
NP-53.8 Defense Cooperation Agreement
NP-53.9 - Small Value Procurement
NP-53.10 Lease of Real Property and Venue
NP-53.11 NGO Participation
NP-53.12 Community Participation
NP-53.13 UN Agencies, Int'l Organizations or International Financing Institutions
Others - Foreign-funded procurement