## pmr
|  | ANNEX A | [18 empty] | ANNEX B
|  | Department of Budget and Management Annual Procurement Plan for FY 2006 | [18 empty] | (PA BAC3) Procurement Monitoring Report as of June/30/2023
Code (PAP) | Procurement Project | PMO/ End-User | Mode of Procurement | Schedule for Each Procurement Activity | [11 empty] | Source of Funds | ABC (PhP) |  |  | Remarks (brief description of Program/Project) | PMO/ End-User | Is this an Early Procurement Activity? | Mode of Procurement | Actual Procurement Activity | [12 empty] | Source of Funds | ABC (PhP) |  |  | Contract Cost (PhP) |  |  | List of Invited Observers | Date of Receipt of Invitation | [5 empty] | Remarks (Explaining changes from the APP)
|  |  |  | Pre-Proc Conference | Ads/Post of IAEB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Contract Award | Contract Signing | Notice to Proceed | Delivery/ Accept | Payment Process |  | Total | MOOE | CO |  |  |  |  | Pre-Proc Conference | Ads/Post of IB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Date of BAC Resolution Recommending Award | Notice of Award | Contract Signing | Notice to Proceed | Delivery/ Completion | Inspection & Acceptance |  | Total | MOOE | CO | Total | MOOE | CO |  | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Delivery/ Completion/ Acceptance (If applicable)
COMPLETED PROCUREMENT ACTIVITIES
| Supply and Delivery of Construction Materials for the Enhancement Various Firing Range at Camp O'Donnell, Capas, Tarlac | [19 empty] | 51EBde | NO | Competitive Bidding | [13 empty] | GoP | 47224642 | 47224642 |  | 46301993 | 46301993 |  | 3 | 2023-04-13 |  | 2023-04-26 |  | 2023-05-02 | N/A
Total Alloted Budget of Procurement Activities | [37 empty] | 47224642
Total Contract Price of Procurement Actitvites Conducted | [40 empty] | 46301993
Total Savings (Total Alloted Budget - Total Contract Price) | [37 empty] | 922649
0N-GOING PROCUREMENT ACTIVITIES
| Comprehensive Master Development Plan | [19 empty] | 51EBde | NO | Competitive Bidding | [13 empty] | GoP | 92459223.53 | 92459223.53
| Enhancement of AARM Park at TRADOC, PA | [19 empty] | 51EBde | NO | Competitive Bidding | [13 empty] | GoP | 29454690 | 29454690
Total Alloted Budget of On-going Procurement Activities | [37 empty] | 121913913.53
| Prepared by: | [30 empty] | Recommended for Approval by: |  |  |  |  | Recommend for Approval | [6 empty] | APPROVED:
| MAJ JOALYN T DINGLASAN PAF | [30 empty] | BAC Chairperson |  |  |  |  | BGEN MOISES M NAYVE JR PA | [6 empty] | LTGEN ROMEO S BRAWNER JR PA
| PA BAC Secretariat | [35 empty] | Chairperson | [6 empty] | Head of Procuring Entity

## Sheet2
Nr. | UNIT
1 | 51st EBde, PA (114th CO)
2 | 52nd EBde, PA (111 CO)
3 | 53rd EBde, PA (110 CO)
4 | 54th EBde, PA (114 CO)
5 | 55th EBde, PA
6 | First Scout Ranger Regiment
7 | Light Reaction Regiment
8 | Army Signal Regiment
9 | Aviation Regiment
10 | Army Artillery Regiment
11 | 1st Brigade Combat Team
12 | PAPC

## Sheet1 (hidden)
Competitive Bidding | GoP | YES
Limited Source Bidding | Foreign | NO
Direct Contracting | Special Purpose Fund
Repeat Order | Corporate Budget
Shopping | Income
NP-53.1 Two Failed Biddings | Others
NP-53.2 Emergency Cases
NP-53.3 Take-Over of Contracts
NP-53.4 Adjacent or Contiguous
NP-53.5 Agency-to-Agency
NP-53.6 Scientific, Scholarly, Artistic Work, Exclusive Technology and Media Services
NP-53.7 Highly Technical Consultants
NP-53.8 Defense Cooperation Agreement
NP-53.9 - Small Value Procurement
NP-53.10 Lease of Real Property and Venue
NP-53.11 NGO Participation
NP-53.12 Community Participation
NP-53.13 UN Agencies, Int'l Organizations or International Financing Institutions
Others - Foreign-funded procurement