## 3ID
|  | ANNEX A | [18 empty] | ANNEX B
3ID, PA - PROJECT MONITORING REPORT - 01 Jul -31 Dec 2022
Code (PAP) | Procurement Project | PMO/ End-User | Mode of Procurement | Schedule for Each Procurement Activity | [11 empty] | Source of Funds | ABC (PhP) |  |  | Remarks (brief description of Program/Project) | PMO/ End-User | Is this an Early Procurement Activity? | Mode of Procurement | Actual Procurement Activity | [12 empty] | Source of Funds | ABC (PhP) |  |  | Contract Cost (PhP) |  |  | List of Invited Observers | Date of Receipt of Invitation | [5 empty] | Remarks (Explaining changes from the APP)
|  |  |  | Pre-Proc Conference | Ads/Post of IAEB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Contract Award | Contract Signing | Notice to Proceed | Delivery/ Accept | Payment Process |  | Total | MOOE | CO |  |  |  |  | Pre-Proc Conference | Ads/Post of IB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Date of BAC Resolution Recommending Award | Notice of Award | Contract Signing | Notice to Proceed | Delivery/ Completion | Inspection & Acceptance |  | Total | MOOE | CO | Total | MOOE | CO |  | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Delivery/ Completion/ Acceptance (If applicable)
COMPLETED PROCUREMENT ACTIVITIES
5-02-13-040-01 | R&M of Bldg | H3ID | Public bidding | 2021-10-05 | 2021-10-08 | 2021-10-15 | 2021-10-15 | 2021-10-28 | 2021-10-28 | 2021-11-12 | 2021-12-15 | 2022-01-26 | 2022-01-26 | 2022-04-22 | 2022-04-22 | 3ID SBAC |  |  |  |  | H3ID | [10 empty] | 2021-12-15 | 2022-01-26 | 2022-01-26 | 2022-04-22 | 2022-04-22 | 3ID SBAC | 7479744 | 7479744 |  | 7427745 | 7427745 |  | 7 | 2021-10-15 | 2021-10-15 | 2021-10-28 | 2021-10-28 | 2021-11-12
1-06-06-010-00 | Supply & delivery of Motorcycles | H3ID | Negotiated 53.9 | [17 empty] | H3ID |  | MOOE | [8 empty] | 2022-02-07 | 2022-03-14 | 2022-03-14 | 2022-03-29 | 2022-03-29 | Spl Rls | 900000 | 900000 |  | 882000 | 882000
5-02-03-010-00 | Office Supplies | 3DCAU | Negotiated 53.9 | [17 empty] | 3DCAU |  | MOOE | [8 empty] | 2022-02-21 | 2022-03-21 | 2022-03-21 | 2022-03-24 | 2022-03-24 | GAA 2022 | 22895 | 22895 |  | 22800 | 22800
5-02-03-990-00 | Other Supplies | 3DCAU | Negotiated 53.9 | [17 empty] | 3DCAU |  | MOOE | [8 empty] | 2022-02-21 | 2022-03-21 | 2022-03-21 | 2022-03-24 | 2022-03-24 | GAA 2022 | 82000 | 82000 |  | 81920 | 81920
5-02-030-010-00 | Office Supplies | 3CMOBN | Negotiated 53.9 | [17 empty] | 3CMOBN |  | MOOE | [8 empty] | 2022-02-28 | 2022-03-31 | 2022-03-31 | 2022-04-05 | 2022-04-05 | GAA 2022 | 33500 | 33500 |  | 33438 | 33438
5-02-03-990-00 | Other Supplies | 3CMOBN | Negotiated 53.9 | [17 empty] | 3CMOBN |  | MOOE | [8 empty] | 2022-02-28 | 2022-03-24 | 2022-03-24 | 2022-03-28 | 2022-03-28 | GAA 2022 | 48000 | 48000 |  | 47945 | 47945
5-02-13-040-01 | R&M of Bldg | 3CMOBN | Negotiated 53.9 | [17 empty] | 3CMOBN |  | MOOE | [8 empty] | 2022-02-28 | 2022-03-24 | 2022-03-24 | 2022-03-28 | 2022-03-28 | GAA 2022 | 22000 | 22000 |  | 21984 | 21984
5-02-13-050-03 | R&M of ICT | 3CMOBN | Negotiated 53.9 | [17 empty] | 3CMOBN |  | MOOE | [8 empty] | 2022-02-28 | 2022-03-24 | 2022-03-24 | 2022-03-28 | 2022-03-28 | GAA 2022 | 12750 | 12750 |  | 12720 | 12720
5-02-13-050-02 | R&M of Office Eqpmt | CPSH | Negotiated 53.9 | [17 empty] | CPSH |  | MOOE | [8 empty] | 2022-03-04 | 2022-03-24 | 2022-03-24 | 2022-03-28 | 2022-03-28 | GAA 2022 | 23200 | 23200 |  | 23160 | 23160
5-02-13-050-03 | R&M of ICT | CPSH | Negotiated 53.9 | [17 empty] | CPSH |  | MOOE | [8 empty] | 2022-03-04 | 2022-03-31 | 2022-03-31 | 2022-04-05 | 2022-04-05 | GAA 2022 | 27275 | 27275 |  | 27216 | 27216
5-02-03-010-00 | Office Supplies | CPSH | Negotiated 53.9 | [17 empty] | CPSH |  | MOOE | [8 empty] | 2022-03-04 | 2022-03-24 | 2022-03-24 | 2022-03-28 | 2022-03-28 | GAA 2022 | 49050 | 49050 |  | 48892 | 48892
5-02-13-050-03 | R&M of ICT | 3DCAU | Negotiated 53.9 | [17 empty] | 3DCAU |  | MOOE | [8 empty] | 2022-03-04 | 2022-03-24 | 2022-03-24 | 2022-03-28 | 2022-03-28 | GAA 2022 | 9400 | 9400 |  | 9395 | 9395
5-02-03-990-00 | Other Supplies | HHSBN | Negotiated 53.9 | [17 empty] | HHSBN |  | MOOE | [8 empty] | 2022-03-04 | 2022-03-24 | 2022-03-24 | 2022-03-28 | 2022-03-28 | GAA 2022 | 20000 | 20000 |  | 19970 | 19970
5-02-013-050-07 | R&M of Com Eqpmt | 3CMOBN | Negotiated 53.9 | [17 empty] | 3CMOBN |  | MOOE | [8 empty] | 2022-03-07 | 2022-04-19 | 2022-04-19 | 2022-04-26 | 2022-04-26 | GAA 2022 | 102500 | 102500 |  | 102484 | 102484
5-02-03-080-00 | Medical & Laboratory Supplies | CPSH | Negotiated 53.9 | [17 empty] | CPSH |  | MOOE | [8 empty] | 2022-03-07 | 2022-04-06 | 2022-04-06 | 2022-05-06 | 2022-05-06 | GAA 2022 | 294500 | 294500 |  | 294470 | 294470
5-02-03-070-00 | Drugs & Med | CPSH | Negotiated 53.9 | [17 empty] | CPSH |  | MOOE | [8 empty] | 2022-03-07 | 2022-04-06 | 2022-04-06 | 2022-05-31 | 2022-05-31 | GAA 2022 | 184500 | 184500 |  | 184220 | 184220
5-02-02-010-00 | Trng Exp | 82IB | Negotiated 53.9 | [17 empty] | 82IB |  | MOOE | [8 empty] | 2022-03-07 | 2022-03-31 | 2022-03-31 | 2022-04-05 | 2022-04-05 | GAA 2022 | 50000 | 50000 |  | 49990 | 49990
5-02-03-990-00 | Other Supplies | 303BDE | Negotiated 53.9 | [17 empty] | 303BDE |  | MOOE | [8 empty] | 2022-03-14 | 2022-03-31 | 2022-03-31 | 2022-04-05 | 2022-04-05 | GAA 2022 | 25000 | 25000 |  | 24952.5 | 24952.5
5-02-03-010-00 | Office Supplies | 61IB | Negotiated 53.9 | [17 empty] | 61IB |  | MOOE | [8 empty] | 2022-03-14 | 2022-04-08 | 2022-04-08 | 2022-04-19 | 2022-04-19 | GAA 2022 | 6000 | 6000 |  | 5992 | 5992
5-02-03-070-00 | Medical & Laboratory Supplies | 302BDE | Negotiated 53.9 | [17 empty] | 302BDE |  | MOOE | [8 empty] | 2022-03-14 | 2022-03-31 | 2022-03-31 | 2022-04-06 | 2022-04-06 | GAA 2022 | 10000 | 10000 |  | 9965 | 9965
5-02-03-010-00 | Office Supplies | 302BDE | Negotiated 53.9 | [17 empty] | 302BDE |  | MOOE | [8 empty] | 2022-03-14 | 2022-03-28 | 2022-03-28 | 2022-04-05 | 2022-04-05 | GAA 2022 | 7000 | 7000 |  | 6992 | 6992
5-02-03-080-00 | Medical & Laboratory Supplies | 301BDE | Negotiated 53.9 | [17 empty] | 301BDE |  | MOOE | [8 empty] | 2022-03-14 | 2022-03-28 | 2022-03-28 | 2022-03-28 | 2022-03-28 | GAA 2022 | 7200 | 7200 |  | 7140 | 7140
5-02-03-990-00 | Other Supplies | 301BDE | Negotiated 53.9 | [17 empty] | 301BDE |  | MOOE | [8 empty] | 2022-03-14 | 2022-03-24 | 2022-03-24 | 2022-04-05 | 2022-04-05 | GAA 2022 | 86500 | 86500 |  | 86381 | 86381
5-02-13-040-01 | R&M of Bldg | 301BDE | Negotiated 53.9 | [17 empty] | 301BDE |  | MOOE | [8 empty] | 2022-03-14 | 2022-03-31 | 2022-03-31 | 2022-04-05 | 2022-04-05 | GAA 2022 | 262500 | 262500 |  | 262131 | 262131
5-02-13-060-01 | R&M of Motor Veh | 61IB | Negotiated 53.9 | [17 empty] | 61IB |  | MOOE | [8 empty] | 2022-03-21 | 2022-04-08 | 2022-04-08 | 2022-04-19 | 2022-04-19 | GAA 2022 | 10025 | 10025 |  | 10020 | 10020
5-02-99-030-00 | Representation Exp | 61IB | Negotiated 53.9 | [17 empty] | 61IB |  | MOOE | [8 empty] | 2022-03-21 | 2022-04-08 | 2022-04-08 | 2022-04-19 | 2022-04-19 | GAA 2022 | 19500 | 19500 |  | 19493 | 19493
5-02-03-010-00 | Office Supplies | 303BDE | Negotiated 53.9 | [17 empty] | 303BDE |  | MOOE | [8 empty] | 2022-03-21 | 2022-03-31 | 2022-03-31 | 2022-04-05 | 2022-04-05 | GAA 2022 | 170000 | 170000 |  | 169781 | 169781
5-02-13-040-01 | R&M of Bldg | 303BDE | Negotiated 53.9 | [17 empty] | 303BDE |  | MOOE | [8 empty] | 2022-03-21 | 2022-04-06 | 2022-04-06 | 2022-04-19 | 2022-04-19 | GAA 2022 | 210000 | 210000 |  | 209692 | 209692
5-02-13-040-99 | R&M of Other Structures | 303BDE | Negotiated 53.9 | [17 empty] | 303BDE |  | MOOE | [8 empty] | 2022-03-21 | 2022-04-19 | 2022-04-19 | 2022-04-26 | 2022-04-26 | GAA 2022 | 40000 | 40000 |  | 39237.5 | 39237.5
5-02-13-050-03 | R&M of ICT | H3ID | Negotiated 53.9 | [17 empty] | H3ID |  | MOOE | [8 empty] | 2022-03-21 | 2022-06-24 | 2022-06-24 | 2022-06-30 | 2022-06-30 | GAA 2022 | 18500 | 18500 |  | 18490 | 18490
5-02-03-990-00 | Other Supplies | SSBN | Negotiated 53.9 | [17 empty] | SSBN |  | MOOE | [8 empty] | 2022-03-21 | 2022-04-19 | 2022-04-19 | 2022-04-26 | 2022-04-26 | GAA 2022 | 31875 | 31875 |  | 31816 | 31816
5-02-13-050-03 | R&M of ICT | SSBN | Negotiated 53.9 | [17 empty] | SSBN |  | MOOE | [8 empty] | 2022-03-21 | 2022-04-08 | 2022-04-08 | 2022-04-19 | 2022-04-19 | GAA 2022 | 12500 | 12500 |  | 12375 | 12375
5-02-13-040-01 | R&M of Bldg | SSBN | Negotiated 53.9 | [17 empty] | SSBN |  | MOOE | [8 empty] | 2022-03-21 | 2022-04-07 | 2022-04-07 | 2022-04-19 | 2022-04-19 | GAA 2022 | 115000 | 115000 |  | 114497 | 114497
5-02-02-010-00 | Trng Exp | 11IB | Negotiated 53.9 | [17 empty] | 11IB |  | MOOE | [8 empty] | 2022-03-21 | 2022-04-19 | 2022-04-19 | 2022-04-26 | 2022-04-26 | GAA 2022 | 57700 | 57700 |  | 57644 | 57644
5-02-03-070-00 | Drugs & Med | 3DCAU | Negotiated 53.9 | [17 empty] | 3DCAU |  | MOOE | [8 empty] | 2022-03-21 | 2022-05-18 | 2022-05-18 | 2022-05-31 | 2022-05-31 | GAA 2022 | 15020.5 | 15020.5 |  | 15019 | 15019
5-02-13-050-03 | R&M of ICT | 31DRC | Negotiated 53.9 | [17 empty] | 31DRC |  | MOOE | [8 empty] | 2022-03-21 | 2022-05-06 | 2022-05-06 | 2022-05-19 | 2022-05-19 | GAA 2022 | 20000 | 20000 |  | 19979 | 19979
5-02-13-040-01 | R&M of Bldg | 302BDE | Negotiated 53.9 | [17 empty] | 302BDE |  | MOOE | [8 empty] | 2022-03-21 | 2022-04-19 | 2022-04-19 | 2022-04-26 | 2022-04-26 | GAA 2022 | 150000 | 150000 |  | 149858 | 149858
5-02-13-040-01 | R&M of Bldg | 79IB | Negotiated 53.9 | [17 empty] | 79IB |  | MOOE | [8 empty] | 2022-03-21 | 2022-05-19 | 2022-05-19 | 2022-05-31 | 2022-05-31 | GAA 2022 | 168679 | 168679 |  | 168640.5 | 168640.5
5-02-03-010-00 | Office Supplies | H3ID | Negotiated 53.9 | [17 empty] | H3ID |  | MOOE | [8 empty] | 2022-03-21 | 2022-04-07 | 2022-04-07 | 2022-04-19 | 2022-04-19 | GAA 2022 | 134103 | 134103 |  | 133927 | 133927
5-02-03-990-00 | Other Supplies | H3ID | Negotiated 53.9 | [17 empty] | H3ID |  | MOOE | [8 empty] | 2022-03-21 | 2022-04-08 | 2022-04-08 | 2022-04-19 | 2022-04-19 | GAA 2022 | 128360 | 128360 |  | 128260 | 128260
5-02-13-040-01 | R&M of Bldg | CPSH | Negotiated 53.9 | [17 empty] | CPSH |  | MOOE | [8 empty] | 2022-03-25 | 2022-04-06 | 2022-04-06 | 2022-04-19 | 2022-04-19 | GAA 2022 | 60000 | 60000 |  | 59685 | 59685
5-02-13-040-01 | R&M of Bldg | 62IB | Negotiated 53.9 | [17 empty] | 62IB |  | MOOE | [8 empty] | 2022-03-28 | 2022-06-08 | 2022-06-08 | 2022-06-17 | 2022-06-17 | GAA 2022 | 54968 | 54968 |  | 54815 | 54815
5-02-03-010-00 | Office Supplies | CPSH | Negotiated 53.9 | [17 empty] | CPSH |  | MOOE | [8 empty] | 2022-03-28 | 2022-04-19 | 2022-04-19 | 2022-04-26 | 2022-04-26 | GAA 2022 | 49050 | 49050 |  | 48892 | 48892
5-02-13-050-02 | R&M of Office Eqpmt | CPSH | Negotiated 53.9 | [17 empty] | CPSH |  | MOOE | [8 empty] | 2022-03-28 | 2022-04-19 | 2022-04-19 | 2022-04-26 | 2022-04-26 | GAA 2022 | 23200 | 23200 |  | 23160 | 23160
5-02-13-050-03 | R&M of ICT | 302BDE | Negotiated 53.9 | [17 empty] | 302BDE | [10 empty] | 2022-03-28 | 2022-04-19 | 2022-04-19 | 2022-04-26 | 2022-04-26 | GAA 2022 | 20550 | 20550 |  | 20411 | 20411
5-02-02-010-00 | Trng Exp | 62IB | Negotiated 53.9 | [17 empty] | 62IB | [10 empty] | 2022-03-28 | 2022-06-13 | 2022-06-13 | 2022-06-21 | 2022-06-21 | GAA 2022 | 10000 | 10000 |  | 9992 | 9992
5-02-02-010-00 | Trng Exp | 47IB | Negotiated 53.9 | [17 empty] | 47IB | [10 empty] | 2022-03-28 | 2022-04-28 | 2022-04-28 | 2022-05-06 | 2022-05-06 | GAA 2022 | 38000 | 38000 |  | 37890 | 37890
5-02-02-010-00 | Trng Exp | 47IB | Negotiated 53.9 | [17 empty] | 47IB | [10 empty] | 2022-03-28 | 2022-04-28 | 2022-04-28 | 2022-05-06 | 2022-05-06 | GAA 2022 | 30000 | 30000 |  | 29919.5 | 29919.5
5-02-03-080-00 | Medical & Laboratory Supplies | 303BDE | Negotiated 53.9 | [17 empty] | 303BDE | [10 empty] | 2022-03-31 | 2022-05-06 | 2022-05-06 | 2022-05-19 | 2022-05-19 | GAA 2022 | 5000 | 5000 |  | 4986 | 4986
5-02-03-080-00 | Medical & Laboratory Supplies | CPSH | Negotiated 53.9 | [17 empty] | CPSH | [10 empty] | 2022-04-01 | 2022-05-05 | 2022-05-05 | 2022-05-20 | 2022-05-20 | GAA 2022 | 274500 | 274500 |  | 230565 | 230565
5-02-03-070-00 | Drugs & Med | CPSH | Negotiated 53.9 | [17 empty] | CPSH | [10 empty] | 2022-04-01 | 2022-05-18 | 2022-05-18 | 2022-05-31 | 2022-05-31 | GAA 2022 | 184500 | 184500 |  | 183800 | 183800
5-02-13-050-03 | R&M of ICT | 301BDE | Negotiated 53.9 | [17 empty] | 301BDE | [10 empty] | 2022-04-08 | 2022-05-05 | 2022-05-05 | 2022-05-20 | 2022-05-20 | GAA 2022 | 44000 | 44000 |  | 43805 | 43805
5-02-13-040-01 | R&M of Bldg | SSBN | Negotiated 53.9 | [17 empty] | SSBN | [10 empty] | 2022-04-08 | 2022-05-19 | 2022-05-19 | 2022-05-31 | 2022-05-31 | GAA 2022 | 60000 | 60000 |  | 59749 | 59749
5-02-13-050-03 | R&M of ICT | 3DTS | Negotiated 53.9 | [17 empty] | 3DTS | [10 empty] | 2022-04-08 | 2022-08-24 | 2022-08-24 | 2022-09-07 | 2022-09-07 | GAA 2022 | 14900 | 14900 |  | 14800 | 14800
5-02-13-050-03 | R&M of ICT | 3DTS | Negotiated 53.9 | [17 empty] | 3DTS | [10 empty] | 2022-04-08 | 2022-09-21 | 2022-09-21 | 2022-09-30 | 2022-09-30 | GAA 2022 | 14900 | 14900 |  | 14800 | 14800
5-02-13-040-01 | R&M of Bldg | 15IB | Negotiated 53.9 | [17 empty] | 15IB | [10 empty] | 2022-04-08 | 2022-06-07 | 2022-06-07 | 2022-06-17 | 2022-06-17 | GAA 2022 | 19968 | 19968 |  | 19942 | 19942
5-02-02-010-00 | Trng Exp | 33DRC | Negotiated 53.9 | [17 empty] | 33DRC | [10 empty] | 2022-04-08 | 2022-05-05 | 2022-05-05 | 2022-05-19 | 2022-05-19 | GAA 2022 | 9994.5 | 9994.5 |  | 9684 | 9684
5-02-03-010-00 | Office Supplies | H3ID | Negotiated 53.9 | [17 empty] | H3ID | [10 empty] | 2022-04-25 | 2022-07-21 | 2022-07-21 | 2022-08-03 | 2022-08-03 | GAA 2022 | 611870 | 611870 |  | 611652 | 611652
5-02-13-050-03 | R&M of ICT | H3ID | Negotiated 53.9 | [17 empty] | H3ID | [10 empty] | 2022-04-25 | 2022-10-05 | 2022-10-05 | 2022-10-18 | 2022-10-18 | GAA 2022 | 75500 | 75500 |  | 75214.5 | 75214.5
5-02-03-010-00 | Office Supplies | 3DCAU | Negotiated 53.9 | [17 empty] | 3DCAU | [10 empty] | 2022-04-25 | 2022-06-17 | 2022-06-17 | 2022-06-24 | 2022-06-24 | GAA 2022 | 52120 | 52120 |  | 52077.5 | 52077.5
5-02-03-990-00 | Other Supplies | H3ID | Negotiated 53.9 | [17 empty] | H3ID | [10 empty] | 2022-04-25 | 2022-05-25 | 2022-05-25 | 2022-05-31 | 2022-05-31 | GAA 2022 | 48868 | 48868 |  | 48176 | 48176
5-02-13-050--07 | R&M of Communication Eqpmt | 3CMOBN | Negotiated 53.9 | [17 empty] | 3CMOBN | [10 empty] | 2022-04-25 | 2022-05-25 | 2022-05-25 | 2022-05-31 | 2022-05-31 | GAA 2022 | 23100 | 23100 |  | 22970 | 22970
5-02-03-010-00 | Office Supplies | 3CMOBN | Negotiated 53.9 | [17 empty] | 3CMOBN | [10 empty] | 2022-04-25 | 2022-06-15 | 2022-06-15 | 2022-06-24 | 2022-06-24 | GAA 2022 | 33500 | 33500 |  | 32998 | 32998
5-02-13-050-03 | R&M of ICT | 3CMOBN | Negotiated 53.9 | [17 empty] | 3CMOBN | [10 empty] | 2022-04-25 | 2022-06-08 | 2022-06-08 | 2022-06-17 | 2022-06-17 | GAA 2022 | 12750 | 12750 |  | 12547 | 12547
5-02-03-990-00 | Other Supplies | SSBN | Negotiated 53.9 | [17 empty] | SSBN | [10 empty] | 2022-04-25 | 2022-05-19 | 2022-05-19 | 2022-05-31 | 2022-05-31 | GAA 2022 | 40375 | 40375 |  | 40132 | 40132
5-02-03-010-00 | Office Supplies | SSBN | Negotiated 53.9 | [17 empty] | SSBN | [10 empty] | 2022-04-25 | 2022-06-23 | 2022-06-23 | 2022-06-30 | 2022-06-30 | GAA 2022 | 8645 | 8645 |  | 8614 | 8614
5-02-02-010-00 | Trng Exp | 12IB | Negotiated 53.9 | [17 empty] | 12IB | [10 empty] | 2022-04-25 | 2022-05-19 | 2022-05-19 | 2022-05-31 | 2022-05-31 | GAA 2022 | 39385 | 39385 |  | 39356 | 39356
5-02-13-040-01 | R&M of Bldg | 3DCAU | Negotiated 53.9 | [17 empty] | 3DCAU | [10 empty] | 2022-04-29 | 2022-04-29 | 2022-04-29 | 2022-05-31 | 2022-05-31 | GAA 2022 | 146371 | 146371 |  | 146255 | 146255
5-02-13-050-03 | R&M of ICT | 3DCAU | Negotiated 53.9 | [17 empty] | 3DCAU | [10 empty] | 2022-04-29 | 2022-05-25 | 2022-05-25 | 2022-05-31 | 2022-05-31 | GAA 2022 | 9400 | 9400 |  | 9350 | 9350
5-02-13-040-01 | R&M of Bldg | 301BDE | Negotiated 53.9 | [17 empty] | 301BDE | [10 empty] | 2022-05-02 | 2022-06-08 | 2022-06-08 | 2022-06-17 | 2022-06-17 | GAA 2022 | 242500 | 242500 |  | 242300 | 242300
5-02-13-040-01 | R&M of Bldg | 3CMOBN | Negotiated 53.9 | [17 empty] | 3CMOBN | [10 empty] | 2022-05-02 | 2022-06-15 | 2022-06-15 | 2022-06-24 | 2022-06-24 | GAA 2022 | 40000 | 40000 |  | 39968 | 39968
5-02-03-990-00 | Other Supplies | 3CMOBN | Negotiated 53.9 | [17 empty] | 3CMOBN | [10 empty] | 2022-05-02 | 2022-06-15 | 2022-06-15 | 2022-06-24 | 2022-06-24 | GAA 2022 | 61032 | 61032 |  | 60882 | 60882
5-02-03-010-00 | Office Supplies | 301BDE | Negotiated 53.9 | [17 empty] | 301BDE | [10 empty] | 2022-05-02 | 2022-06-08 | 2022-06-08 | 2022-06-17 | 2022-06-17 | GAA 2022 | 85060 | 85060 |  | 85031 | 85031
5-02-03-990-00 | Other Supplies | 301BDE | Negotiated 53.9 | [17 empty] | 301BDE | [10 empty] | 2022-05-16 | 2022-06-13 | 2022-06-13 | 2022-06-21 | 2022-06-21 | GAA 2022 | 71700 | 71700 |  | 71567 | 71567
5-02-02-010-00 | Trng Exp | 47IB | Negotiated 53.9 | [17 empty] | 47IB | [10 empty] | 2022-05-17 | 2022-06-13 | 2022-06-13 | 2022-06-21 | 2022-06-21 | GAA 2022 | 33000 | 33000 |  | 32647 | 32647
5-02-02-010-00 | Trng Exp | 47IB | Negotiated 53.9 | [17 empty] | 47IB | [10 empty] | 2022-05-17 | 2022-06-17 | 2022-06-17 | 2022-06-24 | 2022-06-24 | GAA 2022 | 20000 | 20000 |  | 19996 | 19996
5-02-03-070-00 | Drugs & Med | 301BDE | Negotiated 53.9 | [17 empty] | 301BDE | [10 empty] | 2022-05-17 | 2022-06-24 | 2022-06-24 | 2022-06-30 | 2022-06-30 | GAA 2022 | 10000 | 10000 |  | 9997 | 9997
5-02-03-080-00 | Medical & Laboratory Supplies | 301BDE | Negotiated 53.9 | [17 empty] | 301BDE | [10 empty] | 2022-05-17 | 2022-06-08 | 2022-06-08 | 2022-06-21 | 2022-06-21 | GAA 2022 | 7200 | 7200 |  | 7180 | 7180
5-02-13-040-99 | R&M of Other Structure | 12IB | Negotiated 53.9 | [17 empty] | 12IB | [10 empty] | 2022-05-26 | 2022-11-16 | 2022-11-16 | 2022-11-21 | 2022-11-21 | GAA 2022 | 41000 | 41000 |  | 40897 | 40897
5-02-13-050-03 | R&M of ICT | 12IB | Negotiated 53.9 | [17 empty] | 12IB | [10 empty] | 2022-05-26 | 2022-05-25 | 2022-05-25 | 2022-06-30 | 2022-06-30 | GAA 2022 | 10500 | 10500 |  | 10490 | 10490
5-02-02-010-00 | Trng Exp | 31DRC | Negotiated 53.9 | [17 empty] | 31DRC | [10 empty] | 2022-05-26 | 2022-06-23 | 2022-06-23 | 2022-06-30 | 2022-06-30 | GAA 2022 | 20000 | 20000 |  | 19989 | 19989
5-02-13-040-01 | R&M of Bldg | 31DRC | Negotiated 53.9 | [17 empty] | 31DRC | [10 empty] | 2022-05-26 | 2022-06-15 | 2022-06-15 | 2022-06-24 | 2022-06-24 | GAA 2022 | 25000 | 25000 |  | 24974 | 24974
5-02-03-990-00 | Other Supplies | HHSBN | Negotiated 53.9 | [17 empty] | HHSBN | [10 empty] | 2022-05-30 | 2022-06-23 | 2022-06-23 | 2022-06-30 | 2022-06-30 | GAA 2022 | 22000 | 22000 |  | 21920 | 21920
5-02-13-040-01 | R&M of Bldg | 302BDE | Negotiated 53.9 | [17 empty] | 302BDE | [10 empty] | 2022-05-30 | 2022-07-21 | 2022-07-21 | 2022-08-03 | 2022-08-03 | GAA 2022 | 177500 | 177500 |  | 177372 | 177372
5-02-03-010-00 | Office Supplies | 302BDE | Negotiated 53.9 | [17 empty] | 302BDE | [10 empty] | 2022-05-30 | 2022-06-17 | 2022-06-17 | 2022-06-24 | 2022-06-24 | GAA 2022 | 59000 | 59000 |  | 58884 | 58884
5-02-13-050-02 | R&M of Office Eqpmt | 302BDE | Negotiated 53.9 | [17 empty] | 302BDE | [10 empty] | 2022-05-30 | 2022-07-21 | 2022-07-21 | 2022-08-03 | 2022-08-03 | GAA 2022 | 22500 | 22500 |  | 22400 | 22400
5-02-03-070-00 | Drugs & Med | 302BDE | Negotiated 53.9 | [17 empty] | 302BDE | [10 empty] | 2022-05-30 | 2022-06-23 | 2022-06-23 | 2022-06-30 | 2022-06-30 | GAA 2022 | 10000 | 10000 |  | 9987 | 9987
5-02-03-010-00 | Office Supplies | 303BDE | Negotiated 53.9 | [17 empty] | 303BDE | [10 empty] | 2022-06-06 | 2022-06-23 | 2022-06-23 | 2022-06-30 | 2022-06-30 | GAA 2022 | 91000 | 91000 |  | 90880 | 90880
5-02-03-990-00 | Other Supplies | 303BDE | Negotiated 53.9 | [17 empty] | 303BDE | [10 empty] | 2022-06-06 | 2022-06-23 | 2022-06-23 | 2022-06-30 | 2022-06-30 | GAA 2022 | 25000 | 25000 |  | 24825 | 24825
5-02-13-050-03 | R&M of ICT | 302BDE | Negotiated 53.9 | [17 empty] | 302BDE | [10 empty] | 2022-06-06 | 2022-07-21 | 2022-07-21 | 2022-08-03 | 2022-08-03 | GAA 2022 | 49150 | 49150 |  | 49020 | 49020
5-02-03-080-00 | Medical & Laboratory Supplies | CPSH | Negotiated 53.9 | [17 empty] | CPSH | [10 empty] | 2022-07-04 | 2022-08-03 | 2022-08-03 | 2022-08-16 | 2022-08-16 | GAA 2022 | 274500 | 274500 |  | 274345 | 274345
5-02-03-070-00 | Drugs & Med | CPSH | Negotiated 53.9 | [17 empty] | CPSH | [10 empty] | 2022-07-04 | 2022-08-03 | 2022-08-03 | 2022-08-16 | 2022-08-16 | GAA 2022 | 184500 | 184500 |  | 184130 | 184130
5-02-03-010-00 | Office Supplies | CPSH | Negotiated 53.9 | [17 empty] | CPSH | [10 empty] | 2022-07-04 | 2022-08-15 | 2022-08-15 | 2022-08-19 | 2022-08-19 | GAA 2022 | 49050 | 49050 |  | 48892 | 48892
5-02-13-050-03 | R&M of ICT | 3DCAU | Negotiated 53.9 | [17 empty] | 3DCAU | [10 empty] | 2022-07-04 | 2022-08-09 | 2022-08-09 | 2022-08-19 | 2022-08-19 | GAA 2022 | 9400 | 9400 |  | 9250 | 9250
5-02-03-990-00 | Other Supplies | 31DRC | Negotiated 53.9 | [17 empty] | 31DRC | [10 empty] | 2022-07-12 | 2022-08-03 | 2022-08-03 | 2022-08-10 | 2022-08-10 | GAA 2022 | 20000 | 20000 |  | 19980 | 19980
5-02-13-050-03 | R&M of ICT | 31DRC | Negotiated 53.9 | [17 empty] | 31DRC | [10 empty] | 2022-07-12 | 2022-08-15 | 2022-08-15 | 2022-08-19 | 2022-08-19 | GAA 2022 | 20000 | 20000 |  | 19984 | 19984
5-02-02-010-00 | Trng Exp | 31DRC | Negotiated 53.9 | [17 empty] | 31DRC | [10 empty] | 2022-07-12 | 2022-08-03 | 2022-08-03 | 2022-08-10 | 2022-08-10 | GAA 2022 | 20000 | 20000 |  | 19985 | 19985
5-02-13-040-01 | R&M of Bldg | SSBN | Negotiated 53.9 | [17 empty] | SSBN | [10 empty] | 2022-07-12 | 2022-08-09 | 2022-08-09 | 2022-08-19 | 2022-08-19 | GAA 2022 | 10000 | 10000 |  | 9985 | 9985
5-02-03-010-00 | Office Supplies | SSBN | Negotiated 53.9 | [17 empty] | SSBN | [10 empty] | 2022-07-12 | 2022-08-09 | 2022-08-09 | 2022-08-19 | 2022-08-19 | GAA 2022 | 9330 | 9330 |  | 9253 | 9253
5-02-03-010-00 | Office Supplies | 3DCAU | Negotiated 53.9 | [17 empty] | 3DCAU | [10 empty] | 2022-07-12 | 2022-09-02 | 2022-09-02 | 2022-09-09 | 2022-09-09 | GAA 2022 | 21840 | 21840 |  | 21726 | 21726
5-02-13-060-01 | R&M of Motor Veh | 82IB | Negotiated 53.9 | [17 empty] | 82IB | [10 empty] | 2022-07-18 | 2022-08-03 | 2022-08-03 | 2022-08-10 | 2022-08-10 | GAA 2022 | 25000 | 25000 |  | 24950 | 24950
5-02-05-020-01 | Mobile Exp | 82IB | Negotiated 53.9 | [17 empty] | 82IB | [10 empty] | 2022-07-18 | 2022-08-03 | 2022-08-03 | 2022-08-10 | 2022-08-10 | GAA 2022 | 15000 | 15000 |  | 15000 | 15000
5-02-13-050-03 | R&M of ICT | 302BDE | Negotiated 53.9 | [17 empty] | 302BDE | [10 empty] | 2022-07-26 | 2022-10-24 | 2022-10-24 | 2022-11-03 | 2022-11-03 | GAA 2022 | 19550 | 19550 |  | 19410 | 19410
5-02-03-010-00 | Office Supplies | 302BDE | Negotiated 53.9 | [17 empty] | 302BDE | [10 empty] | 2022-07-26 | 2022-08-15 | 2022-08-15 | 2022-08-19 | 2022-08-19 | GAA 2022 | 9000 | 9000 |  | 8970 | 8970
5-02-13-050-07 | R&M of Com Eqpmt | 302BDE | Negotiated 53.9 | [17 empty] | 302BDE | [10 empty] | 2022-07-26 | 2022-08-16 | 2022-08-16 | 2022-08-19 | 2022-08-19 | GAA 2022 | 5000 | 5000 |  | 4996 | 4996
5-02-99-030-00 | Representation Exp | 82IB | Negotiated 53.9 | [17 empty] | 82IB | [10 empty] | 2022-07-26 | 2022-08-23 | 2022-08-23 | 2022-09-02 | 2022-09-02 | GAA 2022 | 46700 | 46700 |  | 46600 | 46600
5-02-02-010-00 | Trng Exp | 61IB | Negotiated 53.9 | [17 empty] | 61IB | [10 empty] | 2022-07-26 | 2022-09-14 | 2022-09-14 | 2022-09-23 | 2022-09-23 | GAA 2022 | 9200 | 9200 |  | 9140 | 9140
5-02-02-010-00 | Trng Exp | 33DRC | Negotiated 53.9 | [17 empty] | 33DRC | [10 empty] | 2022-07-26 | 2022-08-23 | 2022-08-23 | 2022-09-02 | 2022-09-02 | GAA 2022 | 9994.5 | 9994.5 |  | 9907 | 9907
5-02-13-040-01 | R&M of Bldg | 302BDE | Negotiated 53.9 | [17 empty] | 302BDE | [10 empty] | 2022-07-29 | 2022-09-14 | 2022-09-14 | 2022-09-23 | 2022-09-23 | GAA 2022 | 140000 | 140000 |  | 139436 | 139436
5-02-03-010-00 | Office Supplies | 301BDE | Negotiated 53.9 | [17 empty] | 301BDE | [10 empty] | 2022-07-29 | 2022-09-02 | 2022-09-02 | 2022-09-09 | 2022-09-09 | GAA 2022 | 83060 | 83060 |  | 82576 | 82576
5-02-03-990-00 | Other Supplies | 301BDE | Negotiated 53.9 | [17 empty] | 301BDE | [10 empty] | 2022-08-08 | 2022-09-02 | 2022-09-02 | 2022-09-09 | 2022-09-09 | GAA 2022 | 71700 | 71700 |  | 71150 | 71150
5-02-03-990-00 | Other Supplies | 303BDE | Negotiated 53.9 | [17 empty] | 303BDE | [10 empty] | 2022-08-09 | 2022-09-02 | 2022-09-02 | 2022-09-09 | 2022-09-09 | GAA 2022 | 25000 | 25000 |  | 24915 | 24915
5-02-02-010-00 | Trng Exp | 94IB | Negotiated 53.9 | [17 empty] | 94IB | [10 empty] | 2022-08-16 | 2022-09-16 | 2022-09-16 | 2022-09-23 | 2022-09-23 | GAA 2022 | 81033 | 81033 |  | 80750 | 80750
5-02-13-050-07 | R&M (Machinery & Equipment) Communication Equipment | 3CMOBN | Negotiated 53.9 | [17 empty] | 3CMOBN | [10 empty] | 2022-08-15 | 2022-09-22 | 2022-09-22 | 2022-09-30 | 2022-09-30 | GAA 2022 | 42500 | 42500 |  | 42340 | 42340
5-02-03-010-00 | Office Supplies | 3CMOBN | Negotiated 53.9 | [17 empty] | 3CMOBN | [10 empty] | 2022-08-15 | 2022-09-14 | 2022-09-14 | 2022-09-20 | 2022-09-20 | GAA 2022 | 33500 | 33500 |  | 33370 | 33370
5-02-05-020-01 | Mobile Exp | 32DRC | Negotiated 53.9 | [17 empty] | 32DRC | [10 empty] | 2022-08-15 | 2022-09-14 | 2022-09-14 | 2022-09-23 | 2022-09-23 | GAA 2022 | 19422 | 19422 |  | 19110 | 19110
5-02-02-010-00 | Trng Exp | 32DRC | Negotiated 53.9 | [17 empty] | 32DRC | [10 empty] | 2022-08-15 | 2022-09-15 | 2022-09-15 | 2022-09-23 | 2022-09-23 | GAA 2022 | 5500 | 5500 |  | 5450 | 5450
5-02-13-050-03 | R&M of ICT | 12IB | Negotiated 53.9 | [17 empty] | 12IB | [10 empty] | 2022-08-15 | 2022-09-21 | 2022-09-21 | 2022-09-30 | 2022-09-30 | GAA 2022 | 10500 | 10500 |  | 10450 | 10450
5-02-03-990-00 | Other Supplies | 3DCAU | Negotiated 53.9 | [17 empty] | 3DCAU | [10 empty] | 2022-08-15 | 2022-09-08 | 2022-09-08 | 2022-09-20 | 2022-09-20 | GAA 2022 | 15000 | 15000 |  | 14875 | 14875
5-02-13-040-01 | R&M of Facilities | 301BDE | Negotiated 53.9 | [17 empty] | 301BDE | [10 empty] | 2022-08-22 | 2022-09-14 | 2022-09-14 | 2022-09-23 | 2022-09-23 | Spl Rls | 996801 | 996801 |  | 995876 | 995876
5-02-13-050-03 | R&M of ICT | 3CMOBN | Negotiated 53.9 | [17 empty] | 3CMOBN | [10 empty] | 2022-08-22 | 2022-09-21 | 2022-09-21 | 2022-09-30 | 2022-09-30 | GAA 2022 | 12750 | 12750 |  | 12700 | 12700
5-02-02-010-00 | Trng Exp | 47IB | Negotiated 53.9 | [17 empty] | 47IB | [10 empty] | 2022-08-24 | 2022-09-14 | 2022-09-14 | 2022-09-23 | 2022-09-23 | GAA 2022 | 33000 | 33000 |  | 32960 | 32960
5-02-03-990-00 | Other Supplies | H3ID | Negotiated 53.9 | [17 empty] | H3ID | [10 empty] | 2022-08-30 | 2022-11-07 | 2022-11-07 | 2022-11-11 | 2022-11-11 | GAA 2022 | 72223.9 | 72223.9 |  | 71726 | 71726
5-02-13-060-01 | R&M of Motor Veh | 12IB | Negotiated 53.9 | [17 empty] | 12IB | [10 empty] | 2022-08-30 | 2022-10-05 | 2022-10-05 | 2022-10-26 | 2022-10-26 | GAA 2022 | 50000 | 50000 |  | 49900 | 49900
5-02-03-080-00 | Medical & Laboratory Supplies | CPSH | Negotiated 53.9 | [17 empty] | CPSH | [10 empty] | 2022-09-20 | 2022-11-07 | 2022-11-07 | 2022-11-11 | 2022-11-11 | GAA 2022 | 274500 | 274500 |  | 274345 | 274345
5-02-03-070-00 | Drugs & Med | CPSH | Negotiated 53.9 | [17 empty] | CPSH | [10 empty] | 2022-09-20 | 2022-11-07 | 2022-11-07 | 2022-11-11 | 2022-11-11 | GAA 2022 | 184500 | 184500 |  | 184220 | 184220
5-02-03-010-00 | Office Supplies | CPSH | Negotiated 53.9 | [17 empty] | CPSH | [10 empty] | 2022-09-20 | 2022-10-19 | 2022-10-19 | 2022-10-26 | 2022-10-26 | GAA 2022 | 49050 | 49050 |  | 48892 | 48892
5-02-13-050-03 | R&M of ICT | CPSH | Negotiated 53.9 | [17 empty] | CPSH | [10 empty] | 2022-09-20 | 2022-10-19 | 2022-10-19 | 2022-10-26 | 2022-10-26 | GAA 2022 | 27275 | 27275 |  | 27200 | 27200
5-02-02-010-00 | Trng Exp | 12IB | Negotiated 53.9 | [17 empty] | 12IB | [10 empty] | 2022-09-27 | 2022-10-20 | 2022-10-20 | 2022-10-26 | 2022-10-26 | GAA 2022 | 15000 | 15000 |  | 14988 | 14988
5-02-03-080-00 | Medical & Laboratory Supplies | 12IB | Negotiated 53.9 | [17 empty] | 12IB | [10 empty] | 2022-09-27 | 2022-10-26 | 2022-10-26 | 2022-11-09 | 2022-11-09 | GAA 2022 | 8000 | 8000 |  | 8000 | 8000
5-02-13-040-01 | R&M of Bldg | 79IB | Negotiated 53.9 | [17 empty] | 79IB | [10 empty] | 2022-09-27 | 2022-10-19 | 2022-10-19 | 2022-10-26 | 2022-10-26 | GAA 2022 | 33040 | 33040 |  | 32995 | 32995
5-02-05-020-01 | Mobile Exp | 32DRC | Negotiated 53.9 | [17 empty] | 32DRC | [10 empty] | 2022-09-27 | 2022-10-19 | 2022-10-19 | 2022-10-26 | 2022-10-26 | GAA 2022 | 19422 | 19422 |  | 19305 | 19305
5-02-13-040-01 | R&M of Bldg | 31DRC | Negotiated 53.9 | [17 empty] | 31DRC | [10 empty] | 2022-10-04 | 2022-11-16 | 2022-11-16 | 2022-11-21 | 2022-11-21 | GAA 2022 | 25000 | 25000 |  | 24810 | 24810
5-02-02-010-00 | Trng Exp | 32DRC | Negotiated 53.9 | [17 empty] | 32DRC | [10 empty] | 2022-10-04 | 2022-11-16 | 2022-11-16 | 2022-11-21 | 2022-11-21 | GAA 2022 | 6488 | 6488 |  | 6423 | 6423
5-02-03-010-00 | Office Supplies | 303BDE | Negotiated 53.9 | [17 empty] | 303BDE | [10 empty] | 2022-10-10 | 2022-11-07 | 2022-11-07 | 2022-11-11 | 2022-11-11 | GAA 2022 | 151000 | 151000 |  | 150611.5 | 150611.5
5-02-03-990-00 | Other Supplies | 303BDE | Negotiated 53.9 | [17 empty] | 303BDE | [10 empty] | 2022-10-10 | 2022-11-07 | 2022-11-07 | 2022-11-11 | 2022-11-11 | GAA 2022 | 25000 | 25000 |  | 24915 | 24915
5-02-02-010-00 | Trng Exp | 47IB | Negotiated 53.9 | [17 empty] | 47IB | [10 empty] | 2022-10-10 | 2022-12-07 | 2022-12-07 | 2022-12-12 | 2022-12-12 | GAA 2022 | 85000 | 85000 |  | 84526 | 84526
5-02-03-010-00 | Office Supplies | 3DCAU | Negotiated 53.9 | [17 empty] | 3DCAU | [10 empty] | 2022-10-10 | 2022-10-20 | 2022-10-20 | 2022-10-26 | 2022-10-26 | GAA 2022 | 21840 | 21840 |  | 21726 | 21726
5-02-13-050-03 | R&M of ICT | 3DCAU | Negotiated 53.9 | [17 empty] | 3DCAU | [10 empty] | 2022-10-10 | 2022-11-16 | 2022-11-16 | 2022-11-21 | 2022-11-21 | GAA 2022 | 9350 | 9350 |  | 9350 | 9350
5-02-03-010-00 | Office Supplies | 302BDE | Negotiated 53.9 | [17 empty] | 302BDE | [10 empty] | 2022-10-10 | 2022-10-24 | 2022-10-24 | 2022-11-03 | 2022-11-03 | GAA 2022 | 12000 | 12000 |  | 11978 | 11978
5-02-03-010-00 | Office Supplies | 3CMOBN | Negotiated 53.9 | [17 empty] | 3CMOBN | [10 empty] | 2022-10-10 | 2022-10-24 | 2022-10-24 | 2022-11-04 | 2022-11-04 | GAA 2022 | 33500 | 33500 |  | 33370 | 33370
5-02-03-010-00 | Office Supplies | 301BDE | Negotiated 53.9 | [17 empty] | 301BDE | [10 empty] | 2022-10-14 | 2022-10-24 | 2022-10-24 | 2022-11-03 | 2022-11-03 | GAA 2022 | 85060 | 85060 |  | 84676 | 84676
5-02-03-990-00 | Other Supplies | 301BDE | Negotiated 53.9 | [17 empty] | 301BDE | [10 empty] | 2022-10-14 | 2022-10-24 | 2022-10-24 | 2022-11-03 | 2022-11-03 | GAA 2022 | 71700 | 71700 |  | 71525 | 71525
5-02-13-050-07 | R&M of Radio Broadcasting System | 3CMOBN | Negotiated 53.9 | [17 empty] | 3CMOBN | [10 empty] | 2022-10-14 | 2022-11-07 | 2022-11-07 | 2022-11-10 | 2022-11-10 | GAA 2022 | 23100 | 23100 |  | 23080 | 23080
5-02-13-050-03 | R&M of ICT | 3CMOBN | Negotiated 53.9 | [17 empty] | 3CMOBN | [10 empty] | 2022-10-14 | 2022-11-07 | 2022-11-07 | 2022-11-10 | 2022-11-10 | GAA 2022 | 12750 | 12750 |  | 12700 | 12700
5-02-13-050-02 | R&M Equipment | 302BDE | Negotiated 53.9 | [17 empty] | 302BDE | [10 empty] | 2022-10-14 | 2022-11-16 | 2022-11-16 | 2022-11-21 | 2022-11-21 | GAA 2022 | 22500 | 22500 |  | 22400 | 22400
5-02-05-020-01 | Mobile Exp | 82IB | Negotiated 53.9 | [17 empty] | 82IB | [10 empty] | 2022-10-14 | 2022-11-16 | 2022-11-16 | 2022-11-21 | 2022-11-21 | GAA 2022 | 15000 | 15000 |  | 15000 | 15000
Total Alloted Budget of Procurement Activities | [37 empty] | 17865462.4
Total Contract Price of Procurement Actitvites Conducted | [40 empty] | 17731197.5
Total Savings (Total Alloted Budget - Total Contract Price) | [37 empty] | 134264.9
0N-GOING PROCUREMENT ACTIVITIES
5-02-03-010-00 | Office Supplies | 301BDE | Negotiated 53.9 | [17 empty] | 301BDE | [10 empty] | 2022-02-28 | 2022-03-31 | 2022-03-31 | 2022-04-05 | 2022-04-05 | GAA 2022 | 83060 | 83060 |  | 82989 | 82989
5-02-13-040-01 | R&M of Bldg | 61IB | Negotiated 53.9 | [17 empty] | 61IB | [10 empty] | 2022-03-21 | 2022-04-19 | 2022-04-19 | 2022-04-26 | 2022-04-26 | GAA 2022 | 25500 | 25500 |  | 25452 | 25452
5-02-02-010-00 | Trng Exp | 32DRC | Negotiated 53.9 | [17 empty] | 32DRC | [10 empty] | 2022-05-16 | 2022-07-15 | 2022-07-15 | 2022-07-27 | 2022-07-27 | GAA 2022 | 49994 | 49994 |  | 49863.5 | 49863.5
5-02-13-050-02 | R&M Office Equipment | CPSH | Negotiated 53.9 | [17 empty] | CPSH | [10 empty] | 2022-07-12 | 2022-08-03 | 2022-08-03 | 2022-08-10 | 2022-08-10 | GAA 2022 | 23200 | 23200 |  | 23160 | 23160
5-02-02-010-00 | Trng Exp | 82IB | Negotiated 53.9 | [17 empty] | 82IB | [10 empty] | 2022-07-18 | 2022-08-09 | 2022-08-09 | 2022-08-19 | 2022-08-19 | GAA 2022 | 50000 | 50000 |  | 49858 | 49858
5-02-13-040-01 | R&M of Facilities | 3DCAU | Negotiated 53.9 | [17 empty] | 3DCAU | [10 empty] | 2022-07-26 | 2022-08-23 | 2022-08-23 | 2022-09-02 | 2022-09-02 | GAA 2022 | 41000 | 41000 |  | 40846 | 40846
5-02-13-060-01 | R&M of Motor Veh | 61IB | Negotiated 53.9 | [17 empty] | 61IB | [10 empty] | 2022-07-26 | 2022-08-25 | 2022-08-25 | 2022-09-02 | 2022-09-02 | GAA 2022 | 4250 | 4250 |  | 4250 | 4250
5-02-02-010-00 | Trng Exp | 12IB | Negotiated 53.9 | [17 empty] | 12IB | [10 empty] | 2022-07-26 | 2022-09-02 | 2022-09-02 | 2022-09-15 | 2022-09-15 | GAA 2022 | 20415 | 20415 |  | 20407 | 20407
5-02-13-040-01 | R&M of Facilities | 301BDE | Negotiated 53.9 | [17 empty] | 301BDE | [10 empty] | 2022-07-29 | 2022-09-21 | 2022-09-21 | 2022-09-30 | 2022-09-30 | GAA 2022 | 407500 | 407500 |  | 406565 | 406565
5-02-03-010-00 | Office Supplies | 303BDE | Negotiated 53.9 | [17 empty] | 303BDE | [10 empty] | 2022-07-29 | 2022-10-05 | 2022-10-05 | 2022-10-17 | 2022-10-17 | GAA 2022 | 105000 | 105000 |  | 104908 | 104908
5-02-13-040-01 | R&M of Facilities | 303BDE | Negotiated 53.9 | [17 empty] | 303BDE | [10 empty] | 2022-08-09 | 2022-10-05 | 2022-10-05 | 2022-10-17 | 2022-10-17 | GAA 2022 | 90000 | 90000 |  | 89720 | 89720
5-02-02-010-00 | Trng Exp | 47IB | Negotiated 53.9 | [17 empty] | 47IB | [10 empty] | 2022-08-24 | 2022-09-22 | 2022-09-22 | 2022-09-30 | 2022-09-30 | GAA 2022 | 20000 | 20000 |  | 19954 | 19954
5-02-13-050-03 | R&M of ICT | H3ID | Negotiated 53.9 | [17 empty] | H3ID | [10 empty] | 2022-08-30 | 2022-12-09 | 2022-12-09 | 2022-12-12 | 2022-12-12 | GAA 2022 | 38500 | 38500 |  | 38300 | 38300
5-02-13-040-01 | R&M of Facilities | 3CMOBN | Negotiated 53.9 | [17 empty] | 3CMOBN | [10 empty] | 2022-08-30 | 2022-09-21 | 2022-09-21 | 2022-09-30 | 2022-09-30 | GAA 2022 | 42000 | 42000 |  | 41860 | 41860
5-02-03-010-00 | Office Supplies | H3ID | Negotiated 53.9 | [17 empty] | H3ID | [10 empty] | 2022-09-05 | 2022-12-09 | 2022-12-09 | 2022-12-12 | 2022-12-12 | GAA 2022 | 338014.1 | 338014.1 |  | 337812 | 337812
5-02-13-040-01 | R&M of Facilities | 3DTS | Negotiated 53.9 | [17 empty] | 3DTS | [10 empty] | 2022-09-05 | 2022-11-16 | 2022-11-16 | 2022-11-21 | 2022-11-21 | GAA 2022 | 162500 | 162500 |  | 162311 | 162311
5-02-13-050-03 | R&M of ICT | 12IB | Negotiated 53.9 | [17 empty] | 12IB | [10 empty] | 2022-09-27 | 2022-10-19 | 2022-10-19 | 2022-12-16 | 2022-12-16 | GAA 2022 | 14800 | 14800 |  | 14700 | 14700
5-02-02-010-00 | Trng Exp | 31DRC | Negotiated 53.9 | [17 empty] | 31DRC | [10 empty] | 2022-10-04 | 2022-12-05 | 2022-12-05 | 2022-12-12 | 2022-12-12 | GAA 2022 | 20000 | 20000 |  | 19977 | 19977
5-02-02-010-00 | Trng Exp | 33DRC | Negotiated 53.9 | [17 empty] | 33DRC | [10 empty] | 2022-10-04 | 2022-12-05 | 2022-12-05 | 2022-12-12 | 2022-12-12 | GAA 2022 | 9994.5 | 9994.5 |  | 9897 | 9897
5-02-03-080-00 | Medical & Laboratory Supplies | 302BDE | Negotiated 53.9 | [17 empty] | 302BDE | [10 empty] | 2022-10-10 | 2022-11-16 | 2022-11-16 | 2022-11-21 | 2022-11-21 | GAA 2022 | 10000 | 10000 |  | 9987 | 9987
5-02-13-040-01 | R&M of Bldg | 301BDE | Negotiated 53.9 | [17 empty] | 301BDE | [10 empty] | 2022-10-14 | 2022-11-07 | 2022-11-07 | 2022-11-11 | 2022-11-11 | GAA 2022 | 133500 | 133500 |  | 133251 | 133251
5-02-03-010-00 | Office Supplies | 3DTS | Negotiated 53.9 | [17 empty] | 3DTS | [10 empty] | 2022-10-14 | 2022-12-06 | 2022-12-06 | 2022-12-12 | 2022-12-12 | GAA 2022 | 25000 | 25000 |  | 24823 | 24823
5-02-13-050-03 | R&M of ICT | 3DTS | Negotiated 53.9 | [17 empty] | 3DTS | [10 empty] | 2022-10-14 | 2022-12-09 | 2022-12-09 | 2022-12-12 | 2022-12-12 | GAA 2022 | 14900 | 14900 |  | 14800 | 14800
5-02-13-050-02 | R&M Equipment | CPSH | Negotiated 53.9 | [17 empty] | CPSH | [10 empty] | 2022-10-14 | 2022-12-07 | 2022-12-07 | 2022-12-12 | 2022-12-12 | GAA 2022 | 23200 | 23200 |  | 23160 | 23160
5-02-13-050-03 | R&M of ICT | 303BDE | Negotiated 53.9 | [17 empty] | 303BDE | [10 empty] | 2022-10-14 | 2022-12-15 | 2022-12-15 | 2022-12-16 | 2022-12-16 | GAA 2022 | 7500 | 7500 |  | 7500 | 7500
5-02-03-010-00 | Office Supplies | H3ID | Negotiated 53.9 | [17 empty] | H3ID | [10 empty] | 2022-10-24 | 2022-12-09 | 2022-12-09 | 2022-12-12 | 2022-12-12 | GAA 2022 | 338794 | 338794 |  | 337503 | 337503
5-02-03-990-00 | Other Supplies | H3ID | Negotiated 53.9 | [17 empty] | H3ID | [10 empty] | 2022-10-24 | 2022-12-09 | 2022-12-09 | 2022-12-12 | 2022-12-12 | GAA 2022 | 168295.9 | 168295.9 |  | 167507 | 167507
5-02-13-050-03 | R&M of ICT | 302BDE | Negotiated 53.9 | [17 empty] | 302BDE | [10 empty] | 2022-10-24 | 2022-12-05 | 2022-12-05 | 2022-12-12 | 2022-12-12 | GAA 2022 | 49150 | 49150 |  | 48800 | 48800
Total Alloted Budget of On-going Procurement Activities | [37 empty] | 2316067.5
Total Contract Price of Procurement Actitvites Conducted | [40 empty] | 2310160.5
Total Savings (Total Alloted Budget - Total Contract Price) | [37 empty] | 5907
Prepared by:
Teofisto F Pagayon
TSg (FS) PA
First Sgt /Operations NCO
Noted by:
JONIEFER G DELA TORRE
MAJ (CE) PA
Commanding Officer