## PMR, AAR, PA
|  | ANNEX A | [18 empty] | ANNEX B
|  | Department of Budget and Management Annual Procurement Plan for FY 2006 | [18 empty] | (Army Artillery Regiment, Philippine Army) Procurement Monitoring Report as of July 2022
Code (PAP) | Procurement Project | PMO/ End-User | Mode of Procurement | Schedule for Each Procurement Activity | [11 empty] | Source of Funds | ABC (PhP) |  |  | Remarks (brief description of Program/Project) | PMO/ End-User | Is this an Early Procurement Activity? | Mode of Procurement | Actual Procurement Activity | [12 empty] | Source of Funds | ABC (PhP) |  |  | Contract Cost (PhP) |  |  | List of Invited Observers | Date of Receipt of Invitation | [5 empty] | Remarks (Explaining changes from the APP)
|  |  |  | Pre-Proc Conference | Ads/Post of IAEB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Contract Award | Contract Signing | Notice to Proceed | Delivery/ Accept | Payment Process |  | Total | MOOE | CO |  |  |  |  | Pre-Proc Conference | Ads/Post of IB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Date of BAC Resolution Recommending Award | Notice of Award | Contract Signing | Notice to Proceed | Delivery/ Completion | Inspection & Acceptance |  | Total | MOOE | CO | Total | MOOE | CO |  | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Delivery/ Completion/ Acceptance (If applicable)
COMPLETED PROCUREMENT ACTIVITIES
NAF 49 | R&M of Building | [19 empty] | HAAR | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-05-30 | N/A | 2022-06-27 | 2022-07-05 | 2022-07-06 | MOOE | 651125 |  |  | 650680 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NAF 50 | R&M of Other Structures | [19 empty] | HAAR | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-05-30 | N/A | 2022-06-27 | 2022-07-05 | 2022-07-06 | MOOE | 84000 |  |  | 83720 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NAF 51 | Other Supplies and Materials Exps | [19 empty] | HAAR | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-05-30 | N/A | 2022-06-27 | 2022-07-05 | 2022-07-06 | MOOE | 185290 |  |  | 184990 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NAF 52 | R&M of Furnitures and Fixtures | [19 empty] | HAAR | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-05-30 | N/A | 2022-06-27 | 2022-07-05 | 2022-07-06 | MOOE | 40000 |  |  | 39876 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NAF 53 | R&M of ICT Equipment | [19 empty] | HAAR | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-05-30 | N/A | 2022-06-27 | 2022-07-05 | 2022-07-06 | MOOE | 20000 |  |  | 19850 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NAF 54 | R&M of Machinery and Equipment | [19 empty] | HAAR | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-05-30 | N/A | 2022-06-27 | 2022-07-05 | 2022-07-06 | MOOE | 35000 |  |  | 34783 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NAF 55 | R&M of Office Equipment | [19 empty] | HAAR | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-05-30 | N/A | 2022-06-27 | 2022-07-05 | 2022-07-06 | MOOE | 20000 |  |  | 19763 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NAF 56 | R&M of Other Machinery and Equipment | [19 empty] | HAAR | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-05-30 | N/A | 2022-06-27 | 2022-07-05 | 2022-07-06 | MOOE | 10000 |  |  | 9890 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NAF 57 | Representation Exps | [19 empty] | HAAR | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-05-30 | N/A | 2022-06-27 | 2022-07-05 | 2022-07-06 | MOOE | 351000 |  |  | 350600 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NAF 58 | Office Supplies Exps | [19 empty] | HAAR | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-05-30 | N/A | 2022-06-27 | 2022-07-05 | 2022-07-06 | MOOE | 768743 |  |  | 768291 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NAF 59 | Semi-Expendable ICT Equipment | [19 empty] | HAAR | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-05-30 | N/A | 2022-06-27 | 2022-07-05 | 2022-07-06 | MOOE | 89920 |  |  | 89560 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NAF 60 | Training Expenses | [19 empty] | HAAR | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-05-30 | N/A | 2022-06-27 | 2022-07-05 | 2022-07-06 | MOOE | 121500 |  |  | 121120 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NAF 61 | R&M of Motor Vehicle | [19 empty] | HAAR | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-05-30 | N/A | 2022-06-27 | 2022-07-05 | 2022-07-06 | MOOE | 296000 |  |  | 295576 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NAF 62 | Semi-Expendable Sports Equipment | [19 empty] | HAAR | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-05-30 | N/A | 2022-06-27 | 2022-07-05 | 2022-07-06 | MOOE | 10000 |  |  | 9800 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NAF 63 | Semi-Expendable F&F | [19 empty] | HAAR | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-05-30 | N/A | 2022-06-27 | 2022-07-05 | 2022-07-06 | MOOE | 50000 |  |  | 49800 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NAF-64 | Representation Expenses | [19 empty] | HAAR | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-05-30 | N/A | 2022-06-27 | 2022-07-05 | 2022-07-06 | MOOE | 33315 |  |  | 33160 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NAF-65 | Training Expenses (1st 155SP) | [19 empty] | Separate Batteries | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-06-16 | N/A | 2022-07-14 | 2022-07-21 | 2022-07-21 | MOOE | 48000 |  |  | 47800 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NAF-66 | Representation Expenses (1st 155SP) | [19 empty] | Separate Batteries | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-06-16 | N/A | 2022-07-14 | 2022-07-21 | 2022-07-21 | MOOE | 23750 |  |  | 23500 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NAF-67 | R&M of ICT Equipment (1st 155SP) | [19 empty] | Separate Batteries | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-06-16 | N/A | 2022-07-14 | 2022-07-21 | 2022-07-21 | MOOE | 20000 |  |  | 19850 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NAF-68 | R&M of Commo Equipment (1st 155SP) | [19 empty] | Separate Batteries | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-06-16 | N/A | 2022-07-14 | 2022-07-21 | 2022-07-21 | MOOE | 15000 |  |  | 14850 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NAF-69 | Representation Expenses | [19 empty] | Separate Batteries | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-06-16 | N/A | 2022-07-14 | 2022-07-21 | 2022-07-21 | MOOE | 53000 |  |  | 52757 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NAF-70 | R&M of Building (2nd 155SP & 1MLRS) | [19 empty] | Separate Batteries |  | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-06-16 | N/A | 2022-07-14 | 2022-07-21 | 2022-07-21 | MOOE | 42000 |  |  | 41700 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NAF-71 | R&M of Other Structure (2MLRS) | [19 empty] | Separate Batteries |  | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-06-16 | N/A | 2022-07-14 | 2022-07-21 | 2022-07-21 | MOOE | 10000 |  |  | 9850 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NAF-72 | R&M of Office Equipment (1st 155SP) | [19 empty] | Separate Batteries |  | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-06-16 | N/A | 2022-07-14 | 2022-07-21 | 2022-07-21 | MOOE | 5000 |  |  | 4900 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NAF-73 | Training Expenses | [19 empty] | Separate Batteries |  | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-06-16 | N/A | 2022-07-14 | 2022-07-21 | 2022-07-21 | MOOE | 66000 |  |  | 65725 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NAF-74 | R&M of Machinery and Equipment | [19 empty] | Separate Batteries |  | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-06-16 | N/A | 2022-07-14 | 2022-07-21 | 2022-07-21 | MOOE | 15000 |  |  | 14800 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NAF-01 | R&M of Buildings | [19 empty] | Separate Batteries |  | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-06-21 | N/A | 2022-07-14 | 2022-07-21 | 2022-07-21 | MOOE | 15000 |  |  | 14800 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NAF-02 | R&M of Other Structures | [19 empty] | Separate Batteries |  | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-06-21 | N/A | 2022-07-14 | 2022-07-21 | 2022-07-21 | MOOE | 39000 |  |  | 38709 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NAF-03 | R&M of Furnitures & Fixtures | [19 empty] | Separate Batteries |  | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-06-21 | N/A | 2022-07-14 | 2022-07-21 | 2022-07-21 | MOOE | 15000 |  |  | 14802 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NAF 79 | R&M of Building | [19 empty] | HAAR |  | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-19 | N/A | 2022-10-26 | 2022-11-03 | 2022-11-03 | MOOE | 465000 |  |  | 464482 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NAF 80 | R&M of Other Structure | [19 empty] | HAAR |  | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-19 | N/A | 2022-10-26 | 2022-11-03 | 2022-11-03 | MOOE | 20000 |  |  | 19850 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NAF 81 | Other Supplies and Materials Exps | [19 empty] | HAAR |  | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-19 | N/A | 2022-10-26 | 2022-11-03 | 2022-11-03 | MOOE | 169540 |  |  | 169090 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NAF 82 | R&M of Office Equipment | [19 empty] | HAAR |  | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-19 | N/A | 2022-10-26 | 2022-11-03 | 2022-11-03 | MOOE | 20000 |  |  | 19750 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NAF 83 | R&M of Machinery & Equipment | [19 empty] | HAAR |  | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-19 | N/A | 2022-10-26 | 2022-11-03 | 2022-11-03 | MOOE | 15000 |  |  | 14764 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NAF 84 | R&M of Other Machinery & Equipment | [19 empty] | HAAR |  | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-19 | N/A | 2022-10-26 | 2022-11-03 | 2022-11-03 | MOOE | 10000 |  |  | 9835 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NAF 85 | R&M of Motor Veh | [19 empty] | HAAR |  | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-19 | N/A | 2022-10-26 | 2022-11-03 | 2022-11-03 | MOOE | 282000 |  |  | 281640 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NAF 86 | Office Supplies | [19 empty] | HAAR |  | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-19 | N/A | 2022-10-26 | 2022-11-03 | 2022-11-03 | MOOE | 721343 |  |  | 720687 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NAF 87 | Representation Exps | [19 empty] | HAAR |  | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-19 | N/A | 2022-10-26 | 2022-11-03 | 2022-11-03 | MOOE | 542935 |  |  | 542285 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NAF 88 | Semi-Expendable Equipment | [19 empty] | HAAR |  | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-19 | N/A | 2022-10-26 | 2022-11-03 | 2022-11-03 | MOOE | 55530 |  |  | 55210 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NAF 89 | Semi-Expendable-Sport Equipment | [19 empty] | HAAR |  | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-19 | N/A | 2022-10-26 | 2022-11-03 | 2022-11-03 | MOOE | 10000 |  |  | 9800 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NAF 90 | Semi-Expendable-Furniture and Fixtures | [19 empty] | HAAR |  | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-19 | N/A | 2022-10-26 | 2022-11-03 | 2022-11-03 | MOOE | 50000 |  |  | 49700 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NAF 91 | Semi-Expendable-Commo Equipment | [19 empty] | HAAR |  | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-19 | N/A | 2022-10-26 | 2022-11-03 | 2022-11-03 | MOOE | 6000 |  |  | 5850 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NAF 92 | Representation Exps | [19 empty] | HAAR |  | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-19 | N/A | 2022-10-26 | 2022-11-03 | 2022-11-03 | MOOE | 137550 |  |  | 137175 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NAF 93 | R&M of Other Structure | [19 empty] | HAAR |  | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-19 | N/A | 2022-10-26 | 2022-11-03 | 2022-11-03 | MOOE | 10000 |  |  | 9880 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NAF 95 | R&M of Machinery & Equipment | [19 empty] | HAAR |  | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-19 | N/A | 2022-10-26 | 2022-11-03 | 2022-11-03 | MOOE | 5000 |  |  | 4860 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NAF 94 | R&M of ICT Equipment | [19 empty] | HAAR |  | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-19 | N/A | 2022-10-26 | 2022-11-03 | 2022-11-03 | MOOE | 25000 |  |  | 24700 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NAF 96 | R&M of Building | [19 empty] | HAAR |  | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-19 | N/A | 2022-10-26 | 2022-11-03 | 2022-11-03 | MOOE | 15500 |  |  | 15300 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NAF 98 | R&M of Motor Vehicle - OSS | [19 empty] | HAAR |  | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-19 | N/A | 2022-10-26 | 2022-11-03 | 2022-11-03 | MOOE | 55000 |  |  | 54700 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NAF 99 | R&M of Other Machinery and Equipment | [19 empty] | HAAR |  | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-19 | N/A | 2022-10-26 | 2022-11-03 | 2022-11-03 | MOOE | 40000 |  |  | 39700 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NAF 100 | R&M of ICT Equipment | [19 empty] | HAAR |  | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-19 | N/A | 2022-10-26 | 2022-11-03 | 2022-11-03 | MOOE | 30000 |  |  | 29700 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NAF 102 | R&M of Building-OSS | [19 empty] | HAAR |  | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-19 | N/A | 2022-10-26 | 2022-11-03 | 2022-11-03 | MOOE | 15000 |  |  | 14800 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NAF 103 | Fire Base Station | [19 empty] | ATS, AAR,PA |  | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-17 | N/A | 2022-11-09 | 2022-11-15 | 2022-11-15 | Special Release | 424530 |  |  | 424005 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NAF 104 | Obstacle Course | [19 empty] | ATS, AAR,PA |  | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-17 | N/A | 2022-11-09 | 2022-11-15 | 2022-11-15 | Special Release | 429219 |  |  | 428650 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NAF 105 | Pistol Firing Range | [19 empty] | ATS, AAR,PA |  | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-17 | N/A | 2022-11-09 | 2022-11-15 | 2022-11-15 | Special Release | 609915 |  |  | 609135 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NAF 106 | Spt for the repair of Personnel Barracks ADA, AAR | [19 empty] | ADA, AAR, PA |  | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-11 | N/A | 2022-11-25 | 2022-11-29 | 2022-11-29 | Special Release | 179918 |  |  | 179510 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NAF-107 | Repair of Admin Building | [19 empty] | HAAR |  | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-11 | N/A | 2022-11-25 | 2022-11-29 | 2022-11-29 | Special Release | 261100 |  |  | 260750 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NAF-108 | Repair Billeted Officer Quarters | [19 empty] | HAAR |  | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-11 | N/A | 2022-11-25 | 2022-11-29 | 2022-11-29 | Special Release | 202500 |  |  | 202126 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NAF-109 | Repair E-Type Building | [19 empty] | HAAR |  | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-11 | N/A | 2022-11-25 | 2022-11-29 | 2022-11-29 | Special Release | 132050 |  |  | 131670 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NAF-110 | Repair MPF | [19 empty] | HAAR |  | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-11 | N/A | 2022-11-25 | 2022-11-29 | 2022-11-29 | Special Release | 70390 |  |  | 70075 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NAF-111 | Repair Parking Fire Truck | [19 empty] | HAAR |  | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-11 | N/A | 2022-11-25 | 2022-11-29 | 2022-11-29 | Special Release | 133181 |  |  | 132840 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NAF-112 | Repair PED Barracks | [19 empty] | HAAR |  | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-11 | N/A | 2022-11-25 | 2022-11-29 | 2022-11-29 | Special Release | 124285 |  |  | 123880 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NAF-113 | Repair RC Quarters | [19 empty] | HAAR |  | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-11 | N/A | 2022-11-25 | 2022-11-29 | 2022-11-29 | Special Release | 56067 |  |  | 55691 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NAF-114 | Repair of Street Lights | [19 empty] | HAAR |  | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-11 | N/A | 2022-11-25 | 2022-11-29 | 2022-11-29 | Special Release | 149483 |  |  | 149115 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NAF-115 | R&M of Motor Vehicle | [19 empty] | HAAR |  | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-14 | N/A | 2022-12-13 | 2022-12-15 | 2022-12-15 | MOOE | 55000 |  |  | 54620 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NAF-116 | Other Machinery and Equipment | [19 empty] | HAAR |  | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-14 | N/A | 2022-12-13 | 2022-12-15 | 2022-12-15 | MOOE | 40000 |  |  | 39730 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
[38 empty] | 8700679 | 0 |  | 8681057
Total Alloted Budget of Procurement Activities | [37 empty] | 8700679
Total Contract Price of Procurement Actitvites Conducted | [40 empty] | 8681057
Total Savings (Total Alloted Budget - Total Contract Price) | [37 empty] | 19622
[21 empty] | Prepared by: | [10 empty] | Recommended for Approval by: | [10 empty] | APPROVED:
[21 empty] | Jovilyn T Perez | [10 empty] | ENSTIEN L DELA CRUZ | [10 empty] | Head of the Procuring Entity
[21 empty] | Sgt (Art) PA | [10 empty] | Major (ART) PA
[21 empty] | Procurement NCO | [10 empty] | AC of S for Logistics, G4

## Sheet1 (hidden)
Competitive Bidding | GoP | YES
Limited Source Bidding | Foreign | NO
Direct Contracting | Special Purpose Fund
Repeat Order | Corporate Budget
Shopping | Income
NP-53.1 Two Failed Biddings | Others
NP-53.2 Emergency Cases
NP-53.3 Take-Over of Contracts
NP-53.4 Adjacent or Contiguous
NP-53.5 Agency-to-Agency
NP-53.6 Scientific, Scholarly, Artistic Work, Exclusive Technology and Media Services
NP-53.7 Highly Technical Consultants
NP-53.8 Defense Cooperation Agreement
NP-53.9 - Small Value Procurement
NP-53.10 Lease of Real Property and Venue
NP-53.11 NGO Participation
NP-53.12 Community Participation
NP-53.13 UN Agencies, Int'l Organizations or International Financing Institutions
Others - Foreign-funded procurement