## pmr
|  | ANNEX A | [18 empty] | ANNEX B
|  | Department of Budget and Management Annual Procurement Plan for FY 2006 | [18 empty] | (PAPC) Procurement Monitoring Report as of December 31, 2022
Code (PAP) | Procurement Project | PMO/ End-User | Mode of Procurement | Schedule for Each Procurement Activity | [11 empty] | Source of Funds | ABC (PhP) |  |  | Remarks (brief description of Program/Project) | PMO/ End-User | Is this an Early Procurement Activity? | Mode of Procurement | Actual Procurement Activity | [12 empty] | Source of Funds | ABC (PhP) |  |  | Contract Cost (PhP) |  |  | List of Invited Observers | Date of Receipt of Invitation | [5 empty] | Remarks (Explaining changes from the APP)
|  |  |  | Pre-Proc Conference | Ads/Post of IAEB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Contract Award | Contract Signing | Notice to Proceed | Delivery/ Accept | Payment Process |  | Total | MOOE | CO |  |  |  |  | Pre-Proc Conference | Ads/Post of IB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Date of BAC Resolution Recommending Award | Notice of Award | Contract Signing | Notice to Proceed | Delivery/ Completion | Inspection & Acceptance |  | Total | MOOE | CO | Total | MOOE | CO |  | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Delivery/ Completion/ Acceptance (If applicable)
COMPLETED PROCUREMENT ACTIVITIES
| S/D of 1 pc Laptop & 4 others | [19 empty] | APAO | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-11 | 2022-10-11 | 2022-10-26 | 2022-11-02 | 2022-11-02 | GoP | 78000 | 78000 | 0 | 76000 | 76000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of 1 set Valve cover gasket & 44 others | [19 empty] | APAO | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-04 | 2022-11-04 | 2022-11-28 | 2022-12-05 | 2022-12-05 | GoP | 135000 | 135000 | 0 | 133750 | 133750 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of 1 unit Air-conditioned .5HP & 3 others | [19 empty] | APAO | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-18 | 2022-10-18 | 2022-11-02 | 2022-11-09 | 2022-11-09 | GoP | 152640 | 152640 | 0 | 150640 | 150640 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of 125 pack Soda in can 330ml 3s & 10 others | [19 empty] | APAO | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-13 | 2022-09-13 | 2022-10-26 | 2022-11-02 | 2022-11-02 | GoP | 81250 | 81250 | 0 | 80992 | 80992 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of 2 ea Scanner-Single Function Printer (Monochrome) & 6 others | [19 empty] | APAO | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-31 | 2022-08-31 | 2022-10-14 | 2022-10-21 | 2022-10-21 | GoP | 70000 | 70000 | 0 | 69750 | 69750 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of 2 pcs Laptop & 8 others | [19 empty] | APAO | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-09 | 2022-08-09 | 2022-08-16 | 2022-08-23 | 2022-08-23 | GoP | 350000 | 350000 | 0 | 346200 | 346200 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of 2 units Desktop Intel Core i5-1100 & 6 others | [19 empty] | APAO | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-02 | 2022-09-02 | 2022-10-21 | 2022-10-28 | 2022-10-28 | GoP | 90000 | 90000 | 0 | 89500 | 89500 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of 48 pcs Ordinary Plywood 3/4"x4'x8' & 20 others | [19 empty] | APAO | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-31 | 2022-08-31 | 2022-10-14 | 2022-10-21 | 2022-10-21 | GoP | 180000 | 180000 | 0 | 176040 | 176040 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Total Alloted Budget of Procurement Activities | [37 empty] | 1136890
Total Contract Price of Procurement Actitvites Conducted | [40 empty] | 1122872
Total Savings (Total Alloted Budget - Total Contract Price) | [37 empty] | 14018
0N-GOING PROCUREMENT ACTIVITIES
Total Alloted Budget of On-going Procurement Activities | [37 empty] | #REF!
| Prepared by: | [32 empty] | Certified Correct By | [6 empty] | Noted By
| CLAIRE R AURE-REYES | [32 empty] | JOHN KENNETH D BABICA | [6 empty] | MANOLO V SANTIAGO
| Major (QMS) PA | [32 empty] | Major (INF) PA | [6 empty] | Colonel CE (GSC) PA
| Operations Officer | [32 empty] | Executive Officer | [6 empty] | Commanding Officer

## Sheet2
|  | ANNEX A | [18 empty] | ANNEX B
|  | Department of Budget and Management Annual Procurement Plan for FY 2006 | [18 empty] | (PAPC) Procurement Monitoring Report as of December 31, 2022
AMRY PROPERTY ACCOUNTABILITY OFFICE
Code (PAP) | Procurement Project | PMO/ End-User | Mode of Procurement | Schedule for Each Procurement Activity | [11 empty] | Source of Funds | ABC (PhP) |  |  | Remarks (brief description of Program/Project) | PMO/ End-User | Is this an Early Procurement Activity? | Mode of Procurement | Actual Procurement Activity | [12 empty] | Source of Funds | ABC (PhP) |  |  | Contract Cost (PhP) |  |  | List of Invited Observers | Date of Receipt of Invitation | [5 empty] | Remarks (Explaining changes from the APP)
|  |  |  | Pre-Proc Conference | Ads/Post of IAEB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Contract Award | Contract Signing | Notice to Proceed | Delivery/ Accept | Payment Process |  | Total | MOOE | CO |  |  |  |  | Pre-Proc Conference | Ads/Post of IB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Date of BAC Resolution Recommending Award | Notice of Award | Contract Signing | Notice to Proceed | Delivery/ Completion | Inspection & Acceptance |  | Total | MOOE | CO | Total | MOOE | CO |  | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Delivery/ Completion/ Acceptance (If applicable)
COMPLETED PROCUREMENT ACTIVITIES
| S/D of 1 pc Laptop & 4 others | [19 empty] | APAO | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-11 | 2022-10-11 | 2022-10-26 | 2022-11-02 | 2022-11-02 | GoP | 78000 | 78000 | 0 | 76000 | 76000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of 1 set Valve cover gasket & 44 others | [19 empty] | APAO | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-04 | 2022-11-04 | 2022-11-28 | 2022-12-05 | 2022-12-05 | GoP | 135000 | 135000 | 0 | 133750 | 133750 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of 1 unit Air-conditioned .5HP & 3 others | [19 empty] | APAO | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-18 | 2022-10-18 | 2022-11-02 | 2022-11-09 | 2022-11-09 | GoP | 152640 | 152640 | 0 | 150640 | 150640 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of 125 pack Soda in can 330ml 3s & 10 others | [19 empty] | APAO | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-13 | 2022-09-13 | 2022-10-26 | 2022-11-02 | 2022-11-02 | GoP | 81250 | 81250 | 0 | 80992 | 80992 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of 2 ea Scanner-Single Function Printer (Monochrome) & 6 others | [19 empty] | APAO | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-31 | 2022-08-31 | 2022-10-14 | 2022-10-21 | 2022-10-21 | GoP | 70000 | 70000 | 0 | 69750 | 69750 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of 2 pcs Laptop & 8 others | [19 empty] | APAO | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-09 | 2022-08-09 | 2022-08-16 | 2022-08-23 | 2022-08-23 | GoP | 350000 | 350000 | 0 | 346200 | 346200 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of 2 units Desktop Intel Core i5-1100 & 6 others | [19 empty] | APAO | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-02 | 2022-09-02 | 2022-10-21 | 2022-10-28 | 2022-10-28 | GoP | 90000 | 90000 | 0 | 89500 | 89500 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of 48 pcs Ordinary Plywood 3/4"x4'x8' & 20 others | [19 empty] | APAO | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-31 | 2022-08-31 | 2022-10-14 | 2022-10-21 | 2022-10-21 | GoP | 180000 | 180000 | 0 | 176040 | 176040 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of 30 reams of Bond Paper, A4 Size & 16 others | [19 empty] | 11FPAO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-02-08 | 2022-02-08 | 2022-03-04 | 2022-03-07 | 2022-03-07 | GoP | 27730 | 27730 | 0 | 27655 | 27635 | 0 | [7 empty] | N/A
| S/D of 20 Box Ballpen Blue and Black & 25 others | [19 empty] | 11FPAO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-05-16 | 2022-05-16 | 2022-06-07 | 2007-22 | 2022-07-20 | GoP | 35550 | 35550 | 0 | 33135.14 | 33135.14 | 0 | [7 empty] | N/A
| S/D of 10 packs Coffee 500g & 13 others | [19 empty] | 11FPAO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-08-22 | 2022-08-22 | 2022-08-25 | 2022-10-25 | 2022-10-25 | GoP | 15750 | 15750 | 0 | 15750 | 15750 | 0 | [7 empty] | N/A
| S/D of 24 each Side Clip Lever Arch File Folder F4 4 9 others | [19 empty] | 11FPAO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-10-25 | 2022-10-25 | 2022-11-07 | 2022-12-06 | 2022-12-06 | GoP | 10700 | 10700 | 0 | 10700 | 10700 | 0 | [7 empty] | N/A
| S/D of 1 pc Laptop & 4 others | [19 empty] | 15FPAO | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-11 | 2022-10-11 | 2022-10-26 | 2022-11-02 | 2022-11-02 | GoP | 78000 | 78000 | 0 | 76000 | 76000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of 1 set Valve cover gasket & 44 others | [19 empty] | 15FPAO | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-04 | 2022-11-04 | 2022-11-28 | 2022-12-01 | 2022-12-01 | GoP | 135000 | 135000 | 0 | 133750 | 133750 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of 1 unit Air-conditioned .5HP & 3 others | [19 empty] | 15FPAO | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-18 | 2022-10-18 | 2022-11-02 | 2022-11-03 | 2022-11-03 | GoP | 152640 | 152640 | 0 | 150640 | 150640 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of 2 pcs Laptop & 8 others | [19 empty] | 15FPAO | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-09 | 2022-08-09 | 2022-08-16 | 2022-08-22 | 2022-08-22 | GoP | 350000 | 350000 | 0 | 346200 | 346200 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| (30) Each Ball pen and Five (5) Line Item | [19 empty] | 12FPAO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-03-04 | 2022-03-16 | 2022-03-16 | 2022-03-17 | 2023-03-21 | GoP | 16841 | 16841 | 0 | 16841 | 16841 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Thirty Nine (39) Pcs Prepaid Card 500 (Smart) and One (1) Line Item | [19 empty] | 12FPAO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-03-04 | 2022-03-16 | 2022-03-16 | 2022-03-17 | 2022-03-21 | GoP | 19970 | 19970 | 0 | 19970 | 19970 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Thirty Two (32) Pack Coffee 3 in 1 and Twenty (20) Line Item | [19 empty] | 12FPAO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-03-04 | 2022-03-16 | 2022-03-16 | 2022-03-17 | 2022-03-21 | GoP | 54910 | 54910 | 0 | 54910 | 54910 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Two (2) Set Cup & Saucer and Seven (7) Line Item | [19 empty] | 12FPAO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-03-04 | 2022-03-16 | 2022-03-16 | 2022-03-17 | 2022-03-21 | GoP | 16694 | 16694 | 0 | 16694 | 16694 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Two (2) Set Cup & Saucer and Seven (7) Line Item | [19 empty] | 12 FPAO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-04-21 | 2022-05-25 | 2022-05-25 | 2022-05-26 | 2022-05-30 | GoP | 16681 | 16681 | 0 | 16681 | 16681 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| (13) Bottles Printer Epson Ink and Three (3) Line Item | [19 empty] | 12FPAO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-04-21 | 2022-05-25 | 2022-05-25 | 2022-05-26 | 2022-05-30 | GoP | 7165 | 7165 | 0 | 7165 | 7165 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Thirty One (31) Each Ball Pen and Six (6) Line Items | [19 empty] | 12FPAO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-04-21 | 2022-05-25 | 2022-05-25 | 2022-05-26 | 2022-05-30 | GoP | 5896 | 5896 | 0 | 5896 | 5896 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Thirty Nine (39) Pcs Prepaid Card 500 (Smart) and One (1) Line Item | [19 empty] | 12FPAO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-04-21 | 2022-05-25 | 2022-05-25 | 2022-05-26 | 2022-05-30 | GoP | 19977 | 19977 | 0 | 19977 | 19977 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Eight (8) Pack Bihon 500g and Fifteen (15) Line Item | [19 empty] | 12FPAO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-04-25 | 2022-05-25 | 2022-05-25 | 2022-05-26 | 2022-05-30 | GoP | 62222 | 62222 | 0 | 62222 | 62222 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Two (2) pack Biscuit and Fourteen (14) other line items | [19 empty] | 12FPAO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-07-11 | 2022-09-06 | 2022-09-06 | 2022-09-07 | 2022-09-08 | GoP | 60029 | 60029 | 0 | 60029 | 60029 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Two (2) set Cup & saucer and Seven (7) other line items | [19 empty] | 12FPAO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-07-11 | 2022-09-06 | 2022-09-06 | 2022-09-07 | 2022-09-08 | GoP | 16725 | 16725 | 0 | 16725 | 16725 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Thirty One (31) pcs Ball pen and Five (5) other line items | [19 empty] | 12FPAO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-07-11 | 2022-09-06 | 2022-09-06 | 2022-09-07 | 2022-09-08 | GoP | 4960 | 4960 | 0 | 4960 | 4960 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| One (1) unit Printer with scanner and One (1) other line items | [19 empty] | 12FPAO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-07-08 | 2022-09-06 | 2022-09-06 | 2022-09-07 | 2022-09-08 | GoP | 14800 | 14800 | 0 | 14800 | 14800 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Ten (10) Bottle Alcohol and Four (4) Line Items | [19 empty] | 12FPAO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-09-12 | 2022-11-17 | 2022-11-17 | 2022-11-23 | 2022-11-24 | GoP | 4920 | 4920 | 0 | 4920 | 4920 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Two (2) pack Biscuit and Fifteen (15) other line items | [19 empty] | 12FPAO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-09-13 | 2022-10-20 | 2022-10-20 | 2022-10-21 | 2022-10-24 | GoP | 92419 | 92419 | 0 | 92419 | 92419 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Two (2) Set Cup & Saucer and Seven (7) Line Item | [19 empty] | 12FPAO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-09-12 | 2022-10-20 | 2022-10-20 | 2022-10-21 | 2022-10-24 | GoP | 16681 | 16681 | 0 | 16681 | 16681 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Two (2) Each Mouse and Three (3) Line Items | [19 empty] | 12FPAO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-09-12 | 2022-10-20 | 2022-10-20 | 2022-10-21 | 2022-10-24 | GoP | 7250 | 7250 | 0 | 7250 | 7250 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Thirty One (31) Pcs Ball pen and Six (6) Line Items | [19 empty] | 12FPAO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-09-12 | 2022-10-20 | 2022-10-20 | 2022-10-21 | 2022-10-24 | GoP | 5924 | 5924 | 0 | 5924 | 5924 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| RM Building | [19 empty] | 4FPAO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-02-14 | 2022-02-14 | 2022-06-22 | 2022-06-28 | 2022-06-28 | GoP | 145000 | 145000 | 0 | 143516 | 143516 | 0 | [7 empty] | N/A
| Training Expenses | [19 empty] | 4FPAO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-08-18 | 2022-08-18 | 2022-10-27 | 2022-11-03 | 2022-11-03 | GoP | 100000 | 100000 | 0 | 96686 | 96686 | 0 | [7 empty] | N/A
5-02-99-030-00 | Assorted candies & 18 other | [19 empty] | 7FPAO | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-03-18 | 2022-05-13 | 2022-05-13 | 2022-05-24 | 2022-05-24 | GAA 2022 | 44000 | 44000 | 0 | 43105 | 43105 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-13-060-01 | Engine oil & 2 other | [19 empty] | 7FPAO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-05-11 | 2022-06-20 | 2022-06-20 | 2022-06-28 | 2022-06-28 | GAA 2022 | 12000 | 12000 | 0 | 11700 | 11700 | [8 empty] | Completed
5-02-03-010-00 | Computer ink black for Epson & 24 other | [19 empty] | 7FPAO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-06-03 | 2022-07-02 | 2022-07-02 | 2022-07-11 | 2022-07-11 | GAA 2022 | 94000 | 94000 | 0 | 93750 | 93750 | [8 empty] | Completed
5-02-12-050-02 | 5m 3/8" Coil Pipe Copper brass tube & 2 other | [19 empty] | 7FPAO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-06-03 | 2022-08-31 | 2022-08-31 | 2022-09-08 | 2022-09-08 | GAA 2022 | 11000 | 11000 | 0 | 10800 | 10800 | [8 empty] | Completed
5-02-03-210-03 | Computer desktop & 2 other | [19 empty] | 7FPAO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-06-14 | 2022-07-20 | 2022-07-20 | 2022-07-29 | 2022-07-29 | GAA 2022 | 34248 | 34248 | 0 | 34000 | 34000 | [8 empty] | Completed
5-02-05-020-01 | Cell Card Globe 500 & 1 other | [19 empty] | 7FPAO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-08-03 | 2022-08-31 | 2022-08-31 | 2022-09-08 | 2022-09-08 | GAA 2022 | 35000 | 35000 | 0 | 35000 | 35000 | [8 empty] | Completed
5-02-13-060-01 | Engine oil & 2 other | [19 empty] | 7FPAO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-08-03 | 2022-08-31 | 2022-08-31 | 2022-09-08 | 2022-09-08 | GAA 2022 | 12000 | 12000 | 0 | 11700 | 11700 | [8 empty] | Completed
5-02-13-040-01 | Cement 40kg & 16 other | [19 empty] | 7FPAO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-08-03 | 2022-09-05 | 2022-09-05 | 2022-09-14 | 2022-09-14 | GAA 2022 | 40000 | 40000 | 0 | 39200 | 39200 | [8 empty] | Completed
5-02-02-010-00 | Ballpen & 13 other | [19 empty] | 7FPAO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-08-03 | 2022-09-05 | 2022-09-05 | 2022-09-14 | 2022-09-14 | GAA 2022 | 16000 | 16000 | 0 | 15750 | 15750 | [8 empty] | Completed
5-02-13-050-03 | Anti Virus & 7 other | [19 empty] | 7FPAO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-08-03 | 2022-09-05 | 2022-09-05 | 2022-09-14 | 2022-09-14 | GAA 2022 | 22500 | 22500 | 0 | 22200 | 22200 | [8 empty] | Completed
5-02-03-010-00 | Bond Paper A4 & 35 other | [19 empty] | 7FPAO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-08-03 | 2022-09-05 | 2022-09-05 | 2022-11-10 | 2022-11-10 | GAA 2022 | 125100 | 125100 | 0 | 124370 | 124370 | [8 empty] | Completed
5-02-13-040-01 | Coco lumber 2x3x10 | [19 empty] | 7FPAO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-09-22 | 2022-09-05 | 2022-09-05 | 2022-11-11 | 2022-11-11 | GAA 2022 | 40000 | 40000 | 0 | 39570 | 39570 | [8 empty] | Completed
| S/D of 1 pc Laptop & 4 others | [19 empty] | 7 FPAO | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-11 | 2022-10-11 | 2022-10-26 | 2022-11-02 | 2022-11-02 | GoP | 78000 | 78000 | 0 | 76000 | 76000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of 1 set Valve cover gasket & 44 others | [19 empty] | 7 FPAO | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-04 | 2022-11-04 | 2022-11-28 | 2022-12-05 | 2022-12-05 | GoP | 135000 | 135000 | 0 | 133750 | 133750 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of 1 unit Air-conditioned .5HP & 3 others | [19 empty] | 7 FPAO | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-18 | 2022-10-18 | 2022-11-02 | 2022-11-09 | 2022-11-09 | GoP | 152640 | 152640 | 0 | 150640 | 150640 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of 125 pack Soda in can 330ml 3s & 10 others | [19 empty] | 7 FPAO | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-13 | 2022-09-13 | 2022-10-26 | 2022-11-02 | 2022-11-02 | GoP | 81250 | 81250 | 0 | 80992 | 80992 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of 2 ea Scanner-Single Function Printer (Monochrome) & 6 others | [19 empty] | 7 FPAO | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-31 | 2022-08-31 | 2022-10-14 | 2022-10-21 | 2022-10-21 | GoP | 70000 | 70000 | 0 | 69750 | 69750 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of 2 pcs Laptop & 8 others | [19 empty] | 7 FPAO | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-09 | 2022-08-09 | 2022-08-16 | 2022-08-23 | 2022-08-23 | GoP | 350000 | 350000 | 0 | 346200 | 346200 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of 2 units Desktop Intel Core i5-1100 & 6 others | [19 empty] | 7 FPAO | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-02 | 2022-09-02 | 2022-10-21 | 2022-10-28 | 2022-10-28 | GoP | 90000 | 90000 | 0 | 89500 | 89500 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of 48 pcs Ordinary Plywood 3/4"x4'x8' & 20 others | [19 empty] | 7FPAO | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-31 | 2022-08-31 | 2022-10-14 | 2022-10-21 | 2022-10-21 | GoP | 180000 | 180000 | 0 | 176040 | 176040 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-03-010-00 | Office Supplies Expenses | [19 empty] | 5FPAO | NO | Shopping 52.1 (b) | [8 empty] | 2022-05-05 | 26 May 22 | 26 May 22 | 2022-06-01 | 2022-06-01 | MOOE | 27000 | 27000 | 0 | 26823 | 26823
5-02-03-010-00 | Office Supplies Expenses | [19 empty] | 5FPAO | NO | Shopping 52.1 (b) | [8 empty] | 2022-10-03 | 07 Nov 22 | 07 Nov 22 | 2022-11-11 | 2022-11-11 | MOOE | 88750 | 88750 | 0 | 88080 | 88080
5-02-13-040-01 | S/D of 20 bags Cement &50 others | [19 empty] | 14FPAO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 02 Mar 22 | 02 Mar 22 | 08 Mar 22 | 14 Mar 22 | 14 Mar 22 | GoP | 132000 | 132000 | 0 | 131900 | 131900 | 0 | [7 empty] | N/A
5-02-03-010-00 | S/D of 7 pack Folder with Tab A4 & 26 others | [19 empty] | 14FPAO | NO | NP-52.1 (b) - Shopping | [8 empty] | 02 Mar 22 | 02 Mar 22 | 08 Mar 22 | 14 Mar 22 | 14 Mar 22 | GoP | 91800 | 91800 | 0 | 91735 | 91735 | 0
5-02-02-010-00 | S/D of 10 rms Bond Paper A4 Size | [19 empty] | 14FPAO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 02 Mar 22 | 02 Mar 22 | 08 Mar 22 | 14 Mar 22 | 14 Mar 22 | GoP | 35000 | 35000 | 0 | 34960 | 34960 | 0
5-02-03-210-01 | S/D of 1 ea KC1500 Portable Gasoline Generator & 1 other | [19 empty] | 14FPAO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 02 Mar 22 | 02 Mar 22 | 22 Mar 22 | 16 Mar 22 | 16 Mar 22 | GoP | 30000 | 30000 | 0 | 29950 | 29950 | 0
5-02-03-990-00 | S/D of 10 pack Coffee 3 in 1 &7 others | [19 empty] | 14FPAO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 30 Mar 22 | 30 Mar 22 | 13 Apr 22 | 18 Apr 22 | 18 Apr 22 | GoP | 18850 | 18850 | 0 | 18815 | 18815 | 0
5-02-03-990-00 | S/D of 10 pack Coffee 3 in 1 &12 others | [19 empty] | 14FPAO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 27 April 22 | 27 April 22 | 20 May 22 | 23 May 22 | 23 May 22 | GoP | 18850 | 18850 | 0 | 18715 | 18715 | 0
5-02-13-040-01 | S/D of 60 pcs Ceramic Floor Tiles 30x30 &30 others | [19 empty] | 14FPAO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 27 Apr 22 | 27 Apr 22 | 20 May 22 | 23 May 22 | 23 May 22 | GoP | 50000 | 50000 | 0 | 49700 | 49700 | 0
5-02-03-210-08 | S/D 4 ea Fire Extinguisher | [19 empty] | 14FPAO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 27 April 22 | 27 April 22 | 20 May 22 | 23 May 22 | 23 May 22 | GoP | 20000 | 20000 | 0 | 19840 | 19840 | 0
5-02-13-060-01 | S/D of 1 ea Air Filter & 5 others | [19 empty] | 14FPAO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 27 April 22 | 27 April 22 | 20 May 22 | 23 May 22 | 23 May 22 | GoP | 15000 | 15000 | 0 | 14920 | 14920 | 0
5-02-13-050-03 | S/D of 1 ea Processor Intel Core i5 | [19 empty] | 14FPAO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 27 April 22 | 27 April 22 | 20 May 22 | 23 May 22 | 23 May 22 | GoP | 12000 | 12000 | 0 | 11960 | 11960 | 0
5-02-03-050-02 | S/D of 2 ea Condenser & 6 othes | [19 empty] | 14FPAO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 27 April 22 | 27 April 22 | 20 May 22 | 23 May 22 | 23 May 22 | GoP | 15000 | 15000 | 0 | 14900 | 14900 | 0
5-02-03-990-00 | S/D of 10 pack Coffee 3 in 1 &9 others | [19 empty] | 14FPAO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 18 May 22 | 18 May 22 | 02 Jun 22 | 07 Jun 22 | 07 Jun 22 | GoP | 19000 | 19000 | 0 | 18905 | 18905 | 0
5-02-02-010-00 | S/D of 100 pcs Notebook & 29 others | [19 empty] | 14FPAO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 18 May 22 | 18 May 22 | 03 Jun 22 | 07 Jun 22 | 07 Jun 22 | GoP | 73000 | 73000 | 0 | 72810 | 72810 | 0
5-02-05-020-01 | S/D of 20 pcs Smart Prepaid Card & 1 other | [19 empty] | 14FPAO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 18 May 22 | 18 May 22 | 03 Jun 22 | 07 Jun 22 | 07 Jun 22 | GoP | 12000 | 12000 | 0 | 11920 | 11920 | 0
5-02-03-010-00 | S/D of 8 reams Paper, Multi Purpose Legal 70gsm & 26 others | [19 empty] | 14FPAO | NO | NP-52.1 (b) - Shopping | [8 empty] | 18 May 22 | 18 May 22 | 02 Jun 22 | 07 Jun 22 | 07 Jun 22 | GoP | 91800 | 91800 | 0 | 91450 | 91450 | 0
5-02-99-030-00 | S/D of 4 box Bottled Distilled Water 40 350ml & 13 others | [19 empty] | 14FPAO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 18 May 22 | 18 May 22 | 02 Jun 22 | 07 Jun 22 | 07 Jun 22 | GoP | 29000 | 29000 | 0 | 28550 | 28550 | 0
5-02-03-990-00 | S/D of 10 pack Coffee 3 in 1 &11 others | [19 empty] | 14FPAO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 02 Jun 22 | 02 Jun 22 | 15 Jun 22 | 18 Jun 22 | 18 Jun 22 | GoP | 18850 | 18850 | 0 | 18690 | 18690 | 0
5-02-03-990-00 | S/D of 10 box Brewed Coffee & 9 others | [19 empty] | 14FPAO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 17 Aug 22 | 17 Aug 22 | 06 Sep 22 | 08 Sep 22 | 08 Sep 22 | GoP | 19000 | 19000 | 0 | 18920 | 18920 | 0
5-02-99-030-00 | S/D of 4 box Bottled Distilled Water 40 350ml & 13 others | [19 empty] | 14FPAO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 17 Aug 22 | 17 Aug 22 | 06 Sep 22 | 08 Sep 22 | 08 Sep 22 | GoP | 29000 | 29000 | 0 | 28910 | 28910 | 0
5-02-05-020-01 | S/D of 20 pcs Smart Prepaid Card & 1 other | [19 empty] | 14FPAO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 17 Aug 22 | 17 Aug 22 | 06 Sep 22 | 08 Sep 22 | 08 Sep 22 | GoP | 12000 | 12000 | 0 | 11196 | 11196 | 0
5-02-03-010-00 | S/D of 100 pcs Permanent Marker & 26 others | [19 empty] | 14FPAO | NO | NP-52.1 (b) - Shopping | [8 empty] | 17 Aug 22 | 17 Aug 22 | 06 Sep 22 | 08 Sep 22 | 08 Sep 22 | GoP | 91800 | 91800 | 0 | 91680 | 91680 | 0
5-02-03-990-00 | S/D of 10 pack Coffee 3 in 1 &11 others | [19 empty] | 14FPAO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 21 Sep 22 | 21 Sep 22 | 17 Oct 22 | 24 Oct 22 | 24 Oct 22 | GoP | 18850 | 18850 | 0 | 18670 | 18670 | 0
5-02-03-210-12 | S/D of 1 ea Weightlifting Benach Press & 3 others | [19 empty] | 14FPAO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 26 Oct 22 | 26 Oct 22 | 06 Dec 22 | 09 Dec 22 | 09 Dec 22 | GoP | 13000 | 13000 | 0 | 13000 | 13000 | 0
5-02-03-210-03 | S/D of 1 ea Digital Camera | [19 empty] | 14FPAO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 26 Oct 22 | 26 Oct 22 | 06 Dec 22 | 09 Dec 22 | 09 Dec 22 | GoP | 30000 | 30000 | 0 | 29000 | 29000 | 0
5-02-02-010-00 | S/D of 15 rms Bond Paper A4 size & 29 others | [19 empty] | 14FPAO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 16 Nov 22 | 16 Nov 22 | 06 Dec 22 | 09 Dec 22 | 09 Dec 22 | GoP | 73000 | 73000 | 0 | 72810 | 72810 | 0
5-02-99-030-00 | S/D of 8 box Bottled Water & 14 others | [19 empty] | 14FPAO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 16 Nov 22 | 16 Nov 22 | 06 Dec 22 | 09 Dec 22 | 09 Dec 22 | GoP | 49000 | 49000 | 0 | 48800 | 48800 | 0
5-02-03-990-00 | S/D of 10 pack Coffee 3 in 1 & 9 others | [19 empty] | 14FPAO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 26 Oct 22 | 26 Oct 22 | 06 Dec 22 | 09 Dec 22 | 09 Dec 22 | GoP | 19000 | 19000 | 0 | 18900 | 18900 | 0
5-02-013-060-01 | S/D of 1 ea Rotor Disc & 5 others | [19 empty] | 14FPAO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 26 Oct 22 | 26 Oct 22 | 06 Dec 22 | 09 Dec 22 | 09 Dec 22 | GoP | 15000 | 15000 | 0 | 14997 | 14997 | 0
5-02-05-020-01 | S/D of 20 pcs Smart Prepaid Card & 1 other | [19 empty] | 14FPAO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 26 Oct 22 | 26 Oct 22 | 06 Dec 22 | 09 Dec 22 | 09 Dec 22 | GoP | 12000 | 12000 | 0 | 11880 | 11880 | 0
5-02-13-040-01 | S/D of 1 tin Flat Wall Latex | [19 empty] | 14FPAO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 26 Oct 22 | 26 Oct 22 | 06 Dec 22 | 09 Dec 22 | 09 Dec 22 | GoP | 20000 | 20000 | 0 | 19900 | 19900 | 0
5-02-03-010-00 | S/D of 6 cart Ink Cartridge Black & 32 others | [19 empty] | 14FPAO | NO | NP-52.1 (b) - Shopping | [8 empty] | 26 Oct 22 | 26 Oct 22 | 06 Dec 22 | 09 Dec 22 | 09 Dec 22 | GoP | 91800 | 91800 | 0 | 91662 | 91662 | 0
5-02-13-050-02 | S/D of 2 ea Condenser & 6 others | [19 empty] | 14FPAO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 26 Oct 22 | 26 Oct 22 | 06 Dec 22 | 09 Dec 22 | 09 Dec 22 | GoP | 15000 | 15000 | 0 | 14910 | 14910 | 0
5-02-13-050-03 | S/D of 1 ea Processor Core i5 & 3 other | [19 empty] | 14FPAO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 26 Oct 22 | 26 Oct 22 | 06 Dec 22 | 09 Dec 22 | 09 Dec 22 | GoP | 12000 | 12000 | 0 | 11940 | 11940 | 0
5-02-03-990-00 | S/D of 3 box Bottled Water & 11 others | [19 empty] | 14FPAO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 16 Nov 22 | 16 Nov 22 | 06 Dec 22 | 09 Dec 22 | 09 Dec 22 | GoP | 18750 | 18750 | 0 | 18600 | 18600 | 0
5-02-99-030-00 | S/D of 3 sack Rice & 11 others | [19 empty] | 14FPAO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 26 Oct 22 | 26 Oct 22 | 06 Dec 22 | 09 Dec 22 | 09 Dec 22 | GoP | 20000 | 20000 | 0 | 19995 | 19995 | 0
| S/D of 11 unit Copper Tube 5/8 of aircon.5HP | [19 empty] | 10FPAO | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-03-16 | 2022-03-16 | 2022-04-04 | 2022-04-07 | 2022-04-07 | GoP | 33000 | 33000 | 0 | 32725 | 32725 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of 2 ea Tire & 6 others | [19 empty] | 10FPAO | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-03-16 | 2022-03-16 | 2022-04-04 | 2022-04-07 | 2022-04-07 | GoP | 83600 | 83600 | 0 | 83100 | 83100 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of 1 set Split type Compressor & 1 other | [19 empty] | 10FPAO | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-03-16 | 2022-03-16 | 2022-03-31 | 2022-04-04 | 2022-04-04 | GoP | 31000 | 31000 | 0 | 30800 | 30800 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of 15 ea Plywood and 15 others | [19 empty] | 10FPAO | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-03-16 | 2022-03-16 | 2022-04-04 | 2022-04-07 | 2022-04-07 | GoP | 50450 | 50450 | 0 | 50085 | 50085 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of 30 Copier Paper A4 ultra white hard copy & 39 others | [19 empty] | 10FPAO | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-03-16 | 2022-03-16 | 2022-03-30 | 2022-04-04 | 2022-04-04 | GoP | 45000 | 45000 | 0 | 44777 | 44777 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of 2 ea Tire & 6 others | [19 empty] | 10FPAO | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-03-29 | 2022-03-29 | 2022-05-11 | 2022-05-16 | 2022-05-16 | GoP | 83600 | 83600 | 0 | 83070 | 83070 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of 2 ea Motherboard and 6 others | [19 empty] | 10FPAO | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-03-29 | 2022-03-29 | 2022-04-29 | 2022-05-02 | 2022-05-02 | GoP | 31000 | 31000 | 0 | 30700 | 30700 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of 16 ea Prepaid card , smart 500 & 3 others | [19 empty] | 10FPAO | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-03-29 | 2022-03-29 | 2022-04-29 | 2022-05-02 | 2022-05-02 | GoP | 20000 | 20000 | 0 | 19840 | 19840 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of 15 ea Plywood and 15 others | [19 empty] | 10FPAO | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-03-29 | 2022-03-29 | 2022-05-20 | 2022-05-23 | 2022-05-23 | GoP | 50450 | 50450 | 0 | 50249 | 50249 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of 4 ea Handrail (comfort room) | [19 empty] | 10FPAO | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-05-12 | 2022-05-12 | 2022-06-13 | 2022-06-15 | 2022-06-15 | GoP | 7600 | 7600 | 0 | 7400 | 7400 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of 2 ea Motherboard and 6 others | [19 empty] | 10FPAO | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-07-11 | 2022-07-11 | 2022-07-29 | 2022-08-01 | 2022-08-01 | GoP | 31000 | 31000 | 0 | 30800 | 30800 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of 2 set Screen window & 2 others | [19 empty] | 10FPAO | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-07-11 | 2022-07-11 | 2022-07-29 | 2022-08-01 | 2022-08-01 | GoP | 19000 | 19000 | 0 | 18800 | 18800 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of 15 ea Plywood and 15 others | [19 empty] | 10FPAO | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-07-11 | 2022-07-11 | 2022-08-04 | 2022-08-08 | 2022-08-08 | GoP | 50450 | 50450 | 0 | 50149 | 50149 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of 16 ea Prepaid card , smart 500 & 3 others | [19 empty] | 10FPAO | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-07-04 | 2022-07-04 | 2022-07-18 | 2022-07-20 | 2022-07-20 | GoP | 20000 | 20000 | 0 | 19840 | 19840 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of 20 gal Ethyl Alcohol & 2 others | [19 empty] | 10FPAO | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-07-04 | 2022-07-04 | 2022-07-18 | 2022-07-20 | 2022-07-20 | GoP | 20000 | 20000 | 0 | 19756 | 19756 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of 6 set Ink Brother Printer & 5 Others | [19 empty] | 10FPAO | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-07-11 | 2022-07-11 | 2022-01-29 | 2022-08-01 | 2022-08-01 | GoP | 35250 | 35250 | 0 | 35050 | 35050 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of 30 Copier Paper A4 ultra white hard copy & 39 others | [19 empty] | 10FPAO | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-07-11 | 2022-07-11 | 2022-07-29 | 2022-08-01 | 2022-08-01 | GoP | 45000 | 45000 | 0 | 44644 | 44644 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of 2 ea Handrail (comfort room) | [19 empty] | 10FPAO | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-27 | 2022-09-27 | 2022-11-08 | 2022-11-10 | 2022-11-10 | GoP | 3800 | 3800 | 0 | 3700 | 3700 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of 2 ea Motherboard and 6 others | [19 empty] | 10FPAO | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-27 | 2022-09-27 | 2022-10-19 | 2022-10-21 | 2022-10-21 | GoP | 31000 | 31000 | 0 | 30880 | 30880 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of 15 ea Plywood and 15 others | [19 empty] | 10FPAO | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-27 | 2022-09-27 | 2022-11-24 | 2022-11-28 | 2022-11-28 | GoP | 50450 | 50450 | 0 | 50229 | 50229 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of 16 ea Prepaid card , smart 500 & 3 others | [19 empty] | 10FPAO | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-27 | 2022-09-27 | 2022-10-19 | 2022-10-21 | 2022-10-21 | GoP | 20000 | 20000 | 0 | 19840 | 19840 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of 20 gal Ethyl Alcohol & 2 others | [19 empty] | 10FPAO | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-27 | 2022-09-27 | 2022-10-19 | 2022-10-21 | 2022-10-21 | GoP | 20000 | 20000 | 0 | 19820 | 19820 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of 30 Copier Paper A4 ultra white hard copy & 39 others | [19 empty] | 10FPAO | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-27 | 2022-09-27 | 2022-11-24 | 2022-11-28 | 2022-11-28 | GoP | 45000 | 45000 | 0 | 44769 | 44769 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of 2 ea Handrail (comfort room ) | [19 empty] | 10FPAO | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-13 | 2022-12-13 | 2022-12-20 | 2022-12-22 | 2022-12-22 | GoP | 3800 | 3800 | 0 | 3700 | 3700 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of 10 loaf Bread Classic white and 12 others | [19 empty] | 10FPAO | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-04-11 | 2022-04-11 | 2022-04-29 | 2022-05-02 | 2022-05-02 | GoP | 18750 | 18750 | 0 | 18500 | 18500 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of 10 loaf Bread Classic white and 12 others | [19 empty] | 10FPAO | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-05-31 | 2022-05-31 | 2022-06-21 | 2022-06-23 | 2022-06-23 | GoP | 18750 | 18750 | 0 | 18530 | 18530 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of Internet Cards | [19 empty] | 8FPAO | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-03-10 | 2022-03-10 | 2022-03-31 | 2022-04-07 | 2022-04-07 | GoP | 5700 | 5700 | 0 | 5700 | 5700 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of Cell Cards | [19 empty] | 8FPAO | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-03-10 | 2022-03-10 | 2022-03-31 | 2022-04-07 | 2022-04-07 | GoP | 35000 | 35000 | 0 | 35000 | 35000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of Office Supplies | [19 empty] | 8FPAO | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-03-10 | 2022-03-10 | 2022-04-04 | 2022-04-12 | 2022-04-12 | GoP | 35000 | 35000 | 0 | 35000 | 35000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of Internet Cards | [19 empty] | 8FPAO | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-05-23 | 2022-05-23 | 2022-06-21 | 2022-06-24 | 2022-06-24 | GoP | 5700 | 5700 | 0 | 5700 | 5700 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of Cell Cards | [19 empty] | 8FPAO | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-05-23 | 2022-05-23 | 2022-06-21 | 2022-06-24 | 2022-06-24 | GoP | 35000 | 35000 | 0 | 35000 | 35000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of Office Supplies | [19 empty] | 8FPAO | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-05-23 | 2022-05-23 | 2022-06-22 | 2022-06-30 | 2022-06-30 | GoP | 35000 | 35000 | 0 | 35000 | 35000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of Internet Cards | [19 empty] | 8FPAO | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-01 | 2022-08-01 | 2022-09-21 | 2022-09-26 | 2022-09-26 | GoP | 5700 | 5700 | 0 | 5700 | 5700 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of Cell Cards | [19 empty] | 8FPAO | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-01 | 2022-08-01 | 2022-09-21 | 2022-09-26 | 2022-09-26 | GoP | 35000 | 35000 | 0 | 35000 | 35000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of Office Supplies | [19 empty] | 8FPAO | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-01 | 2022-08-01 | 2022-09-27 | 2022-09-30 | 2022-09-30 | GoP | 35000 | 35000 | 0 | 35000 | 35000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of Internet Cards | [19 empty] | 8FPAO | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-15 | 2022-10-15 | 2022-12-07 | 2022-12-12 | 2022-12-12 | GoP | 5700 | 5700 | 0 | 5700 | 5700 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of Cell Cards | [19 empty] | 8FPAO | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-13 | 2022-10-13 | 2022-12-07 | 2022-12-12 | 2022-12-12 | GoP | 35000 | 35000 | 0 | 35000 | 35000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of Office Supplies | [19 empty] | 8FPAO | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-19 | 2022-10-19 | 2022-12-12 | 2022-12-19 | 2022-12-19 | GoP | 35000 | 35000 | 0 | 35000 | 35000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
02-018 | S/D of 1 pc Curtain & 12 others | [19 empty] | 16FPAO | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-02-18 | N/A | 2022-03-03 | 2022-03-04 | 2022-03-04 | MOOE | 28800 | 28800 | 0 | 28640 | 28640 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
02-019 | S/D of 2 pc Motherboard & 7 others | [19 empty] | 16FPAO | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-02-18 | N/A | 2022-03-03 | 2022-03-04 | 2022-03-04 | MOOE | 38000 | 38000 | 0 | 37848 | 37848 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
02-023 | S/D of 15 Gallons of Metal Primer & 28 others | [19 empty] | 16FPAO | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-02-21 | N/A | 2022-03-03 | 2022-03-04 | 2022-03-04 | MOOE | 95000 | 95000 | 0 | 94923 | 94923 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
03-026 | S/D of 1pc Curtain & 10 others | [19 empty] | 16FPAO | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-03-01 | N/A | 2022-03-14 | 2022-03-17 | 2022-03-17 | MOOE | 16000 | 16000 | 0 | 15895 | 15895 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
03-029 | S/D of 1 Unit Laptop & 5 others | [19 empty] | 16FPAO | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-03-01 | N/A | 2022-03-14 | 2022-03-17 | 2022-03-17 | MOOE | 38200 | 38200 | 0 | 38098 | 38098 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
03-030 | S/D of 2pcs Motherboard & 7 others | [19 empty] | 16FPAO | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-03-01 | N/A | 2022-03-14 | 2022-03-18 | 2022-03-18 | MOOE | 38000 | 38000 | 0 | 37820 | 37820 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
03-043 | S/D of 15 Pack Biscuit Assrted Flavored 30gms & 55 others | [19 empty] | 16FPAO | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-03-04 | N/A | 2022-03-21 | 2022-03-22 | 2022-03-22 | MOOE | 55000 | 55000 | 0 | 54834 | 54834 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
03-057 | S/D of 1 unit Laptop & 5 others | [19 empty] | 16FPAO | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-03-07 | N/A | 2022-03-23 | 2022-03-24 | 2022-03-24 | MOOE | 76000 | 76000 | 0 | 75884 | 75884 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
03-074 | S/D of 100 Ream A4 Bond Paper & 72 others | [19 empty] | 16FPAO | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-03-11 | N/A | 2022-03-24 | 2022-03-28 | 2022-03-28 | MOOE | 115891.74 | 115891.74 | 0 | 115636.5 | 115636.5 | 0 | [7 empty] | COMPLETED
04-165 | S/D of 100 Ream A4 Bond Paper & 75 others | [19 empty] | 16FPAO | NO | Shopping 52.1b | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-04-11 | N/A | 2022-04-22 | 2022-04-26 | 2022-04-26 | MOOE | 117000 | 117000 | 0 | 116825.25 | 116825.25 | 0 | [7 empty] | COMPLETED
05-237 | S/D of 2 unit Air Condition & 2 others | [19 empty] | 16FPAO | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-05-18 | N/A | 2022-06-02 | 2022-06-06 | 2022-06-06 | MOOE | 36000 | 36000 | 0 | 35891 | 35891 | 0 | [7 empty] | COMPLETED
05-240 | S/D of 1pc Curtain & 10 others | [19 empty] | 16FPAO | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-05-18 | N/A | 2022-06-02 | 2022-06-06 | 2022-06-06 | MOOE | 16000 | 16000 | 0 | 15883 | 15883 | 0 | [7 empty] | COMPLETED
05-246 | S/D of 1 unit Desktop Computer & 4 others | [19 empty] | 16FPAO | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-05-20 | N/A | 2022-06-09 | 2022-06-16 | 2022-06-16 | MOOE | 32248 | 32248 | 0 | 32042 | 32042 | 0 | [7 empty] | COMPLETED
05-247 | S/D of 2 pcs Motherboard & 7 others | [19 empty] | 16FPAO | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-05-20 | N/A | 2022-06-16 | 2022-06-17 | 2022-06-17 | MOOE | 38000 | 38000 | 0 | 37841 | 37841 | 0 | [7 empty] | COMPLETED
06-282 | S/D of 1pc Plaque(Instructor & GOHAS) & 27 others | [19 empty] | 16FPAO | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-06-16 | N/A | 2022-07-25 | 2022-07-27 | 2022-07-27 | MOOE | 17000 | 17000 | 0 | 16947 | 16947 | 0 | [7 empty] | COMPLETED
06-303 | S/D of 50 ream A4 Bond Paper & 60 others | [19 empty] | 16FPAO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-06-28 | N/A | 2022-07-22 | 2022-07-25 | 2022-07-25 | MOOE | 95938.82 | 95938.82 | 0 | 95814 | 95814 | 0 | [7 empty] | COMPLETED
09-370 | S/D of 2 unit of Air Condition & 2 others | [19 empty] | 16FPAO | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-06 | N/A | 2022-09-16 | 2022-09-20 | 2022-09-20 | MOOE | 36000 | 36000 | 0 | 35893 | 35893 | 0 | [7 empty] | COMPLETED
09-371 | S/D of 1pc Curtain & 10 others | [19 empty] | 16FPAO | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-06 | N/A | 2022-09-16 | 2022-09-20 | 2022-09-20 | MOOE | 16000 | 16000 | 0 | 15930 | 15930 | 0 | [7 empty] | COMPLETED
09-384 | S/D of 14meters Box Gutter .40mm x18x8 & 28 others | [19 empty] | 16FPAO | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-09 | N/A | 2022-09-21 | 2022-09-23 | 2022-09-23 | MOOE | 85000 | 85000 | 0 | 84836 | 84836 | 0 | [7 empty] | COMPLETED
09-385 | S/D of 2pc Brake Shoe Hold Down Springs & 14 others | [19 empty] | 16FPAO | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-09 | N/A | 2022-09-22 | 2022-09-23 | 2022-09-23 | MOOE | 70000 | 70000 | 0 | 69884 | 69884 | 0 | [7 empty] | COMPLETED
09-387 | S/D of 15 Pack Biscuit Assrted Flavored 30gms 10s & 58 others | [19 empty] | 16FPAO | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-13 | N/A | 2022-10-07 | 2022-10-11 | 2022-10-11 | MOOE | 61000 | 61000 | 0 | 59907.5 | 59907.5 | 0 | [7 empty] | COMPLETED
10-434 | S/D of 100 Ream A4 Bond Paper & 71 others | [19 empty] | 16FPAO | NO | Shopping 52.1b | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-03 | N/A | 2022-11-03 | 2022-11-07 | 2022-11-07 | MOOE | 115852.14 | 115852.14 | 0 | 115671 | 115671 | 0 | [7 empty] | COMPLETED
10-460 | S/D of 1pc Plaque(Instructor & GOHAS) & 27 others | [19 empty] | 16FPAO | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-20 | N/A | 2022-11-09 | 2022-11-11 | 2022-11-11 | MOOE | 17000 | 17000 | 0 | 16935 | 16935 | 0 | [7 empty] | COMPLETED
| 6 ea Fuel Filter & 8 others | [19 empty] | 6FPAO | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-06-28 | 2022-06-28 | 2022-07-11 | 2022-07-25 | 2022-07-27 | GoP | 50000 | 50000 | 0 | 40000 | 40000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| 45 roll concertina wire & 2 others | [19 empty] | 6FPAO | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-03-28 | 2022-03-28 | 2022-03-31 | 2022-04-11 | 2022-04-13 | GoP | 58000 | 58000 | 0 | 55000 | 55000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| 10 pcs Steel Pipe & 10 bxs Welding rod | [19 empty] | 6FPAO | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-06-28 | 2022-06-28 | 2022-07-07 | 2022-07-25 | 2022-07-27 | GoP | 12800 | 12800 | 0 | 12000 | 12000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| 2 ea Motherboard & 3 others | [19 empty] | 6FPAO | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-11 | 2022-10-11 | 2022-10-20 | 2022-11-07 | 2022-11-09 | GoP | 55000 | 55000 | 0 | 45000 | 45000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| 4 units Stand Fan & 3 others | [19 empty] | 6FPAO | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-06-08 | 2022-06-08 | 2022-06-13 | 2022-06-21 | 2022-06-21 | GoP | 50000 | 50000 | 0 | 40000 | 40000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| 4 units Refill of Fire Extinguisher | [19 empty] | 6FPAO | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-04-11 | 2022-04-11 | 2022-04-19 | 2022-04-28 | 2022-05-02 | GoP | 16100 | 16100 | 0 | 14000 | 14000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| 30 pcs Notebooks & 19 others | [19 empty] | 6FPAO | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-05-27 | 2022-05-27 | 2022-06-16 | 2022-06-24 | 2022-06-24 | GoP | 32000 | 32000 | 0 | 28000 | 28000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| 7 rms Bondpapers & 5 others | [19 empty] | 6FPAO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-06-28 | 2022-06-28 | 2022-07-11 | 2022-07-25 | 2022-07-27 | GoP | 20000 | 20000 | 0 | 18000 | 18000 | 0
| 12 btls Computer Ink & 7 others | [18 empty] | 6FPAO | 6FPAO | NO | NP-53.9 - Small Value Procurement | [7 empty] | 2022-05-27 | 2022-05-27 | 2022-05-27 | 2022-06-13 | 2022-06-21 | 2022-06-21 | GoP | 18000 | 18000 | 0 | 17000 | 17000 | 0
| 4 ea Record Book 500p & 12 others | [19 empty] | 6FPAO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-10-11 | 2022-10-11 | 2022-10-20 | 2022-11-07 | 2022-11-09 | GoP | 18000 | 18000 | 0 | 17000 | 17000 | 0
| 4 set Refill Ink (T664 and colored) L360 printer & 12 others | [19 empty] | 6FPAO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-04-25 | 2022-04-25 | 2022-05-05 | 2022-05-18 | 2022-05-20 | GoP | 18000 | 18000 | 0 | 17000 | 17000 | 0
| 11 ea Globe prepaid card & 4 ea Smart prepaid Card | [19 empty] | 6FPAO | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-03-28 | 2022-03-28 | 2022-03-31 | 2022-04-11 | 2022-04-13 | GoP | 11800 | 11800 | 0 | 11000 | 11000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R/M Motor Vehicles | [19 empty] | 17FPAO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-02-11 | 2022-02-11 | 2022-03-04 | 2022-03-18 | 2022-03-18 | MOOE | 36866 | 36866 | 0 | 36800 | 36800 | 0 | [7 empty] | N/A
| R/M Office Eqpmt | [19 empty] | 17FPAO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-02-11 | 2022-02-11 | 2022-03-04 | 2022-03-18 | 2022-03-18 | MOOE | 15960 | 15960 | 0 | 15900 | 15900 | 0 | [7 empty] | N/A
| DRRE | [19 empty] | 17FPAO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-02-11 | 2022-02-11 | 2022-03-04 | 2022-03-18 | 2022-03-18 | MOOE | 5700 | 5700 | 0 | 5652 | 5652 | 0 | [7 empty] | N/A
| R/M ICT Eqpmt | [19 empty] | 17FPAO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-03-29 | 2022-03-29 | 2022-05-27 | 2022-06-10 | 2022-06-10 | MOOE | 27000 | 27000 | 0 | 26800 | 26800 | 0 | [7 empty] | N/A
| R/M Bldg | [19 empty] | 17FPAO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-04-27 | 2022-04-27 | 2022-05-20 | 2022-06-03 | 2022-06-03 | MOOE | 185380 | 185380 | 0 | 184480 | 184480 | 0 | [7 empty] | N/A
| R/M Motor Vehicles | [19 empty] | 17FPAO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-08-13 | 2022-08-13 | 2022-11-08 | 2022-11-22 | 2022-11-22 | MOOE | 36866 | 36866 | 0 | 36640 | 36640 | 0 | [7 empty] | N/A
| R/M Bldg | [19 empty] | 17FPAO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-08-13 | 2022-08-13 | 2022-10-14 | 2022-10-28 | 2022-10-28 | MOOE | 138513 | 138513 | 0 | 138013 | 138013 | 0 | [7 empty] | N/A
| Other Structures | [19 empty] | 17FPAO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-09-05 | 2022-09-05 | 2022-10-14 | 2022-10-28 | 2022-10-28 | MOOE | 117565 | 117565 | 0 | 116985 | 116985 | 0 | [7 empty] | N/A
| R/M Office Eqpmt | [19 empty] | 17FPAO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-11-19 | 2022-11-19 | 2022-12-28 | 2022-12-28 | 2022-12-28 | MOOE | 15960 | 15960 | 0 | 15870 | 15870 | 0 | [7 empty] | N/A
| R/M ICT Eqpmt | [19 empty] | 17FPAO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-11-19 | 2022-11-19 | 2022-12-28 | 2022-12-28 | 2022-12-28 | MOOE | 27000 | 27000 | 0 | 26820 | 26820 | 0 | [7 empty] | N/A
5-02-13-050-03 | ICT Supplies, Parts & Accessories | [19 empty] | 2FPAO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-03-11 | 2022-03-11 | 2022-03-30 | 2022-04-05 | 2022-04-05 | MOOE | 50000 | 50000 | 0 | 49945 | 49945 | 0 | [7 empty] | N/A
5-02-99-030-00 | Representation Exp/Food Supplies | [19 empty] | 2FPAO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-03-11 | 2022-03-11 | 2022-04-05 | 2022-04-07 | 2022-04-07 | MOOE | 42500 | 42500 | 0 | 42460 | 42460 | 0 | [7 empty] | N/A
5-02-13-060-01 | Vehicle Parts & Accessories | [19 empty] | 2FPAO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-05-10 | 2022-05-10 | 2022-05-30 | 2022-06-02 | 2022-06-02 | MOOE | 40000 | 40000 | 3 | 38500 | 38500 | 0 | [7 empty] | N/A
5-02-13-040-01 | Construction Materials & Supplies | [19 empty] | 2FPAO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-05-17 | 2022-05-17 | 2022-06-07 | 2022-06-08 | 2022-06-08 | MOOE | 70000 | 70000 | 0 | 68685 | 68685 | 0 | [7 empty] | N/A
5-02-13-050-03 | ICT Supplies, Parts & Accessories | [19 empty] | 2FPAO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-05-17 | 2022-05-17 | 2022-05-30 | 2022-06-05 | 2022-06-05 | MOOE | 50055 | 50055 | 5 | 50025 | 50025 | 0 | [7 empty] | N/A
5-02-99-030-00 | Representation Expenses | [19 empty] | 2FPAO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-05-19 | 2022-05-19 | 2022-05-27 | 2022-05-31 | 2022-05-31 | MOOE | 42540 | 42540 | 6 | 36808 | 36808 | 0 | [7 empty] | N/A
5-02-99-030-00 | Representation Expenses | [19 empty] | 2FPAO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-07-06 | 2022-07-06 | 2022-07-15 | 2022-07-19 | 2022-07-19 | MOOE | 42500 | 42500 | 0 | 39832 | 39832 | 0 | [7 empty] | N/A
5-02-13-050-03 | R&M-ICT Equipment | [19 empty] | 2FPAO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-07-08 | 2022-07-08 | 2022-07-19 | 2022-07-21 | 2022-07-21 | MOOE | 50000 | 50000 | 8 | 49950 | 49950 | 0 | [7 empty] | N/A
5-02-05-020-01 | Telephone Expenses-Mobile | [19 empty] | 2FPAO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-07-28 | 2022-07-28 | 2022-08-10 | 2022-08-12 | 2022-08-12 | MOOE | 40000 | 40000 | 0 | 39940 | 39940 | 0 | [7 empty] | N/A
5-02-03-210-03 | R&M-ICT Equipment | [19 empty] | 2FPAO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-09-26 | 2022-09-26 | 2022-11-08 | 2022-11-10 | 2022-11-10 | MOOE | 18750 | 18750 | 0 | 18700 | 18700 | 0 | [7 empty] | N/A
5-02-03-210-03 | Semi-Expendable-ICT Equipment | [19 empty] | 2FPAO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-10-17 | 2022-10-17 | 2022-11-08 | 2022-11-10 | 2022-11-10 | MOOE | 18750 | 18750 | 0 | 18700 | 18700 | 0 | [7 empty] | N/A
5-02-03-990-00 | Other Supplies & Materials | [19 empty] | 2FPAO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-10-17 | 2022-10-17 | 2022-10-27 | 2022-11-02 | 2022-11-02 | MOOE | 40000 | 40000 | 0 | 39240 | 39240 | 0 | [7 empty] | N/A
5-02-05-020-01 | Telephone Expense-Mobile | [19 empty] | 2FPAO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-10-17 | 2022-10-17 | 2022-10-27 | 2022-11-02 | 2022-11-02 | MOOE | 40000 | 40000 | 0 | 39950 | 39950 | 0 | [7 empty] | N/A
5-02-05-020-01 | R&M-ICT Equipment | [19 empty] | 2FPAO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-11-10 | 2022-11-10 | 2022-11-29 | 2022-11-02 | 2022-11-02 | MOOE | 50000 | 50000 | 0 | 49940 | 49940 | 0 | [7 empty] | N/A
| Prepared By: | [32 empty] | Certified By: | [6 empty] | Noted By:
| Mark Kevin T Maramag | [32 empty] | MS ELSIE R RUBIO,MBA | [6 empty] | MS EVANGELINE M SINGUEO PhD
| Assistant Budget Clerk | [32 empty] | Administrative Officer V | [6 empty] | Chief Administrative Officer
[34 empty] | Chief MFO | [6 empty] | Chief APAO,PA
Formulas:
Contract Signing = [Notice to Proceed]

## Sheet1 (hidden)
Competitive Bidding | GoP | YES
Limited Source Bidding | Foreign | NO
Direct Contracting | Special Purpose Fund
Repeat Order | Corporate Budget
Shopping | Income
NP-53.1 Two Failed Biddings | Others
NP-53.2 Emergency Cases
NP-53.3 Take-Over of Contracts
NP-53.4 Adjacent or Contiguous
NP-53.5 Agency-to-Agency
NP-53.6 Scientific, Scholarly, Artistic Work, Exclusive Technology and Media Services
NP-53.7 Highly Technical Consultants
NP-53.8 Defense Cooperation Agreement
NP-53.9 - Small Value Procurement
NP-53.10 Lease of Real Property and Venue
NP-53.11 NGO Participation
NP-53.12 Community Participation
NP-53.13 UN Agencies, Int'l Organizations or International Financing Institutions
Others - Foreign-funded procurement