## pmr
|  | ANNEX A | [18 empty] | ANNEX B
|  | Department of Budget and Management Annual Procurement Plan for FY 2006 | [18 empty] | (APMC) Procurement Monitoring Report as of December 31, 2022
Code (PAP) | Procurement Project | PMO/ End-User | Mode of Procurement | Schedule for Each Procurement Activity | [11 empty] | Source of Funds | ABC (PhP) |  |  | Remarks (brief description of Program/Project) | PMO/ End-User | Is this an Early Procurement Activity? | Mode of Procurement | Actual Procurement Activity | [12 empty] | Source of Funds | ABC (PhP) |  |  | Contract Cost (PhP) |  |  | List of Invited Observers | Date of Receipt of Invitation | [5 empty] | Remarks (Explaining changes from the APP)
|  |  |  | Pre-Proc Conference | Ads/Post of IAEB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Contract Award | Contract Signing | Notice to Proceed | Delivery/ Accept | Payment Process |  | Total | MOOE | CO |  |  |  |  | Pre-Proc Conference | Ads/Post of IB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Date of BAC Resolution Recommending Award | Notice of Award | Contract Signing | Notice to Proceed | Delivery/ Completion | Inspection & Acceptance |  | Total | MOOE | CO | Total | MOOE | CO |  | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Delivery/ Completion/ Acceptance (If applicable)
COMPLETED PROCUREMENT ACTIVITIES
5-02-99-030-00 | CATERING SERVICES | [19 empty] | APMC | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-07-15 | 2022-07-15 | 2022-09-07 | 2022-09-14 | 2022-09-14 | GoP | 916000 | 916000 | 0 | 908000 | 908000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-13-040-01 | S/D of 76 sq.mtrs Pre-painted RFG Sht .05mm thk (Rib Type) & 93 Others | [19 empty] | APMC | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-07-19 | 2022-07-19 | 2022-09-05 | 2022-09-12 | 2022-09-12 | GoP | 880000 | 880000 | 0 | 872685 | 872685 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-99-030-00 | CATERING SERVICES | [19 empty] | APMC | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-07-29 | 2022-07-29 | 2022-09-23 | 2022-09-30 | 2022-09-30 | GoP | 676070 | 676070 | 0 | 670500 | 670500 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-13-040-01 | S/D 22 pcs Angle Bar (fascia frame) 1" x 1" x 1/8" and 67 others | [19 empty] | APMC | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-07-29 | 2022-07-29 | 2022-09-23 | 2022-09-30 | 2022-09-30 | GoP | 999385 | 999385 | 0 | 975395 | 975395 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-13-040-01 | S/D of 455 pcs Metal furring 1"x 2" x 16' & 67 others | [19 empty] | APMC | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-03-22 | 2022-03-22 | 2022-08-10 | 2022-08-17 | 2022-08-17 | GoP | 800000 | 800000 | 0 | 795798 | 795798 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5--02-99-050-04 | RENTAL SERVICES | [19 empty] | APMC | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-24 | 2022-08-24 | 2022-11-02 | 2022-11-09 | 2022-11-09 | GoP | 84000 | 84000 | 0 | 81000 | 81000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5--02-99-050-04 | RENTAL SERVICES | [19 empty] | APMC | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-24 | 2022-08-24 | 2022-11-02 | 2022-11-09 | 2022-11-09 | GoP | 102000 | 102000 | 0 | 99000 | 99000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-13-040-01 | S/D of 52 pcs Hardiflex 1/4" x4 x 8' and 24 Others | [19 empty] | APMC | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-31 | 2022-08-31 | 2022-11-02 | 2022-11-09 | 2022-11-09 | GoP | 100000 | 100000 | 0 | 99313 | 99313 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-99-030-00 | CATERING SERVICES | [19 empty] | APMC | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-13 | 2022-09-13 | 2022-12-14 | 2022-12-21 | 2022-12-21 | GoP | 716500 | 716500 | 0 | 714400 | 714400 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5--02-99-050-04 | RENTAL SERVICES | [19 empty] | APMC | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-30 | 2022-09-30 | 2022-10-26 | 2022-11-02 | 2022-11-02 | GoP | 84000 | 84000 | 0 | 81000 | 81000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5--02-99-050-04 | RENTAL SERVICES | [19 empty] | APMC | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-30 | 2022-09-30 | 2022-10-26 | 2022-11-02 | 2022-11-02 | GoP | 102000 | 102000 | 0 | 99000 | 99000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-03-990-00 | S/D of 1200 pcs Mineral Water 500ml & 16 Others | [19 empty] | APMC | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-11 | 2022-10-11 | 2022-10-26 | 2022-11-02 | 2022-11-02 | GoP | 307410 | 307410 | 0 | 305275 | 305275 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-13-040-01 | S/D of 52 pcs Hardiflex 1/4"x4'x8' and 24 Others | [19 empty] | APMC | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-11 | 2022-10-11 | 2022-12-02 | 2022-12-09 | 2022-12-09 | GoP | 100000 | 100000 | 0 | 98120 | 98120 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-99-030-00 | S/D of 121 pck Choco Chip Delight Cookies 600g 18 Others | [19 empty] | APMC | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-04 | 2022-11-04 | 2022-11-28 | 2022-12-05 | 2022-12-05 | GoP | 520496 | 520496 | 0 | 518496 | 518496 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-05-020-01 | S/D of 250 pcs Globe Cellcards 500 and 3 Others | [19 empty] | APMC | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-09 | 2022-11-09 | 2022-11-28 | 2022-12-05 | 2022-12-05 | GoP | 310600 | 310600 | 0 | 309600 | 309600 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Total Alloted Budget of Procurement Activities | [37 empty] | 6698461
Total Contract Price of Procurement Actitvites Conducted | [40 empty] | 6627582
Total Savings (Total Alloted Budget - Total Contract Price) | [37 empty] | 70879
0N-GOING PROCUREMENT ACTIVITIES
| S/D of 200 box Bottle Water 500ml and 18 Others | [19 empty] | APMC | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-24 | 2022-11-24 | N/A | N/A | N/A | GoP | 387070 | 387070 | 0 | 386370 | 386370 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Total Alloted Budget of On-going Procurement Activities | [37 empty] | 387070
| Prepared by: | [32 empty] | Certified Correct By | [6 empty] | Noted By
| Reynato F Borbo | [32 empty] | DEOREYNO JAY J MANIWANG | [6 empty] | PATRICK B DE VILLA
| Sgt (OS) PA | [32 empty] | Major (QMS) PA | [6 empty] | Colonel INF (GSC) PA
| Logistics NCO | [32 empty] | Logistics Officer | [6 empty] | Director

## Sheet1 (hidden)
Competitive Bidding | GoP | YES
Limited Source Bidding | Foreign | NO
Direct Contracting | Special Purpose Fund
Repeat Order | Corporate Budget
Shopping | Income
NP-53.1 Two Failed Biddings | Others
NP-53.2 Emergency Cases
NP-53.3 Take-Over of Contracts
NP-53.4 Adjacent or Contiguous
NP-53.5 Agency-to-Agency
NP-53.6 Scientific, Scholarly, Artistic Work, Exclusive Technology and Media Services
NP-53.7 Highly Technical Consultants
NP-53.8 Defense Cooperation Agreement
NP-53.9 - Small Value Procurement
NP-53.10 Lease of Real Property and Venue
NP-53.11 NGO Participation
NP-53.12 Community Participation
NP-53.13 UN Agencies, Int'l Organizations or International Financing Institutions
Others - Foreign-funded procurement