## pmr
|  | ANNEX A | [18 empty] | ANNEX B
|  | Department of Budget and Management Annual Procurement Plan for FY 2006 | [18 empty] | FSRR, PA Procurement Monitoring Report as of 23 December 2022
Code (PAP) | Procurement Project | PMO/ End-User | Mode of Procurement | Schedule for Each Procurement Activity | [11 empty] | Source of Funds | ABC (PhP) |  |  | Remarks (brief description of Program/Project) | PMO/ End-User | Is this an Early Procurement Activity? | Mode of Procurement | Actual Procurement Activity | [12 empty] | Source of Funds | ABC (PhP) |  |  | Contract Cost (PhP) |  |  | List of Invited Observers | Date of Receipt of Invitation | [5 empty] | Remarks (Explaining changes from the APP)
|  |  |  | Pre-Proc Conference | Ads/Post of IAEB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Contract Award | Contract Signing | Notice to Proceed | Delivery/ Accept | Payment Process |  | Total | MOOE | CO |  |  |  |  | Pre-Proc Conference | Ads/Post of IB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Date of BAC Resolution Recommending Award | Notice of Award | Contract Signing | Notice to Proceed | Delivery/ Completion | Inspection & Acceptance |  | Total | MOOE | CO | Total | MOOE | CO |  | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Delivery/ Completion/ Acceptance (If applicable)
COMPLETED PROCUREMENT ACTIVITIES
5-02-99-030-00 | Representation Expenses | [19 empty] | FSRR, PA | NO | Shopping 52.1a | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-02-19 | N/A | 2022-03-18 | 2022-03-23 | 2022-03-23 | GoP | 609611 | 609611 |  | 609611 | 609611 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-99-030-00 | Representation Expenses | [19 empty] | FSRR, PA | NO | Shopping 52.1a | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-03-29 | N/A | 2022-04-27 | 2022-05-02 | 2022-05-02 | GoP | 1299393 | 1299393 |  | 1299393 | 1299393 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-03-010-00 | Office Supplies | [19 empty] | FSRR, PA | NO | Negotiated 53.5 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-03-03 | N/A | 2022-03-28 | 2022-04-01 | 2022-04-01 | GoP | 44712 | 44712 |  | 44712 | 44712 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-03-010-00 | Office Supplies | [19 empty] | FSRR, PA | NO | Negotiated 53.5 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-05-05 | N/A | 2022-05-30 | 2022-06-02 | 2022-06-02 | GoP | 37287.2 | 37287.2 |  | 37287.2 | 37287.2 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-03-070-00 | Drugs and Medicines | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-02-15 | N/A | 2022-03-18 | 2022-03-22 | 2022-03-22 | GoP | 28935 | 28935 |  | 28360 | 28360 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-13-040-01 | R/M of Building | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-02-18 | N/A | 2022-03-18 | 2022-03-23 | 2022-03-23 | GoP | 774542 | 774542 |  | 773115 | 773115 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-03-080-00 | Medical & Dental Expns | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-02-18 | N/A | 2022-03-18 | 2022-03-23 | 2022-03-23 | GoP | 200030 | 200030 |  | 198852 | 198852 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-13-050-02 | R/M of Office Equipment | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-02-19 | N/A | 2022-03-18 | 2022-03-22 | 2022-03-22 | GoP | 161000 | 161000 |  | 160189 | 160189 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-13-050-03 | R/M of ICT Equipment | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-02-18 | N/A | 2022-03-18 | 2022-03-22 | 2022-03-22 | GoP | 766932 | 766932 |  | 765370 | 765370 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-13-050-07 | R/M of Commo Equipment | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-02-18 | N/A | 2022-03-18 | 2022-03-22 | 2022-03-22 | GoP | 144003 | 144003 |  | 143512 | 143512 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-13-060-01 | R/M Motor Vehicles | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-02-18 | N/A | 2022-03-18 | 2022-03-23 | 2022-03-23 | GoP | 659039.75 | 659039.75 |  | 658053 | 658053 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-03-990-00 | Other Supplies and Materials | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-02-18 | N/A | 2022-03-18 | 2022-03-22 | 2022-03-22 | GoP | 256768.5 | 256768.5 |  | 256074 | 256074 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-02-010-00 | Training Expenses | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-02-18 | N/A | 2022-03-18 | 2022-03-23 | 2022-03-23 | GoP | 739280 | 739280 |  | 738257 | 738257 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-99-030-00 | Representation Expenses | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-02-18 | N/A | 2022-03-18 | 2022-03-23 | 2022-03-23 | GoP | 326527 | 326527 |  | 325897 | 325897 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-03-010-00 | Office Supplies | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-02-21 | N/A | 2022-03-18 | 2022-03-22 | 2022-03-22 | GoP | 688193.75 | 688193.75 |  | 687143 | 687143 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-02-010-00 | Training Expenses | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-02-21 | N/A | 2022-03-18 | 2022-03-22 | 2022-03-22 | GoP | 171000 | 171000 |  | 170200 | 170200 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-03-080-00 | Medical & Dental Expns | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-02-21 | N/A | 2022-03-18 | 2022-03-23 | 2022-03-23 | GoP | 62000 | 62000 |  | 61505 | 61505 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-13-040-01 | R/M of Building | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-02-21 | N/A | 2022-03-18 | 2022-03-23 | 2022-03-23 | GoP | 377500 | 377500 |  | 376700 | 376700 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-13-050-03 | R/M of ICT Equipment | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-02-21 | N/A | 2022-03-18 | 2022-03-23 | 2022-03-23 | GoP | 231000 | 231000 |  | 230120 | 230120 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-13-050-07 | R/M of Commo Equipment | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-02-21 | N/A | 2022-03-18 | 2022-03-22 | 2022-03-22 | GoP | 115000 | 115000 |  | 114200 | 114200 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-13-060-01 | R/M Motor Vehicles | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-02-21 | N/A | 2022-03-18 | 2022-03-22 | 2022-03-22 | GoP | 294000 | 294000 |  | 293300 | 293300 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-03-080-00 | Medical & Dental Expns | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-03-28 | N/A | 2022-04-27 | 2022-05-02 | 2022-05-02 | GoP | 124030 | 124030 |  | 123480 | 123480 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-13-040-01 | R/M of Building | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-03-28 | N/A | 2022-04-27 | 2022-05-02 | 2022-05-02 | GoP | 752894 | 752894 |  | 752300 | 752300 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-13-050-02 | R/M of Office Equipment | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-03-28 | N/A | 2022-04-27 | 2022-05-02 | 2022-05-02 | GoP | 155000 | 155000 |  | 154500 | 154500 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-13-050-03 | R/M of ICT Equipment | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-03-28 | N/A | 2022-04-27 | 2022-05-02 | 2022-05-02 | GoP | 661244 | 661244 |  | 660700 | 660700 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-13-050-07 | R/M of Commo Equipment | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-04-04 | N/A | 2022-05-13 | 2022-05-18 | 2022-05-18 | GoP | 301000 | 301000 |  | 300460 | 300460 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-13-060-01 | R/M Motor Vehicles | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-04-25 | N/A | 2022-06-06 | 2022-06-08 | 2022-06-08 | GoP | 836054.75 | 836054.75 |  | 835520 | 835520 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-03-990-00 | Other Supplies and Materials | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-03-29 | N/A | 2022-04-27 | 2022-05-02 | 2022-05-02 | GoP | 284436 | 284436 |  | 283942 | 283942 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-02-010-00 | Training Expenses | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-04-18 | N/A | 2022-06-06 | 2022-06-08 | 2022-06-08 | GoP | 813200 | 813200 |  | 812600 | 812600 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-99-030-00 | Representation Expenses | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-04-18 | N/A | 2022-06-06 | 2022-06-08 | 2022-06-08 | GoP | 371100 | 371100 |  | 370182 | 370182 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-03-990-00 | Other Supplies and Materials | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-03-28 | N/A | 2022-04-27 | 2022-05-02 | 2022-05-02 | GoP | 500000 | 500000 |  | 499470 | 499470 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-03-990-00 | Other Supplies and Materials | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-03-28 | N/A | 2022-04-27 | 2022-05-02 | 2022-05-02 | GoP | 500000 | 500000 |  | 499544 | 499544 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-03-010-00 | Office Supplies | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-04-08 | N/A | 2022-05-13 | 2022-05-18 | 2022-05-18 | GoP | 851707 | 851707 |  | 851068 | 851068 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-03-990-00 | Other Supplies and Materials | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-04-08 | N/A | 2022-05-13 | 2022-05-18 | 2022-05-18 | GoP | 713371 | 713371 |  | 712738 | 712738 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-03-990-00 | Other Supplies and Materials | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-04-08 | N/A | 2022-05-13 | 2022-05-18 | 2022-05-18 | GoP | 659513 | 659513 |  | 658958 | 658958 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-03-990-00 | Other Supplies and Materials | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-04-08 | N/A | 2022-05-13 | 2022-05-18 | 2022-05-18 | GoP | 951399 | 951399 |  | 950839 | 950839 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-02-010-00 | Training Expenses | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-04-12 | N/A | 2022-06-22 | 2022-07-05 | 2022-07-05 | GoP | 530040 | 530040 |  | 529450 | 529450 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-99-030-00 | Representation Expenses | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-04-08 | N/A | 2022-06-06 | 2022-06-08 | 2022-06-08 | GoP | 950274 | 950274 |  | 949752 | 949752 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-03-010-00 | Office Supplies | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-04-18 | N/A | 2022-05-13 | 2022-05-18 | 2022-05-18 | GoP | 455603.55 | 455603.55 |  | 454553.5 | 454553.5 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-03-990-00 | Other Supplies and Materials | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-05-02 | N/A | 2022-06-06 | 2022-06-08 | 2022-06-08 | GoP | 895000 | 895000 |  | 894584 | 894584 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-13-040-01 | R/M of Building | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-05-13 | N/A | 2022-06-29 | 2022-07-05 | 2022-07-05 | GoP | 499315 | 499315 |  | 498840 | 498840 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-03-080-00 | Medical & Dental Expns | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-05-16 | N/A | 2022-06-29 | 2022-07-05 | 2022-07-05 | GoP | 699050 | 699050 |  | 698599 | 698599 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-03-080-00 | Medical & Dental Expns | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-05-13 | N/A | 2022-06-30 | 2022-07-05 | 2022-07-05 | GoP | 276528 | 276528 |  | 276159 | 276159 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-13-060-01 | R/M Motor Vehicles | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-05-13 | N/A | 2022-06-30 | 2022-07-05 | 2022-07-05 | GoP | 553500 | 553500 |  | 553050 | 553050 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-13-040-01 | R/M of Building | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-05-16 | N/A | 2022-06-29 | 2022-07-05 | 2022-07-05 | GoP | 412700 | 412700 |  | 412230 | 412230 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-99-030-00 | Representation Expenses | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-05-20 | N/A | 2022-06-30 | 2022-07-05 | 2022-07-05 | GoP | 873736 | 873736 |  | 873096 | 873096 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-03-220-01 | Semi Expendable Furniture and Fixtures | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-07-11 | N/A | 2022-08-30 | 2022-09-01 | 2022-09-01 | GoP | 105800 | 105800 |  | 105610 | 105610 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-02-010-00 | Training Expenses | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-05-24 | N/A | 2022-06-30 | 2022-07-06 | 2022-07-06 | GoP | 735000 | 735000 |  | 734500 | 734500 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-03-990-00 | Other Supplies and Materials | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-05-24 | N/A | 2022-06-30 | 2022-07-05 | 2022-07-05 | GoP | 674643 | 674643 |  | 674191 | 674191 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-03-990-00 | Other Supplies and Materials | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-05-24 | N/A | 2022-06-30 | 2022-07-06 | 2022-07-06 | GoP | 657000 | 657000 |  | 656561 | 656561 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-02-010-00 | Training Expenses | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-05-24 | N/A | 2022-06-30 | 2022-07-06 | 2022-07-06 | GoP | 677500 | 677500 |  | 676840 | 676840 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-99-030-00 | Representation Expenses | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-05-27 | N/A | 2022-06-29 | 2022-07-05 | 2022-07-05 | GoP | 112500 | 112500 |  | 112128 | 112128 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-03-210-03 | Semi Expendable ICT | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-05-24 | N/A | 2022-06-30 | 2022-07-06 | 2022-07-06 | GoP | 768000 | 768000 |  | 767570 | 767570 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-02-010-00 | Training Expenses | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-05-31 | N/A | 2022-08-05 | 2022-08-12 | 2022-08-12 | GoP | 800391 | 800391 |  | 799745 | 799745 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-03-990-00 | Other Supplies and Materials | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-06-06 | N/A | 2022-07-02 | 2022-08-03 | 2022-08-03 | GoP | 339072 | 339072 |  | 338772 | 338772 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-03-080-00 | Medical & Dental Expns | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-06-06 | N/A | 2022-07-29 | 2022-08-03 | 2022-08-03 | GoP | 145030 | 145030 |  | 144640 | 144640 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-99-030-00 | Representation Expenses | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-06-06 | N/A | 2022-07-28 | 2022-08-03 | 2022-08-03 | GoP | 325527 | 325527 |  | 325227 | 325227 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-99-030-00 | Representation Expenses | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-06-06 | N/A | 2022-07-29 | 2022-08-03 | 2022-08-03 | GoP | 835692 | 835692 |  | 835386 | 835386 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-13-040-01 | R/M of Building | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-05-31 | N/A | 2022-07-02 | 2022-08-03 | 2022-08-03 | GoP | 905310 | 905310 |  | 904655 | 904655 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-13-050-02 | R/M of Office Equipment | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-06-27 | N/A | 2022-08-05 | 2022-08-12 | 2022-08-12 | GoP | 298994 | 298994 |  | 298660 | 298660 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-13-050-03 | R/M of ICT Equipment | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-06-27 | N/A | 2022-08-08 | 2022-08-12 | 2022-08-12 | GoP | 482632 | 482632 |  | 482240 | 482240 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-13-050-07 | R/M of Commo Equipment | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-06-27 | N/A | 2022-07-28 | 2022-08-03 | 2022-08-03 | GoP | 346000 | 346000 |  | 345620 | 345620 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-13-060-01 | R/M Motor Vehicles | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-06-27 | N/A | 2022-07-29 | 2022-08-03 | 2022-08-03 | GoP | 726239.75 | 726239.75 |  | 725860 | 725860 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-02-010-00 | Training Expenses | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-06-06 | N/A | 2022-07-28 | 2022-08-03 | 2022-08-03 | GoP | 468500 | 468500 |  | 467928 | 467928 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-03-210-03 | Semi Expendable ICT | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-06-27 | N/A | 2022-07-29 | 2022-08-03 | 2022-08-03 | GoP | 260592 | 260592 |  | 260300 | 260300 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-13-040-01 | R/M of Building | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-06-27 | N/A | 2022-08-05 | 2022-08-12 | 2022-08-12 | GoP | 499965 | 499965 |  | 499525 | 499525 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-03-990-00 | Other Supplies and Materials | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-06-06 | N/A | 2022-07-29 | 2022-08-03 | 2022-08-03 | GoP | 862319 | 862319 |  | 861719 | 861719 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-03-990-00 | Other Supplies and Materials | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-06-06 | N/A | 2022-07-29 | 2022-08-03 | 2022-08-03 | GoP | 737593 | 737593 |  | 737025 | 737025 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-99-030-00 | Representation Expenses | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-06-06 | N/A | 2022-08-05 | 2022-08-12 | 2022-08-12 | GoP | 593792 | 593792 |  | 593296.5 | 593296.5 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-99-030-00 | Representation Expenses | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-06-06 | N/A | 2022-07-29 | 2022-08-03 | 2022-08-03 | GoP | 538200 | 538200 |  | 537602.5 | 537602.5 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-02-010-00 | Training Expenses | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-06-06 | N/A | 2022-09-28 | 2022-10-05 | 2022-10-05 | GoP | 123330 | 123330 |  | 123045 | 123045 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-03-010-00 | Office Supplies | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-06-06 | N/A | 2022-07-02 | 2022-08-03 | 2022-08-03 | GoP | 843707 | 843707 |  | 843210 | 843210 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-03-010-00 | Office Supplies | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-06-27 | N/A | 2022-08-08 | 2022-08-12 | 2022-08-12 | GoP | 696771.31 | 696771.31 |  | 696413 | 696413 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-02-010-00 | Training Expenses | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-06-27 | N/A | 2022-08-08 | 2022-08-12 | 2022-08-12 | GoP | 451420 | 451420 |  | 451010 | 451010 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-13-060-01 | R/M Motor Vehicles | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-07-04 | N/A | 2022-08-08 | 2022-08-12 | 2022-08-12 | GoP | 122676.56 | 122676.56 |  | 122505 | 122505 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-03-010-00 | Office Supplies | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-07-19 | N/A | 2022-08-30 | 2022-09-01 | 2022-09-01 | GoP | 167665 | 167665 |  | 167369 | 167369 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-03-990-00 | Other Supplies and Materials | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-07-19 | N/A | 2022-08-08 | 2022-08-12 | 2022-08-12 | GoP | 361667 | 361667 |  | 361440 | 361440 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-03-010-00 | Office Supplies | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-07-19 | N/A | 2022-09-27 | 2022-10-05 | 2022-10-05 | GoP | 399530 | 399530 |  | 399140 | 399140 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-03-990-00 | Other Supplies and Materials | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-07-19 | N/A | 2022-08-23 | 2022-08-26 | 2022-08-26 | GoP | 200000 | 200000 |  | 199725 | 199725 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-03-990-00 | Other Supplies and Materials | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-07-19 | N/A | 2022-08-30 | 2022-09-01 | 2022-09-01 | GoP | 713371 | 713371 |  | 713068 | 713068 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-13-040-01 | R/M of Building | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-05 | N/A | 2022-08-30 | 2022-09-01 | 2022-09-01 | GoP | 999985 | 999985 |  | 999430 | 999430 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-03-210-03 | Semi Expendable ICT | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-01 | N/A | 2022-08-30 | 2022-09-01 | 2022-09-01 | GoP | 200000 | 200000 |  | 199760 | 199760 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-03-210-07 | Semi Expendable Commo | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-07-29 | N/A | 2022-08-30 | 2022-09-01 | 2022-09-01 | GoP | 100000 | 100000 |  | 99700 | 99700 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-03-080-00 | Medical & Dental Expns | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-07-29 | N/A | 2022-08-30 | 2022-09-01 | 2022-09-01 | GoP | 151250 | 151250 |  | 150944 | 150944 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-03-080-00 | Medical & Dental Expns | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-15 | N/A | 2022-09-09 | 2022-09-14 | 2022-09-14 | GoP | 752788 | 752788 |  | 752372 | 752372 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-03-990-00 | Other Supplies and Materials | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-15 | N/A | 2022-09-09 | 2022-09-14 | 2022-09-14 | GoP | 943968 | 943968 |  | 943505 | 943505 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-02-010-00 | Training Expenses | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-15 | N/A | 2022-10-17 | 2022-10-19 | 2022-10-19 | GoP | 400000 | 400000 |  | 399555 | 399555 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-99-070-01 | ICT Software | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-15 | N/A | 2022-09-09 | 2022-09-14 | 2022-09-14 | GoP | 147150 | 147150 |  | 146800 | 146800 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-03-210-03 | Semi Expendable ICT | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-22 | N/A | 2022-09-09 | 2022-09-14 | 2022-09-14 | GoP | 899350 | 899350 |  | 899045 | 899045 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-02-010-02 | Training Expenses | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-22 | N/A | 2022-11-02 | 2022-11-08 | 2022-11-08 | GoP | 944640 | 944640 |  | 944230 | 944230 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-13-040-99 | R/M of Other Structure | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-30 | N/A | 2022-10-17 | 2022-10-19 | 2022-10-19 | GoP | 213486 | 213486 |  | 213070 | 213070 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-03-210-03 | Semi Expendable ICT | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-05 | N/A | 2022-10-17 | 2022-10-19 | 2022-10-19 | GoP | 299915 | 299915 |  | 299575 | 299575 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-13-040-01 | R/M of Building | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-17 | N/A | 2022-11-10 | 2022-11-16 | 2022-11-16 | GoP | 664985 | 664985 |  | 664564 | 664564 |  | N/A
5-02-13-050-02 | R/M of Office Equipment | [19 empty] | FSRR, PA | NO | Negotiated 53.10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-03 | N/A | 2022-11-10 | 2022-11-16 | 2022-11-16 | GoP | 86000 | 86000 |  | 85700 | 85700 |  | N/A
5-02-13-050-03 | R/M of ICT Equipment | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-03 | N/A | 2022-11-10 | 2022-11-16 | 2022-11-16 | GoP | 592500 | 592500 |  | 592060 | 592060 |  | N/A
5-02-13-050-07 | R/M of Commo Equipment | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-03 | N/A | 2022-11-10 | 2022-11-16 | 2022-11-16 | GoP | 90000 | 90000 |  | 89600 | 89600 |  | N/A
5-02-13-060-01 | R/M Motor Vehicles | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-03 | N/A | 2022-11-11 | 2022-11-16 | 2022-11-16 | GoP | 744480 | 744480 |  | 744060 | 744060 |  | N/A
5-02-03-080-00 | Medical & Dental Expns | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-03 | N/A | 2022-11-10 | 2022-11-16 | 2022-11-16 | GoP | 200000 | 200000 |  | 199700 | 199700 |  | N/A
5-02-13-040-01 | R/M of Building | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-17 | N/A | 2022-11-10 | 2022-11-16 | 2022-11-16 | GoP | 331000 | 331000 |  | 330565 | 330565 |  | N/A
5-02-03-990-00 | Other Supplies and Materials | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-07 | N/A | 2022-11-10 | 2022-11-16 | 2022-11-16 | GoP | 500000 | 500000 |  | 499575 | 499575 |  | N/A
5-02-13-050-02 | R/M of Office Equipment | [19 empty] | FSRR, PA | NO | Negotiated 53.10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-11 | N/A | 2022-11-10 | 2022-11-16 | 2022-11-16 | GoP | 105000 | 105000 |  | 104670 | 104670 |  | N/A
5-02-13-050-03 | R/M of ICT Equipment | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-11 | N/A | 2022-11-10 | 2022-11-16 | 2022-11-16 | GoP | 161000 | 161000 |  | 160630 | 160630 |  | N/A
5-02-13-050-07 | R/M of Commo Equipment | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-17 | N/A | 2022-11-11 | 2022-11-16 | 2022-11-16 | GoP | 95000 | 95000 |  | 94630 | 94630 |  | N/A
5-02-13-060-01 | R/M Motor Vehicles | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-11 | N/A | 2022-11-10 | 2022-11-16 | 2022-11-16 | GoP | 366000 | 366000 |  | 365575 | 365575 |  | N/A
5-02-02-010-02 | Training Expenses | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-11 | N/A | 2022-12-14 | 2022-12-19 | 2022-12-19 | GoP | 277700 | 277700 |  | 276655 | 276655 |  | N/A
5-02-03-080-00 | Medical & Dental Expns | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-25 | N/A | 2022-11-18 | 2022-11-23 | 2022-11-23 | GoP | 300000 | 300000 |  | 299625 | 299625 |  | N/A
5-02-03-990-00 | Other Supplies and Materials | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-17 | N/A | 2022-11-11 | 2022-11-16 | 2022-11-16 | GoP | 150000 | 150000 |  | 149691 | 149691 |  | N/A
5-02-03-080-00 | Medical & Dental Expns | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-25 | N/A | 2022-11-18 | 2022-11-23 | 2022-11-23 | GoP | 132040 | 132040 |  | 131660 | 131660 |  | N/A
5-02-13-040-99 | R/M of Other Structure | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-25 | N/A | 2022-11-18 | 2022-11-23 | 2022-11-23 | GoP | 990380 | 990380 |  | 989580 | 989580 |  | N/A
5-02-13-040-99 | R/M of Other Structure | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-07 | N/A | 2022-12-07 | 2022-12-12 | 2022-12-12 | GoP | 199985 | 199985 |  | 199575 | 199575 |  | N/A
5-02-03-210-03 | Semi Expendable ICT | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-25 | N/A | 2022-11-28 | 2022-12-01 | 2022-12-01 | GoP | 825293 | 825293 |  | 824684 | 824684 |  | N/A
5-02-03-990-00 | Other Supplies and Materials | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-21 | N/A | 2022-12-14 | 2022-12-19 | 2022-12-19 | GoP | 517453 | 517453 |  | 516574 | 516574 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-03-210-02 | Semi Expendable Office Equipment | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-21 | N/A | 2022-12-14 | 2022-12-19 | 2022-12-19 | GoP | 75600 | 75600 |  | 75150 | 75150 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-03-210-03 | Semi Expendable ICT | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-21 | N/A | 2022-12-14 | 2022-12-19 | 2022-12-19 | GoP | 149500 | 149500 |  | 149120 | 149120 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-03-120-00 | Military Police and Traffic Supplies Expenses | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-21 | N/A | 2022-12-14 | 2022-12-19 | 2022-12-19 | GoP | 147600 | 147600 |  | 147150 | 147150 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
[38 empty] | 53337927.12 | 53337927.12 |  | 53279769.7 | 53279769.7 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Total Alloted Budget of Procurement Activities | [37 empty] | 53337927.12
Total Contract Price of Procurement Actitvites Conducted | [40 empty] | 53279769.7
Total Savings (Total Alloted Budget - Total Contract Price) | [37 empty] | 58157.42
0N-GOING PROCUREMENT ACTIVITIES
5-02-99-030-00 | Representation Expenses | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-02 | N/A |  |  |  | GoP | 711018 | 711018 |  | 710433 | 710433 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Obligate Sign for Accountant
5-02-99-030-00 | Representation Expenses | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-02 | N/A |  |  |  | GoP | 461000 | 461000 |  | 460363 | 460363 |  | N/A | [6 empty] | Obligate Sign for Accountant
5-02-03-990-00 | Other Supplies and Materials | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-21 | N/A |  |  |  | GoP | 219625 | 219625 |  | 219217 | 219217 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Obligate Sign for Accountant
5-02-02-010-02 | Training Expenses | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-21 | N/A |  |  |  | GoP | 84850 | 84850 |  | 84417 | 84417 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Obligate Sign for Accountant
5-02-99-030-00 | Representation Expenses | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-21 | N/A |  |  |  | GoP | 240400 | 240400 |  | 239960 | 239960 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Obligate Sign for Accountant
5-02-03-080-00 | Medical & Dental Expns | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-06 | N/A |  |  |  | GoP | 290000 | 290000 |  | 289575 | 289575 |  | N/A | [6 empty] | Obligate Sign for Accountant
5-02-13-040-01 | R/M of Building | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-06 | N/A |  |  |  | GoP | 369400 | 369400 |  | 368800 | 368800 |  | N/A | [6 empty] | Obligate Sign for Accountant
5-02-13-050-02 | R/M of Office Equipment | [19 empty] | FSRR, PA | NO | Negotiated 53.10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-06 | N/A |  |  |  | GoP | 80000 | 80000 |  | 79560 | 79560 |  | N/A | [6 empty] | Obligate Sign for Accountant
5-02-13-050-03 | R/M of ICT Equipment | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-06 | N/A |  |  |  | GoP | 316600 | 316600 |  | 315400 | 315400 |  | N/A | [6 empty] | Obligate Sign for Accountant
5-02-13-050-07 | R/M of Commo Equipment | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-06 | N/A |  |  |  | GoP | 66000 | 66000 |  | 65610 | 65610 |  | N/A | [6 empty] | Obligate Sign for Accountant
5-02-13-060-01 | R/M Motor Vehicles | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-06 | N/A |  |  |  | GoP | 438500 | 438500 |  | 437820 | 437820 |  | N/A | [6 empty] | Obligate Sign for Accountant
5-02-03-210-03 | Semi Expendable ICT | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-06 | N/A |  |  |  | GoP | 500000 | 500000 |  | 499365 | 499365 |  | N/A | [6 empty] | Obligate Sign for Accountant
5-02-13-020-99 | R/M Other Land Improvements | [19 empty] | FSRR, PA | NO | Negotiated 53.10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-06 | N/A |  |  |  | GoP | 828000 | 828000 |  | 827325 | 827325 |  | N/A | [6 empty] | Obligate Sign for Accountant
Total Alloted Budget of On-going Procurement Activities | [37 empty] | 2888500
[21 empty] | Prepared by: | [10 empty] | Recommended for Approval by: | [10 empty] | APPROVED:
[21 empty] | Signed | [10 empty] | Signed | [10 empty] | Signed
[21 empty] | DON ADRIAN A CABOTAJE | [10 empty] | CARLO CANICO V IRIBERRI III | [10 empty] | FREDDIE T DELA CRUZ
[21 empty] | LTC (INF) PA | [10 empty] | MAJ (INF) PA | [10 empty] | BGEN PA
[21 empty] | AC of S for Logistics, G4 | [10 empty] | MFO | [10 empty] | Regiment Commander

## Sheet1 (hidden)
Competitive Bidding | GoP | YES
Limited Source Bidding | Foreign | NO
Direct Contracting | Special Purpose Fund
Repeat Order | Corporate Budget
Shopping | Income
NP-53.1 Two Failed Biddings | Others
NP-53.2 Emergency Cases
NP-53.3 Take-Over of Contracts
NP-53.4 Adjacent or Contiguous
NP-53.5 Agency-to-Agency
NP-53.6 Scientific, Scholarly, Artistic Work, Exclusive Technology and Media Services
NP-53.7 Highly Technical Consultants
NP-53.8 Defense Cooperation Agreement
NP-53.9 - Small Value Procurement
NP-53.10 Lease of Real Property and Venue
NP-53.11 NGO Participation
NP-53.12 Community Participation
NP-53.13 UN Agencies, Int'l Organizations or International Financing Institutions
Others - Foreign-funded procurement