## Sheet1
|  | ANNEX A | [18 empty] | ANNEX B
|  | Department of Budget and Management Annual Procurement Plan for FY 2006 | [18 empty] | (PAPC) Procurement Monitoring Report as of December 31, 2022
Code (PAP) | Procurement Project | PMO/ End-User | Mode of Procurement | Schedule for Each Procurement Activity | [11 empty] | Source of Funds | ABC (PhP) |  |  | Remarks (brief description of Program/Project) | PMO/ End-User | Is this an Early Procurement Activity? | Mode of Procurement | Actual Procurement Activity | [12 empty] | Source of Funds | ABC (PhP) |  |  | Contract Cost (PhP) |  |  | List of Invited Observers | Date of Receipt of Invitation | [5 empty] | Remarks (Explaining changes from the APP)
|  |  |  | Pre-Proc Conference | Ads/Post of IAEB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Contract Award | Contract Signing | Notice to Proceed | Delivery/ Accept | Payment Process |  | Total | MOOE | CO |  |  |  |  | Pre-Proc Conference | Ads/Post of IB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Date of BAC Resolution Recommending Award | Notice of Award | Contract Signing | Notice to Proceed | Delivery/ Completion | Inspection & Acceptance |  | Total | MOOE | CO | Total | MOOE | CO |  | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Delivery/ Completion/ Acceptance (If applicable)
COMPLETED PROCUREMENT ACTIVITIES
| S/D of 6ltrs Acri Color verify and 31 Others | [19 empty] | AREC | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-07-26 | 2022-07-26 | 2022-08-30 | 2022-09-06 | 2022-09-06 | GoP | 149865 | 149865 | 0 | 148345 | 148345 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of 4pcs Spark Plug (Toyota Innova) and 41 Others | [19 empty] | AREC | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-07-29 | 2022-07-29 | 2022-08-30 | 2022-09-06 | 2022-09-06 | GoP | 149950 | 149950 | 0 | 148450 | 148450 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of 2pcs C100 120GB SSD VIDEO CARD 4GB and 8 Others | [19 empty] | AREO | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-02 | 2022-08-02 | 2022-09-12 | 2022-09-19 | 2022-09-19 | GoP | 49995 | 49995 | 0 | 49695 | 49695 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of 1piece C100 SSD VIDEO CARD 120GB and 9 Others | [19 empty] | AREO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-08-19 | 2022-08-19 | 2022-09-09 | 2022-09-16 | 2022-09-16 | GoP | 49995 | 49995 | 0 | 49595 | 49595 | 0 | [7 empty] | N/A
| S/D of 2units 2.0HP Compressor Motor and 12 Others | [19 empty] | AREO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-08-19 | 2022-08-19 | 2022-09-29 | 2022-10-06 | 2022-10-06 | GoP | 49980 | 49980 | 0 | 49480 | 49480 | 0 | [7 empty] | N/A
| S/D of 3ltrs Acri Color Raw Sienna and 25 Others | [19 empty] | AREO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-09-02 | 2022-09-02 | 2022-09-29 | 2022-10-06 | 2022-10-06 | GoP | 49950 | 49950 | 0 | 47170 | 47170 | 0 | [7 empty] | N/A
| S/D of 138cans AIR FRESHENER aerosol 280ml/150g and 21 Others | [19 empty] | AREO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-09-13 | 2022-09-13 | 2022-09-29 | 2022-10-06 | 2022-10-06 | GoP | 290000 | 290000 | 0 | 288726 | 288726 | 0 | [7 empty] | N/A
| S/D of 1unit Split Type Aircon Inverter 2HP and 1 Other | [19 empty] | AREO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-09-23 | 2022-09-23 | 2022-11-04 | 2022-11-11 | 2022-11-11 | GoP | 74810 | 74810 | 0 | 74490 | 74490 | 0 | [7 empty] | N/A
| S/D of 340 pieces Antigen Rapid Test Kit and 2 others | [19 empty] | AREO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-10-11 | 2022-10-11 | 2022-10-28 | 2022-11-04 | 2022-11-04 | GoP | 134249 | 134249 | 0 | 133690 | 133690 | 0 | [7 empty] | N/A
| CATERING SERVICES | [19 empty] | AREO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-10-21 | 2022-10-21 | 2022-11-18 | 2022-11-25 | 2022-11-25 | GoP | 144750 | 144750 | 0 | 143500 | 143500 | 0 | [7 empty] | N/A
| S/D of 1set Office Workstation for 4 Seater Partition includes 4pcs Mobile Cabinet Dimension: L100” x W50” x 43” | [19 empty] | AREO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-10-28 | 2022-10-28 | 2022-11-25 | 2022-12-02 | 2022-12-02 | GoP | 49945 | 49945 | 0 | 49500 | 49500 | 0 | [7 empty] | N/A
| S/D of 1 set of Office Workstation for 4 Seater Partition with 4 pieces Mobile Cabinet Dimension L100" x W50" x 43" and 1 other | [19 empty] | AREO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-11-04 | 2022-11-04 | 2022-11-25 | 2022-12-02 | 2022-12-02 | GoP | 49945 | 49945 | 0 | 49445 | 49445 | 0 | [7 empty] | N/A
| S/D of 45 pcs Ficem Board 1/4 (Hardiflex) & 19 others | [19 empty] | 9PED | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-07-08 | 2022-07-08 | 2022-09-08 | 2022-09-15 | 2022-09-15 | GoP | 128279 | 128279 | 0 | 123779 | 123779 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of 1 set Overhaul Gasket & 43 OTHERS | [19 empty] | 9PED | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-07-12 | 2022-07-12 | 2022-09-12 | 2022-09-19 | 2022-09-19 | GoP | 85000 | 85000 | 0 | 83398 | 83398 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of 90 box Bottled Water 500ml & 16 others | [19 empty] | 9PED | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-07-26 | 2022-07-26 | 2022-09-19 | 2022-09-26 | 2022-09-26 | GoP | 67494 | 67494 | 0 | 66634 | 66634 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of 25 Hardiflex 1/4" x 4' x 8' & 17 others | [19 empty] | 9PED | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-07-26 | 2022-07-26 | 2022-09-27 | 2022-10-04 | 2022-10-04 | GoP | 80515 | 80515 | 0 | 79205 | 79205 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| CATERING SERVICES | [19 empty] | 9PED | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-07-29 | 2022-07-29 | 2022-09-12 | 2022-09-19 | 2022-09-19 | GoP | 125000 | 125000 | 0 | 116800 | 116800 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of 1 set Fuel Pressure Regulator & 19 Others | [19 empty] | 9PED | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-02 | 2022-08-02 | 2022-09-09 | 2022-09-16 | 2022-09-16 | GoP | 47812.5 | 47812.5 | 0 | 47200 | 47200 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of 3 ea Hard Disk 1TB & 3 others | [19 empty] | 9PED | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-02 | 2022-08-02 | 2022-09-27 | 2022-10-04 | 2022-10-04 | GoP | 20000 | 20000 | 0 | 18875 | 18875 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D 2 roll Copper tube 5/8A & 5 others | [19 empty] | 9PED | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-02 | 2022-08-02 | 2022-09-27 | 2022-10-04 | 2022-10-04 | GoP | 10000 | 10000 | 0 | 9400 | 9400 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of 1 unit Video Camera & 1 other | [19 empty] | 9PED | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-02 | 2022-08-02 | 2022-09-09 | 2022-09-16 | 2022-09-16 | GoP | 44970 | 44970 | 0 | 43000 | 43000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of 41 box Face Mask 50pcs/bx & 31 others | [19 empty] | 9PED | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-24 | 2022-08-24 | 2022-10-12 | 2022-10-19 | 2022-10-19 | GoP | 866750 | 866750 | 0 | 864750 | 864750 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of 108 reams Bond paper A4 & 16 others | [19 empty] | 9PED | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-24 | 2022-08-24 | 2022-10-28 | 2022-11-04 | 2022-11-04 | GoP | 100398 | 100398 | 0 | 99183 | 99183 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of 6 pcs Hydrualic Hose 1/2 x 1m & 7 others | [19 empty] | 9PED | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-02 | 2022-09-02 | 2022-10-07 | 2022-10-14 | 2022-10-14 | GoP | 30000 | 30000 | 0 | 28920 | 28920 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of 6 pcs Hydraulic Hose 1/2 X 1m & 7 others | [19 empty] | 9PED | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-30 | 2022-09-30 | 2022-11-14 | 2022-11-21 | 2022-11-21 | GoP | 30000 | 30000 | 0 | 29220 | 29220 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of 130 bags Cement Portland & 9 others | [19 empty] | 9PED | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-18 | 2022-10-18 | 2022-11-14 | 2022-11-21 | 2022-11-21 | GoP | 170383 | 170383 | 0 | 169801 | 169801 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D SSD 500GB 23 pcs and 2 others | [19 empty] | IMCOM | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-07-12 | 2022-07-12 | 2022-08-31 | 2022-09-07 | 2022-09-07 | GoP | 175200 | 175200 | 0 | 170200 | 170200 | 0 | [7 empty] | N/A
| S/D Broom Soft (tambo) 80 pcs and 51 others | [19 empty] | IMCOM | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-07-12 | 2022-07-12 | 2022-08-11 | 2022-08-18 | 2022-08-18 | GoP | 893981 | 893981 | 0 | 890781 | 890781 | 0 | [7 empty] | N/A
| S/D Executive Chair 10 pcs and 2 others | [19 empty] | IMCOM | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-07-12 | 2022-07-12 | 2022-08-31 | 2022-09-07 | 2022-09-07 | GoP | 200000 | 200000 | 0 | 196700 | 196700 | 0 | [7 empty] | N/A
| S/D 1hp Window type aircon 6 units and 2 others | [19 empty] | IMCOM | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-07-12 | 2022-07-12 | 2022-08-31 | 2022-09-07 | 2022-09-07 | GoP | 575000 | 575000 | 0 | 568950 | 568950 | 0 | [7 empty] | N/A
| S/D Oil Filter (Ford Ranger) 10 pcs and 66 others | [19 empty] | IMCOM | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-07-12 | 2022-07-12 | 2022-09-12 | 2022-09-19 | 2022-09-19 | GoP | 542000 | 542000 | 0 | 532650 | 532650 | 0 | [7 empty] | N/A
| SD of 100 reams PAPER, Multi-Purpose (COPY) A4, 70 gsm & 26 others | [19 empty] | IMCOM | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-07-15 | 2022-07-15 | 2022-08-31 | 2022-09-07 | 2022-09-07 | GoP | 165000 | 165000 | 0 | 164500 | 164500 | 0 | [7 empty] | N/A
| SD of 50 box Table Tissue & 19 others | [19 empty] | IMCOM | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-07-15 | 2022-07-15 | 2022-08-10 | 2022-08-17 | 2022-08-17 | GoP | 81000 | 81000 | 0 | 80650 | 80650 | 0 | [7 empty] | N/A
| SD of 10 pcks Gatorade and 19 others | [19 empty] | IMCOM | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-07-19 | 2022-07-19 | 2022-08-10 | 2022-08-17 | 2022-08-17 | GoP | 60000 | 60000 | 0 | 59800 | 59800 | 0 | [7 empty] | N/A
| SD of 80 tubs Choco chips and 10 others | [19 empty] | IMCOM | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-07-29 | 2022-07-29 | 2022-08-31 | 2022-09-07 | 2022-09-07 | GoP | 123412.5 | 123412.5 | 0 | 121437.5 | 121437.5 | 0 | [7 empty] | N/A
| S/D 100 bxs Antigen Test Kits 20pcs/bx | [19 empty] | IMCOM | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-08-02 | 2022-08-02 | 2022-09-05 | 2022-09-12 | 2022-09-12 | GoP | 1000000 | 1000000 | 0 | 750000 | 750000 | 0 | [7 empty] | N/A
| S/D of 32 pcs Pinlight (Clear White) & 16 others | [19 empty] | IMCOM | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-08-02 | 2022-08-02 | 2022-09-08 | 2022-09-15 | 2022-09-15 | GoP | 120000 | 120000 | 0 | 116988 | 116988 | 0 | [7 empty] | N/A
| S/D 70 pcs Globe Prepaid Card 500 and 4 Others | [19 empty] | IMCOM | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-08-02 | 2022-08-02 | 2022-08-31 | 2022-09-07 | 2022-09-07 | GoP | 102000 | 102000 | 0 | 100700 | 100700 | 0 | [7 empty] | N/A
| S/D 180 pcs BISCUITS CHOCO FLVR 600G/12 and 25 others | [19 empty] | IMCOM | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-08-02 | 2022-08-02 | 2022-08-31 | 2022-09-07 | 2022-09-07 | GoP | 1000000 | 1000000 | 0 | 981802 | 981802 | 0 | [7 empty] | N/A
| S/D of 750 pcs 4in x 8in 16in CHB and 127 others | [19 empty] | IMCOM | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-08-12 | 2022-08-12 | 2022-09-12 | 2022-09-19 | 2022-09-19 | GoP | 963100 | 963100 | 0 | 955440 | 955440 | 0 | [7 empty] | N/A
| S/D of 290 pcs Mugs and 16 others | [19 empty] | IMCOM | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-08-16 | 2022-08-16 | 2022-08-31 | 2022-09-07 | 2022-09-07 | GoP | 751492 | 751492 | 0 | 743359 | 743359 | 0 | [7 empty] | N/A
| S/D Ballpen 12pcs/bx 75 bxs and 51 others | [19 empty] | IMCOM | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-08-16 | 2022-08-16 | 2022-09-27 | 2022-10-04 | 2022-10-04 | GoP | 926350 | 926350 | 0 | 905437 | 905437 | 0 | [7 empty] | N/A
| S/D of 164 pcs Curtain 12ft dimmer (brown) Rod Pocket Curtain fabric: Polycotton blackout Fabric and 6 others 28 others | [19 empty] | IMCOM | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-09-09 | 2022-09-09 | 2022-10-06 | 2022-10-13 | 2022-10-13 | GoP | 618416 | 618416 | 0 | 617760 | 617760 | 0 | [7 empty] | N/A
| S/D of USB 32gb 65 pcs and 3 others | [19 empty] | IMCOM | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-09-13 | 2022-09-13 | 2022-10-06 | 2022-10-13 | 2022-10-13 | GoP | 100256.25 | 100256.25 | 0 | 99200 | 99200 | 0 | [7 empty] | N/A
| S/D of 3 unit Intel Core i7 Laptop and 12 Others | [19 empty] | IMCOM | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-09-13 | 2022-09-13 | 2022-11-21 | 2022-11-28 | 2022-11-28 | GoP | 730872.75 | 730872.75 | 0 | 725900 | 725900 | 0 | [7 empty] | N/A
| S/D of 465 bags Cement and 74 others | [19 empty] | IMCOM | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-09-20 | 2022-09-20 | 2022-10-07 | 2022-10-14 | 2022-10-14 | GoP | 944774 | 944774 | 0 | 944159 | 944159 | 0 | [7 empty] | N/A
| S/D of 500 pcs CHB 4in x 8in x 16in and 56 others | [19 empty] | IMCOM | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-09-20 | 2022-09-20 | 2022-10-07 | 2022-10-14 | 2022-10-14 | GoP | 750000 | 750000 | 0 | 748100 | 748100 | 0 | [7 empty] | N/A
| S/D Bond Paper A4 70gsm 500sheets 500 ream and 23 Others | [19 empty] | IMCOM | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-09-27 | 2022-09-27 | 2022-10-17 | 2022-10-24 | 2022-10-24 | GoP | 872770 | 872770 | 0 | 861510 | 861510 | 0 | [7 empty] | N/A
| S/D of 62 bags Cement and 23 others | [19 empty] | IMCOM | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-09-27 | 2022-09-27 | 2022-10-12 | 2022-10-19 | 2022-10-19 | GoP | 949680 | 949680 | 0 | 949070 | 949070 | 0 | [7 empty] | N/A
| S/D of 4 sets Printer Ink set C M Bk and Y and 5 others | [19 empty] | IMCOM | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-09-30 | 2022-09-30 | 2022-10-17 | 2022-10-24 | 2022-10-24 | GoP | 25000 | 25000 | 0 | 24500 | 24500 | 0 | [7 empty] | N/A
| S/D of 3 set Desktop i5 11Gen & 2 others | [19 empty] | IMCOM | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-10-11 | 2022-10-11 | 2022-10-28 | 2022-11-04 | 2022-11-04 | GoP | 375000 | 375000 | 0 | 370800 | 370800 | 0 | [7 empty] | N/A
| S/D of 4 pcs Ignition Coil (Toyota Vios) and 30 others | [19 empty] | IMCOM | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-10-11 | 2022-10-11 | 2022-11-21 | 2022-11-28 | 2022-11-28 | GoP | 301000 | 301000 | 0 | 297320 | 297320 | 0 | [7 empty] | N/A
| S/D of 24 pcs Office Chairs & 5 others | [19 empty] | IMCOM | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-10-11 | 2022-10-11 | 2022-11-04 | 2022-11-11 | 2022-11-11 | GoP | 200000 | 200000 | 0 | 197200 | 197200 | 0 | [7 empty] | N/A
| S/D of 150 pcs Floor mat length 52cm width 34cm (fabric) & 23 others | [19 empty] | IMCOM | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-10-11 | 2022-10-11 | 2022-11-07 | 2022-11-14 | 2022-11-14 | GoP | 874142.5 | 874142.5 | 0 | 871142.5 | 871142.5 | 0 | [7 empty] | N/A
| S/D of 140 box Mineral water 330ml x 24pcs & 24 others | [19 empty] | IMCOM | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-10-11 | 2022-10-11 | 2022-12-09 | 2022-12-16 | 2022-12-16 | GoP | 882590 | 882590 | 0 | 881405 | 881405 | 0 | [7 empty] | N/A
| S/D of 16 pcs 2TB External Drive & 30 others | [19 empty] | IMCOM | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-10-11 | 2022-10-11 | 2022-11-08 | 2022-11-15 | 2022-11-15 | GoP | 570750 | 570750 | 0 | 569510 | 569510 | 0 | [7 empty] | N/A
| S/D of 22 pcS Globe 500 & 3 others | [19 empty] | IMCOM | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-10-11 | 2022-10-11 | 2022-11-04 | 2022-11-11 | 2022-11-11 | GoP | 24000 | 24000 | 0 | 23640 | 23640 | 0 | [7 empty] | N/A
| S/D of 90 bags Portland Cement & 11 others | [19 empty] | IMCOM | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-10-11 | 2022-10-11 | 2022-11-04 | 2022-11-11 | 2022-11-11 | GoP | 920245 | 920245 | 0 | 905445 | 905445 | 0 | [7 empty] | N/A
| S/D of 161 pcs Hardiflex 1/4in x 4ft x8ft & 88 others | [19 empty] | IMCOM | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-10-18 | 2022-10-18 | 2022-11-21 | 2022-11-28 | 2022-11-28 | GoP | 665500 | 665500 | 0 | 661090 | 661090 | 0 | [7 empty] | N/A
| S/D of 60 pcs Globe Prepaid Card 500 & 25 others | [19 empty] | IMCOM | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-10-18 | 2022-10-18 | 2022-11-04 | 2022-11-11 | 2022-11-11 | GoP | 330500 | 330500 | 0 | 323769 | 323769 | 0 | [7 empty] | N/A
| S/D of 12 pcs Hot Dip Galvanized Cross Arm 10ft & 12 others | [19 empty] | IMCOM | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-10-18 | 2022-10-18 | 2022-11-21 | 2022-11-28 | 2022-11-28 | GoP | 500000 | 500000 | 0 | 499760 | 499760 | 0 | [7 empty] | N/A
| S/D of 88 pcs Smart Prepaid Card 500 & 5 others | [19 empty] | IMCOM | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-10-21 | 2022-10-21 | 2022-11-21 | 2022-11-28 | 2022-11-28 | GoP | 140600 | 140600 | 0 | 138925 | 138925 | 0 | [7 empty] | N/A
| S/D of 6 pcs Office Executive Chair & 2 others | [19 empty] | IMCOM | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-10-21 | 2022-10-21 | 2022-11-09 | 2022-11-16 | 2022-11-16 | GoP | 100000 | 100000 | 0 | 99000 | 99000 | 0 | [7 empty] | N/A
| S/D of 50 reams PAPER Multi-Purpose (COPY) A4 70 gsm & 8 others | [19 empty] | IMCOM | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-10-21 | 2022-10-21 | 2022-11-21 | 2022-11-28 | 2022-11-28 | GoP | 55000 | 55000 | 0 | 54500 | 54500 | 0 | [7 empty] | N/A
| S/D of 36 rream Bond Paper A4 & 16 others | [19 empty] | IMCOM | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-10-28 | 2022-10-28 | 2022-11-25 | 2022-12-02 | 2022-12-02 | GoP | 33466 | 33466 | 0 | 32866 | 32866 | 0 | [7 empty] | N/A
| S/D of 12 pcs Smart Load Card (500) & 3 others | [19 empty] | IMCOM | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-10-28 | 2022-10-28 | 2022-11-21 | 2022-11-28 | 2022-11-28 | GoP | 16200 | 16200 | 0 | 16044 | 16044 | 0 | [7 empty] | N/A
| S/D of 100 pcs Coffee (3 in 1) & 11 others | [19 empty] | IMCOM | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-10-28 | 2022-10-28 | 2022-11-24 | 2022-12-01 | 2022-12-01 | GoP | 38900 | 38900 | 0 | 38600 | 38600 | 0 | [7 empty] | N/A
| S/D of 50 pcs Hardiflex 1/4" X 4' X 8' & 17 others | [19 empty] | IMCOM | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-11-04 | 2022-11-04 | 2022-11-25 | 2022-12-02 | 2022-12-02 | GoP | 131972 | 131972 | 0 | 130822 | 130822 | 0 | [7 empty] | N/A
| S/D of 4 pcs Electric Jig Saw 600w (heavy duty) & 9 others | [19 empty] | IMCOM | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-11-04 | 2022-11-04 | 2022-11-24 | 2022-12-01 | 2022-12-01 | GoP | 200000 | 200000 | 0 | 198700 | 198700 | 0 | [7 empty] | N/A
| S/D of 500 bags Cement and 37 others | [19 empty] | IMCOM | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-11-04 | 2022-11-04 | 2022-11-24 | 2022-12-01 | 2022-12-01 | GoP | 991331 | 991331 | 0 | 988831 | 988831 | 0 | [7 empty] | N/A
| S/D of Copper Tube 1/2 2 rolls and 9 Others | [19 empty] | IMCOM | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-11-04 | 2022-11-04 | 2022-11-24 | 2022-12-01 | 2022-12-01 | GoP | 30000 | 30000 | 0 | 29910 | 29910 | 0 | [7 empty] | N/A
| CATERING SERVICES | [19 empty] | IMCOM | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-11-09 | 2022-11-09 | 2022-11-24 | 2022-12-01 | 2022-12-01 | GoP | 486928.5 | 486928.5 | 0 | 482460 | 482460 | 0 | [7 empty] | N/A
| S/D of 10 pcs Hardiflex 1/4" x 4' x 8' & 57 others | [19 empty] | MPBn, IMCOM | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-07-26 | 2022-07-26 | 2022-09-19 | 2022-09-26 | 2022-09-26 | GoP | 175000 | 175000 | 0 | 161320 | 161320 | 0 | [7 empty] | N/A
| S/D of 1 pc Oil Filter (Toyota altis) & 46 others | [19 empty] | MPBn, IMCOM | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-07-26 | 2022-07-26 | 2022-09-08 | 2022-09-15 | 2022-09-15 | GoP | 164250 | 164250 | 0 | 163250 | 163250 | 0 | [7 empty] | N/A
| S/D of 11 set BOBLOV M6 Body Camera | [19 empty] | MPBn, IMCOM | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-07-26 | 2022-07-26 | 2022-09-05 | 2022-09-12 | 2022-09-12 | GoP | 55000 | 55000 | 0 | 54780 | 54780 | 0 | [7 empty] | N/A
| S/D of 15 pcs Wheel clamps for big size vehicle wheels & 8 others | [19 empty] | MPBn, IMCOM | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-07-26 | 2022-07-26 | 2022-09-05 | 2022-09-12 | 2022-09-12 | GoP | 284052 | 284052 | 0 | 283302 | 283302 | 0 | [7 empty] | N/A
| S/D of 300 pcs Air freshener & 26 others | [19 empty] | MPBn, IMCOM | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-07-29 | 2022-07-29 | 2022-09-19 | 2022-09-26 | 2022-09-26 | GoP | 165000 | 165000 | 0 | 164400 | 164400 | 0 | [7 empty] | N/A
| S/D of 1 set Condenser Aluminum Fin and coil tube & 6 others | [19 empty] | MPBn, IMCOM | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-08-02 | 2022-08-02 | 2022-09-05 | 2022-09-12 | 2022-09-12 | GoP | 12500 | 12500 | 0 | 12320 | 12320 | 0 | [7 empty] | N/A
| S/D of 10 reams Bond Paper A4 & 14 others | [19 empty] | MPBn, IMCOM | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-08-02 | 2022-08-02 | 2022-09-19 | 2022-09-26 | 2022-09-26 | GoP | 15000 | 15000 | 0 | 14880 | 14880 | 0 | [7 empty] | N/A
| S/D of 1 pc Oil Filter (KM450) & 7 Others | [19 empty] | MPBn, IMCOM | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-08-02 | 2022-08-02 | 2022-09-09 | 2022-09-16 | 2022-09-16 | GoP | 30000 | 30000 | 0 | 29800 | 29800 | 0 | [7 empty] | N/A
| S/D of 3 pcs A4TECH KRS-83 USB Black Keyboard & 7 others | [19 empty] | MPBn, IMCOM | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-08-02 | 2022-08-02 | 2022-09-09 | 2022-09-16 | 2022-09-16 | GoP | 17500 | 17500 | 0 | 17350 | 17350 | 0 | [7 empty] | N/A
| S/D of 13 set UHF/FM Handheld Radio | [19 empty] | MPBn, IMCOM | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-08-02 | 2022-08-02 | 2022-09-08 | 2022-09-15 | 2022-09-15 | GoP | 61100 | 61100 | 0 | 60710 | 60710 | 0 | [7 empty] | N/A
| S/D of 36 pcs Prepaid Cards Globe(500) & 3 others | [19 empty] | MPBn, IMCOM | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-08-12 | 2022-08-12 | 2022-09-05 | 2022-09-12 | 2022-09-12 | GoP | 33750 | 33750 | 0 | 33105 | 33105 | 0 | [7 empty] | N/A
| S/D of 25 pcs Hardiflex 1/4 " X 4 X 8' & 70 others | [19 empty] | MPBn, IMCOM | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-08-16 | 2022-08-16 | 2022-09-09 | 2022-09-16 | 2022-09-16 | GoP | 170000 | 170000 | 0 | 169100 | 169100 | 0 | [7 empty] | N/A
| S/D of 1 pc Oil Filter (nissan navarra) & 59 others | [19 empty] | MPBn, IMCOM | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-08-31 | 2022-08-31 | 2022-09-29 | 2022-10-06 | 2022-10-06 | GoP | 151750 | 151750 | 0 | 151150 | 151150 | 0 | [7 empty] | N/A
| S/D of 3 pcs CP1660 Battery Pack & 9 others | [19 empty] | MPBn, IMCOM | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-09-02 | 2022-09-02 | 2022-10-12 | 2022-10-19 | 2022-10-19 | GoP | 31300 | 31300 | 0 | 31120 | 31120 | 0 | [7 empty] | N/A
| S/D of 3 pcs A4TECH KRS-83 USB Black Keyboard & 11 others | [19 empty] | MPBn, IMCOM | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-09-02 | 2022-09-02 | 2022-09-27 | 2022-10-04 | 2022-10-04 | GoP | 17500 | 17500 | 0 | 17300 | 17300 | 0 | [7 empty] | N/A
| S/D of 21 pcs Handheld Radio UV-82 & 1 other | [19 empty] | MPBn, IMCOM | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-09-27 | 2022-09-27 | 2022-11-04 | 2022-11-11 | 2022-11-11 | GoP | 55000 | 55000 | 0 | 54853 | 54853 | 0 | [7 empty] | N/A
| S/D of 20 bxs Mineral Water 330ml/24* & 26 others | [19 empty] | MPBn, IMCOM | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-09-27 | 2022-09-27 | 2022-10-17 | 2022-10-24 | 2022-10-24 | GoP | 110250 | 110250 | 0 | 109854 | 109854 | 0 | [7 empty] | N/A
| S/D of 501 packs Coffee 3 in 1 Twin Pack (10x50g)/Pack & 17 others | [19 empty] | MPBn, IMCOM | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-09-30 | 2022-09-30 | 2022-11-09 | 2022-11-16 | 2022-11-16 | GoP | 922500 | 922500 | 0 | 913990 | 913990 | 0 | [7 empty] | N/A
| S/D of 200 bxs Bottled Water 330mL/24* & 31 others | [19 empty] | MPBn, IMCOM | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-09-30 | 2022-09-30 | 2022-12-09 | 2022-12-16 | 2022-12-16 | GoP | 922500 | 922500 | 0 | 913700 | 913700 | 0 | [7 empty] | N/A
| S/D of 100 cans Air freshener, 150g & 11 others | [19 empty] | MPBn, IMCOM | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-10-11 | 2022-10-11 | 2022-10-28 | 2022-11-04 | 2022-11-04 | GoP | 80000 | 80000 | 0 | 79700 | 79700 | 0 | [7 empty] | N/A
| S/D of 6 bxs Binder Clips, 7.13"x5.04"x2.05",12 pcs/box & 18 others | [19 empty] | MPBn, IMCOM | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-10-11 | 2022-10-11 | 2022-10-28 | 2022-11-04 | 2022-11-04 | GoP | 16000 | 16000 | 0 | 15860 | 15860 | 0 | [7 empty] | N/A
| S/D of 1 set Condenser Aluminum Fin and coil tube & 6 others | [19 empty] | MPBn, IMCOM | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-10-11 | 2022-10-11 | 2022-10-28 | 2022-11-04 | 2022-11-04 | GoP | 12500 | 12500 | 0 | 12300 | 12300 | 0 | [7 empty] | N/A
| S/D of 1 set Intel Core i5, Computer Desktop set | [19 empty] | MPBn, IMCOM | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-10-11 | 2022-10-11 | 2022-10-28 | 2022-11-04 | 2022-11-04 | GoP | 37950 | 37950 | 0 | 37600 | 37600 | 0 | [7 empty] | N/A
| S/D of 30 cards Prepaid Cards Globe(500) & 3 others | [19 empty] | MPBn, IMCOM | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-10-11 | 2022-10-11 | 2022-10-28 | 2022-11-04 | 2022-11-04 | GoP | 30750 | 30750 | 0 | 30600 | 30600 | 0 | [7 empty] | N/A
| S/D of 1 pc Oil Filter (O-407A1) (ford ranger) & 30 others | [19 empty] | MPBn, IMCOM | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-10-18 | 2022-10-18 | 2022-11-09 | 2022-11-16 | 2022-11-16 | GoP | 64250 | 64250 | 0 | 63450 | 63450 | 0 | [7 empty] | N/A
| S/D of 6 pcs Bicycle Inner Tube 26/27.5/29 & 5 others | [19 empty] | MPBn, IMCOM | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-10-21 | 2022-10-21 | 2022-11-21 | 2022-11-28 | 2022-11-28 | GoP | 9500 | 9500 | 0 | 9080 | 9080 | 0 | [7 empty] | N/A
| S/D of 20 pcs Lanyard & 7 others | [19 empty] | MPBn, IMCOM | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-10-21 | 2022-10-21 | 2022-11-18 | 2022-11-25 | 2022-11-25 | GoP | 34000 | 34000 | 0 | 33100 | 33100 | 0 | [7 empty] | N/A
| S/D of 8 reams Paper , Multi-Purpose, 70gsm, A4, 500 sheets/ream & 16 others | [19 empty] | MPBn, IMCOM | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-10-28 | 2022-10-28 | 2022-11-25 | 2022-12-02 | 2022-12-02 | GoP | 15000 | 15000 | 0 | 14900 | 14900 | 0 | [7 empty] | N/A
| S/D of 1 pc Oil Filter (CCB13)& 8 others | [19 empty] | MPBn, IMCOM | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-11-04 | 2022-11-04 | 2022-12-06 | 2022-12-13 | 2022-12-13 | GoP | 30000 | 30000 | 0 | 29750 | 29750 | 0 | [7 empty] | N/A
| S/D of1 set Timing Belt & 26 Others | [19 empty] | PATGB | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-07-08 | 2022-07-08 | 2022-09-08 | 2022-09-15 | 2022-09-15 | GoP | 60000 | 60000 | 0 | 59285 | 59285 | 0 | [7 empty] | N/A
| S/D of 345 packs Bottled Water 500 ml x 24 & 5 Others Items | [19 empty] | PATGB | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-07-22 | 2022-07-22 | 2022-09-05 | 2022-09-12 | 2022-09-12 | GoP | 269250 | 269250 | 0 | 268150 | 268150 | 0 | [7 empty] | N/A
| S/D of 12 pcs of Sealed Beam & 15 other Items | [19 empty] | PATGB | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-07-12 | 2022-07-12 | 2022-09-09 | 2022-09-16 | 2022-09-16 | GoP | 40000 | 40000 | 0 | 39105 | 39105 | 0 | [7 empty] | N/A
| S/D of 2 Gal Soy Souce & 17 Others Items | [19 empty] | PATGB | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-08-02 | 2022-08-02 | 2022-09-12 | 2022-09-19 | 2022-09-19 | GoP | 30000 | 30000 | 0 | 29586 | 29586 | 0 | [7 empty] | N/A
| S/D of Four (4) boxes Envelope Documents A4 & 22 Others Items | [19 empty] | PATGB | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-08-19 | 2022-08-19 | 2022-09-09 | 2022-09-16 | 2022-09-16 | GoP | 16000 | 16000 | 0 | 15862.5 | 15862.5 | 0 | [7 empty] | N/A
| S/D of 200 packs of Biscuits 30 grams | [19 empty] | PATGB | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-08-24 | 2022-08-24 | 2022-10-06 | 2022-10-13 | 2022-10-13 | GoP | 82500 | 82500 | 0 | 81780 | 81780 | 0 | [7 empty] | N/A
| S/D of 2 unit of Grass Cutter | [19 empty] | PATGB | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-09-27 | 2022-09-27 | 2022-10-17 | 2022-10-24 | 2022-10-24 | GoP | 30000 | 30000 | 0 | 29600 | 29600 | 0 | [7 empty] | N/A
| S/D of 1 ea Recoil Starter Assy & 11 Others | [19 empty] | PATGB | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-10-11 | 2022-10-11 | 2022-11-24 | 2022-12-01 | 2022-12-01 | GoP | 25000 | 25000 | 0 | 24500 | 24500 | 0 | [7 empty] | N/A
| S/D of two (2) units 1.0HP Compressor Motor & 6 Others | [19 empty] | PATGB | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-10-11 | 2022-10-11 | 2022-11-24 | 2022-12-01 | 2022-12-01 | GoP | 30000 | 30000 | 0 | 29700 | 29700 | 0 | [7 empty] | N/A
| S/D of 5 cart Ink Cart,Epson C13T664100 (T6641)- Black & 8 others | [19 empty] | PATGB | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-11-04 | 2022-11-04 | 2022-11-24 | 2022-12-01 | 2022-12-01 | GoP | 16000 | 16000 | 0 | 15504 | 15504 | 0 | [7 empty] | N/A
| S/D of 1 pc Water pump Assy & 17 others | [19 empty] | PATGB | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-11-04 | 2022-11-04 | 2022-11-24 | 2022-12-01 | 2022-12-01 | GoP | 40000 | 40000 | 0 | 39500 | 39500 | 0 | [7 empty] | N/A
| S/D of 1 ea Oil Filter (Team Army Bus SKD-153) & 48 others | [19 empty] | SEBN | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-07-08 | 2022-07-08 | 2022-09-09 | 2022-09-16 | 2022-09-16 | GoP | 139024 | 139024 | 0 | 135307.5 | 135307.5 | 0 | [7 empty] | N/A
| S/D of 50 box Paper, Multi Copy (A4) & 32 others | [19 empty] | SEBN | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-07-08 | 2022-07-08 | 2022-09-19 | 2022-09-26 | 2022-09-26 | GoP | 250656 | 250656 | 0 | 246602 | 246602 | 0 | [7 empty] | N/A
| S/D of 24 pcs Marine Plywood 1/4" x4'x 8' & 34 others | [19 empty] | SEBN | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-07-15 | 2022-07-15 | 2022-09-09 | 2022-09-16 | 2022-09-16 | GoP | 80000 | 80000 | 0 | 76315 | 76315 | 0 | [7 empty] | N/A
| S/D of 15 box Paper Multi Copy A4 & 25 others | [19 empty] | SEBN | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-07-26 | 2022-07-26 | 2022-09-19 | 2022-09-26 | 2022-09-26 | GoP | 77000 | 77000 | 0 | 76300 | 76300 | 0 | [7 empty] | N/A
| S/D of 3 pcs Coffee Maker 1.2 Liters & 5 others | [19 empty] | SEBN | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-07-26 | 2022-07-26 | 2022-09-19 | 2022-09-26 | 2022-09-26 | GoP | 157407.5 | 157407.5 | 0 | 157000 | 157000 | 0 | [7 empty] | N/A
| S/D of 301 pcs Cheese 165g & 30 others | [19 empty] | SEBN | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-07-26 | 2022-07-26 | 2022-09-14 | 2022-09-21 | 2022-09-21 | GoP | 281017.5 | 281017.5 | 0 | 279415 | 279415 | 0 | [7 empty] | N/A
| S/D of 215 ea Pershing Cap for EP & 1 other | [19 empty] | SEBN | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-08-24 | 2022-08-24 | 2022-10-03 | 2022-10-10 | 2022-10-10 | GoP | 772500 | 772500 | 0 | 761650 | 761650 | 0 | [7 empty] | N/A
| S/D of 50 pcs Shoes polish 17.5ml & 5 others | [19 empty] | SEBN | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-09-27 | 2022-09-27 | 2022-10-27 | 2022-11-03 | 2022-11-03 | GoP | 77075 | 77075 | 0 | 76830 | 76830 | 0 | [7 empty] | N/A
| S/D of 4 units Desktop widescreen (16:9) SD 720 x 576 HD 1280 x 720/HDMI & 5 others | [19 empty] | SEBN | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-09-27 | 2022-09-27 | 2022-10-26 | 2022-11-02 | 2022-11-02 | GoP | 323702 | 323702 | 0 | 322702 | 322702 | 0 | [7 empty] | N/A
| S/D of Speaker mic 2 pcs and 2 others | [19 empty] | SEBN | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-09-27 | 2022-09-27 | 2022-11-23 | 2022-11-30 | 2022-11-30 | GoP | 12500 | 12500 | 0 | 12100 | 12100 | 0 | [7 empty] | N/A
| S/D of 11 pcs Anti-Riot Helmet & 4 others | [19 empty] | SEBN | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-09-27 | 2022-09-27 | 2022-11-08 | 2022-11-15 | 2022-11-15 | GoP | 500000 | 500000 | 0 | 480810 | 480810 | 0 | [7 empty] | N/A
| S/D of 2 pcs Fan Motor and 1 Other | [19 empty] | SEBN | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-09-27 | 2022-09-27 | 2022-11-23 | 2022-11-30 | 2022-11-30 | GoP | 13000 | 13000 | 0 | 12850 | 12850 | 0 | [7 empty] | N/A
| S/D of 2 pcs Window 10 Professional Operating system | [19 empty] | SEBN | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-09-27 | 2022-09-27 | 2022-11-23 | 2022-11-30 | 2022-11-30 | GoP | 14750 | 14750 | 0 | 14600 | 14600 | 0 | [7 empty] | N/A
| S/D of 1 pc Slit Type Aircon Inverter 1.5hp & 1 other | [19 empty] | SEBN | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-10-11 | 2022-10-11 | 2022-10-27 | 2022-11-03 | 2022-11-03 | GoP | 54887.5 | 54887.5 | 0 | 54417.5 | 54417.5 | 0 | [7 empty] | N/A
| S/D of Fire Extinguisher, Dry chemical 5 pcs and 7 others | [19 empty] | SEBN | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-10-11 | 2022-10-11 | 2022-12-02 | 2022-12-09 | 2022-12-09 | GoP | 106445 | 106445 | 0 | 104845 | 104845 | 0 | [7 empty] | N/A
| S/D of 350 cans Fruit Cock Tail 836g & 23 others | [19 empty] | SEBN | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-10-11 | 2022-10-11 | 2022-10-27 | 2022-11-03 | 2022-11-03 | GoP | 368301.5 | 368301.5 | 0 | 366833.5 | 366833.5 | 0 | [7 empty] | N/A
| S/D of 2 pcs Trombone Slide Lubricant (SN:17301) and 12 others | [19 empty] | SEBN | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-10-11 | 2022-10-11 | 2022-10-28 | 2022-11-04 | 2022-11-04 | GoP | 31702 | 31702 | 0 | 30730 | 30730 | 0 | [7 empty] | N/A
| S/D of Wiper blade w/ arm (Team Army Bus SKD 152) 1 set and 43 others | [19 empty] | SEBN | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-10-18 | 2022-10-18 | 2022-11-23 | 2022-11-30 | 2022-11-30 | GoP | 151000 | 151000 | 0 | 150860 | 150860 | 0 | [7 empty] | N/A
| S/D of 20 ream Bond Paper A4 & 16 others | [19 empty] | SEBN | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-10-28 | 2022-10-28 | 2022-11-25 | 2022-12-02 | 2022-12-02 | GoP | 50000 | 50000 | 0 | 49567.5 | 49567.5 | 0 | [7 empty] | N/A
| S/D of 30 Globe Prepaid card 1000 pcs & 1 Other | [19 empty] | SSC, IMCOM | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-08-02 | 2022-08-02 | 2022-09-09 | 2022-09-19 | 2022-09-19 | GoP | 45000 | 45000 | 0 | 44790 | 44790 | 0 | [7 empty] | N/A
| S/D of 12 pcs Prepaid Cignal Card Load 1,000 | [19 empty] | SSC, IMCOM | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-08-02 | 2022-08-02 | 2022-09-08 | 2022-09-15 | 2022-09-15 | GoP | 12000 | 12000 | 0 | 11856 | 11856 | 0 | [7 empty] | N/A
| S/D of 24 pcs Prepaid Globe internet Load 1000 | [19 empty] | SSC, IMCOM | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-08-02 | 2022-08-02 | 2022-09-09 | 2022-09-16 | 2022-09-16 | GoP | 24000 | 24000 | 0 | 23712 | 23712 | 0 | [7 empty] | N/A
| S/D of 40 ream A4 Bond Paper & 21 others | [19 empty] | SSC, IMCOM | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-08-24 | 2022-08-24 | 2022-09-27 | 2022-10-04 | 2022-10-04 | GoP | 122000 | 122000 | 0 | 121200 | 121200 | 0 | [7 empty] | N/A
| S/D of 49 pck Spaghetti Pasta 900g & 14 others | [19 empty] | SSC, IMCOM | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-08-24 | 2022-08-24 | 2022-09-27 | 2022-10-04 | 2022-10-04 | GoP | 464785 | 464785 | 0 | 462613 | 462613 | 0 | [7 empty] | N/A
| S/D of 125 can Pineapple Juice & 14 others | [19 empty] | SSC, IMCOM | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-08-31 | 2022-08-31 | 2022-09-27 | 2022-10-04 | 2022-10-04 | GoP | 526020 | 526020 | 0 | 524890 | 524890 | 0 | [7 empty] | N/A
| S/D of 5 unit Computer desktop (windows 11 Intel core i3 12100 processor with monitor) & 1 other | [19 empty] | SSC, IMCOM | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-09-20 | 2022-09-20 | 2022-10-12 | 2022-10-19 | 2022-10-19 | GoP | 261500 | 261500 | 0 | 259900 | 259900 | 0 | [7 empty] | N/A
| S/D of 200 box Vitamins with Gensing 10per box & 1 other | [19 empty] | SSC, IMCOM | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-10-11 | 2022-10-11 | 2022-10-28 | 2022-11-04 | 2022-11-04 | GoP | 100000 | 100000 | 0 | 99200 | 99200 | 0 | [7 empty] | N/A
| S/D of 199 pack Spaghetti Pasta 900g & 14 others | [19 empty] | SSC, IMCOM | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-10-11 | 2022-10-11 | 2022-10-28 | 2022-11-04 | 2022-11-04 | GoP | 305420 | 305420 | 0 | 302520 | 302520 | 0 | [7 empty] | N/A
| S/D of 30 sheet GI sheet #12 (yero) & 8 others | [19 empty] | SSC, IMCOM | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-10-11 | 2022-10-11 | 2022-10-28 | 2022-11-04 | 2022-11-04 | GoP | 112000 | 112000 | 0 | 111700 | 111700 | 0 | [7 empty] | N/A
| S/D of 2 unit Computer desktop (windows 11 Intel core i3 12100 processor with monitor) & 2 others | [19 empty] | SSC, IMCOM | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-10-11 | 2022-10-11 | 2022-10-28 | 2022-11-04 | 2022-11-04 | GoP | 176000 | 176000 | 0 | 174800 | 174800 | 0 | [7 empty] | N/A
| procurement of FIFTEEN (15) rms A4 bond paper sub 20/70 gsm and 15 Other Line Items | [19 empty] | 1IMB | NO | Shopping |  | 2022-07-22 |  |  | 2022-07-26 |  |  |  | 2022-07-26 | 2022-07-26 | 2022-08-23 | 2022-09-06 | 2022-08-02 | GoP | 33290 | 33290 |  | 32781 | 32781 |  | RG SANTOS TRADING | [6 empty] | N/A
| Procurement of TWO (2) set Desktop Computer Core i5, Windows 11, RAM 16,SSD 240G/1TB w/ Monitor,21LED, w/ keyboard and mouse (usb type) and 2 other line items | [19 empty] | 1IMB | NO | NP-53.9 - Small Value Procurement |  | 2022-07-28 |  |  | 2022-08-02 |  |  |  | 2022-08-02 | 2022-08-02 | 2022-08-02 | 2022-08-05 | 2022-08-05 | GoP | 100000 | 100000 |  | 100000 | 100000 |  | EVERYBODYS TRADING & GEN MDSE | [6 empty] | N/A
5-02-99-030-00 | Representation Exp | [19 empty] | 2IMB | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-02-21 | 2022-02-21 | 2022-04-19 | 2022-04-27 | 2022-04-27 | MOOE | 114650 | 114650 |  | 114650 | 113852 | [8 empty] | N/A
5-02-03-990-00 | Other Supplies & Materials Exp | [19 empty] | 2IMB | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-04-11 | 2022-04-11 | 2022-05-27 | 2022-06-02 | 2022-06-02 | MOOE | 152500 | 152500 |  | 152500 | 150450 | [8 empty] | N/A
5-02-99-030-00 | Representation Exp | [19 empty] | 2IMB | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-04-11 | 2022-04-11 | 2022-04-04 | 2022-04-11 | 2022-04-11 | MOOE | 110650 | 110650 |  | 110650 | 110279 | [8 empty] | N/A
5-02-13-040-01 | RM Building | [19 empty] | 2IMB | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-05-18 | 2022-05-18 | 2022-06-15 | 2022-06-21 | 2022-06-21 | MOOE | 6000 | 6000 |  | 6000 | 5971 | [8 empty] | N/A
5-02-13-050-01 | RM Machinery | [19 empty] | 2IMB | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-03-03 | 2022-03-03 | 2022-05-19 | 2022-05-24 | 2022-05-24 | MOOE | 45000 | 45000 |  | 45000 | 44826 | [8 empty] | N/A
5-02-13-040-99 | RM Other Structures | [19 empty] | 2IMB | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-03-07 | 2022-03-07 | 2022-04-12 | 2022-04-19 | 2022-04-19 | MOOE | 166000 | 166000 |  | 166000 | 165818 | [8 empty] | N/A
5-02-03-990-00 | Other Supplies & Materials Exp | [19 empty] | 2IMB | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-03-07 | 2022-03-07 | 2022-06-06 | 2022-06-13 | 2022-06-13 | MOOE | 50500 | 50500 |  | 50500 | 50400 | [8 empty] | N/A
5-02-13-060-01 | RM Motor Vehicle | [19 empty] | 2IMB | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-05-16 | 2022-05-16 | 2022-07-11 | 2022-07-18 | 2022-07-18 | MOOE | 70000 | 70000 |  | 70000 | 69880 | [8 empty] | N/A
5-02-13-060-01 | RM Motor Vehicle | [19 empty] | 2IMB | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-06-24 | 2022-06-24 | 2022-06-15 | 2022-06-22 | 2022-06-22 | MOOE | 70000 | 70000 |  | 70000 | 69868 | [8 empty] | N/A
5-02-13-050-03 | RM ICT Equipment | [19 empty] | 2IMB | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-05-16 | 2022-05-16 | 2022-08-11 | 2022-08-17 | 2022-08-17 | MOOE | 81500 | 81500 |  | 81500 | 81390 | [8 empty] | N/A
5-02-99-030-00 | Representation Exp | [19 empty] | 2IMB | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-06-20 | 2022-06-20 | 2022-09-19 | 2022-09-23 | 2022-09-23 | MOOE | 106150 | 106150 |  | 106150 | 105777 | [8 empty] | N/A
5-02-13-040-01 | RM Building | [19 empty] | 2IMB | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-07-12 | 2022-07-12 | 2022-09-09 | 2022-09-16 | 2022-09-16 | MOOE | 154000 | 154000 |  | 154000 | 153753 | [8 empty] | N/A
5-02-13-050-03 | RM ICT Equipment | [19 empty] | 2IMB | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-07-12 | 2022-07-12 | 2022-09-09 | 2022-09-16 | 2022-09-16 | MOOE | 11000 | 11000 |  | 11000 | 10855 | [8 empty] | N/A
5-02-13-040-01 | RM BUILDING | [19 empty] | 2IMB | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-09-28 | 2022-09-28 | 2022-11-09 | 2022-11-16 | 2022-11-16 | MOOE | 90500 | 90500 |  | 90500 | 90020 | [8 empty] | N/A
5-02-13-040-02 | Semi Exp Furniture & Fixture | [19 empty] | 2IMB | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-06-20 | 2022-06-20 | 2022-10-06 | 2022-10-13 | 2022-10-13 | MOOE | 75000 | 75000 |  | 75000 | 74960 | [8 empty] | N/A
5-02-13-050-13 | RM Sports Equipment | [19 empty] | 2IMB | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-07-12 | 2022-07-12 | 2022-11-25 | 2022-12-02 | 2022-12-02 | MOOE | 100000 | 100000 |  | 100000 | 99780 | [8 empty] | N/A
5-02-03-200-01 | SEMI FUR & FIXTURES | [19 empty] | 2IMB | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-09-09 | 2022-09-09 | 2022-11-11 | 2022-11-18 | 2022-11-18 | MOOE | 18000 | 18000 |  | 18000 | 17940 | [8 empty] | N/A
5-02-03-210-00 | SEMI EXP Machinery Exp | [19 empty] | 2IMB | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-09-09 | 2022-09-09 | 2022-11-11 | 2022-11-18 | 2022-11-18 | MOOE | 50000 | 50000 |  | 50000 | 49920 | [8 empty] | N/A
5-02-05-040-00 | Cable Expenses | [19 empty] | 2IMB | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-09-09 | 2022-09-09 | 2022-10-19 | 2022-10-26 | 2022-10-26 | MOOE | 9000 | 9000 |  | 9000 | 8946 | [8 empty] | N/A
5-02-05-030-00 | Internet Expenses | [19 empty] | 2IMB | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-09-09 | 2022-09-09 | 2022-10-19 | 2022-10-26 | 2022-10-26 | MOOE | 9000 | 9000 |  | 9000 | 8964 | [8 empty] | N/A
5-02-03-990-00 | OTHER SUPPLIES & Materials | [19 empty] | 2IMB | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-09-09 | 2022-09-09 | 2022-11-23 | 2022-11-29 | 2022-11-29 | MOOE | 11500 | 11500 |  | 11500 | 11430 | [8 empty] | N/A
5-02-13-050-13 | Sports Equipment | [19 empty] | 2IMB | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-09-28 | 2022-09-28 | 2022-11-22 | 2022-11-29 | 2022-11-29 | MOOE | 30000 | 30000 |  | 30000 | 29415 | [8 empty] | N/A
5-02-13-050-03 | RM ICT Equipment | [19 empty] | 2IMB | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-09-12 | 2022-09-12 | 2022-11-16 | 2022-11-22 | 2022-11-22 | MOOE | 6500 | 6500 |  | 6500 | 6380 | [8 empty] | N/A
5-02-13-050-08 | R&M-Construction & Heavy Eqpt | [19 empty] | 5IMB | NO | NP-53.9 - Small Value Procurement | [8 empty] | 15 Jul 22 | 29 Jul 22 | 29 Jul 22 | 29 Jul 22 | 02 Aug 22 | MOOE | 35000 | 35000 |  | 35000 | 34500 | [8 empty] | N/A
5-02-03-990-00 | Other Supplies & Materials | [19 empty] | 5IMB | NO | NP-53.9 - Small Value Procurement | [8 empty] | 15 Jul 22 | 29 Jul 22 | 29 Jul 22 | 29 Jul 22 | 02 Aug 22 | MOOE | 5000 | 5000 |  | 5000 | 4990 | [8 empty] | N/A
5-02-05-020-01 | Telephone Expenses-Mobile | [19 empty] | 5IMB | NO | NP-53.9 - Small Value Procurement | [8 empty] | 15 Jul 22 | 29 Jul 22 | 29 Jul 22 | 29 Jul 22 | 02 Aug 22 | MOOE | 6000 | 6000 |  | 6000 | 5987 | [8 empty] | N/A
5-02-03-080-00 | Medical, Dental & Lab Supplies | [19 empty] | 5IMB | NO | NP-53.9 - Small Value Procurement | [8 empty] | 15 Jul 22 | 29 Jul 22 | 29 Jul 22 | 29 Jul 22 | 02 Aug 22 | MOOE | 12500 | 12500 |  | 12500 | 10595 | [8 empty] | N/A
5-02-03-070-00 | Drugs and Medicines | [19 empty] | 5IMB | NO | NP-53.9 - Small Value Procurement | [8 empty] | 22 Jul 22 | 29 Jul 22 | 29 Jul 22 | 29 Jul 22 | 02 Aug 22 | MOOE | 10000 | 10000 |  | 10000 | 6300 | [8 empty] | N/A
5-02-13-040-01 | R&M-Buildings | [19 empty] | 5IMB | NO | NP-53.9 - Small Value Procurement | [8 empty] | 25 Jul 22 | 29 Jul 22 | 29 Jul 22 | 29 Jul 22 | 02 Aug 22 | MOOE | 222000 | 222000 |  | 222000 | 221470 | [8 empty] | N/A
5-02-99-030-00 | Representation Expenses | [19 empty] | 5IMB | NO | NP-53.9 - Small Value Procurement | [8 empty] | 25 Jul 22 | 08 Aug 22 | 08 Aug 22 | 08 Aug 22 | 11 Aug 22 | MOOE | 15000 | 15000 |  | 15000 | 14895 | [8 empty] | N/A
5-02-99-030-00 | Representation Expenses/Catering | [19 empty] | 5IMB | NO | NP-53.9 - Small Value Procurement | [8 empty] | 25 Jul 22 | 18 Aug 22 | 18 Aug 22 | 19 Aug 22 | 22 Aug 22 | MOOE | 23500 | 23500 |  | 23500 | 23311 | [8 empty] | N/A
5-02-13-060-01 | Vehicle Parts & Accessories | [19 empty] | 5IMB | NO | NP-53.9 - Small Value Procurement | [8 empty] | 10 Oct 22 | 2022-10-21 | 2022-10-21 | 2022-10-21 | 2022-10-25 | MOOE | 80000 | 80000 |  | 80000 | 79700 | [8 empty] | N/A
5-02-13-040-01 | Construction Materials & Supplies | [19 empty] | 5IMB | NO | NP-53.9 - Small Value Procurement | [8 empty] | 10 Oct 22 | 2022-10-21 | 2022-10-21 | 2022-10-24 | 2022-10-25 | MOOE | 95530 | 95530 |  | 95530 | 91840 | [8 empty] | N/A
5-02-03-080-00 | Medical, Dental & Lab Supplies | [19 empty] | 5IMB | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-10-07 | 2022-10-19 | 2022-10-19 | 2022-10-20 | 2022-10-25 | MOOE | 14405 | 14405 |  | 14405 | 13720 | [8 empty] | N/A
5-02-99-030-00 | Representation Expense | [19 empty] | 5IMB | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-10-07 | 2022-10-19 | 2022-10-19 | 2022-10-20 | 2022-10-25 | MOOE | 16000 | 16000 |  | 16000 | 15975 | [8 empty] | N/A
5-02-03-070-00 | Drugs and Medicines | [19 empty] | 5IMB | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-10-17 | 2022-11-04 | 2022-11-04 | 2022-11-07 | 2022-11-08 | MOOE | 13700 | 13700 |  | 13700 | 13315 | [8 empty] | N/A
5-02-02-010-00 | TRAINING SUPPLIES | [19 empty] | 5IMB | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-11-11 | 2022-11-28 | 2022-11-28 | 2022-11-28 | 2022-12-01 | MOOE | 39570 | 39570 |  | 39570 | 38990 | [8 empty] | N/A
5-02-99-070-01 | ICT SOFTWARE SUBSCRIPTION | [19 empty] | 5IMB | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-11-11 | 2022-09-26 | 2022-09-26 | 2022-09-27 | 2022-09-29 | MOOE | 112500 | 112500 |  | 112500 | 112000 | [8 empty] | N/A
5-02-99-030-00 | Representation Expense | [19 empty] | 5IMB | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-11-18 | 2022-12-09 | 2022-12-09 | 2022-12-12 | 2022-12-13 | MOOE | 42500 | 42500 |  | 42500 | 42480 | [8 empty] | N/A
5-02-99-030-00 | Representation Expense | [19 empty] | 5IMB | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-11-18 | 2022-11-28 | 2022-11-28 | 2022-11-28 | 2022-12-01 | MOOE | 5000 | 5000 |  | 5000 | 4980 | [8 empty] | N/A
5-02-13-040-01 | R&M-Buildings | [19 empty] | 5IMB | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-11-23 | 2022-12-07 | 2022-12-07 | 2022-12-12 | 2022-12-13 | MOOE | 73690 | 73690 |  | 73690 | 73520 | [8 empty] | N/A
| ICT Equipment | [19 empty] | 7IMB | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-03-07 | 2022-03-21 | 2022-03-22 | 2022-03-29 | 2022-03-29 | GoP | 33000 | 33000 | 0 | 32792 | 32792 | 0 | N/A | [6 empty] | N/A
| Other Machinery Equipment | [19 empty] | 7IMB | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-03-07 | 2022-03-21 | 2022-03-22 | 2022-03-29 | 2022-03-29 | GoP | 53500 | 53500 | 0 | 53150 | 53150 | 0 | N/A | [6 empty] | N/A
| RM EP Barracks | [19 empty] | 7IMB | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-03-07 | 2022-03-21 | 2022-03-22 | 2022-03-29 | 2022-03-29 | GoP | 941543 | 941543 | 0 | 939423 | 939423 | 0 | N/A | [6 empty] | N/A
| Semi Expendable Other Machinery | [19 empty] | 7IMB | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-03-07 | 2022-03-21 | 2022-03-22 | 2022-03-29 | 2022-03-29 | GoP | 53500 | 53500 | 0 | 53150 | 53150 | 0 | N/A | [6 empty] | N/A
| Drugs & Medicine | [19 empty] | 7IMB | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-03-07 | 2022-03-21 | 2022-03-22 | 2022-03-29 | 2022-03-29 | GoP | 16000 | 16000 | 0 | 15884 | 15884 | 0 | N/A | [6 empty] | N/A
| RM Barraks | [19 empty] | 7IMB | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-03-07 | 2022-03-21 | 2022-03-22 | 2022-03-29 | 2022-03-29 | GoP | 941543 | 941543 | 0 | 939423 | 939423 | 0 | N/A | [6 empty] | N/A
| Office Equipment | [19 empty] | 7IMB | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-04-22 | 2022-04-22 | 2022-05-18 | 2022-05-25 | 2022-05-25 | GoP | 74000 | 74000 | 0 | 73600 | 73600 | 0 | N/A | [6 empty] | N/A
| Office Equipment | [19 empty] | 7IMB | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-04-22 | 2022-04-22 | 2022-05-18 | 2022-05-25 | 2022-05-25 | GoP | 40000 | 40000 | 0 | 39800 | 39800 | 0 | N/A | [6 empty] | N/A
| Office Equipment | [19 empty] | 7IMB | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-04-22 | 2022-04-22 | 2022-05-18 | 2022-05-25 | 2022-05-25 | GoP | 74000 | 74000 | 0 | 73600 | 73600 | 0 | N/A | [6 empty] | N/A
| REPIPING OF SOCOM WATER SYSTEM | [19 empty] | 7IMB | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-10-27 | 2022-10-10 | 2022-04-22 | 2022-04-22 | 2022-04-22 | GoP | 109000 | 109000 | 0 | 108679 | 108679 | 0 | N/A | [6 empty] | N/A
| R&M OF TOQ PARKING AREA AT SOCOM | [19 empty] | 7IMB | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-10-27 | 2022-10-10 | 2022-04-22 | 2022-10-07 | 2022-10-07 | GoP | 215000 | 215000 | 0 | 214710 | 214710 | 0 | N/A | [6 empty] | N/A
| R&M OF MOTORPOOL BARRACKS AT SOCOM | [19 empty] | 7IMB | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-10-27 | 2022-10-10 | 2022-04-22 | 2022-10-07 | 2022-10-07 | GoP | 378082 | 378082 | 0 | 377662 | 377662 | 0 | N/A | [6 empty] | N/A
| Office Supplies | [19 empty] | 7IMB | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-10-13 | 2022-11-24 | 2022-11-28 | 2022-12-05 | 2022-12-05 | GoP | 40000 | 40000 | 0 | 39800 | 39800 | 0 | N/A | [6 empty] | N/A
| Telephone Expense | [19 empty] | 7IMB | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-10-13 | 2022-11-24 | 2022-11-28 | 2022-12-05 | 2022-12-05 | GoP | 15000 | 15000 | 0 | 14994.75 | 14994.75 | 0 | N/A | [6 empty] | N/A
| Telephone Expense | [19 empty] | 7IMB | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-10-13 | 2022-11-24 | 2022-11-28 | 2022-12-05 | 2022-12-05 | GoP | 15000 | 15000 | 0 | 14994.75 | 14994.75 | 0 | N/A | [6 empty] | N/A
| Office Supplies | [19 empty] | 7IMB | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-10-13 | 2022-11-24 | 2022-11-28 | 2022-12-05 | 2022-12-05 | GoP | 40000 | 40000 | 0 | 39800 | 39800 | 0 | N/A | [6 empty] | N/A
5-02-02-10-00 | Training Expense | Training Expense | [18 empty] | 9IMB | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-09-23 | 13 Oct 22 | 13 Oct 22 | 2022-10-18 | 2022-10-18 | MOOE | 35000 | 35000 | 0 | 34948 | 34948 | [8 empty] | N/A
5-02-03-210-03 | Semi-Expandable ICT Equipment | Semi-Expandable ICT Equipment | [18 empty] | 9IMB | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-10-03 | 26 Oct 22 | 26 Oct 22 | 2022-11-02 | 2022-11-02 | MOOE | 105400 | 105400 | 0 | 105300 | 105300 | [8 empty] | N/A
5-02-99-030-00 | Representation | Representation | [18 empty] | 9IMB | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-10-03 | 24 Oct 22 | 24 Oct 22 | 2022-10-28 | 2022-10-28 | MOOE | 105000 | 105000 | 0 | 104903 | 104903 | [8 empty] | N/A
5-02-03-210-03 | Semi-Expendable ICT Equipment Expenses | Semi-Expendable ICT Equipment Expenses | [18 empty] | 9IMB | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-10-03 | 07 Nov 22 | 07 Nov 22 | 2022-11-11 | 2022-11-11 | MOOE | 14999 | 14999 | 0 | 14990 | 14990 | [8 empty] | N/A
5-02-03-990-00 | Other Supplies Expenses | Other Supplies Expenses | [18 empty] | 9IMB | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-10-03 | 26 Oct 22 | 26 Oct 22 | 2022-11-02 | 2022-11-02 | MOOE | 3750 | 3750 | 0 | 3743 | 3743 | [8 empty] | N/A
5-02-99-030-00 | Representation Expenses | Representation Expenses | [18 empty] | 9IMB | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-10-14 | 2022-11-07 | 2022-11-07 | 2022-11-11 | 2022-11-11 | MOOE | 10000 | 10000 | 0 | 9969 | 9969 | [8 empty] | N/A
5-02-99-030-00 | Representation Expenses | Representation Expenses | [18 empty] | 9IMB | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-10-03 | 2022-10-26 | 2022-10-26 | 2022-11-02 | 2022-11-02 | MOOE | 19750 | 19750 | 0 | 19721 | 19721 | [8 empty] | N/A
5-02-13-060-01 | R & M Motor Vehicles Expense | [19 empty] | 9IMB | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-10-14 | 2022-11-07 | 2022-11-07 | 2022-11-11 | 2022-11-11 | MOOE | 10000 | 10000 | 0 | 9980 | 9980 | [8 empty] | N/A
5-02-13-040-01 | R & M Buildings | [19 empty] | 9IMB | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-10-14 | 16 Nov 22 | 16 Nov 22 | 2022-11-21 | 2022-11-21 | MOOE | 29100 | 29100 | 0 | 29045 | 29045 | [8 empty] | N/A
5-02-03-990-00 | Other Supplies | [19 empty] | 9IMB | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-10-25 | 25 Nov 22 | 25 Nov 22 | 2022-11-28 | 2022-11-28 | MOOE | 65000 | 65000 | 0 | 64895 | 64895 | [8 empty] | N/A
5-02-03-080-00 | Medical, Dental and Laboratory Supplies | [19 empty] | 9IMB | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-11-24 | 2022-12-12 | 2022-12-12 | 2022-12-14 | 2022-12-14 | MOOE | 37550 | 37550 | 0 | 37502 | 37502 | [8 empty] | N/A
5-02-03-990-00 | Other Supply & Material Expense | [19 empty] | 9IMB | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-12-05 | 16 Dec 22 | 16 Dec 22 | 2022-12-19 | 2022-12-19 | MOOE | 20000 | 20000 | 0 | 19905 | 19905 | [8 empty] | N/A
5-02-99-030-00 | Representation Expense | [19 empty] | 9IMB | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-12-05 | 16 Dec 22 | 16 Dec 22 | 2022-12-19 | 2022-12-19 | MOOE | 10000 | 10000 | 0 | 9920 | 9920 | [8 empty] | N/A
5-02-05-030-00 | Internet Exp | [19 empty] | 14IMB | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-04-05 | 2022-04-05 | 2022-04-19 | 2022-04-27 | 2022-04-27 | MOOE | 30000 | 30000 | 0 | 29840 | 29840 | [8 empty] | N/A
5-02-13-040-01 | RM Building | [19 empty] | 14IMB | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-05-04 | 2022-05-04 | 2022-05-30 | 2022-06-06 | 2022-06-06 | MOOE | 24000 | 24000 | 0 | 23710 | 23710 | [8 empty] | N/A
5-02-13-040-01 | RM Building | [19 empty] | 14IMB | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-02-21 | 2022-02-21 | 2022-04-07 | 2022-04-12 | 2022-04-12 | MOOE | 264000 | 264000 | 0 | 262300 | 262300 | [8 empty] | N/A
5-02-05-020-01 | Telephone Mobile | [19 empty] | 14IMB | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-07-13 | 2022-07-13 | 2022-08-23 | 2022-08-30 | 2022-08-30 | MOOE | 30000 | 30000 | 0 | 29864 | 29864 | [8 empty] | N/A
5-02-13-040-01 | RM Other structure | [19 empty] | 14IMB | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-07-26 | 2022-07-26 | 2022-10-04 | 2022-10-11 | 2022-10-11 | MOOE | 156000 | 156000 | 0 | 155134 | 155134 | [8 empty] | N/A
5-02-03-010-02 | OFFICE SUPPLY EXP | [19 empty] | 14IMB | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-09-30 | 2022-09-30 | 2022-11-19 | 2022-11-22 | 2022-11-22 | MOOE | 65000 | 65000 | 0 | 63794 | 63794 | [8 empty] | N/A
5-02-99-030-00 | Representation Expenses | [19 empty] | 14IMB | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-07-28 | 2022-07-28 | 2022-10-14 | 2022-10-20 | 2022-10-20 | MOOE | 252000 | 252000 | 0 | 250270 | 250270 | [8 empty] | N/A
5-02-13-060-01 | RM Motor Vehicle | [19 empty] | 14IMB | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-07-26 | 2022-07-26 | 2022-11-03 | 2022-11-07 | 2022-11-07 | MOOE | 140000 | 140000 | 0 | 135114 | 135114 | [8 empty] | N/A
Total Alloted Budget of Procurement Activities | [37 empty] | 40519162 | [13 empty] | 40519162
Total Contract Price of Procurement Actitvites Conducted | [37 empty] | 39934132 | [13 empty] | 39934132
Total Savings (Total Alloted Budget - Total Contract Price) | [37 empty] | 585030 | [13 empty] | 585030
0N-GOING PROCUREMENT ACTIVITIES
| CATERING SERVICES | [19 empty] | AREO | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-11 | 2022-11-11 | 2022-12-12 | N/A | N/A | GoP | 906300 | 906300 | 0 | 902947.5 | 902947.5 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of 4pieces Heater Glow Plug (Toyota Revo) and 11 Others | [19 empty] | AREO | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-11 | 2022-11-11 | N/A | N/A | N/A | GoP | 100275 | 100275 | 0 | 99875 | 99875 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of 1piece Air Filter (Toyota Hi-Lux) and 19 others | [19 empty] | AREO | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-11 | 2022-11-11 | 2022-12-15 | 2022-12-21 | N/A | GoP | 99960 | 99960 | 0 | 99660 | 99660 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of 3kilograms GI Tie Wire #16 and 44 others | [19 empty] | AREO | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-18 | 2022-11-18 | N/A | N/A | N/A | GoP | 77274 | 77274 | 0 | 76874 | 76874 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of 4 sets of Office Workstation for 4 Seater Partition with 4 pieces Mobile Cabinet Dimension L100" x W50" x 43" | [19 empty] | AREO | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-13 | 2022-12-13 | N/A | N/A | N/A | GoP | 178000 | 178000 | 0 | 177000 | 177000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of 2 sets Con Rod Bearing (ISUZU ELF) & 48 others | [19 empty] | 9PED | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-18 | 2022-11-18 | 2022-12-13 | 2022-12-23 | N/A | GoP | 100000 | 100000 | 0 | 98392 | 98392 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of 250 Antigen Test Kits | [19 empty] | HIMCOM | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-24 | 2022-11-24 | N/A | N/A | N/A | GoP | 80000 | 80000 | 0 | 47250 | 47250 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of Binding Machine 1 Unit | [19 empty] | HIMCOM | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-24 | 2022-11-24 | N/A | N/A | N/A | GoP | 13320 | 13320 | 0 | 13000 | 13000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of Ink set 4 Colors and 1 other | [19 empty] | HIMCOM | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-24 | 2022-11-24 | N/A | N/A | N/A | GoP | 24848 | 24848 | 0 | 24500 | 24500 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of 31 pcs Globe Prepaid Card 500 & 1 other | [19 empty] | HIMCOM | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-24 | 2022-11-24 | N/A | N/A | N/A | GoP | 31000 | 31000 | 0 | 30690 | 30690 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of 4 unit Desktop Ryzen i3 and 2 others | [19 empty] | HIMCOM | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-09 | 2022-12-09 | 2022-12-22 | N/A | N/A | GoP | 410000 | 410000 | 0 | 404500 | 404500 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of 12 pcs MS Home Student 2021 | [19 empty] | HIMCOM | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-09 | 2022-12-09 | N/A | N/A | N/A | GoP | 87600 | 87600 | 0 | 84000 | 84000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of 20 pcs Data Folder and 17 others | [19 empty] | HIMCOM | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-13 | 2022-12-13 | N/A | N/A | N/A | GoP | 53052 | 53052 | 0 | 52042 | 52042 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of 1220 bdft 2in x 3in x 12ft Coco Lumber and 30 others | [19 empty] | IMCOM | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-11 | 2022-11-11 | 2022-12-07 | N/A | N/A | GoP | 909700 | 909700 | 0 | 907160 | 907160 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of 11 pc Oil Filter (Ford Ranger) and 25 Others | [19 empty] | IMCOM | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-11 | 2022-11-11 | N/A | N/A | N/A | GoP | 266000 | 266000 | 0 | 261200 | 261200 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of 493 pairs Slippers and 14 others | [19 empty] | IMCOM | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-11 | 2022-11-11 | 2022-12-15 | 2022-12-19 | N/A | GoP | 433750 | 433750 | 0 | 424085 | 424085 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of Mineral water 330ml x 24pcs per box 148 bxs and 24 Others | [19 empty] | IMCOM | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-11 | 2022-11-11 | 2022-12-09 | N/A | N/A | GoP | 998810 | 998810 | 0 | 996210 | 996210 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of 100 pcs Hardiflex 1/4in x 4ft x 8ft and 91 others | [19 empty] | IMCOM | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-11 | 2022-11-11 | 2022-12-12 | 2022-12-16 | N/A | GoP | 993435 | 993435 | 0 | 987260 | 987260 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of 1 set Hydraulic Pump Oil Seal & 3 others | [19 empty] | IMCOM | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-18 | 2022-11-18 | 2022-12-12 | N/A | N/A | GoP | 47812.5 | 47812.5 | 0 | 47700 | 47700 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of 12 pcs External Hardrive & 4 others | [19 empty] | IMCOM | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-24 | 2022-11-24 | N/A | N/A | N/A | GoP | 97812.5 | 97812.5 | 0 | 97512.5 | 97512.5 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of 2 units Laptop | [19 empty] | IMCOM | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-24 | 2022-11-24 | N/A | N/A | N/A | GoP | 100000 | 100000 | 0 | 99600 | 99600 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of 17 tins Flat Latex White and 17 others | [19 empty] | IMCOM | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-13 | 2022-12-13 | N/A | N/A | N/A | GoP | 407550 | 407550 | 0 | 406750 | 406750 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of 20 pcs Hardiflex 1/4in x 4ft x8ft and 43 others | [19 empty] | IMCOM | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-13 | 2022-12-13 | N/A | N/A | N/A | GoP | 300000 | 300000 | 0 | 295000 | 295000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of 610 gals Acreex Spanish Green w/ Catalyst & 8 others | [19 empty] | IMCOM | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-13 | 2022-12-13 | N/A | N/A | N/A | GoP | 967100 | 967100 | 0 | 966300 | 966300 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of 112 pcs Antigen Test Kit & 2 others | [19 empty] | IMCOM | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-13 | 2022-12-13 | N/A | N/A | N/A | GoP | 50000 | 50000 | 0 | 49580 | 49580 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of 12 pcs Smart Load Card (500) & 3 others | [19 empty] | IMCOM | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-13 | 2022-12-13 | N/A | N/A | N/A | GoP | 16200 | 16200 | 0 | 15936 | 15936 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of 8 pcs Cignal Prepaid Load (450) & 3 others | [19 empty] | IMCOM | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-13 | 2022-12-13 | N/A | N/A | N/A | GoP | 12000 | 12000 | 0 | 11880 | 11880 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of 10 pcs Hardiflex 1/4in x 4ftx 8ft and 77 others | [19 empty] | IMCOM | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-14 | 2022-12-14 | N/A | N/A | N/A | GoP | 311518.07 | 311518.07 | 0 | 309518.07 | 309518.07 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of 2 sets Desktop Computer | [19 empty] | MPBn, IMCOM | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-11 | 2022-11-11 | 2022-12-16 | 2022-12-22 | N/A | GoP | 81250 | 81250 | 0 | 80800 | 80800 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of 22 pcs ICT Software (Anti-Virus) | [19 empty] | MPBn, IMCOM | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-24 | 2022-11-24 | N/A | N/A | N/A | GoP | 55000 | 55000 | 0 | 54736 | 54736 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of 1 unit of intel Core i3-7100 & Eight (8) Others | [19 empty] | PATGB | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-11-18 | 2022-11-18 | 2022-12-15 | 2022-12-21 | N/A | GoP | 45000 | 45000 | 0 | 44870 | 44870 | 0 | [7 empty] | N/A
| S/D of 160 pack Bottled Water 500ml & 16 others | [19 empty] | PATGB | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-11-24 | 2022-11-24 | 2022-12-22 | N/A | N/A | GoP | 392250 | 392250 | 0 | 391266 | 391266 | 0 | [7 empty] | N/A
| S/D of 160 packs Bicuits Crackers 30g & 9 others | [19 empty] | PATGB | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-11-24 | 2022-11-24 | 2022-12-22 | N/A | N/A | GoP | 72500 | 72500 | 0 | 72223 | 72223 | 0 | [7 empty] | N/A
| S/D of 1 unit Portable Jack Hammer & Portable Generator | [19 empty] | PATGB | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-12-13 | 2022-12-13 | N/A | N/A | N/A | GoP | 25000 | 25000 | 0 | 24600 | 24600 | 0 | [7 empty] | N/A
| S/D of 1 ea Needle Bearing 1212 and 11 Others | [19 empty] | PATGB | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-12-14 | 2022-12-14 | N/A | N/A | N/A | GoP | 30000 | 30000 | 0 | 29570 | 29570 | 0 | [7 empty] | N/A
| S/D of 2 unit Printer Continue Ink with Scanner and 2 Others | [19 empty] | PATGB | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-12-14 | 2022-12-14 | N/A | N/A | N/A | GoP | 45000 | 45000 | 0 | 44800 | 44800 | 0 | [7 empty] | N/A
| S/D of 120 pack Mineral Water 350ml x 20 and 6 Others | [19 empty] | PATGB | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-12-14 | 2022-12-14 | N/A | N/A | N/A | GoP | 91016 | 91016 | 0 | 91016 | 91016 | 0 | [7 empty] | N/A
| S/D of 38 sets Gala Green Uniform with Green Pants and Extra White Pants & 3 others | [19 empty] | SEBN | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-11-11 | 2022-11-11 | 2022-12-12 | N/A | N/A | GoP | 619400 | 619400 | 0 | 614840 | 614840 | 0 | [7 empty] | N/A
| S/D of 40 box Bottle Drinking Water 300ml & 14 others | [19 empty] | SEBN | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-11-18 | 2022-11-18 | N/A | N/A | N/A | GoP | 105000 | 105000 | 0 | 104600 | 104600 | 0 | [7 empty] | N/A
| S/D of 8 pcs Ms Plate 12mm x o.60m w/ Holes & 35 others | [19 empty] | SEBN | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-11-18 | 2022-11-18 | 2022-12-12 | N/A | N/A | GoP | 411425 | 411425 | 0 | 407925 | 407925 | 0 | [7 empty] | N/A
| S/D of 52 ea Ceremonial Boots & 6 others | [19 empty] | SEBN | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-11-24 | 2022-11-24 | N/A | N/A | N/A | GoP | 683012.5 | 683012.5 | 0 | 682600 | 682600 | 0 | [7 empty] | N/A
| S/D of 15 card Globe Prepaid card 1000 & 1 other | [19 empty] | SSC, IMCOM | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-11-18 | 2022-11-18 | 2022-12-12 | N/A | N/A | GoP | 22500 | 22500 | 0 | 22350 | 22350 | 0 | [7 empty] | N/A
| S/D of 50 bags Cement & 68 others | [19 empty] | SSC, IMCOM | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-11-24 | 2022-11-24 | N/A | N/A | N/A | GoP | 605336 | 605336 | 0 | 601736 | 601736 | 0 | [7 empty] | N/A
| S/D of 40 ream A4 Bond Paper & 21 others | [19 empty] | SSC, IMCOM | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-11-24 | 2022-11-24 | 2022-12-22 | N/A | N/A | GoP | 122000 | 122000 | 0 | 120520 | 120520 | 0 | [7 empty] | N/A
| S/D of 12 card Prepaid Globe internet Load 1000 | [19 empty] | SSC, IMCOM | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-11-24 | 2022-11-24 | N/A | N/A | N/A | GoP | 12000 | 12000 | 0 | 11940 | 11940 | 0 | [7 empty] | N/A
| S/D of 6 card Prepaid Cignal Card Load 1,000 | [19 empty] | SSC, IMCOM | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-11-24 | 2022-11-24 | 2022-12-15 | 2022-12-22 | N/A | GoP | 6000 | 6000 | 0 | 5970 | 5970 | 0 | [7 empty] | N/A
| S/D of 2 reams A4 bond paper & 11 others | [19 empty] | SSC, IMCOM | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-11-24 | 2022-11-24 | N/A | N/A | N/A | GoP | 10000 | 10000 | 0 | 9570 | 9570 | 0 | [7 empty] | N/A
| S/D of 2 unit Aircondition Unit Split Type 1.5HP & 1 other | [19 empty] | SSC, IMCOM | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-11-24 | 2022-11-24 | N/A | N/A | N/A | GoP | 110000 | 110000 | 0 | 109000 | 109000 | 0 | [7 empty] | N/A
| S/D of 1 unit 1.5 HP Motor Pump & 2 others | [19 empty] | SSC, IMCOM | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-11-24 | 2022-11-24 | N/A | N/A | N/A | GoP | 60000 | 60000 | 0 | 57000 | 57000 | 0 | [7 empty] | N/A
| S/D of 3 ea Solid State Drives (SSD) & 9 others | [19 empty] | SSC, IMCOM | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-11-24 | 2022-11-24 | N/A | N/A | N/A | GoP | 50500 | 50500 | 0 | 49000 | 49000 | 0 | [7 empty] | N/A
| S/D of 255 pck Spaghetti Pasta 900g & 16 others | [19 empty] | SSC, IMCOM | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-11-24 | 2022-11-24 | N/A | N/A | N/A | GoP | 517320 | 517320 | 0 | 512277 | 512277 | 0 | [7 empty] | N/A
| S/D of 245 pcs Antigen Test Kits & 1 Other | [19 empty] | SSC, IMCOM | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-12-13 | 2022-12-13 | N/A | N/A | N/A | GoP | 50000 | 50000 | 0 | 49900 | 49900 | 0 | [7 empty] | N/A
| S/D of 600 can Pineapple juice 220ml & 41 others | [19 empty] | SSC, IMCOM | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-13 | 2022-12-13 | N/A | N/A | N/A | GoP | 762910 | 762910 | 0 | 755740 | 755740 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Procurement of ONE HUNDRED FORTY (140) Metal Furring (19mm x 50 mm x 0.4mm ) & 47 Other Line Items | [19 empty] | 1IMB | NO | NP-53.9 - Small Value Procurement |  | 2022-07-22 |  |  | 2022-07-26 |  |  |  | 2022-07-26 | 2022-07-26 | 2022-09-29 |  |  | GoP | 166760 | 166760 | 0 | 166560 | 166560 | 0 | RG SANTOS TRADING | [6 empty] | N/A
| Procurement of THIRTEEN (13) pcs Roof Long Span, Rib Type, 1.5mm x 23 ft (Green ) and 8 Other Line Items | [19 empty] | 1IMB | NO | NP-53.9 - Small Value Procurement |  | 2022-10-13 |  |  | 2022-10-18 |  |  |  | 2022-10-18 | 2022-10-18 | 2022-12-05 |  |  | GoP | 70400 | 70400 | 0 | 70320 | 70320 | 0 | RG SANTOS TRADING | [6 empty] | N/A
| Procurement of THREE HUNDRED FORTY-NINE (349) bags cement & 43 Other Line Items | [19 empty] | 1IMB | NO | NP-53.9 - Small Value Procurement |  | 2022-10-27 |  |  | 2022-11-04 |  |  |  | 2022-11-04 | 2022-11-04 |  |  |  | GoP | 455577 | 455577 | 0 | 455317 | 455317 | 0 | Choi Computer and Hardware & Construction Supplies | [6 empty] | N/A
| Procuement of FOUR (4) Oil Filter & 4 Other Line Items | [19 empty] | 1IMB | NO | NP-53.9 - Small Value Procurement |  | 2022-10-27 |  |  | 2022-11-04 |  |  |  | 2022-11-04 | 2022-11-04 | 2022-12-05 |  |  | GoP | 21750 | 21750 | 0 | 21690 | 21690 | 0 | TRQUI AUTO SUPPLY | [6 empty] | N/A
| Procurement of ONE (1) Lot Land Survey of Baybay and San Isidro Military Reservation | [19 empty] | 1IMB | NO | NP-53.9 - Small Value Procurement |  | 2022-12-13 |  |  | 2022-12-19 |  |  |  | 2022-12-19 | 2022-12-19 |  |  |  | GoP | 243800 | 243800 | 0 | 243800 | 243800 | 0 | ROMIN SURVEYING OFFICE | [6 empty] | N/A
5-02-13-060-01 | RM Motor vehicle | [17 empty] | 114000 |  | 2IMB | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-08-15 | 2022-08-15 | 2022-09-19 | 2022-09-26 | 2022-09-26 | MOOE | 114000 |  | 0 | 113888 |  | 0 | [7 empty] | N/A
5-02-99-030-00 | Representation exp | [17 empty] | 92250 |  | 2IMB | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-09-09 | 2022-09-09 | 2022-12-12 | 2022-12-19 | 2022-12-19 | MOOE | 92250 |  | 0 | 92109 |  | 0 | [7 empty] | N/A
5-02-030-010-00 | Office Supplies Exp | [17 empty] | 46575 |  | 2IMB | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-09-16 | 2022-09-16 | 2022-12-02 | 2022-12-09 | 2022-12-09 | MOOE | 46575 |  | 0 | 46385 |  | 0 | [7 empty] | N/A
5-02-02-010-00 | Training Expenses | [17 empty] | 40000 |  | 2IMB | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-09-16 | 2022-09-16 | 2022-12-02 | 2022-12-09 | 2022-12-09 | MOOE | 40000 |  | 0 | 39680 |  | 0 | [7 empty] | N/A
5-02-13-060-01 | RM Motor Vehicle | [17 empty] | 60000 |  | 2IMB | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-09-16 | 2022-09-16 | 2022-12-02 | 2022-12-09 | 2022-12-09 | MOOE | 60000 |  | 0 | 59675 |  | 0 | [7 empty] | N/A
5-02-13-050-99 | RM Other Machinery | [17 empty] | 15000 |  | 2IMB | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-09-16 | 2022-09-16 |  |  |  | MOOE | 15000 |  | 0 | 14795 |  | 0 | [7 empty] | N/A
5-02-13-040-00 | RM BUILDING | [17 empty] | 89000 |  | 2IMB | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-11-08 | 2022-11-08 |  |  |  | MOOE | 89000 |  | 0 | 88624 |  | 0 | [7 empty] | N/A
5-02-030-010-00 | Office Supplies Exp | [17 empty] | 48575 |  | 2IMB | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-12-27 | 2022-12-27 |  |  |  | MOOE | 48575 |  | 0 | 48158 |  | 0 | [7 empty] | N/A
5-02-030-010-00 | Office Supplies Exp | [17 empty] | 38575 |  | 2IMB | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-12-27 | 2022-12-27 |  |  |  | MOOE | 38575 |  | 0 | 38308 |  | 0 | [7 empty] | N/A
5-02-030-010-00 | Office Supplies Exp | [17 empty] | 38575 |  | 2IMB | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-12-27 | 2022-12-27 |  |  |  | MOOE | 38575 |  | 0 | 38288 |  | 0 | [7 empty] | N/A
5-02-05-030-00 | Internet subcription Expenses | Internet subcription Expenses | [18 empty] | 9IMB | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-09-22 | 2022-10-03 | 2022-10-03 | 2022-10-07 | 2022-10-07 | MOOE | 6000 | 6000 | 0 | 6000 | 6000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-05-030-00 | Internet subcription Expenses | Internet subcription Expenses | [18 empty] | 9IMB | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-10-03 | 16 Nov 22 | 16 Nov 22 | 2022-11-23 | 2022-11-23 | MOOE | 3800 | 3800 | 0 | 3800 | 3800 | 0 | [7 empty] | N/A
5-02-05-020-01 | Mobile Expenses | Mobile Expenses | [18 empty] | 9IMB | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-10-03 | 16 Nov 22 | 16 Nov 22 | 2022-11-23 | 2022-11-23 | MOOE | 1500 | 1500 | 0 | 1500 | 1500 | 0 | [7 empty] | N/A
5-02-13-060-01 | RM Motor Vehicle | [19 empty] | 14IMB | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-05-06 | 2022-05-06 | 2022-05-27 | 2022-06-02 | 2022-06-02 | MOOE | 70000 | 70000 | 0 | 69180 | 69180 | 0 | [7 empty] | N/A
5-02-03-210-03 | Semi Exp ICT | [19 empty] | 14IMB | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-07-18 | 2022-07-18 |  |  |  | MOOE | 101750 | 101750 | 0 | 101130 | 101130 | 0 | [7 empty] | N/A
5-02-03-210-03 | Semi Exp ICT Equipment | [19 empty] | 14IMB | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-10-10 | 2022-10-10 |  |  |  | MOOE | 26750 | 26750 | 0 | 26500 | 26500 | 0 | [7 empty] | N/A
5-02-03-210-03 | Semi Exp Office Equipment | [19 empty] | 14IMB | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-10-10 | 2022-10-10 |  |  |  | MOOE | 75000 | 75000 | 0 | 74300 | 74300 | 0 | [7 empty] | N/A
5-02-99-030-00 | Representation Exp | [19 empty] | 14IMB | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-10-10 | 2022-10-10 |  |  |  | MOOE | 301500 | 301500 | 0 | 299199 | 299199 | 0 | [7 empty] | N/A
5-02-05-020-01 | Telephone Mobile Exp | [19 empty] | 14IMB | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-10-11 | 2022-10-11 | 2022-11-22 | 2022-11-29 | 2022-11-29 | MOOE | 19500 | 19500 | 0 | 19382 | 19382 | 0 | [7 empty] | N/A
5-02-05-030-00 | Internet Expenses | [19 empty] | 14IMB | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-10-11 | 2022-10-11 | 2022-11-22 | 2022-11-29 | 2022-11-29 | MOOE | 10500 | 10500 | 0 | 10474 | 10474 | 0 | [7 empty] | N/A
5-02-13-060-00 | RM MOTOR VEHICLE | [19 empty] | 14IMB | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-11-08 | 2022-11-08 |  |  |  | MOOE | 70000 | 70000 | 0 | 69340 | 69340 | 0 | [7 empty] | N/A
5-02-13-060-00 | RM MOTOR VEHICLE | [19 empty] | 14IMB | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-11-08 | 2022-11-08 |  |  |  | MOOE | 70000 | 70000 | 0 | 69340 | 69340 | 0 | [7 empty] | N/A
Total Alloted Budget of On-going Procurement Activities | [37 empty] | 15354873.57
| Prepared by: | [32 empty] | Certified Correct By | [6 empty] | Noted By
| CLAIRE R AURE-REYES | [32 empty] | JOHN KENNETH D BABICA | [6 empty] | MANOLO V SANTIAGO
| Major (QMS) PA | [32 empty] | Major (INF) PA | [6 empty] | Colonel CE (GSC) PA
| Operations Officer | [32 empty] | Executive Officer | [6 empty] | Commanding Officer