## 1BCT, PA PMR 2ND SEM CY 2022
|  | ANNEX A | [18 empty] | ANNEX B
|  | Department of Budget and Management Annual Procurement Plan for FY 2006 | [18 empty] | (Name of Agency) Procurement Monitoring Report as of month/day/year
Code (PAP) | Procurement Project | PMO/ End-User | Mode of Procurement | Schedule for Each Procurement Activity | [11 empty] | Source of Funds | ABC (PhP) |  |  | Remarks (brief description of Program/Project) | PMO/ End-User | Is this an Early Procurement Activity? | Mode of Procurement | Actual Procurement Activity | [12 empty] | Source of Funds | ABC (PhP) |  |  | Contract Cost (PhP) |  |  | List of Invited Observers | Date of Receipt of Invitation | [5 empty] | Remarks (Explaining changes from the APP)
|  |  |  | Pre-Proc Conference | Ads/Post of IAEB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Contract Award | Contract Signing | Notice to Proceed | Delivery/ Accept | Payment Process |  | Total | MOOE | CO |  |  |  |  | Pre-Proc Conference | Ads/Post of IB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Date of BAC Resolution Recommending Award | Notice of Award | Contract Signing | Notice to Proceed | Delivery/ Completion | Inspection & Acceptance |  | Total | MOOE | CO | Total | MOOE | CO |  | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Delivery/ Completion/ Acceptance (If applicable)
COMPLETED PROCUREMENT ACTIVITIES
5-02-03-080-00 | Medical and Dental Supplies | [18 empty] | Procurement of Requierments for CY 2023 | G1 | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2023-01-27 | N/A | 2023-03-14 | 2023-04-03 | 2023-04-03 | GoP | 50000 | 50000 |  | 49675 | 49675 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-03-070-00 | Drugs and Medicines | [18 empty] | Procurement of Requierments for CY 2023 | G1 | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2023-01-26 | N/A | 2023-02-23 | 2023-03-01 | 2023-03-01 | GoP | 50000 | 50000 |  | 49700 | 49700 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-03-210-07 | R&M ICT Equipment | [18 empty] | Procurement of Requierments for CY 2023 | G6 | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2023-01-27 | N/A | 2023-02-23 | 2023-03-01 | 2023-03-01 | GoP | 48000 | 48000 |  | 47640 | 47640 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-13-050-07 | R&M Machinery Equipment | [18 empty] | Procurement of Requierments for CY 2023 | G6 | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2023-01-30 | N/A | 2023-02-23 | 2023-03-01 | 2023-03-01 | GoP | 70000 | 70000 |  | 69750 | 69750 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-13-040-99 | Other Structure of Building | [18 empty] | Procurement of Requierments for CY 2023 | G4 | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2023-01-30 | N/A | 2023-02-23 | 2023-03-01 | 2023-03-01 | GoP | 91500 | 91500 |  | 91000 | 91000 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-13-040-01 | R&M Buildings | [18 empty] | Procurement of Requierments for CY 2023 | G4 | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2023-03-03 | N/A | 2023-03-23 | 2023-04-03 | 2023-04-03 | GoP | 260000 | 260000 |  | 259245 | 259245 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-03-010-02 | Office Supplies | [18 empty] | Procurement of Requierments for CY 2023 | G4 | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2023-03-03 | N/A | 2023-03-31 | 2023-04-19 | 2023-04-19 | GoP | 175000 | 175000 |  | 174492 | 174492 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-13-210-03 | Water Supply System | [18 empty] | Procurement of Requierments for CY 2023 | G4 | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2023-01-30 | N/A | 2023-02-23 | 2023-03-01 | 2023-03-01 | GoP | 100000 | 100000 |  | 99660 | 99660 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-03-210-03 | Semi- Expendable ICT Equipment | [18 empty] | Procurement of Requierments for CY 2023 | G6 | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2023-02-27 | N/A | 2023-03-23 | 2023-04-03 | 2023-04-03 | GoP | 233000 | 233000 |  | 232450 | 232450 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-13-040-01 | R&M Building Pistol Ranges | [18 empty] | Procurement of Requierments for CY 2023 | G4 | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2023-03-10 | N/A | 2023-04-28 | 2023-05-19 | 2023-05-19 | GoP | 850000 | 850000 |  | 849380 | 849380 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-13-040-01 | R&M Building of Rifle Ranges | [18 empty] | Procurement of Requierments for CY 2023 | G4 | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2023-03-06 | N/A | 2023-03-23 | 2023-04-03 | 2023-04-03 | GoP | 950000 | 950000 |  | 949400 | 949400 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-03-080-00 | Medical Supply | [18 empty] | Procurement of Requierments for CY 2023 | G1 | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2023-02-28 | N/A | 2023-04-14 | 2023-04-27 | 2023-04-27 | GoP | 50000 | 50000 |  | 49650 | 49650 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-03-210-07 | ICT Equipment | [18 empty] | Procurement of Requierments for CY 2023 | G6 | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2023-03-13 | N/A | 2023-04-14 | 2023-04-27 | 2023-04-27 | GoP | 105500 | 105500 |  | 105000 | 105000 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-13-050-07 | Semi Expendable Machinery Equipment Communication | [18 empty] | Procurement of Requierments for CY 2023 | G6 | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2023-03-08 | N/A | 2023-04-20 | 2023-04-27 | 2023-04-27 | GoP | 35000 | 35000 |  | 34680 | 34680 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-13-210-07 | Semi-Expendable Communication | [18 empty] | Procurement of Requierments for CY 2023 | G6 | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2023-03-06 | N/A | 2023-04-25 | 2023-05-17 | 2023-05-17 | GoP | 92000 | 92000 |  | 91600 | 91600 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-03-010-02 | Office Supply | [18 empty] | Procurement of Requierments for CY 2023 | G4 | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2023-03-10 | N/A | 2023-03-31 | 2023-04-19 | 2023-04-19 | GoP | 160000 | 160000 |  | 159398 | 159398 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-13-040-01 | R&M Building | [18 empty] | Procurement of Requierments for CY 2023 | G4 | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2023-03-10 | N/A | 2023-04-20 | 2023-04-27 | 2023-04-27 | GoP | 300000 | 300000 |  | 299409 | 299409 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-03-220-01 | Simi-Expendable Furniture | [18 empty] | Procurement of Requierments for CY 2023 | G4 | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2023-03-24 | N/A | 2023-04-14 | 2023-04-27 | 2023-04-27 | GoP | 40000 | 40000 |  | 39835 | 39835 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-03-070-00 | Drugs & Medicine | [18 empty] | Procurement of Requierments for CY 2023 | G1 | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2023-03-08 | N/A | 2023-03-31 | 2023-04-19 | 2023-04-19 | GoP | 40000 | 40000 |  | 39720 | 39720 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Total Alloted Budget of Procurement Activities | [37 empty] | 3700000
Total Contract Price of Procurement Actitvites Conducted | [40 empty] | 3691684
Total Savings (Total Alloted Budget - Total Contract Price) | [37 empty] | 8316
0N-GOING PROCUREMENT ACTIVITIES
5-02-13-040-01 | Damage Facility of 1BCT; PA | [18 empty] | Procurement of Requierments for CY 2023 | G4 | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | GoP | 821024 | 821024 |  | 820239 | 820239 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-03-080-00 | Medical & Dental Supply | [18 empty] | Procurement of Requierments for CY 2023 | G1 | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | GoP | 50000 | 50000 |  | 49700 | 49700 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-03-070-00 | Drugs & Medicine | [18 empty] | Procurement of Requierments for CY 2023 | G1 | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | GoP | 50000 | 50000 |  | 49675 | 49675 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-13-040-01 | Enhancement of Liaison | [18 empty] | Procurement of Requierments for CY 2023 | G4 | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | GoP | 627750 | 627750 |  | 627000 | 627000 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-03-080-00 | Medical & Dental Supply | [18 empty] | Procurement of Requierments for CY 2023 | G1 | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | GoP | 344000 | 344000 |  | 343475 | 343475 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-03-070-00 | Drugs & Medicine | [18 empty] | Procurement of Requierments for CY 2023 | G1 | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | GoP | 40000 | 40000 |  | 39680 | 39680 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-03-080-00 | Medical & Dental Supply | [18 empty] | Procurement of Requierments for CY 2023 | G1 | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | GoP | 50000 | 50000 |  | 49800 | 49800 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-13-040-01 | R&M Building | [18 empty] | Procurement of Requierments for CY 2023 | G4 | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | GoP | 90000 | 90000 |  | 89525 | 89525 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-13-040-01 | Generator House | [18 empty] | Procurement of Requierments for CY 2023 | G4 | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | GoP | 489867 | 489867 |  | 489286 | 489286 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-03-210-03 | Telephone Expenses / ICT | [18 empty] | Procurement of Requierments for CY 2023 | G6 | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | GoP | 215268 | 215268 |  | 214850 | 214850 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Total Alloted Budget of On-going Procurement Activities | [37 empty] | 2777909
`
[21 empty] | Prepared by: | [10 empty] | Recommended for Approval by: | [10 empty] | APPROVED:
[21 empty] | WILMER S BARLUADO | [21 empty] | LEODEVIC B GUINID
[21 empty] | Major (SC) PA | [21 empty] | Colonel INF (GSC) PA
[21 empty] | AC of S for Logistics, G4 | [21 empty] | Commander