## pmr
|  | ANNEX A | [18 empty] | ANNEX B
|  | Department of Budget and Management Annual Procurement Plan for FY 2006 | [18 empty] | 114th CO, AFPPS Procurement Monitoring Report for 54EBDE, PA - 1st Semester 2023
Code (PAP) | Procurement Project | PMO/ End-User | Mode of Procurement | Schedule for Each Procurement Activity | [11 empty] | Source of Funds | ABC (PhP) |  |  | Remarks (brief description of Program/Project) | PMO/ End-User | Is this an Early Procurement Activity? | Mode of Procurement | Actual Procurement Activity | [12 empty] | Source of Funds | ABC (PhP) |  |  | Contract Cost (PhP) |  |  | List of Invited Observers | Date of Receipt of Invitation | [5 empty] | Remarks (Explaining changes from the APP)
|  |  |  | Pre-Proc Conference | Ads/Post of IAEB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Contract Award | Contract Signing | Notice to Proceed | Delivery/ Accept | Payment Process |  | Total | MOOE | CO |  |  |  |  | Pre-Proc Conference | Ads/Post of IB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Date of BAC Resolution Recommending Award | Notice of Award | Contract Signing | Notice to Proceed | Delivery/ Completion | Inspection & Acceptance |  | Total | MOOE | CO | Total | MOOE | CO |  | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Delivery/ Completion/ Acceptance (If applicable)
COMPLETED PROCUREMENT ACTIVITIES
02-1 | Other Supplies & Materials Expenses | [19 empty] | 54EBDE PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | 2023-02-07 | N/A | N/A | N/A | 2023-02-07 | N/A | 2023-02-22 | 2023-02-23 | 2023-02-23 | MOOE | 37950 | 37950 |  | 37860 | 37860 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
02-3 | Printing and Publication Expenses | [19 empty] | 54EBDE PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | 2023-02-07 | N/A | N/A | N/A | 2023-02-07 | N/A | 2023-02-22 | 2023-02-23 | 2023-02-23 | MOOE | 19450 | 19450 |  | 19342 | 19342 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
02-16 | Representation Expenses | [19 empty] | 54EBDE PA | NO | Negotiated 53.9 | N/A | 2023-02-07 | N/A | N/A | 2023-02-10 | N/A | N/A | N/A | 2023-02-10 | N/A | 2023-03-06 | 2023-03-07 | 2023-03-07 | MOOE | 217758 | 217758 |  | 217574.5 | 217574.5 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
02-17 | ICT Equipment | [19 empty] | 54EBDE PA | NO | Negotiated 53.9 | N/A | 2023-02-07 | N/A | N/A | 2023-02-10 | N/A | N/A | N/A | 2023-02-10 | N/A | 2023-02-24 | 2023-03-07 | 2023-03-07 | MOOE | 119100 | 119100 |  | 118976 | 118976 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
02-18 | Mobile Expenses | [19 empty] | 54EBDE PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | 2023-02-10 | N/A | N/A | N/A | 2023-02-10 | N/A | 2023-03-07 | 2023-03-08 | 2023-03-08 | MOOE | 10500 | 10500 |  | 10498 | 10498 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
02-27 | Technical Scientific Equipment | [19 empty] | 54EBDE PA | NO | Negotiated 53.9 | N/A | 2023-02-10 | N/A | N/A | 2023-02-14 | N/A | N/A | N/A | 2023-02-14 | N/A | 2023-03-06 | 2023-03-09 | 2023-03-09 | MOOE | 314067 | 314067 |  | 313761 | 313761 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
02-28 | Training Expenses | [19 empty] | 54EBDE PA | NO | Negotiated 53.9 | N/A | 2023-02-10 | N/A | N/A | 2023-02-14 | N/A | N/A | N/A | 2023-02-14 | N/A | 2023-03-08 | 2023-03-10 | 2023-03-10 | MOOE | 85190 | 85190 |  | 84930.5 | 84930.5 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
02-32 | Drugs and Medicines Expenses | [19 empty] | 54EBDE PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | 2023-02-16 | N/A | N/A | N/A | 2023-02-16 | N/A | 2023-03-08 | 2023-03-10 | 2023-03-10 | MOOE | 17620 | 17620 |  | 17577.5 | 17577.5 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
02-33 | Medical, Dental and Laboratory Supplies Expns | [19 empty] | 54EBDE PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | 2023-02-16 | N/A | N/A | N/A | 2023-02-16 | N/A | 2023-03-06 | 2023-03-09 | 2023-03-09 | MOOE | 47935 | 47935 |  | 47847 | 47847 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
02-46 | R/M of Motor Vehicle | [19 empty] | 54EBDE PA | NO | Negotiated 53.9 | N/A | 2023-02-16 | N/A | N/A | 2023-02-20 | N/A | N/A | N/A | 2023-02-20 | N/A | 2023-03-06 | 2023-03-08 | 2023-03-08 | MOOE | 441620 | 441620 |  | 441457 | 441457 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
02-48 | Training Expenses | [19 empty] | 54EBDE PA | NO | Negotiated 53.9 | N/A | 2023-02-16 | N/A | N/A | 2023-02-20 | N/A | N/A | N/A | 2023-02-20 | N/A | 2023-03-08 | 2023-03-10 | 2023-03-10 | MOOE | 50826 | 50826 |  | 50673 | 50673 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
02-49 | Semi-Expendable Med Eqpmnt | [19 empty] | 54EBDE PA | NO | Negotiated 53.9 | N/A | 2023-02-16 | N/A | N/A | 2023-02-20 | N/A | N/A | N/A | 2023-02-20 | N/A | 2023-03-06 | 2023-03-09 | 2023-03-09 | MOOE | 495500 | 495500 |  | 495172 | 495172 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
02-54 | Printing and Publication Expenses | [19 empty] | 54EBDE PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | 2023-02-21 | N/A | N/A | N/A | 2023-02-21 | N/A | 2023-03-06 | 2023-03-08 | 2023-03-08 | MOOE | 12290 | 12290 |  | 12176 | 12176 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
02-55 | Representation Expenses | [19 empty] | 54EBDE PA | NO | Negotiated 53.9 | N/A | 2023-02-21 | N/A | N/A | 2023-02-24 | N/A | N/A | N/A | 2023-02-24 | N/A | 2023-03-10 | 2023-03-13 | 2023-03-13 | MOOE | 124636 | 124636 |  | 124517.5 | 124517.5 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
02-56 | R/M of Motor Vehicle | [19 empty] | 54EBDE PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | 2023-02-24 | N/A | N/A | N/A | 2023-02-24 | N/A | 2023-03-10 | 2023-03-13 | 2023-03-13 | MOOE | 19590 | 19590 |  | 19423 | 19423 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
02-57 | Medical, Dental and Laboratory Supplies Expns | [19 empty] | 54EBDE PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | 2023-02-24 | N/A | N/A | N/A | 2023-02-24 | N/A | 2023-03-10 | 2023-03-13 | 2023-03-13 | MOOE | 25000 | 25000 |  | 24800 | 24800 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
02-58 | Other Supplies & Materials Expenses | [19 empty] | 54EBDE PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | 2023-02-24 | N/A | N/A | N/A | 2023-02-24 | N/A | 2023-03-13 | 2023-03-20 | 2023-03-20 | MOOE | 1823 | 1823 |  | 1764 | 1764 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
02-59 | Mobile Expenses | [19 empty] | 54EBDE PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | 2023-02-24 | N/A | N/A | N/A | 2023-02-24 | N/A | 2023-04-13 | 2023-04-19 | 2023-04-19 | MOOE | 7500 | 7500 |  | 7478 | 7478 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
02-65 | R/M of Communication Equipment | [19 empty] | 54EBDE PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | 2023-02-24 | N/A | N/A | N/A | 2023-02-24 | N/A | 2023-03-10 | 2023-03-13 | 2023-03-13 | MOOE | 10240 | 10240 |  | 10112 | 10112 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
03-115 | Representation Expenses | [19 empty] | 54EBDE PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | 2023-03-08 | N/A | N/A | N/A | 2023-03-08 | N/A | 2023-04-05 | 2023-04-14 | 2023-04-14 | Special Release | 20000 | 20000 |  | 19959 | 19959 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
03-118 | Representation Expenses | [19 empty] | 54EBDE PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | 2023-03-08 | N/A | N/A | N/A | 2023-03-08 | N/A | 2023-04-05 | 2023-04-14 | 2023-04-14 | Special Release | 30000 | 30000 |  | 29930 | 29930 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
03-141 | Representation Expenses | [19 empty] | 54EBDE PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | 2023-03-10 | N/A | N/A | N/A | 2023-03-10 | N/A | 2023-04-05 | 2023-04-14 | 2023-04-14 | Special Release | 10000 | 10000 |  | 9951 | 9951 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
03-142 | Printing and Publication Expenses | [19 empty] | 54EBDE PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | 2023-03-10 | N/A | N/A | N/A | 2023-03-10 | N/A | 2023-04-05 | 2023-04-14 | 2023-04-14 | MOOE | 2000 | 2000 |  | 1991 | 1991 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
03-144 | Mobile Expenses | [19 empty] | 54EBDE PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | 2023-03-10 | N/A | N/A | N/A | 2023-03-10 | N/A | 2023-04-13 | 2023-04-19 | 2023-04-19 | MOOE | 24000 | 24000 |  | 23946.25 | 23946.25 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
03-145 | Other Supplies & Materials Expenses | [19 empty] | 54EBDE PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | 2023-03-10 | N/A | N/A | N/A | 2023-03-10 | N/A | 2023-04-05 | 2023-04-17 | 2023-04-17 | MOOE | 31251 | 31251 |  | 31119.5 | 31119.5 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
03-148 | Training Expenses | [19 empty] | 54EBDE PA | NO | Negotiated 53.9 | N/A | 2023-03-10 | N/A | N/A | 2023-03-13 | N/A | N/A | N/A | 2023-03-13 | N/A | 2023-04-05 | 2023-04-17 | 2023-04-17 | Special Release | 150000 | 150000 |  | 149860.75 | 149860.75 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
03-164 | Representation Expenses | [19 empty] | 54EBDE PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | 2023-03-14 | N/A | N/A | N/A | 2023-03-14 | N/A | 2023-04-05 | 2023-04-14 | 2023-04-14 | Special Release | 12500 | 12500 |  | 12462 | 12462 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
03-169 | Representation Expenses | [19 empty] | 54EBDE PA | NO | Negotiated 53.9 | N/A | 2023-03-14 | N/A | N/A | 2023-03-17 | N/A | N/A | N/A | 2023-03-17 | N/A | 2023-04-03 | 2023-04-13 | 2023-04-13 | Special Release | 50000 | 50000 |  | 49943.25 | 49943.25 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
03-170 | Conduct of Quarterly AGP Validation | [19 empty] | 54EBDE PA | NO | Negotiated 53.9 | N/A | 2023-03-14 | N/A | N/A | 2023-03-17 | N/A | N/A | N/A | 2023-03-17 | N/A | 2023-04-03 | 2023-04-12 | 2023-04-12 | Special Release | 60000 | 60000 |  | 59913.75 | 59913.75 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
03-182 | Medical, Dental and Laboratory Supplies Expns | [19 empty] | 54EBDE PA | NO | Negotiated 53.9 | N/A | 2023-03-17 | N/A | N/A | 2023-03-20 | N/A | N/A | N/A | 2023-03-20 | N/A | 2023-04-03 | 2023-04-12 | 2023-04-12 | MOOE | 65015 | 65015 |  | 64943 | 64943 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
03-188 | Repair enchance Facilities | [19 empty] | 54EBDE PA | NO | Negotiated 53.9 | N/A | 2023-03-16 | N/A | N/A | 2023-03-20 | N/A | N/A | N/A | 2023-03-20 | N/A | 2023-04-05 | 2023-04-17 | 2023-04-17 | Special Release | 768000 | 768000 |  | 767661 | 767661 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
03-190 | Office Supplies Expenses | [19 empty] | 54EBDE PA | NO | Shopping 52.1b | N/A | 2023-03-16 | N/A | N/A | 2023-03-20 | N/A | N/A | N/A | 2023-03-20 | N/A | 2023-04-11 | 2023-04-18 | 2023-04-18 | MOOE | 65260 | 65260 |  | 64168.5 | 64168.5 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
03-195 | Representation Expenses | [19 empty] | 54EBDE PA | NO | Negotiated 53.9 | N/A | 2023-03-18 | N/A | N/A | 2023-03-22 | N/A | N/A | N/A | 2023-03-22 | N/A | 2023-04-05 | 2023-04-14 | 2023-04-14 | MOOE | 164836 | 164836 |  | 164716.25 | 164716.25 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
03-197 | Printing and Publication Expenses | [19 empty] | 54EBDE PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | 2023-03-22 | N/A | N/A | N/A | 2023-03-22 | N/A | 2023-04-11 | 2023-04-18 | 2023-04-18 | MOOE | 36450 | 36450 |  | 36335 | 36335 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
03-198 | Training Expenses | [19 empty] | 54EBDE PA | NO | Negotiated 53.9 | N/A | 2023-03-18 | N/A | N/A | 2023-03-22 | N/A | N/A | N/A | 2023-03-22 | N/A | 2023-04-11 | 2023-04-18 | 2023-04-18 | MOOE | 75685 | 75685 |  | 75553 | 75553 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
03-207 | ICT Equipment | [19 empty] | 54EBDE PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | 2023-03-22 | N/A | N/A | N/A | 2023-03-22 | N/A | 2023-04-05 | 2023-04-15 | 2023-04-15 | MOOE | 30422 | 30422 |  | 30225 | 30225 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
03-213 | Representation Expenses | [19 empty] | 54EBDE PA | NO | Negotiated 53.9 | N/A | 2023-03-21 | N/A | N/A | 2023-03-24 | N/A | N/A | N/A | 2023-03-24 | N/A | 2023-04-14 | 2023-04-19 | 2023-04-19 | MOOE | 115901 | 115901 |  | 115688.5 | 115688.5 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
03-214 | Training Expenses | [19 empty] | 54EBDE PA | NO | Negotiated 53.9 | N/A | 2023-03-21 | N/A | N/A | 2023-03-24 | N/A | N/A | N/A | 2023-03-24 | N/A | 2023-04-15 | 2023-04-17 | 2023-04-17 | MOOE | 76803 | 76803 |  | 76699 | 76699 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
03-218 | Printing and Publication Expenses | [19 empty] | 54EBDE PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | 2023-03-24 | N/A | N/A | N/A | 2023-03-24 | N/A | 2023-04-05 | 2023-04-14 | 2023-04-14 | Special Release | 2500 | 2500 |  | 2465 | 2465 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
03-220 | Mobile Expenses | [19 empty] | 54EBDE PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | 2023-03-24 | N/A | N/A | N/A | 2023-03-24 | N/A | 2023-04-11 | 2023-04-18 | 2023-04-18 | MOOE | 7500 | 7500 |  | 7443.5 | 7443.5 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
03-225 | Drugs and Medicines Expenses | [19 empty] | 54EBDE PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | 2023-03-28 | N/A | N/A | N/A | 2023-03-28 | N/A | 2023-04-11 | 2023-04-18 | 2023-04-18 | MOOE | 23024 | 23024 |  | 22975.25 | 22975.25 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
03-226 | Medical, Dental and Laboratory Supplies Expns | [19 empty] | 54EBDE PA | NO | Negotiated 53.9 | N/A | 2023-03-24 | N/A | N/A | 2023-03-28 | N/A | N/A | N/A | 2023-03-28 | N/A | 2023-04-11 | 2023-04-18 | 2023-04-18 | Special Release | 87500 | 87500 |  | 87230 | 87230 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
03-227 | Representation Expenses | [19 empty] | 54EBDE PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | 2023-03-28 | N/A | N/A | N/A | 2023-03-28 | N/A | 2023-04-12 | 2023-04-15 | 2023-04-15 | Special Release | 41250 | 41250 |  | 41133.25 | 41133.25 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
03-238 | R/M of Other Structure | [19 empty] | 54EBDE PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | 2023-03-31 | N/A | N/A | N/A | 2023-03-31 | N/A | 2023-04-12 | 2023-04-24 | 2023-04-24 | MOOE | 25842 | 25842 |  | 25663 | 25663 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
04-240 | R/M OF Machinery and Equipment | [19 empty] | 54EBDE PA | NO | Negotiated 53.9 | N/A | 2023-03-31 | N/A | N/A | 2023-04-03 | N/A | N/A | N/A | 2023-04-03 | N/A | 2023-04-20 | 2023-04-21 | 2023-04-21 | MOOE | 68490 | 68490 |  | 68249 | 68249 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
04-241 | R/M Building | [19 empty] | 54EBDE PA | NO | Negotiated 53.9 | N/A | 2023-03-31 | N/A | N/A | 2023-04-03 | N/A | N/A | N/A | 2023-04-03 | N/A | 2023-04-20 | 2023-04-24 | 2023-04-24 | MOOE | 163038 | 163038 |  | 162888.5 | 162888.5 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
04-242 | Support for the Enhancement of brigade main Gate | [19 empty] | 54EBDE PA | NO | Negotiated 53.9 | N/A | 2023-03-31 | N/A | N/A | 2023-04-03 | N/A | N/A | N/A | 2023-04-03 | N/A | 2023-04-27 | 2023-04-28 | 2023-04-28 | Special Release | 478000 | 478000 |  | 477561.5 | 477561.5 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
04-243 | Support for the Enhancement of brigade Brigade ClubHouse | [19 empty] | 54EBDE PA | NO | Negotiated 53.9 | N/A | 2023-03-31 | N/A | N/A | 2023-04-03 | N/A | N/A | N/A | 2023-04-03 | N/A | 2023-04-18 | 2023-04-19 | 2023-04-19 | Special Release | 369000 | 369000 |  | 368637 | 368637 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
04-249 | R/M Motor Vehicle | [19 empty] | 54EBDE PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | 2023-04-04 | N/A | N/A | N/A | 2023-04-04 | N/A | 2023-04-16 | 2023-04-19 | 2023-04-19 | MOOE | 28285 | 28285 |  | 28131 | 28131 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
04-250 | R/M Construction and Heavy Equipment | [19 empty] | 54EBDE PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | 2023-04-04 | N/A | N/A | N/A | 2023-04-04 | N/A | 2023-04-20 | 2023-04-21 | 2023-04-21 | MOOE | 37700 | 37700 |  | 37559 | 37559 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
04-251 | Office Supplies Expenses | [19 empty] | 54EBDE PA | NO | Shopping 52.1b | N/A | N/A | N/A | N/A | 2023-04-04 | N/A | N/A | N/A | 2023-04-04 | N/A | 2023-05-09 | 2023-05-15 | 2023-05-15 | Special Release | 12120 | 12120 |  | 12012.75 | 12012.75 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
04-255 | R/M Building | [19 empty] | 54EBDE PA | NO | Negotiated 53.9 | N/A | 2023-04-21 | N/A | N/A | 2023-04-25 | N/A | N/A | N/A | 2023-04-25 | N/A | 2023-05-23 | 2023-05-25 | 2023-05-25 | Special Release | 200000 | 200000 |  | 199842 | 199842 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
04-257 | Training Expenses | [19 empty] | 54EBDE PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | 2023-04-25 | N/A | N/A | N/A | 2023-04-25 | N/A | 2023-05-15 | 2023-05-17 | 2023-05-17 | Special Release | 41000 | 41000 |  | 40852.75 | 40852.75 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
04-259 | Other Supplies & Materials Expenses | [19 empty] | 54EBDE PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | 2023-04-25 | N/A | N/A | N/A | 2023-04-25 | N/A | 2023-05-12 | 2023-05-15 | 2023-05-15 | Special Release | 44855 | 44855 |  | 44732.5 | 44732.5 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
04-260 | Training Expenses | [19 empty] | 54EBDE PA | NO | Negotiated 53.9 | N/A | 2023-04-21 | N/A | N/A | 2023-04-25 | N/A | N/A | N/A | 2023-04-25 | N/A | 2023-05-12 | 2023-05-16 | 2023-05-16 | Special Release | 75300 | 75300 |  | 75151 | 75151 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
04-261 | Representation Expenses | [19 empty] | 54EBDE PA | NO | Negotiated 53.9 | N/A | 2023-04-21 | N/A | N/A | 2023-04-25 | N/A | N/A | N/A | 2023-04-25 | N/A | 2023-05-25 | 2023-05-29 | 2023-05-29 | Special Release | 55145 | 55145 |  | 55034.75 | 55034.75 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
05-271 | Training Expenses | [19 empty] | 54EBDE PA | NO | Negotiated 53.9 | N/A | 2023-05-06 | N/A | N/A | 2023-05-09 | N/A | N/A | N/A | 2023-05-09 | N/A | 2023-06-08 | 2023-06-09 | 2023-06-09 | Special Release | 55000 | 55000 |  | 54945.25 | 54945.25 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
02-10 | Representation Expenses | [19 empty] | 547EB PA | NO | Negotiated 53.9 | N/A | 2023-02-07 | N/A | N/A | 2023-02-10 | N/A | N/A | N/A | 2023-02-10 | N/A | 2023-03-06 | 2023-03-07 | 2023-03-07 | MOOE | 135848 | 135848 |  | 135672.75 | 135672.75 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
02-11 | Mobile Expenses | [19 empty] | 547EB PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | 2023-02-10 | N/A | N/A | N/A | 2023-02-10 | N/A | 2023-03-07 | 2023-03-08 | 2023-03-08 | MOOE | 3000 | 3000 |  | 2992.5 | 2992.5 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
02-36 | Drugs and Medicines Expenses | [19 empty] | 547EB PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | 2023-02-16 | N/A | N/A | N/A | 2023-02-16 | N/A | 2023-03-06 | 2023-03-09 | 2023-03-09 | MOOE | 7308 | 7308 |  | 7253 | 7253 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
02-37 | Other Supplies & Materials Expenses | [19 empty] | 547EB PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | 2023-02-16 | N/A | N/A | N/A | 2023-02-16 | N/A | 2023-02-28 | 2023-03-02 | 2023-03-02 | MOOE | 27354 | 27354 |  | 27285.5 | 27285.5 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
02-38 | Training Expenses | [19 empty] | 547EB PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | 2023-02-16 | N/A | N/A | N/A | 2023-02-16 | N/A | 2023-02-28 | 2023-03-02 | 2023-03-02 | MOOE | 44335 | 44335 |  | 44233 | 44233 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
02-52 | Office Supplies Expenses | [19 empty] | 547EB PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | 2023-02-21 | N/A | N/A | N/A | 2023-02-21 | N/A | 2023-03-07 | 2023-03-09 | 2023-03-09 | MOOE | 4786 | 4786 |  | 4712.5 | 4712.5 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
02-61 | R/M of Building | [19 empty] | 547EB PA | NO | Negotiated 53.9 | N/A | 2023-02-21 | N/A | N/A | 2023-02-24 | N/A | N/A | N/A | 2023-02-24 | N/A | 2023-03-10 | 2023-03-13 | 2023-03-13 | MOOE | 60700 | 60700 |  | 60596 | 60596 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
03-73 | Representation Expenses | [19 empty] | 547EB PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | 2023-03-01 | N/A | N/A | N/A | 2023-03-01 | N/A | 2023-03-09 | 2023-03-10 | 2023-03-10 | MOOE | 29544 | 29544 |  | 29449.5 | 29449.5 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
03-74 | Other Supplies & Materials Expenses | [19 empty] | 547EB PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | 2023-03-01 | N/A | N/A | N/A | 2023-03-01 | N/A | 2023-03-10 | 2023-03-13 | 2023-03-13 | MOOE | 12601 | 12601 |  | 12519 | 12519 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
03-75 | Drugs and Medicines Expenses | [19 empty] | 547EB PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | 2023-03-01 | N/A | N/A | N/A | 2023-03-01 | N/A | 2023-03-09 | 2023-03-10 | 2023-03-10 | MOOE | 7308 | 7308 |  | 7264.5 | 7264.5 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
03-76 | Mobile Expenses | [19 empty] | 547EB PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | 2023-03-01 | N/A | N/A | N/A | 2023-03-01 | N/A | 2023-03-13 | 2023-03-20 | 2023-03-20 | MOOE | 15000 | 15000 |  | 14996 | 14996 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
03-94 | R/M EP Comfort Room | [19 empty] | 547EB PA | NO | Negotiated 53.9 | N/A | 2023-03-03 | N/A | N/A | 2023-03-06 | N/A | N/A | N/A | 2023-03-06 | N/A | 2023-04-11 | 2023-04-18 | 2023-04-18 | MOOE | 250279.3 | 250279.3 |  | 249971 | 249971 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
03-95 | R/M Building | [19 empty] | 547EB PA | NO | Negotiated 53.9 | N/A | 2023-03-03 | N/A | N/A | 2023-03-06 | N/A | N/A | N/A | 2023-03-06 | N/A | 2023-04-04 | 2023-04-13 | 2023-04-13 | MOOE | 457768.55 | 457768.55 |  | 457373 | 457373 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
03-96 | ICT Equipment | [19 empty] | 547EB PA | NO | Negotiated 53.9 | N/A | 2023-03-03 | N/A | N/A | 2023-03-06 | N/A | N/A | N/A | 2023-03-06 | N/A | 2023-04-04 | 2023-04-13 | 2023-04-13 | MOOE | 80000 | 80000 |  | 79817 | 79817 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
03-97 | R/M Construction and Heavy Equipment | [19 empty] | 547EB PA | NO | Negotiated 53.9 | N/A | 2023-03-03 | N/A | N/A | 2023-03-06 | N/A | N/A | N/A | 2023-03-06 | N/A | 2023-04-04 | 2023-04-13 | 2023-04-13 | MOOE | 72640 | 72640 |  | 72425 | 72425 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
03-98 | R/M Motor Vehicle | [19 empty] | 547EB PA | NO | Negotiated 53.9 | N/A | 2023-03-03 | N/A | N/A | 2023-03-06 | N/A | N/A | N/A | 2023-03-06 | N/A | 2023-04-04 | 2023-04-14 | 2023-04-14 | MOOE | 64270 | 64270 |  | 64057 | 64057 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
03-129 | Medical, Dental and Laboratory Supplies Expns | [19 empty] | 547EB PA | NO | Negotiated 53.9 | N/A | 2023-03-07 | N/A | N/A | 2023-03-10 | N/A | N/A | N/A | 2023-03-10 | N/A | 2023-04-03 | 2023-04-12 | 2023-04-12 | MOOE | 85200 | 85200 |  | 85152 | 85152 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
03-130 | Representation Expenses | [19 empty] | 547EB PA | NO | Negotiated 53.9 | N/A | 2023-03-07 | N/A | N/A | 2023-03-10 | N/A | N/A | N/A | 2023-03-10 | N/A | 2023-04-04 | 2023-04-13 | 2023-04-13 | MOOE | 104768 | 104768 |  | 104597 | 104597 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
03-168 | Representation Expenses | [19 empty] | 547EB PA | NO | Negotiated 53.9 | N/A | 2023-03-14 | N/A | N/A | 2023-03-17 | N/A | N/A | N/A | 2023-03-17 | N/A | 2023-04-03 | 2023-04-12 | 2023-04-12 | MOOE | 215394 | 215394 |  | 215086.75 | 215086.75 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
03-184 | R/M Motor Vehicle | [19 empty] | 547EB PA | NO | Negotiated 53.9 | N/A | 2023-03-16 | N/A | N/A | 2023-03-20 | N/A | N/A | N/A | 2023-03-20 | N/A | 2023-04-05 | 2023-04-17 | 2023-04-17 | MOOE | 175000 | 175000 |  | 174841 | 174841 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
03-191 | Training Expenses | [19 empty] | 547EB PA | NO | Negotiated 53.9 | N/A | 2023-03-17 | N/A | N/A | 2023-03-20 | N/A | N/A | N/A | 2023-03-20 | N/A | 2023-04-05 | 2023-04-17 | 2023-04-17 | MOOE | 58203 | 58203 |  | 58078 | 58078 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
04-256 | R/M Motor Vehicle | [19 empty] | 547EB PA | NO | Negotiated 53.9 | N/A | 2023-04-21 | N/A | N/A | 2023-04-25 | N/A | N/A | N/A | 2023-04-25 | N/A | 2023-05-12 | 2023-05-15 | 2023-05-15 | Special Release | 175000 | 175000 |  | 174859 | 174859 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
02-8 | ICT Equipment | [19 empty] | 549ECBN PA | NO | Negotiated 53.9 | N/A | 2023-02-07 | N/A | N/A | 2023-02-10 | N/A | N/A | N/A | 2023-02-10 | N/A | 2023-03-06 | 2023-03-07 | 2023-03-07 | MOOE | 90000 | 90000 |  | 89926 | 89926 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
02-9 | Other Supplies & Materials Expenses | [19 empty] | 549ECBN PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | 2023-02-10 | N/A | N/A | N/A | 2023-02-10 | N/A | 2023-02-28 | 2023-03-02 | 2023-03-02 | MOOE | 27900 | 27900 |  | 27817 | 27817 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
02-26 | Training Expenses | [19 empty] | 549ECBN PA | NO | Negotiated 53.9 | N/A | 2023-02-10 | N/A | N/A | 2023-02-14 | N/A | N/A | N/A | 2023-02-14 | N/A | 2023-03-06 | 2023-03-08 | 2023-03-08 | MOOE | 121000 | 121000 |  | 120820 | 120820 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
02-34 | Medical, Dental and Laboratory Supplies Expns | [19 empty] | 549ECBN PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | 2023-02-16 | N/A | N/A | N/A | 2023-02-16 | N/A | 2023-02-22 | 2023-02-23 | 2023-02-23 | MOOE | 5000 | 5000 |  | 4969.75 | 4969.75 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
02-35 | Drugs and Medicines Expenses | [19 empty] | 549ECBN PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | 2023-02-16 | N/A | N/A | N/A | 2023-02-16 | N/A | 2023-02-28 | 2023-03-02 | 2023-03-02 | MOOE | 5000 | 5000 |  | 4889.5 | 4889.5 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
02-47 | Representation Expenses | [19 empty] | 549ECBN PA | NO | Negotiated 53.9 | N/A | 2023-02-16 | N/A | N/A | 2023-02-20 | N/A | N/A | N/A | 2023-02-20 | N/A | 2023-03-06 | 2023-03-09 | 2023-03-09 | MOOE | 184300 | 184300 |  | 184112.5 | 184112.5 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
02-53 | Office Supplies Expenses | [19 empty] | 549ECBN PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | 2023-02-21 | N/A | N/A | N/A | 2023-02-21 | N/A | 2023-03-06 | 2023-03-10 | 2023-03-10 | MOOE | 10808.06 | 10808.06 |  | 10757 | 10757 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
03-103 | Repair and Enchancement of Blacher | [19 empty] | 549ECBN PA | NO | Negotiated 53.9 | N/A | 2023-03-04 | N/A | N/A | 2023-03-07 | N/A | N/A | N/A | 2023-03-07 | N/A | 2023-04-05 | 2023-04-17 | 2023-04-17 | Special Release | 689600 | 689600 |  | 688429 | 688429 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
03-104 | R/M Building | [19 empty] | 549ECBN PA | NO | Negotiated 53.9 | N/A | 2023-03-04 | N/A | N/A | 2023-03-07 | N/A | N/A | N/A | 2023-03-07 | N/A | 2023-04-05 | 2023-04-14 | 2023-04-14 | Special Release | 527198 | 527198 |  | 526857 | 526857 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
03-106 | R/M Building | [19 empty] | 549ECBN PA | NO | Negotiated 53.9 | N/A | 2023-03-04 | N/A | N/A | 2023-03-07 | N/A | N/A | N/A | 2023-03-07 | N/A | 2023-04-05 | 2023-04-17 | 2023-04-17 | Special Release | 649600 | 649600 |  | 648764.25 | 648764.25 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
03-122 | Medical, Dental and Laboratory Supplies Expns | [19 empty] | 549ECBN PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | 2023-03-09 | N/A | N/A | N/A | 2023-03-09 | N/A | 2023-03-30 | 2023-03-31 | 2023-03-31 | MOOE | 5000 | 5000 |  | 4286.5 | 4286.5 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
03-123 | Other Supplies & Materials Expenses | [19 empty] | 549ECBN PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | 2023-03-09 | N/A | N/A | N/A | 2023-03-09 | N/A | 2023-04-14 | 2023-04-19 | 2023-04-19 | MOOE | 17000 | 17000 |  | 16934.5 | 16934.5 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
03-140 | Drugs and Medicines Expenses | [19 empty] | 549ECBN PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | 2023-03-10 | N/A | N/A | N/A | 2023-03-10 | N/A | 2023-04-03 | 2023-04-12 | 2023-04-12 | MOOE | 5000 | 5000 |  | 4953.5 | 4953.5 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
03-152 | Training Expenses | [19 empty] | 549ECBN PA | NO | Negotiated 53.9 | N/A | 2023-03-10 | N/A | N/A | 2023-03-13 | N/A | N/A | N/A | 2023-03-13 | N/A | 2023-04-05 | 2023-04-17 | 2023-04-17 | MOOE | 90000 | 90000 |  | 89908 | 89908 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
03-154 | ICT Equipment | [19 empty] | 549ECBN PA | NO | Negotiated 53.9 | N/A | 2023-03-10 | N/A | N/A | 2023-03-13 | N/A | N/A | N/A | 2023-03-13 | N/A | 2023-03-31 | 2023-04-03 | 2023-04-03 | MOOE | 165000 | 165000 |  | 164878 | 164878 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
03-165 | Representation Expenses | [19 empty] | 549ECBN PA | NO | Negotiated 53.9 | N/A | 2023-03-14 | N/A | N/A | 2023-03-17 | N/A | N/A | N/A | 2023-03-17 | N/A | 2023-04-03 | 2023-04-12 | 2023-04-12 | MOOE | 63900 | 63900 |  | 63734.5 | 63734.5 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
03-167 | R/M Building | [19 empty] | 549ECBN PA | NO | Negotiated 53.9 | N/A | 2023-03-14 | N/A | N/A | 2023-03-17 | N/A | N/A | N/A | 2023-03-17 | N/A | 2023-04-03 | 2023-04-13 | 2023-04-13 | MOOE | 70000 | 70000 |  | 69892.5 | 69892.5 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
03-173 | Representation Expenses | [19 empty] | 549ECBN PA | NO | Negotiated 53.9 | N/A | 2023-03-14 | N/A | N/A | 2023-03-17 | N/A | N/A | N/A | 2023-03-17 | N/A | 2023-04-14 | 2023-04-19 | 2023-04-19 | MOOE | 166800 | 166800 |  | 166638.28 | 166638.28 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
03-174 | Representation Expenses | [19 empty] | 549ECBN PA | NO | Negotiated 53.9 | N/A | 2023-03-14 | N/A | N/A | 2023-03-17 | N/A | N/A | N/A | 2023-03-17 | N/A | 2023-04-12 | 2023-04-18 | 2023-04-18 | MOOE | 63900 | 63900 |  | 63734.5 | 63734.5 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
03-175 | Medical, Dental and Laboratory Supplies Expns | [19 empty] | 549ECBN PA | NO | Negotiated 53.9 | N/A | 2023-03-14 | N/A | N/A | 2023-03-17 | N/A | N/A | N/A | 2023-03-17 | N/A | 2023-04-03 | 2023-04-12 | 2023-04-12 | MOOE | 85200 | 85200 |  | 85102 | 85102 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
03-192 | Semi-Expendable Machinery expenses | [19 empty] | 549ECBN PA | NO | Negotiated 53.9 | N/A | 2023-03-16 | N/A | N/A | 2023-03-20 | N/A | N/A | N/A | 2023-03-20 | N/A | 2023-04-03 | 2023-04-12 | 2023-04-12 | MOOE | 120000 | 120000 |  | 119899 | 119899 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
03-221 | R/M Building | [19 empty] | 549ECBN PA | NO | Negotiated 53.9 | N/A | 2023-03-24 | N/A | N/A | 2023-03-28 | N/A | N/A | N/A | 2023-03-28 | N/A | 2023-04-17 | 2023-04-19 | 2023-04-19 | Special Release | 694600 | 694600 |  | 694188.75 | 694188.75 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
03-222 | R/M Building | [19 empty] | 549ECBN PA | NO | Negotiated 53.9 | N/A | 2023-03-24 | N/A | N/A | 2023-03-28 | N/A | N/A | N/A | 2023-03-28 | N/A | 2023-04-13 | 2023-04-18 | 2023-04-18 | Special Release | 689600 | 689600 |  | 689324.5 | 689324.5 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
03-223 | Office Supplies Expenses | [19 empty] | 549ECBN PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | 2023-03-28 | N/A | N/A | N/A | 2023-03-28 | N/A | 2023-04-12 | 2023-04-18 | 2023-04-18 | MOOE | 14159.6 | 14159.6 |  | 14137.5 | 14137.5 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
04-239 | R/M Building | [19 empty] | 549ECBN PA | NO | Negotiated 53.9 | N/A | 2023-03-31 | N/A | N/A | 2023-04-03 | N/A | N/A | N/A | 2023-04-03 | N/A | 2023-05-12 | 2023-05-15 | 2023-05-15 | Special Release | 175000 | 175000 |  | 174842 | 174842 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
05-270 | Other Supplies & Materials Expenses | [19 empty] | 549ECBN PA | NO | Negotiated 53.9 | N/A | 2023-04-29 | N/A | N/A | 2023-05-03 | N/A | N/A | N/A | 2023-05-03 | N/A | 2023-05-12 | 2023-05-16 | 2023-05-16 | Special Release | 175000 | 175000 |  | 174862 | 174862 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
05-274 | R/M Semi-Expendable ICT Eqpmnt | [19 empty] | 549ECBN PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | 2023-05-09 | N/A | N/A | N/A | 2023-05-09 | N/A | 2023-05-29 | 2023-06-01 | 2023-06-01 | MOOE | 20000 | 20000 |  | 19931 | 19931 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
02-2 | Representation Expenses | [19 empty] | ESC, 54EBDE PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | 2023-02-07 | N/A | N/A | N/A | 2023-02-07 | N/A | 2023-03-02 | 2023-03-03 | 2023-03-03 | MOOE | 42700 | 42700 |  | 42596 | 42596 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
02-4 | ICT Equipment | [19 empty] | ESC, 54EBDE PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | 2023-02-07 | N/A | N/A | N/A | 2023-02-07 | N/A | 2023-03-09 | 2023-03-10 | 2023-03-10 | MOOE | 7500 | 7500 |  | 7445 | 7445 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
02-19 | Training Expenses | [19 empty] | ESC, 54EBDE PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | 2023-02-10 | N/A | N/A | N/A | 2023-02-10 | N/A | 2023-03-06 | 2023-03-07 | 2023-03-07 | MOOE | 30000 | 30000 |  | 29873.5 | 29873.5 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
02-23 | R/M Motor Vehicle | [19 empty] | ESC, 54EBDE PA | NO | Negotiated 53.9 | N/A | 2023-02-10 | N/A | N/A | 2023-02-14 | N/A | N/A | N/A | 2023-02-14 | N/A | 2023-03-06 | 2023-03-08 | 2023-03-08 | MOOE | 50000 | 50000 |  | 49848 | 49848 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
03-107 | Printing and Publication Expenses | [19 empty] | ESC, 54EBDE PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | 2023-03-08 | N/A | N/A | N/A | 2023-03-08 | N/A | 2023-04-03 | 2023-04-13 | 2023-04-13 | MOOE | 10700 | 10700 |  | 10637 | 10637 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
03-113 | Representation Expenses | [19 empty] | ESC, 54EBDE PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | 2023-03-08 | N/A | N/A | N/A | 2023-03-08 | N/A | 2023-04-03 | 2023-04-12 | 2023-04-12 | MOOE | 37500 | 37500 |  | 37403.75 | 37403.75 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
03-120 | Representation Expenses | [19 empty] | ESC, 54EBDE PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | 2023-03-09 | N/A | N/A | N/A | 2023-03-09 | N/A | 2023-04-03 | 2023-04-12 | 2023-04-12 | MOOE | 37500 | 37500 |  | 37433.75 | 37433.75 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
03-147 | R/M of Dozer | [19 empty] | ESC, 54EBDE PA | NO | Negotiated 53.9 | N/A | 2023-03-10 | N/A | N/A | 2023-03-13 | N/A | N/A | N/A | 2023-03-13 | N/A | 2023-03-31 | 2023-04-03 | 2023-04-03 | Special Release | 366650 | 366650 |  | 366349 | 366349 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
03-151 | R/M of Motor Vehicle | [19 empty] | ESC, 54EBDE PA | NO | Negotiated 53.9 | N/A | 2023-03-10 | N/A | N/A | 2023-03-13 | N/A | N/A | N/A | 2023-03-13 | N/A | 2023-03-31 | 2023-04-03 | 2023-04-03 | MOOE | 50000 | 50000 |  | 49949 | 49949 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
03-155 | ICT Equipment | [19 empty] | ESC, 54EBDE PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | 2023-03-14 | N/A | N/A | N/A | 2023-03-14 | N/A | 2023-03-30 | 2023-03-31 | 2023-03-31 | MOOE | 7500 | 7500 |  | 7465 | 7465 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
03-157 | Medical, Dental and Laboratory Supplies Expns | [19 empty] | ESC, 54EBDE PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | 2023-03-14 | N/A | N/A | N/A | 2023-03-14 | N/A | 2023-04-05 | 2023-04-17 | 2023-04-17 | MOOE | 45000 | 45000 |  | 44459.5 | 44459.5 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
03-160 | Medical, Dental and Laboratory Supplies Expns | [19 empty] | ESC, 54EBDE PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | 2023-03-14 | N/A | N/A | N/A | 2023-03-14 | N/A | 2023-03-31 | 2023-04-03 | 2023-04-03 | MOOE | 5000 | 5000 |  | 4969.5 | 4969.5 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
03-162 | Office Supplies Expenses | [19 empty] | ESC, 54EBDE PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | 2023-03-14 | N/A | N/A | N/A | 2023-03-14 | N/A | 2023-04-05 | 2023-04-14 | 2023-04-14 | MOOE | 9113.02 | 9113.02 |  | 9049.5 | 9049.5 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
03-171 | R/M Construction and Heavy Equipment | [19 empty] | ESC, 54EBDE PA | NO | Negotiated 53.9 | N/A | 2023-03-14 | N/A | N/A | 2023-03-17 | N/A | N/A | N/A | 2023-03-17 | N/A | 2023-04-05 | 2023-04-17 | 2023-04-17 | MOOE | 107000 | 107000 |  | 106842 | 106842 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
03-172 | Representation Expenses | [19 empty] | ESC, 54EBDE PA | NO | Negotiated 53.9 | N/A | 2023-03-14 | N/A | N/A | 2023-03-17 | N/A | N/A | N/A | 2023-03-17 | N/A | 2023-03-30 | 2023-03-31 | 2023-03-31 | MOOE | 174670 | 174670 |  | 174457 | 174457 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
03-185 | Admin/Operational Support | [19 empty] | ESC, 54EBDE PA | NO | Negotiated 53.9 | N/A | 2023-03-16 | N/A | N/A | 2023-03-20 | N/A | N/A | N/A | 2023-03-20 | N/A | 2023-04-05 | 2023-04-17 | 2023-04-17 | MOOE | 100000 | 100000 |  | 99852 | 99852 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
03-232 | Training Expenses | [19 empty] | ESC, 54EBDE PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | 2023-03-28 | N/A | N/A | N/A | 2023-03-28 | N/A | 2023-04-11 | 2023-04-18 | 2023-04-18 | MOOE | 30000 | 30000 |  | 29850.75 | 29850.75 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
02-20 | Representation Expenses | [19 empty] | 545EBN, 54EBDE PA | NO | Negotiated 53.9 | N/A | 2023-02-08 | N/A | N/A | 2023-02-10 | N/A | N/A | N/A | 2023-02-10 | N/A | 2023-03-06 | 2023-03-09 | 2023-03-09 | MOOE | 101675 | 101675 |  | 101523.25 | 101523.25 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
02-24 | R/M Building | [19 empty] | 545EBN, 54EBDE PA | NO | Negotiated 53.9 | N/A | 2023-02-10 | N/A | N/A | 2023-02-14 | N/A | N/A | N/A | 2023-02-14 | N/A | 2023-03-07 | 2023-03-09 | 2023-03-09 | MOOE | 51490 | 51490 |  | 51344 | 51344 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
02-43 | Medical, Dental and Laboratory Supplies Expns | [19 empty] | 545EBN, 54EBDE PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | 2023-02-17 | N/A | N/A | N/A | 2023-02-17 | N/A | 2023-03-06 | 2023-03-09 | 2023-03-09 | MOOE | 6250 | 6250 |  | 6143.5 | 6143.5 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
02-44 | Mobile Expenses | [19 empty] | 545EBN, 54EBDE PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | 2023-02-17 | N/A | N/A | N/A | 2023-02-17 | N/A | 2023-03-07 | 2023-03-09 | 2023-03-09 | MOOE | 13500 | 13500 |  | 13265 | 13265 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
02-45 | Drugs and Medicines Expenses | [19 empty] | 545EBN, 54EBDE PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | 2023-02-17 | N/A | N/A | N/A | 2023-02-17 | N/A | 2023-03-06 | 2023-03-09 | 2023-03-09 | MOOE | 5000 | 5000 |  | 4975 | 4975 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
02-60 | Office Supplies Expenses | [19 empty] | 545EBN, 54EBDE PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | 2023-02-24 | N/A | N/A | N/A | 2023-02-24 | N/A | 2023-03-10 | 2023-03-13 | 2023-03-13 | MOOE | 35499.85 | 35499.85 |  | 35332 | 35332 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
03-82 | Medical, Dental and Laboratory Supplies Expns | [19 empty] | 545EBN, 54EBDE PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | 2023-03-03 | N/A | N/A | N/A | 2023-03-03 | N/A | 2023-03-10 | 2023-03-13 | 2023-03-13 | MOOE | 42600 | 42600 |  | 42460 | 42460 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
03-83 | Mobile Expenses | [19 empty] | 545EBN, 54EBDE PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | 2023-03-03 | N/A | N/A | N/A | 2023-03-03 | N/A | 2023-03-10 | 2023-03-13 | 2023-03-13 | MOOE | 13900 | 13900 |  | 13809 | 13809 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
03-102 | Representation Expenses | [19 empty] | 545EBN, 54EBDE PA | NO | Negotiated 53.9 | N/A | 2023-03-04 | N/A | N/A | 2023-03-07 | N/A | N/A | N/A | 2023-03-07 | N/A | 2023-04-04 | 2023-04-14 | 2023-04-14 | MOOE | 50000 | 50000 |  | 49966 | 49966 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
03-105 | ICT Equipment | [19 empty] | 545EBN, 54EBDE PA | NO | Negotiated 53.9 | N/A | 2023-03-04 | N/A | N/A | 2023-03-07 | N/A | N/A | N/A | 2023-03-07 | N/A | 2023-04-04 | 2023-04-13 | 2023-04-13 | MOOE | 110371 | 110371 |  | 110068 | 110068 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
03-109 | Printing and Publication Expenses | [19 empty] | 545EBN, 54EBDE PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | 2023-03-08 | N/A | N/A | N/A | 2023-03-08 | N/A | 2023-04-04 | 2023-04-13 | 2023-04-13 | MOOE | 6520 | 6520 |  | 6486 | 6486 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
03-110 | Sport Equipment | [19 empty] | 545EBN, 54EBDE PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | 2023-03-08 | N/A | N/A | N/A | 2023-03-08 | N/A | 2023-04-12 | 2023-04-18 | 2023-04-18 | MOOE | 14780 | 14780 |  | 14638 | 14638 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
03-111 | Drugs and Medicines Expenses | [19 empty] | 545EBN, 54EBDE PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | 2023-03-08 | N/A | N/A | N/A | 2023-03-08 | N/A | 2023-04-03 | 2023-04-12 | 2023-04-12 | MOOE | 5000 | 5000 |  | 4956.75 | 4956.75 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
03-112 | R/M Construction and Heavy Equipment | [19 empty] | 545EBN, 54EBDE PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | 2023-03-08 | N/A | N/A | N/A | 2023-03-08 | N/A | 2023-04-04 | 2023-04-14 | 2023-04-14 | MOOE | 27214 | 27214 |  | 27054 | 27054 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
03-114 | R/M Building | [19 empty] | 545EBN, 54EBDE PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | 2023-03-08 | N/A | N/A | N/A | 2023-03-08 | N/A | 2023-04-04 | 2023-04-17 | 2023-04-17 | MOOE | 37650 | 37650 |  | 37471 | 37471 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
03-131 | R/M Motor Vehicle | [19 empty] | 545EBN, 54EBDE PA | NO | Negotiated 53.9 | N/A | 2023-03-07 | N/A | N/A | 2023-03-10 | N/A | N/A | N/A | 2023-03-10 | N/A | 2023-03-31 | 2023-04-03 | 2023-04-03 | MOOE | 58745 | 58745 |  | 58633 | 58633 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
03-137 | R/M Building | [19 empty] | 545EBN, 54EBDE PA | NO | Negotiated 53.9 | N/A | 2023-03-07 | N/A | N/A | 2023-03-10 | N/A | N/A | N/A | 2023-03-10 | N/A | 2023-04-04 | 2023-04-13 | 2023-04-13 | Special Release | 304860 | 304860 |  | 304617 | 304617 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
03-138 | Disaster Response and rescue Equipment | [19 empty] | 545EBN, 54EBDE PA | NO | Negotiated 53.9 | N/A | 2023-03-07 | N/A | N/A | 2023-03-10 | N/A | N/A | N/A | 2023-03-10 | N/A | 2023-04-03 | 2023-04-12 | 2023-04-12 | MOOE | 80000 | 80000 |  | 79850 | 79850 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
03-139 | Representation Expenses | [19 empty] | 545EBN, 54EBDE PA | NO | Negotiated 53.9 | N/A | 2023-03-07 | N/A | N/A | 2023-03-10 | N/A | N/A | N/A | 2023-03-10 | N/A | 2023-04-03 | 2023-04-12 | 2023-04-12 | MOOE | 185300 | 185300 |  | 185135.75 | 185135.75 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
03-146 | Training Expenses | [19 empty] | 545EBN, 54EBDE PA | NO | Negotiated 53.9 | N/A | 2023-03-10 | N/A | N/A | 2023-03-13 | N/A | N/A | N/A | 2023-03-13 | N/A | 2023-03-31 | 2023-04-03 | 2023-04-03 | MOOE | 55700 | 55700 |  | 55589.5 | 55589.5 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
03-161 | Other Supplies & Materials Expenses | [19 empty] | 545EBN, 54EBDE PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | 2023-03-14 | N/A | N/A | N/A | 2023-03-14 | N/A | 2023-03-31 | 2023-04-03 | 2023-04-03 | MOOE | 25000 | 25000 |  | 24943.5 | 24943.5 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
03-189 | Representation Expenses | [19 empty] | 545EBN, 54EBDE PA | NO | Negotiated 53.9 | N/A | 2023-03-16 | N/A | N/A | 2023-03-20 | N/A | N/A | N/A | 2023-03-20 | N/A | 2023-03-31 | 2023-04-03 | 2023-04-03 | MOOE | 50000 | 50000 |  | 49949 | 49949 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
03-193 | Admin/Operational Support | [19 empty] | 545EBN, 54EBDE PA | NO | Negotiated 53.9 | N/A | 2023-03-16 | N/A | N/A | 2023-03-20 | N/A | N/A | N/A | 2023-03-20 | N/A | 2023-04-05 | 2023-04-17 | 2023-04-17 | Special Release | 175000 | 175000 |  | 174860 | 174860 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
03-216 | Medical, Dental and Laboratory Supplies Expns | [19 empty] | 545EBN, 54EBDE PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | 2023-03-24 | N/A | N/A | N/A | 2023-03-24 | N/A | 2023-04-11 | 2023-04-18 | 2023-04-18 | MOOE | 42600 | 42600 |  | 42520.5 | 42520.5 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
03-217 | Mobile Expenses | [19 empty] | 545EBN, 54EBDE PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | 2023-03-24 | N/A | N/A | N/A | 2023-03-24 | N/A | 2023-04-05 | 2023-04-17 | 2023-04-17 | MOOE | 13900 | 13900 |  | 13800 | 13800 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
04-254 | Medical, Dental and Laboratory Supplies Expns | [19 empty] | 545EBN, 54EBDE PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | 2023-04-04 | N/A | N/A | N/A | 2023-04-04 | N/A | 2023-04-17 | 2023-04-19 | 2023-04-19 | MOOE | 6250 | 6250 |  | 6120 | 6120 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
05-265 | Semi-Expendable-ICT Eqpmnt | [19 empty] | 545EBN, 54EBDE PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | 2023-05-03 | N/A | N/A | N/A | 2023-05-03 | N/A | 2023-05-15 | 2023-05-16 | 2023-05-16 | MOOE | 25110 | 25110 |  | 25022 | 25022 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
[38 empty] | 15333887.38 | 15333887.38 |  | 15310343.78 | 15310343.78
Total Alloted Budget of Procurement Activities | [37 empty] | 15333887.38
Total Contract Price of Procurement Actitvites Conducted | [40 empty] | 15310343.78
Total Savings (Total Alloted Budget - Total Contract Price) | [37 empty] | 23543.6
0N-GOING PROCUREMENT ACTIVITIES
05-281 | Other Supplies & Materials Expenses | [19 empty] | 54EBDE PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | 2023-05-30 | N/A | N/A | N/A | 2023-05-30 | N/A |  |  |  | MOOE | 3750 | 3750 |  | 3672 | 3672 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | FOR TIAC/INSP
06-282 | Semi-Expendable-ICT Eqpmnt | [19 empty] | 54EBDE PA | NO | Negotiated 53.9 | N/A | 2023-05-30 | N/A | N/A | 2023-06-02 | N/A | N/A | N/A | 2023-06-02 | N/A |  |  |  | Special Release | 50000 | 50000 |  | 49831.5 | 49831.5 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | FOR TIAC/INSP
06-283 | Semi-Expendable Furniture & Fixture | [19 empty] | 54EBDE PA | NO | Negotiated 53.9 | N/A | 2023-05-30 | N/A | N/A | 2023-06-02 | N/A | N/A | N/A | 2023-06-02 | N/A |  |  |  | Special Release | 63500 | 63500 |  | 63372 | 63372 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | FOR PRE AUDIT
06-284 | Semi-Expendable-ICT Eqpmnt | [19 empty] | 54EBDE PA | NO | Negotiated 53.9 | N/A | 2023-05-30 | N/A | N/A | 2023-06-02 | N/A | N/A | N/A | 2023-06-02 | N/A |  |  |  | Special Release | 149371 | 149371 |  | 149059 | 149059 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | FOR PRE AUDIT
06-295 | Support for the amenities of BRF | [19 empty] | 54EBDE PA | NO | Negotiated 53.9 | N/A | 2023-06-01 | N/A | N/A | 2023-06-05 | N/A | N/A | N/A | 2023-06-05 | N/A |  |  |  | Special Release | 220600 | 220600 |  | 220426 | 220426 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | FOR PRE AUDIT
06-296 | Support for the amenities of BRF | [19 empty] | 54EBDE PA | NO | Negotiated 53.9 | N/A | 2023-06-05 | N/A | N/A | 2023-06-06 | N/A | N/A | N/A | 2023-06-06 | N/A |  |  |  | Special Release | 98020 | 98020 |  | 97946 | 97946 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | FOR PRE AUDIT
06-297 | Support for the enhancement ATF (2 Rooms-4pax | [19 empty] | 54EBDE PA | NO | Negotiated 53.9 | N/A | 2023-06-09 | N/A | N/A | 2023-06-09 | N/A | N/A | N/A | 2023-06-09 | N/A |  |  |  | Special Release | 854060 | 854060 |  | 853632.5 | 853632.5 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | FOR CAF
06-298 | Support for the enhancement ATF (2 Rooms-4pax | [19 empty] | 54EBDE PA | NO | Negotiated 53.9 | N/A | 2023-06-09 | N/A | N/A | 2023-06-09 | N/A | N/A | N/A | 2023-06-09 | N/A |  |  |  | Special Release | 854060 | 854060 |  | 853563.5 | 853563.5 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | FOR CAF
06-299 | Support for the enhancement ATF (2 Rooms-4pax | [19 empty] | 54EBDE PA | NO | Negotiated 53.9 | N/A | 2023-06-09 | N/A | N/A | 2023-06-09 | N/A | N/A | N/A | 2023-06-09 | N/A |  |  |  | Special Release | 854060 | 854060 |  | 853563.5 | 853563.5 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | FOR CAF
06-300 | medical, Dental and Laboratory Supplies | [19 empty] | 54EBDE PA | NO | Negotiated 53.9 | N/A | 2023-06-10 | N/A | N/A | 2023-06-13 | N/A | N/A | N/A | 2023-06-13 | N/A |  |  |  | Special Release | 86000 | 86000 |  | 85836.75 | 85836.75 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | FOR CAF
06-311 | Semi-Expendable ICT Eqpmnt | [19 empty] | 54EBDE PA | NO | Negotiated 53.9 | N/A | 2023-06-16 | N/A | N/A | 2023-06-20 | N/A | N/A | N/A | 2023-06-20 | N/A |  |  |  | Special Release | 99185 | 99185 |  | 99047 | 99047 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | FOR FUNDING
06-312 | Medical & Dental Lab Expns | [19 empty] | 54EBDE PA | NO | Negotiated 53.9 | N/A | 2023-06-16 | N/A | N/A | 2023-06-20 | N/A | N/A | N/A | 2023-06-20 | N/A |  |  |  | Special Release | 66250 | 66250 |  | 66064.5 | 66064.5 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | FOR OBR
06-313 | Semi-Expendable Office Eqpmnt | [19 empty] | 54EBDE PA | NO | Negotiated 53.9 | N/A | 2023-06-16 | N/A | N/A | 2023-06-20 | N/A | N/A | N/A | 2023-06-20 | N/A |  |  |  | Special Release | 232600 | 232600 |  | 232352 | 232352 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | FOR OBR
06-314 | Training Expenses | [19 empty] | 54EBDE PA | NO | Negotiated 53.9 | N/A | 2023-06-16 | N/A | N/A | 2023-06-20 | N/A | N/A | N/A | 2023-06-20 | N/A |  |  |  | Special Release | 170550 | 170550 |  | 170268.75 | 170268.75 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | FOR OBR
06-309 | Semi-Expandable ICT Equipmen | [19 empty] | 549ECBN PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | 2023-06-14 | N/A | N/A | N/A | 2023-06-14 | N/A |  |  |  | MOOE | 20000 | 20000 |  | 19926 | 19926 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | FOR TIAC/INSP
06-315 | R/M of Backhoe Loader | [19 empty] | 549ECBN PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | 2023-06-20 | N/A | N/A | N/A | 2023-06-20 | N/A |  |  |  | SR | 175400 | 175400 |  | 175233 | 175233 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | FOR PO FUNDING
06-286 | Admin/Operational Support | [19 empty] | ESC, 54EBDE PA | NO | Negotiated 53.9 | N/A | 2023-05-30 | N/A | N/A | 2023-06-02 | N/A | N/A | N/A | 2023-06-02 | N/A |  |  |  | Special Release | 100000 | 100000 |  | 99897 | 99897 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | FOR TIAC INSP
06-285 | Admin/Operational Support | [19 empty] | 545EBN, 54EBDE PA | NO | Negotiated 53.9 | N/A | 2023-05-30 | N/A | N/A | 2023-06-02 | N/A | N/A | N/A | 2023-06-02 | N/A |  |  |  | SR | 175000 | 175000 |  | 174842 | 174842 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | FOR TIAC/INSP
06-306 | Semi-Expendable ICT Equipment | [19 empty] | 545EBN, 54EBDE PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | 2023-06-14 | N/A | N/A | N/A | 2023-06-14 | N/A |  |  |  | MOOE | 25110 | 25110 |  | 25018 | 25018 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | FOR TIAC/INSP
06-307 | Other Supplies and Materials Expense | [19 empty] | 545EBN, 54EBDE PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | 2023-06-14 | N/A | N/A | N/A | 2023-06-14 | N/A |  |  |  | SR | 10000 | 10000 |  | 9936 | 9936 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | FOR TIAC/INSP
[38 empty] | 4307516 |  |  | 4303487
Total Alloted Budget of On-going Procurement Activities | [37 empty] | 4307516
[21 empty] | Prepared by: | [21 empty] | APPROVED:
[21 empty] | FELIPE V ESTRADA | [21 empty] | RANDY F FAJILAGUTAN
[21 empty] | LTC (CE) PA | [21 empty] | BGEN PA
[21 empty] | Logistics Officer | [21 empty] | Commander

## Sheet2
1 | 02-001 | 9ISU-2022-02 | Drugs and Medicines | 9ISU,AIR,PA | 10000 | 9926.5 | 73.5 | Lifemed Pharma & Gen Mdse | Negotiated 53.9 | MOOE | 5-02-03-070-00 | 5400-2022-0018 | 1st | 1 | 2022-02-08 | 2022-02-08 | 2022-02-09 | 2022-02-10 | 2022-02-18 | 10 | 2022-02-22 | 4 | 14 | 531.7768 | 9394.7232 | 101-03-003-2022 | 2022-03-09 | 15 | 29 | Paid | -44600 | 1
68 | 03-67 | 9ISU-2023-01 | Training Expenses | 9ISU,AIR,PA | 23000 | 22935 | 65 | RRJ Enterprises | Negotiated 53.9 | MOOE | 5-02-02-010-02 | 5400-2023-0009 | 1st | 1 | 2023-02-28 | 2023-02-28 | 2023-03-01 | 2023-03-02 | 2023-03-10 |  | 2023-03-14 |  |  |  |  | 101-04-006-2023 | 2023-04-04 |  |  | Paid
90 | 03-89 | 9ISU-2023-02 | R/M of Building | 9ISU,AIR,PA | 30000 | 29912 | 88 | R.B. Lim Marketing | Negotiated 53.9 | MOOE | 5-02-13-040-01 | 5400-2023-0009 | 1st | 1 | 2023-03-02 | 2023-03-02 | 2023-03-03 | 2023-03-03
184 | 03-183 | 9ISU-2023-03 | Medical, Dental and Laboratory Supplies Expns | 9ISU,AIR,PA | 56000 | 55915 | 85 | Lifemed Pharma & Gen Mdse | Negotiated 53.9 | MOOE | 5-02-03-080-00 | 5400-2023-0077/0115 | 1ST/2ND | 2 | 2023-03-16 | 2023-03-16 | 2023-03-20 | 2023-03-21
188 | 03-187 | 9ISU-2023-04 | R/M Building | 9ISU,AIR,PA | 70000 | 69878 | 122 | R.B. Lim Marketing | Negotiated 53.9 | MOOE | 5-02-13-040-01 | 5400-2023-102 | 2nd | 1 | 2023-03-16 | 2023-03-16 | 2023-03-20 | 2023-03-21
204 | 03-203 | 9ISU-2023-05 | Representation Expenses | 9ISU,AIR,PA | 40000 | 39842.75 | 157.25 | RRJ Enterprises | Negotiated 53.9 | MOOE | 5-02-99-030-00 | 5400-2023-0077 | 1ST/2ND | 2 | 2023-03-20 | 2023-03-20 | 2023-03-22 | 2023-03-23
248 | 04-247 | 9ISU-2023-05 | R/M Other Structure | 9ISU,AIR,PA | 30000 | 29920 | 80 | RRJ Enterprises | Negotiated 53.9 | MOOE | 5-02-13-040-99 | 5400-2023-0102 | 2nd | 1 | 2023-04-03 | 2023-04-03 | 2023-04-04 | 2023-04-04
249 | 04-248 | 9ISU-2023-07 | Mobile Expenses | 9ISU,AIR,PA | 44000 | 43856.5 | 143.5 | R AND W ENTERPRISES | Negotiated 53.9 | MOOE | 5-02-05-020-01 | 5400-2023-0077 | 2ND | 1 | 2023-04-03 | 2023-04-03 | 2023-04-04 | 2023-04-04
276 | 05-275 | 9ISU-2023-08 | Training Expenses | 9ISU,AIR,PA | 48000 | 47897 | 103 | PRINCE MICHAELA ENTERPRISES | Negotiated 53.9 | MOOE | 5-02-02-010-02 | 5400-2023-0102 | 2nd | 1 | 2023-05-30 | 2023-05-30 | 2023-05-30 | 2023-05-31

## Sheet1 (hidden)
Competitive Bidding | GoP | YES
Limited Source Bidding | Foreign | NO
Direct Contracting | Special Purpose Fund
Repeat Order | Corporate Budget
Shopping | Income
NP-53.1 Two Failed Biddings | Others
NP-53.2 Emergency Cases
NP-53.3 Take-Over of Contracts
NP-53.4 Adjacent or Contiguous
NP-53.5 Agency-to-Agency
NP-53.6 Scientific, Scholarly, Artistic Work, Exclusive Technology and Media Services
NP-53.7 Highly Technical Consultants
NP-53.8 Defense Cooperation Agreement
NP-53.9 - Small Value Procurement
NP-53.10 Lease of Real Property and Venue
NP-53.11 NGO Participation
NP-53.12 Community Participation
NP-53.13 UN Agencies, Int'l Organizations or International Financing Institutions
Others - Foreign-funded procurement