## 9ID
|  |  | ANNEX A | [18 empty] | ANNEX B
|  |  | Department of Budget and Management Annual Procurement Plan for FY 2022 | [18 empty] | 109TH CONTRACTING OFFICE - 9ID, PA - PROJECT MONITORING REPORT - 01 Jan- 15 June 2023
| Code (PAP) | Procurement Project | PMO/ End-User | Mode of Procurement | Schedule for Each Procurement Activity | [11 empty] | Source of Funds | ABC (PhP) |  |  | Remarks (brief description of Program/Project) | PMO/ End-User | Is this an Early Procurement Activity? | Mode of Procurement | Actual Procurement Activity | [12 empty] | Source of Funds | ABC (PhP) |  |  | Contract Cost (PhP) |  |  | List of Invited Observers | Date of Receipt of Invitation | [5 empty] | Remarks (Explaining changes from the APP)
[5 empty] | Pre-Proc Conference | Ads/Post of IAEB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Contract Award | Contract Signing | Notice to Proceed | Delivery/ Accept | Payment Process |  | Total | MOOE | CO |  |  |  |  | Pre-Proc Conference | Ads/Post of IB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Date of BAC Resolution Recommending Award | Notice of Award | Contract Signing | Notice to Proceed | Delivery/ Completion | Inspection & Acceptance |  | Total | MOOE | CO | Total | MOOE | CO |  | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Delivery/ Completion/ Acceptance (If applicable)
COMPLETED PROCUREMENT ACTIVITIES
1 | 5-02-03-010-00 | Office Supplies Expenses | 9DPAO | Shopping 52.1 (b) | [17 empty] | 9DPAO | [10 empty] | 2023-01-24 | 2023-02-02 | 2023-02-02 | 2023-02-06 | 2023-02-06 | MOOE | 14865 | 14865 |  | 14864 | 14864
2 | 5-02-03-010-00 | Office Supplies Expenses | OGAD | Shopping 52.1 (b) | [17 empty] | OGAD | [10 empty] | 2023-01-27 | 2023-02-08 | 2023-02-08 | 2023-02-13 | 2023-02-13 | MOOE | 11000 | 11000 |  | 10950 | 10950
3 | 5-02-03-010-00 | Office Supplies Expenses | 1369DEN | Shopping 52.1 (b) | [17 empty] | 1369DEN | [10 empty] | 2023-01-26 | 2023-02-07 | 2023-02-07 | 2023-02-10 | 2023-02-10 | MOOE | 12000 | 12000 |  | 11994 | 11994
4 | 5-02-03-010-00 | Office Supplies Expenses | OG8 | Shopping 52.1 (b) | [17 empty] | OG8 | [10 empty] | 2022-01-27 | 2023-02-08 | 2023-02-08 | 2023-02-13 | 2023-02-13 | MOOE | 27000 | 27000 |  | 26956 | 26956
5 | 5-02-03-010-00 | Office Supplies Expenses | DOC | Shopping 52.1 (b) | [17 empty] | DOC | [10 empty] | 2023-01-30 | 2023-02-09 | 2023-02-09 | 2023-02-13 | 2023-02-13 | MOOE | 20500 | 20500 |  | 20450 | 20450
6 | 5-02-03-010-00 | Office Supplies Expenses | OG10 | Shopping 52.1 (b) | [17 empty] | OG10 | [10 empty] | 2023-01-27 | 2023-02-09 | 2023-02-09 | 2023-02-13 | 2023-02-13 | MOOE | 40000 | 40000 |  | 39054 | 39054
7 | 5-02-03-010-00 | Office Supplies Expenses | HHSC | Shopping 52.1 (b) | [17 empty] | HHSC | [10 empty] | 2023-01-27 | 2023-02-08 | 2023-02-08 | 2023-02-13 | 2023-02-13 | MOOE | 26000 | 26000 |  | 25968 | 25968
8 | 5-02-03-010-00 | Office Supplies Expenses | OG10 | Shopping 52.1 (b) | [17 empty] | OG10 | [10 empty] | 2023-01-30 | 2023-02-09 | 2023-02-09 | 2023-02-13 | 2023-02-13 | MOOE | 88320 | 88320 |  | 88281 | 88281
9 | 5-02-03-010-00 | Office Supplies Expenses | ODA | Shopping 52.1 (b) | [17 empty] | ODA | [10 empty] | 2023-02-02 | 2023-02-15 | 2023-02-15 | 2023-02-20 | 2023-02-20 | MOOE | 22000 | 22000 |  | 21920 | 21920
10 | 5-02-03-010-00 | Office Supplies Expenses | JAGO | Shopping 52.1 (b) | [17 empty] | JAGO | [10 empty] | 2023-02-02 | 2023-02-15 | 2023-02-15 | 2023-02-20 | 2023-02-20 | MOOE | 5000 | 5000 |  | 4999.25 | 4999.25
11 | 5-02-03-010-00 | Office Supplies Expenses | 902BDE | Shopping 52.1 (b) | [17 empty] | 902BDE | [10 empty] | 2023-02-06 | 2023-02-20 | 2023-02-20 | 2023-02-24 | 2023-02-24 | MOOE | 68500 | 68500 |  | 68454 | 68454
12 | 5-02-03-010-00 | Office Supplies Expenses | OG2 | Shopping 52.1 (b) | [17 empty] | OG2 | [10 empty] | 2023-02-02 | 2023-02-15 | 2023-02-15 | 2023-02-20 | 2023-02-20 | MOOE | 15850 | 15850 |  | 15815 | 15815
13 | 5-02-03-010-00 | Office Supplies Expenses | OG6 | Shopping 52.1 (b) | [17 empty] | OG6 | [10 empty] | 2023-02-06 | 2023-02-20 | 2023-02-20 | 2023-02-24 | 2023-02-24 | MOOE | 5000 | 5000 |  | 4990 | 4990
14 | 5-02-03-010-00 | Office Supplies Expenses | 91DRC | Shopping 52.1 (b) | [17 empty] | 91DRC | [10 empty] | 2023-02-09 | 2023-02-22 | 2023-02-22 | 2023-02-27 | 2023-02-27 | MOOE | 3000 | 3000 |  | 2988 | 2988
15 | 5-02-03-010-00 | Office Supplies Expenses | 9CMOBN | Shopping 52.1 (b) | [17 empty] | 9CMOBN | [10 empty] | 2023-02-10 | 2023-02-22 | 2023-02-22 | 2023-02-27 | 2023-02-27 | MOOE | 15000 | 15000 |  | 14997 | 14997
16 | 5-02-03-010-00 | Office Supplies Expenses | 49IB | Shopping 52.1 (b) | [17 empty] | 49IB | [10 empty] | 2023-02-09 | 2023-03-07 | 2023-03-02 | 2023-03-06 | 2023-03-06 | MOOE | 5340 | 5340 |  | 5325 | 5325
17 | 5-02-03-010-00 | Office Supplies Expenses | 92DRC | Shopping 52.1 (b) | [17 empty] | 92DRC | [10 empty] | 2023-02-09 | 2023-03-07 | 2023-02-20 | 2023-02-24 | 2023-02-24 | MOOE | 3500 | 3500 |  | 3486 | 3486
18 | 5-02-03-010-00 | Office Supplies Expenses | 903BDE | Shopping 52.1 (b) | [17 empty] | 903BDE | [10 empty] | 2023-02-10 | 2023-03-07 | 2023-03-07 | 2023-03-10 | 2023-03-10 | MOOE | 28000 | 28000 |  | 27990.75 | 27990.75
19 | 5-02-03-010-00 | Office Supplies Expenses | 83IB | Shopping 52.1 (b) | [17 empty] | 83IB | [10 empty] | 2023-02-17 | 2023-03-07 | 2023-03-07 | 2023-03-09 | 2023-03-09 | MOOE | 10000 | 10000 |  | 9990 | 9990
20 | 5-02-03-010-00 | Office Supplies Expenses | 93DRC | Shopping 52.1 (b) | [17 empty] | 93DRC | [10 empty] | 2023-02-17 | 2023-03-07 | 2023-03-07 | 2023-03-10 | 2023-03-10 | MOOE | 1500 | 1500 |  | 1495 | 1495
21 | 5-02-03-010-00 | Office Supplies Expenses | OG7 | Shopping 52.1 (b) | [17 empty] | OG7 | [10 empty] | 2023-02-27 | 2023-03-17 | 2023-03-17 | 2023-03-21 | 2023-03-21 | MOOE | 20780 | 20780 |  | 20740 | 20740
22 | 5-02-03-010-00 | Office Supplies Expenses | 91DGSMO | Shopping 52.1 (b) | [17 empty] | 91DGSMO | [10 empty] | 2023-02-09 | 2023-03-07 | 2023-03-07 | 2023-03-09 | 2023-03-09 | MOOE | 12220 | 12220 |  | 12205 | 12205
23 | 5-02-03-010-00 | Office Supplies Expenses | ODPM | Shopping 52.1 (b) | [17 empty] | ODPM | [10 empty] | 2023-02-17 | 2023-03-07 | 2023-03-07 | 2023-03-09 | 2023-03-09 | MOOE | 5000 | 5000 |  | 4992 | 4992
24 | 5-02-03-010-00 | Office Supplies Expenses | OESPA | Shopping 52.1 (b) | [17 empty] | OESPA | [10 empty] | 2023-02-20 | 2023-03-10 | 2023-03-10 | 2023-03-15 | 2023-03-15 | MOOE | 15000 | 15000 |  | 14975 | 14975
25 | 5-02-03-010-00 | Office Supplies Expenses | CEASH | Shopping 52.1 (b) | [17 empty] | CEASH | [10 empty] | 2023-02-13 | 2023-03-07 | 2023-03-07 | 2023-03-10 | 2023-03-10 | MOOE | 68000 | 68000 |  | 67954 | 67954
26 | 5-02-03-010-00 | Office Supplies Expenses | 9DTS | Shopping 52.1 (b) | [17 empty] | 9DTS | [10 empty] | 2023-02-20 | 2023-03-17 | 2023-03-17 | 2023-03-21 | 2023-03-21 | MOOE | 42645 | 42645 |  | 42595 | 42595
27 | 5-02-03-010-00 | Office Supplies Expenses | OG4 | Shopping 52.1 (b) | [17 empty] | OG4 | [10 empty] | 2023-02-27 | 2023-03-14 | 2023-03-14 | 2023-03-17 | 2023-03-17 | MOOE | 50000 | 50000 |  | 49743.5 | 49743.5
28 | 5-02-03-010-00 | Office Supplies Expenses | OG10 | Shopping 52.1 (b) | [17 empty] | OG10 | [10 empty] | 2023-02-27 | 2023-03-10 | 2023-03-10 | 2023-03-15 | 2023-03-15 | MOOE | 93320 | 93320 |  | 93226 | 93226
29 | 5-02-03-010-00 | Office Supplies Expenses | HHSC | Shopping 52.1 (b) | [17 empty] | HHSC | [10 empty] | 2023-02-27 | 2023-03-21 | 2023-03-21 | 2023-03-24 | 2023-03-24 | MOOE | 18000 | 18000 |  | 17978 | 17978
30 | 5-02-03-010-00 | Office Supplies Expenses | OG10 | Shopping 52.1 (b) | [17 empty] | OG10 | [10 empty] | 2023-03-13 | 2023-03-30 | 2023-03-30 | 2023-04-04 | 2023-04-04 | MOOE | 42500 | 42500 |  | 41825 | 41825
31 | 5-02-03-010-00 | Office Supplies Expenses | 49IB | Shopping 52.1 (b) | [17 empty] | 49IB | [10 empty] | 2023-03-16 | 2023-03-31 | 2023-03-31 | 2023-04-05 | 2023-04-05 | MOOE | 9340 | 9340 |  | 9325 | 9325
32 | 5-02-03-010-00 | Office Supplies Expenses | SSBN | Shopping 52.1 (b) | [17 empty] | SSBN | [10 empty] | 2023-03-20 | 2023-03-17 | 2023-03-17 | 2023-04-20 | 2023-04-20 | MOOE | 26000 | 26000 |  | 25961 | 25961
33 | 5-02-03-010-00 | Office Supplies Expenses | 92DRC | Shopping 52.1 (b) | [17 empty] | 92DRC | [10 empty] | 2023-03-20 | 2023-03-17 | 2023-03-17 | 2023-04-20 | 2023-04-20 | MOOE | 7250 | 7250 |  | 7230 | 7230
34 | 5-02-03-010-00 | Office Supplies Expenses | 91DRC | Shopping 52.1 (b) | [17 empty] | 91DRC | [10 empty] | 2023-03-20 | 2023-03-17 | 2023-03-17 | 2023-04-20 | 2023-04-20 | MOOE | 11500 | 11500 |  | 11483 | 11483
35 | 5-02-03-010-00 | Office Supplies Expenses | SSBN | Shopping 52.1 (b) | [17 empty] | SSBN | [10 empty] | 2023-03-27 | 2023-03-17 | 2023-03-17 | 2023-04-20 | 2023-04-20 | MOOE | 26000 | 26000 |  | 25967 | 25967
36 | 5-02-03-010-00 | Office Supplies Expenses | OGAD | Shopping 52.1 (b) | [17 empty] | OGAD | [10 empty] | 2023-03-27 | 2023-04-24 | 2023-04-24 | 2023-04-28 | 2023-04-28 | MOOE | 11000 | 11000 |  | 10950 | 10950
37 | 5-02-03-010-00 | Office Supplies Expenses | OG7 | Shopping 52.1 (b) | [17 empty] | OG7 | [10 empty] | 2023-03-27 | 2023-04-24 | 2023-04-24 | 2023-04-28 | 2023-04-28 | MOOE | 20780 | 20780 |  | 20740 | 20740
38 | 5-02-03-010-00 | Office Supplies Expenses | DOC | Shopping 52.1 (b) | [17 empty] | DOC | [10 empty] | 2023-04-03 | 2023-05-08 | 2023-05-08 | 2023-05-11 | 2023-05-11 | MOOE | 20500 | 20500 |  | 20480 | 20480
39 | 5-02-03-010-00 | Office Supplies Expenses | JAGO | Shopping 52.1 (b) | [17 empty] | JAGO | [10 empty] | 2023-04-11 | 2023-05-09 | 2023-05-09 | 2023-05-12 | 2023-05-12 | MOOE | 5000 | 5000 |  | 4978 | 4978
40 | 5-02-05-030-00 | Internet Subscription Expenses | OG10 | Negotiated 53.9 | [17 empty] | OG10 | [10 empty] | 2023-01-23 | 2023-02-02 | 2023-02-02 | 2023-02-06 | 2023-02-06 | MOOE | 27500 | 27500 |  | 27500 | 27500
41 | 5-02-05-020-01 | Mobile Expenses | OG10 | Negotiated 53.9 | [17 empty] | OG10 | [10 empty] | 2023-01-23 | 2023-02-02 | 2023-02-02 | 2023-02-06 | 2023-02-06 | MOOE | 111800 | 111800 |  | 111800 | 111800
42 | 5-02-13-040-01 | R & M Building Expenses | OG10 | Negotiated 53.9 | [17 empty] | OG10 | [10 empty] | 2023-01-23 | 2023-02-02 | 2023-02-02 | 2023-02-06 | 2023-02-06 | MOOE | 200000 | 200000 |  | 199910 | 199910
43 | 5-02-13-040-01 | R & M Building Expenses | OG10 | Negotiated 53.9 | [17 empty] | OG10 | [10 empty] | 2023-01-23 | 2023-02-02 | 2023-02-02 | 2023-02-06 | 2023-02-06 | MOOE | 300000 | 300000 |  | 299905 | 299905
44 | 5-02-13-040-01 | R & M Building Expenses | OG10 | Negotiated 53.9 | [17 empty] | OG10 | [10 empty] | 2023-01-23 | 2023-02-02 | 2023-02-02 | 2023-02-06 | 2023-02-06 | MOOE | 30000 | 30000 |  | 29970 | 29970
45 | 5-02-13-040-01 | R & M Building Expenses | OG10 | Negotiated 53.9 | [17 empty] | OG10 | [10 empty] | 2023-01-23 | 2023-02-02 | 2023-02-02 | 2023-02-06 | 2023-02-06 | MOOE | 130000 | 130000 |  | 129908 | 129908
46 | 5-02-13-040-01 | R & M Building Expenses | OG10 | Negotiated 53.9 | [17 empty] | OG10 | [10 empty] | 2023-01-23 | 2023-02-02 | 2023-02-02 | 2023-02-06 | 2023-02-06 | MOOE | 95030 | 95030 |  | 94940 | 94940
47 | 5-02-03-080-00 | Medical, Dental & Lab Expenses | 96IB | Negotiated 53.9 | [17 empty] | 96IB | [10 empty] | 2023-01-24 | 2023-02-02 | 2023-02-02 | 2023-02-06 | 2023-02-06 | MOOE | 15000 | 15000 |  | 14984 | 14984
48 | 5-02-03-990-00 | Other Supply & Materials Expenses | 96IB | Negotiated 53.9 | [17 empty] | 96IB | [10 empty] | 2023-01-24 | 2023-02-02 | 2023-02-02 | 2023-02-13 | 2023-02-13 | MOOE | 27000 | 27000 |  | 26973 | 26973
49 | 5-02-05-020-01 | Mobile Expenses | HHSC | Negotiated 53.9 | [17 empty] | HHSC | [10 empty] | 2023-01-24 | 2023-02-02 | 2023-02-02 | 2023-02-06 | 2023-02-06 | MOOE | 14500 | 14500 |  | 14500 | 14500
50 | 5-02-03-990-00 | Other Supply & Materials Expenses | HHSC | Negotiated 53.9 | [17 empty] | HHSC | [10 empty] | 2023-01-24 | 2023-02-02 | 2023-02-02 | 2023-02-06 | 2023-02-06 | MOOE | 18000 | 18000 |  | 17940 | 17940
51 | 5-02-05-030-00 | Internet Subscription Expenses | 83IB | Negotiated 53.9 | [17 empty] | 83IB | [10 empty] | 2023-01-24 | 2023-02-02 | 2023-02-02 | 2023-02-06 | 2023-02-06 | MOOE | 13500 | 13500 |  | 13500 | 13500
52 | 5-02-05-040-00 | Cable, Sat, Tel, Radio & Expenses | 83IB | Negotiated 53.9 | [17 empty] | 83IB | [10 empty] | 2023-01-24 | 2023-02-02 | 2023-02-02 | 2023-02-06 | 2023-02-06 | MOOE | 6000 | 6000 |  | 6000 | 6000
53 | 5-02-03-990-00 | Other Supply & Materials Expenses | 83IB | Negotiated 53.9 | [17 empty] | 83IB | [10 empty] | 2023-01-24 | 2023-02-07 | 2023-02-07 | 2023-02-10 | 2023-02-10 | MOOE | 23375 | 23375 |  | 23343 | 23343
54 | 5-02-13-040-99 | R & M Other Structure Expense | 83IB | Negotiated 53.9 | [17 empty] | 83IB | [10 empty] | 2023-01-24 | 2023-02-02 | 2023-02-02 | 2023-02-06 | 2023-02-06 | MOOE | 34200 | 34200 |  | 34168 | 34168
55 | 5-02-05-020-01 | Mobile Expenses | ODSM | Negotiated 53.9 | [17 empty] | ODSM | [10 empty] | 2023-01-24 | 2023-02-02 | 2023-02-02 | 2023-02-06 | 2023-02-06 | MOOE | 4100 | 4100 |  | 4100 | 4100
56 | 5-02-99-030-00 | Representation Expenses | 83IB | Negotiated 53.9 | [17 empty] | 83IB | [10 empty] | 2023-01-27 | 2023-02-09 | 2023-02-09 | 2023-02-13 | 2023-02-13 | MOOE | 33500 | 33500 |  | 33460 | 33460
57 | 5-02-03-080-00 | Cable, Sat, Tel, Radio & Expenses | HHSC | Negotiated 53.9 | [17 empty] | HHSC | [10 empty] | 2023-01-27 | 2023-02-08 | 2023-02-08 | 2023-02-13 | 2023-02-13 | MOOE | 13000 | 13000 |  | 12968 | 12968
58 | 5-02-03-070-00 | Drugs & Medecines Expenses | 96IB | Negotiated 53.9 | [17 empty] | 96IB | [10 empty] | 2023-01-24 | 2023-02-02 | 2023-02-02 | 2023-02-06 | 2023-02-06 | MOOE | 7500 | 7500 |  | 7490 | 7490
59 | 5-02-02-010-00 | Training Expenses (w/o ICT) | 1369DEN | Negotiated 53.9 | [17 empty] | 1369DEN | [10 empty] | 2023-01-26 | 2023-02-07 | 2023-02-07 | 2023-02-10 | 2023-02-10 | MOOE | 5000 | 5000 |  | 4990 | 4990
60 | 5-02-13-060-01 | R & M Motor Vehicle Expenses | 1369DEN | Negotiated 53.9 | [17 empty] | 1369DEN | [10 empty] | 2023-01-26 | 2023-02-07 | 2023-02-07 | 2023-02-10 | 2023-02-10 | MOOE | 18000 | 18000 |  | 17980 | 17980
61 | 5-02-03-210-03 | Semi-Expendable ICT Equipment Expenses | 1369DEN | Negotiated 53.9 | [17 empty] | 1369DEN | [10 empty] | 2022-01-26 | 2023-02-07 | 2023-02-07 | 2023-02-10 | 2023-02-10 | MOOE | 35000 | 35000 |  | 34950 | 34950
62 | 5-02-05-020-01 | Mobile Expenses | OG8 | Negotiated 53.9 | [17 empty] | OG8 | [10 empty] | 2023-01-27 | 2023-02-09 | 2023-02-09 | 2023-02-13 | 2023-02-13 | MOOE | 4500 | 4500 |  | 4500 | 4500
63 | 5-02-05-020-01 | Mobile Expenses | DOC | Negotiated 53.9 | [17 empty] | DOC | [10 empty] | 2023-01-30 | 2023-02-08 | 2023-02-08 | 2023-02-13 | 2023-02-13 | MOOE | 10500 | 10500 |  | 10500 | 10500
64 | 5-02-05-040-00 | Cable Subscription Expenses | DOC | Negotiated 53.9 | [17 empty] | DOC | [10 empty] | 2023-01-27 | 08 Feb 23 | 08 Feb 23 | 2023-02-13 | 2023-02-13 | MOOE | 11500 | 11500 |  | 11500 | 11500
65 | 5-02-03-210-03 | Semi-Expendable ICT Equipment Expenses | HHSC | Negotiated 53.9 | [17 empty] | HHSC | [10 empty] | 2023-01-27 | 09 Feb 23 | 09 Feb 23 | 2023-02-13 | 2023-02-13 | MOOE | 25000 | 25000 |  | 24900 | 24900
66 | 5-02-05-020-01 | Mobile Expenses | 9DPAO | Negotiated 53.9 | [17 empty] | 9DPAO | [10 empty] | 2023-01-24 | 07 Feb 23 | 07 Feb 23 | 2023-02-10 | 2023-02-10 | MOOE | 24000 | 24000 |  | 24000 | 24000
67 | 5-02-03-210-10 | Semi-Expendable Med/Dental Equipment | 1369DEN | Negotiated 53.9 | [17 empty] | 1369DEN | [10 empty] | 2023-01-30 | 2023-02-09 | 2023-02-09 | 2023-02-13 | 2023-02-13 | MOOE | 89250 | 89250 |  | 89200 | 89200
68 | 5-02-05-020-01 | Mobile Expenses | ODA | Negotiated 53.9 | [17 empty] | ODA | [10 empty] | 2023-02-02 | 15 Feb 23 | 15 Feb 23 | 2023-02-20 | 2023-02-20 | MOOE | 2000 | 2000 |  | 2000 | 2000
69 | 5-02-05-020-01 | Mobile Expenses | OG3 | Negotiated 53.9 | [17 empty] | OG3 | [10 empty] | 2023-02-02 | 15 Feb 23 | 15 Feb 23 | 2023-02-20 | 2023-02-20 | MOOE | 12500 | 12500 |  | 12500 | 12500
70 | 5-02-03-130-00 | Chemical & Filtering Supplies Expense | 9DCAU | Negotiated 53.9 | [17 empty] | 9DCAU | [10 empty] | 2023-02-06 | 15 Feb 23 | 15 Feb 23 | 2023-02-20 | 2023-02-20 | MOOE | 5600 | 5600 |  | 5560 | 5560
71 | 5-02-03-080-00 | Cable, Sat, Tel, Radio & Expenses | 9DCAU | Negotiated 53.9 | [17 empty] | 9DCAU | [10 empty] | 2023-02-06 | 15 Feb 23 | 15 Feb 23 | 2023-02-20 | 2023-02-20 | MOOE | 6000 | 6000 |  | 6000 | 6000
72 | 5-02-02-010-00 | Training Expenses | 902BDE | Negotiated 53.9 | [17 empty] | 902BDE | [10 empty] | 2023-02-06 | 16 Feb 23 | 16 Feb 23 | 2023-02-21 | 2023-02-21 | MOOE | 43000 | 43000 |  | 42934 | 42934
73 | 5-02-03-080-00 | Medical Dental & Laboratory Supplies Expenses | 49IB | Negotiated 53.9 | [17 empty] | 49IB | [10 empty] | 2023-02-06 | 16 Feb 23 | 16 Feb 23 | 2023-02-21 | 2023-02-21 | MOOE | 3910 | 3910 |  | 3900 | 3900
74 | 5-02-03-990-00 | Other Supplies & Materials Expenses | 49IB | Negotiated 53.9 | [17 empty] | 49IB | [10 empty] | 2023-02-06 | 16 Feb 23 | 16 Feb 23 | 2023-02-21 | 2023-02-21 | MOOE | 25000 | 25000 |  | 24950 | 24950
75 | 5-02-03-070-00 | Drugs & Medicines Expenses | 49IB | Negotiated 53.9 | [17 empty] | 49IB | [10 empty] | 2023-02-06 | 2023-02-16 | 2023-02-16 | 2023-02-21 | 2023-02-21 | MOOE | 2090 | 2090 |  | 2080 | 2080
76 | 5-02-03-210-03 | Semi-Expendable ICT Equipment Expenses | 49IB | Negotiated 53.9 | [17 empty] | 49IB | [10 empty] | 2023-02-06 | 2023-02-16 | 2023-02-16 | 2023-02-21 | 2023-02-21 | MOOE | 61000 | 61000 |  | 60900 | 60900
77 | 5-02-03-210-07 | Semi-Expendable Communication Equipment Expenses | 83IB | Negotiated 53.9 | [17 empty] | 83IB | [10 empty] | 2023-02-06 | 2023-02-15 | 2023-02-15 | 2023-02-20 | 2023-02-20 | MOOE | 55000 | 55000 |  | 54950 | 54950
78 | 5-02-02-010-00 | Training Expenses | ODPM | Negotiated 53.9 | [17 empty] | ODPM | [10 empty] | 2023-02-02 | 15 Feb 23 | 15 Feb 23 | 2023-02-20 | 2023-02-20 | MOOE | 3000 | 3000 |  | 2990 | 2990
79 | 5-02-13-050-03 | R & M Semi-Expendable ICT Equipment Expenses | OG10 | Negotiated 53.9 | [17 empty] | OG10 | [10 empty] | 2023-02-02 | 15 Feb 23 | 15 Feb 23 | 2023-02-20 | 2023-02-20 | MOOE | 4320 | 4320 |  | 4300 | 4300
80 | 5-02-03-210-03 | Semi-Expendable ICT Equipment Expenses | 91DGSMO | Negotiated 53.9 | [17 empty] | 91DGSMO | [10 empty] | 2023-02-02 | 2023-02-15 | 2023-02-15 | 2023-02-20 | 2023-02-20 | MOOE | 28000 | 28000 |  | 27900 | 27900
81 | 5-02-05-020-01 | Mobile Expenses | OG7 | Negotiated 53.9 | [17 empty] | OG7 | [10 empty] | 2023-02-02 | 22 Feb 23 | 22 Feb 23 | 2023-02-27 | 2023-02-27 | MOOE | 28500 | 28500 |  | 28500 | 28500
1 | 5-02-99-030-00 | Representation Expenses | 31IB | Negotiated 53.9 | [17 empty] | 31IB | [10 empty] | 2023-02-06 | 22 Feb 23 | 22 Feb 23 | 2023-02-27 | 2023-02-27 | MOOE | 31499 | 31499 |  | 31434 | 31434
2 | 5-02-03-070-00 | Drugs & Medicines Expenses | 9DCAU | Negotiated 53.9 | [17 empty] | 9DCAU | [10 empty] | 2023-02-06 | 2023-02-20 | 2023-02-20 | 2023-02-24 | 2023-02-24 | MOOE | 35000 | 35000 |  | 34960 | 34960
3 | 5-02-03-080-00 | Medical, Dental & Lab Expenses | 91DRC | Negotiated 53.9 | [17 empty] | 91DRC | [10 empty] | 2023-02-09 | 22 Feb 23 | 22 Feb 23 | 2023-02-27 | 2023-02-27 | MOOE | 7500 | 7500 |  | 7450 | 7450
4 | 5-02-03-990-00 | Other Supplies & Materials Expenses | 93DRC | Negotiated 53.9 | [17 empty] | 93DRC | [10 empty] | 2023-02-10 | 22 Feb 23 | 22 Feb 23 | 2023-02-27 | 2023-02-27 | MOOE | 5000 | 5000 |  | 4988 | 4988
5 | 5-02-03-130-00 | Chemical & Filtering Supplies Expense | MFO | Negotiated 53.9 | [17 empty] | MFO | [10 empty] | 2023-02-13 | 22 Feb 23 | 22 Feb 23 | 2023-02-27 | 2023-02-27 | MOOE | 60000 | 60000 |  | 59900 | 59900
6 | 5-02-99-030-00 | Representation Expenses | 96IB | Negotiated 53.9 | [17 empty] | 96IB | [10 empty] | 2023-01-24 | 07 Feb 23 | 07 Feb 23 | 2023-02-10 | 2023-02-10 | MOOE | 50000 | 50000 |  | 49940 | 49940
7 | 5-02-05-020-01 | Mobile Expenses | JAGO | Negotiated 53.9 | [17 empty] | JAGO | [10 empty] | 2023-02-02 | 15 Feb 23 | 15 Feb 23 | 2023-02-20 | 2023-02-20 | MOOE | 9000 | 9000 |  | 9000 | 9000
8 | 5-02-05-030-00 | Internet Subscription Expenses | OG6 | Negotiated 53.9 | [17 empty] | OG6 | [10 empty] | 2023-02-06 | 2023-02-20 | 2023-02-20 | 2023-02-24 | 2023-02-24 | MOOE | 12000 | 12000 |  | 12000 | 12000
9 | 5-02-13-050-01 | R & M Machinery Expenses | 31IB | Negotiated 53.9 | [17 empty] | 31IB | [10 empty] | 2023-02-06 | 22 Feb 23 | 22 Feb 23 | 2023-02-27 | 2023-02-27 | MOOE | 2950 | 2950 |  | 2940 | 2940
10 | 5-02-03-210-03 | Semi-Expendable ICT Equipment Expenses | OG7 | Negotiated 53.9 | [17 empty] | OG7 | [10 empty] | 2023-02-06 | 20 Feb 23 | 20 Feb 23 | 2023-02-24 | 2023-02-24 | MOOE | 20000 | 20000 |  | 19950 | 19950
11 | 5-02-13-020-99 | Other Land Improvements Expenses | 903BDE | Negotiated 53.9 | [17 empty] | 903BDE | [10 empty] | 2023-02-06 | 15 Feb 23 | 15 Feb 23 | 2023-02-20 | 2023-02-20 | MOOE | 28000 | 28000 |  | 27945 | 27945
12 | 5-02-13-050-03 | R & M Semi-Expendable ICT Equipment Expenses | 49IB | Negotiated 53.9 | [17 empty] | 49IB | [10 empty] | 2023-02-06 | 20 Feb 23 | 20 Feb 23 | 2023-02-24 | 2023-02-24 | MOOE | 10000 | 10000 |  | 9950 | 9950
13 | 5-02-03-210-99 | Semi-Expendable-Other Machinery and Equipment Expenses | CEASH | Negotiated 53.9 | [17 empty] | CEASH | [10 empty] | 2023-02-09 | 22 Feb 23 | 22 Feb 23 | 2023-02-27 | 2023-02-27 | MOOE | 20000 | 20000 |  | 19950 | 19950
14 | 5-02-13-050-11 | R & M Medical Equipment Expenses | CEASH | Negotiated 53.9 | [17 empty] | CEASH | [10 empty] | 2023-02-09 | 20 Feb 23 | 20 Feb 23 | 2023-02-24 | 2023-02-24 | MOOE | 25000 | 25000 |  | 24950 | 24950
15 | 5-02-13-210-03 | R & M Semi-Expendable ICT Equipment Expenses | CEASH | Negotiated 53.9 | [17 empty] | CEASH | [10 empty] | 2023-02-09 | 20 Feb 23 | 20 Feb 23 | 2023-02-24 | 2023-02-24 | MOOE | 7000 | 7000 |  | 6950 | 6950
16 | 5-02-05-020-01 | Mobile Expenses | ODPM | Negotiated 53.9 | [17 empty] | ODPM | [10 empty] | 2023-02-02 | 2023-02-15 | 2023-02-15 | 2023-02-20 | 2023-02-20 | MOOE | 2000 | 2000 |  | 2000 | 2000
17 | 5-02-05-030-00 | Internet Subscription Expenses | OG3 | Negotiated 53.9 | [17 empty] | OG3 | [10 empty] | 2023-02-02 | 15 Feb 23 | 15 Feb 23 | 2023-02-20 | 2023-02-20 | MOOE | 3000 | 3000 |  | 3000 | 3000
18 | 5-02-03-080-00 | Cable, Sat, Tel, Radio & Expenses | OG3 | Negotiated 53.9 | [17 empty] | OG3 | [10 empty] | 2023-02-06 | 2023-02-22 | 2023-02-22 | 2023-02-27 | 2023-02-27 | MOOE | 3000 | 3000 |  | 3000 | 3000
19 | 5-02-13-060-01 | R & M Motor Vehicle Expenses | 9DCAU | Negotiated 53.9 | [17 empty] | 9DCAU | [10 empty] | 2023-02-06 | 15 Feb 23 | 15 Feb 23 | 2023-02-20 | 2023-02-20 | MOOE | 10000 | 10000 |  | 9988 | 9988
20 | 5-02-02-010-00 | Training Expenses | 49IB | Negotiated 53.9 | [17 empty] | 49IB | [10 empty] | 2023-02-06 | 20 Feb 23 | 20 Feb 23 | 2023-02-24 | 2023-02-24 | MOOE | 40000 | 40000 |  | 39950 | 39950
21 | 5-05-02-010-02 | Training Expenses | 91DRC | Negotiated 53.9 | [17 empty] | 91DRC | [10 empty] | 2023-02-09 | 2023-02-22 | 2023-02-22 | 2023-02-27 | 2023-02-27 | MOOE | 4000 | 4000 |  | 3990 | 3990
22 | 5-02-03-990-00 | Other Supplies & Materials Expenses | 91DRC | Negotiated 53.9 | [17 empty] | 91DRC | [10 empty] | 2023-02-09 | 2 Mar 23 | 2 Mar 23 | 2023-03-06 | 2023-03-06 | MOOE | 1500 | 1500 |  | 1491 | 1491
23 | 5-02-02-010-02 | Training Expenses | 93DRC | Negotiated 53.9 | [17 empty] | 93DRC | [10 empty] | 2023-02-10 | 2023-03-02 | 2023-03-02 | 2023-03-06 | 2023-03-06 | MOOE | 2000 | 2000 |  | 1992 | 1992
24 | 5-02-02-010-00 | Training Supply Expenses | 96IB | Negotiated 53.9 | [17 empty] | 96IB | [10 empty] | 2023-01-24 | 07 Feb 23 | 07 Feb 23 | 2023-02-10 | 2023-02-10 | MOOE | 19000 | 19000 |  | 18980 | 18980
25 | 5-02-13-040-01 | R & M of Building | OGAD | Negotiated 53.9 | [17 empty] | OGAD | [10 empty] | 2023-01-30 | 09 Feb 23 | 09 Feb 23 | 2023-02-13 | 2023-02-13 | MOOE | 130100 | 130100 |  | 130000 | 130000
26 | 5-02-05-020-01 | Mobile Expenses | OG2 | Negotiated 53.9 | [17 empty] | OG2 | [10 empty] | 2023-02-02 | 15 Feb 23 | 15 Feb 23 | 2023-02-20 | 2023-02-20 | MOOE | 2000 | 2000 |  | 2000 | 2000
27 | 5-02-02-010-00 | Training Expenses | OG2 | Negotiated 53.9 | [17 empty] | OG2 | [10 empty] | 2023-02-02 | 15 Feb 23 | 15 Feb 23 | 2023-02-20 | 2023-02-20 | MOOE | 15000 | 15000 |  | 14945 | 14945
28 | 5-02-03-210-03 | Semi-Expendable ICT Equipment Expenses | JAGO | Negotiated 53.9 | [17 empty] | JAGO | [10 empty] | 2023-02-02 | 2023-02-15 | 2023-02-15 | 2023-02-20 | 2023-02-20 | MOOE | 4800 | 4800 |  | 4780 | 4780
29 | 5-02-05-040-00 | Cable Subscription Expenses | OG7 | Negotiated 53.9 | [17 empty] | OG7 | [10 empty] | 2023-02-02 | 22 Feb 23 | 22 Feb 23 | 2023-02-27 | 2023-02-27 | MOOE | 1500 | 1500 |  | 1500 | 1500
30 | 5-02-02-010-00 | Training Expenses | 91DGSMO | Negotiated 53.9 | [17 empty] | 91DGSMO | [10 empty] | 2023-02-06 | 2 Mar 23 | 2 Mar 23 | 2023-03-06 | 2023-03-06 | MOOE | 5100 | 5100 |  | 5080 | 5080
31 | 5-02-05-030-00 | Internet Subscription Expenses | OG7 | Negotiated 53.9 | [17 empty] | OG7 | [10 empty] | 2023-02-06 | 20 Feb 23 | 20 Feb 23 | 2023-02-24 | 2023-02-24 | MOOE | 6000 | 6000 |  | 6000 | 6000
32 | 5-02-13-060-01 | R & M Motor Vehicle Expenses | 9DCAU | Negotiated 53.9 | [17 empty] | 9DCAU | [10 empty] | 2023-02-06 | 22 Feb 23 | 22 Feb 23 | 2023-02-27 | 2023-02-27 | MOOE | 21280 | 21280 |  | 21240 | 21240
33 | 5-02-13-060-01 | R & M Motor Vehicle Expenses | 9DCAU | Negotiated 53.9 | [17 empty] | 9DCAU | [10 empty] | 2023-02-06 | 2 Mar 23 | 2 Mar 23 | 2023-03-06 | 2023-03-06 | MOOE | 50000 | 50000 |  | 49950 | 49950
34 | 5-02-03-210-03 | Semi-Expendable ICT Equipment Expenses | 902BDE | Negotiated 53.9 | [17 empty] | 902BDE | [10 empty] | 2023-02-06 | 20 Feb 23 | 20 Feb 23 | 2023-02-24 | 2023-02-24 | MOOE | 30000 | 30000 |  | 29950 | 29950
35 | 5-02-03-210-09 | Semi-Expendable Mil, Police & Equipment Expenses | 902BDE | Negotiated 53.9 | [17 empty] | 902BDE | [10 empty] | 2023-02-06 | 20 Feb 23 | 20 Feb 23 | 2023-02-24 | 2023-02-24 | MOOE | 37500 | 37500 |  | 37400 | 37400
36 | 5-02-03-210-03 | Semi-Expendable ICT Equipment Expenses | 9DCAU | Negotiated 53.9 | [17 empty] | 9DCAU | [10 empty] | 2023-02-06 | 20 Feb 23 | 20 Feb 23 | 2023-02-24 | 2023-02-24 | MOOE | 66000 | 66000 |  | 65900 | 65900
37 | 5-02-02-010-02 | Training Expenses | OG2 | Negotiated 53.9 | [17 empty] | OG2 | [10 empty] | 2023-02-09 | 20 Feb 23 | 20 Feb 23 | 2023-02-24 | 2023-02-24 | MOOE | 20000 | 20000 |  | 19968 | 19968
38 | 5-02-03-210-99 | Semi-Expendable Other Machinery & Equipment Expenses | 2IB | Negotiated 53.9 | [17 empty] | 2IB | [10 empty] | 2023-02-09 | 2023-03-07 | 2023-03-07 | 2023-03-09 | 2023-03-09 | MOOE | 20000 | 20000 |  | 19950 | 19950
39 | 5-02-13-040-03 | R & M Hospital & Health Centers Expenses | CEASH | Negotiated 53.9 | [17 empty] | CEASH | [10 empty] | 2023-02-09 | 2 Mar 23 | 2 Mar 23 | 2023-03-06 | 2023-03-06 | MOOE | 38000 | 38000 |  | 37968 | 37968
40 | 5-02-02-010-02 | Training Expenses | CEASH | Negotiated 53.9 | [17 empty] | CEASH | [10 empty] | 2023-02-09 | 2 Mar 23 | 2 Mar 23 | 2023-03-06 | 2023-03-06 | MOOE | 26000 | 26000 |  | 25971 | 25971
41 | 5-02-05-020-01 | Mobile Expenses | 93DRC | Negotiated 53.9 | [17 empty] | 93DRC | [10 empty] | 2023-02-09 | 22 Feb 23 | 22 Feb 23 | 2023-02-27 | 2023-02-27 | MOOE | 13000 | 13000 |  | 13000 | 13000
42 | 5-02-99-030-00 | Representation Expenses | 9CMOBN | Negotiated 53.9 | [17 empty] | 9CMOBN | [10 empty] | 2023-02-10 | 2023-03-07 | 2023-03-07 | 2023-03-10 | 2023-03-10 | MOOE | 27750 | 27750 |  | 27735 | 27735
43 | 5-02-03-210-03 | Semi-Expendable ICT Equipment Expenses | OG6 | Negotiated 53.9 | [17 empty] | OG6 | [10 empty] | 2023-02-10 | 22 Feb 23 | 22 Feb 23 | 2023-02-27 | 2023-02-27 | MOOE | 41000 | 41000 |  | 40900 | 40900
44 | 5-02-02-010-02 | Training Expenses | 9CMOBN | Negotiated 53.9 | [17 empty] | 9CMOBN | [10 empty] | 2023-02-13 | 2023-03-14 | 2023-03-14 | 2023-03-17 | 2023-03-17 | MOOE | 60000 | 60000 |  | 59928 | 59928
45 | 5-02-03-080-00 | Medical Dental & Laboratory Supplies Expenses | CEASH | Negotiated 53.9 | [17 empty] | CEASH | [10 empty] | 2023-02-14 | 07 Mar 23 | 07 Mar 23 | 2023-03-09 | 2023-03-09 | MOOE | 168897 | 168897 |  | 168810 | 168810
46 | 5-02-05-020-01 | Mobile Expenses | OG4 | Negotiated 53.9 | [17 empty] | OG4 | [10 empty] | 2023-02-17 | 07 Mar 23 | 07 Mar 23 | 2023-03-10 | 2023-03-10 | MOOE | 600 | 600 |  | 600 | 600
47 | 5-02-99-030-00 | Representation Expenses | 93DRC | Negotiated 53.9 | [17 empty] | 93DRC | [10 empty] | 2023-02-17 | 2023-03-07 | 2023-03-07 | 2023-03-10 | 2023-03-10 | MOOE | 2500 | 2500 |  | 2494 | 2494
48 | 5-02-03-210-03 | Semi-Expendable ICT Equipment Expenses | CEASH | Negotiated 53.9 | [17 empty] | CEASH | [10 empty] | 2023-02-20 | 07 Mar 23 | 07 Mar 23 | 2023-03-10 | 2023-03-10 | MOOE | 72250 | 72250 |  | 72150 | 72150
49 | 5-02-05-020-01 | Mobile Expenses | 22IB | Negotiated 53.9 | [17 empty] | 22IB | [10 empty] | 2023-02-20 | 07 Mar 23 | 07 Mar 23 | 2023-03-10 | 2023-03-10 | MOOE | 12000 | 12000 |  | 12000 | 12000
50 | 5-02-03-080-00 | Cable Expenses | 22IB | Negotiated 53.9 | [17 empty] | 22IB | [10 empty] | 2023-02-20 | 07 Mar 23 | 07 Mar 23 | 2023-03-10 | 2023-03-10 | MOOE | 6000 | 6000 |  | 6000 | 6000
51 | 5-02-03-210-03 | Semi-Expendable ICT Equipment Expenses | 22IB | Negotiated 53.9 | [17 empty] | 22IB | [10 empty] | 2023-02-20 | 07 Mar 23 | 07 Mar 23 | 2023-03-10 | 2023-03-10 | MOOE | 5500 | 5500 |  | 5480 | 5480
52 | 5-02-03-210-08 | Semi-Expendable DRRE EXPENSES | 22IB | Negotiated 53.9 | [17 empty] | 22IB | [10 empty] | 2023-02-20 | 07 Mar 23 | 07 Mar 23 | 2023-03-10 | 2023-03-10 | MOOE | 5000 | 5000 |  | 4980 | 4980
53 | 5-02-03-210-07 | Semi-Expendable Communication Equipment Expenses | 22IB | Negotiated 53.9 | [17 empty] | 22IB | [10 empty] | 2023-02-20 | 07 Mar 23 | 07 Mar 23 | 2023-03-10 | 2023-03-10 | MOOE | 6000 | 6000 |  | 5970 | 5970
54 | 5-02-02-010-00 | Training Expenses | 9DCAU | Negotiated 53.9 | [17 empty] | 9DCAU | [10 empty] | 2023-02-06 | 2023-03-08 | 2023-03-08 | 2023-03-14 | 2023-03-14 | MOOE | 21000 | 21000 |  | 20956 | 20956
55 | 5-02-13-020-99 | Other Land Improvements Expenses | 2IB | Negotiated 53.9 | [17 empty] | 2IB | [10 empty] | 2023-02-09 | 22 Feb 23 | 22 Feb 23 | 2023-02-27 | 2023-02-27 | MOOE | 30000 | 30000 |  | 29935 | 29935
56 | 5-02-13-050-11 | R & M Medical Equipment Expenses | CEASH | Negotiated 53.9 | [17 empty] | CEASH | [10 empty] | 2023-02-09 | 2 Mar 23 | 2 Mar 23 | 2023-03-06 | 2023-03-06 | MOOE | 15000 | 15000 |  | 14950 | 14950
57 | 5-02-03-210-03 | Semi-Expendable ICT Equipment Expenses | OG6 | Negotiated 53.9 | [17 empty] | OG6 | [10 empty] | 2023-02-13 | 07 Mar 23 | 07 Mar 23 | 2023-03-09 | 2023-03-09 | MOOE | 56000 | 56000 |  | 55900 | 55900
58 | 5-02-13-050-03 | R & M ICT Equipment Expenses | 902BDE | Negotiated 53.9 | [17 empty] | 902BDE | [10 empty] | 2023-02-20 | 07 Mar 23 | 07 Mar 23 | 2023-03-09 | 2023-03-09 | MOOE | 21500 | 21500 |  | 21450 | 21450
59 | 5-02-02-010-02 | Training Expenses | 22IB | Negotiated 53.9 | [17 empty] | 22IB | [10 empty] | 2023-02-20 | 07 Mar 23 | 07 Mar 23 | 2023-03-09 | 2023-03-09 | MOOE | 40000 | 40000 |  | 39968 | 39968
60 | 5-02-02-010-02 | Training Expenses | OESPA | Negotiated 53.9 | [17 empty] | OESPA | [10 empty] | 2023-02-13 | 07 Mar 23 | 07 Mar 23 | 2023-03-09 | 2023-03-09 | MOOE | 10000 | 10000 |  | 9964 | 9964
61 | 5-02-05-030-00 | Internet Subscription Expenses | ODPM | Negotiated 53.9 | [17 empty] | ODPM | [10 empty] | 2023-02-13 | 07 Mar 23 | 07 Mar 23 | 2023-03-09 | 2023-03-09 | MOOE | 2500 | 2500 |  | 2500 | 2500
62 | 5-02-03-210-03 | Semi-Expendable ICT Equipment Expenses | OG6 | Negotiated 53.9 | [17 empty] | OG6 | [10 empty] | 2023-02-13 | 07 Mar 23 | 07 Mar 23 | 2023-03-09 | 2023-03-09 | MOOE | 58000 | 58000 |  | 57900 | 57900
63 | 5-02-03-210-03 | Semi-Expendable ICT Equipment Expenses | OG6 | Negotiated 53.9 | [17 empty] | OG6 | [10 empty] | 2023-02-13 | 10 Mar 23 | 10 Mar 23 | 2023-03-15 | 2023-03-15 | MOOE | 163800 | 163800 |  | 163690 | 163690
64 | 5-02-03-080-00 | Cable, Sat, Tel, Radio & Expenses | OG8 | Negotiated 53.9 | [17 empty] | OG8 | [10 empty] | 2023-02-16 | 07 Mar 23 | 07 Mar 23 | 2023-03-10 | 2023-03-10 | MOOE | 1500 | 1500 |  | 1500 | 1500
65 | 5-02-05-030-00 | Internet Subscription Expenses | OG8 | Negotiated 53.9 | [17 empty] | OG8 | [10 empty] | 2023-02-16 | 07 Mar 23 | 07 Mar 23 | 2023-03-10 | 2023-03-10 | MOOE | 6000 | 6000 |  | 6000 | 6000
66 | 5-02-13-210-07 | R & M Communication Equipment Expenses | 902BDE | Negotiated 53.9 | [17 empty] | 902BDE | [10 empty] | 2023-02-20 | 07 Mar 23 | 07 Mar 23 | 2023-03-09 | 2023-03-09 | MOOE | 15000 | 15000 |  | 14980 | 14980
67 | 5-02-03-210-03 | Semi-Expendable ICT Equipment Expenses | 9DPAO | Negotiated 53.9 | [17 empty] | 9DPAO | [10 empty] | 2023-02-23 | 10 Mar 23 | 10 Mar 23 | 2023-03-15 | 2023-03-15 | MOOE | 40220 | 40220 |  | 40170 | 40170
68 | 5-02-03-210-03 | Semi-Expendable ICT Equipment Expenses | 96IB | Negotiated 53.9 | [17 empty] | 96IB | [10 empty] | 2023-01-30 | 08 Feb 23 | 08 Feb 23 | 2023-02-13 | 2023-02-13 | MOOE | 118000 | 118000 |  | 117920 | 117920
69 | 5-02-05-030-00 | Internet Subscription Expenses | 9DCAU | Negotiated 53.9 | [17 empty] | 9DCAU | [10 empty] | 2023-02-06 | 14 Mar 23 | 14 Mar 23 | 2023-03-17 | 2023-03-17 | MOOE | 26100 | 26100 |  | 26100 | 26100
70 | 5-02-02-010-00 | Training Expenses | 31IB | Negotiated 53.9 | [17 empty] | 31IB | [10 empty] | 2023-02-06 | 10 Mar 23 | 10 Mar 23 | 2023-03-15 | 2023-03-15 | MOOE | 22999.95 | 22999.95 |  | 22937 | 22937
71 | 5-02-02-010-00 | Training Supply Expenses | OG2 | Negotiated 53.9 | [17 empty] | OG2 | [10 empty] | 2023-02-06 | 10 Mar 23 | 10 Mar 23 | 2023-03-15 | 2023-03-15 | MOOE | 10000 | 10000 |  | 9940 | 9940
72 | 5-02-03-210-08 | Disaster Response & Rescue Equipment | 2IB | Negotiated 53.9 | [17 empty] | 2IB | [10 empty] | 2023-02-09 | 07 Mar 23 | 07 Mar 23 | 2023-03-10 | 2023-03-10 | MOOE | 30000 | 30000 |  | 29940 | 29940
73 | 5-02-99-030-00 | Representation Expenses | 49IB | Negotiated 53.9 | [17 empty] | 49IB | [10 empty] | 2023-02-13 | 17 Mar 23 | 17 Mar 23 | 2023-03-21 | 2023-03-21 | MOOE | 81760 | 81760 |  | 81670 | 81670
74 | 5-02-02-010-02 | Training Expenses | 83IB | Negotiated 53.9 | [17 empty] | 83IB | [10 empty] | 2023-02-13 | 08 Mar 23 | 08 Mar 23 | 2023-03-14 | 2023-03-14 | MOOE | 24000 | 24000 |  | 23982 | 23982
75 | 5-02-13-040-01 | R & M Building Expenses | OESPA | Negotiated 53.9 | [17 empty] | OESPA | [10 empty] | 2023-02-13 | 07 Mar 23 | 07 Mar 23 | 2023-03-09 | 2023-03-09 | MOOE | 10000 | 10000 |  | 9984 | 9984
76 | 5-02-02-010-02 | Training Expenses | 92DRC | Negotiated 53.9 | [17 empty] | 92DRC | [10 empty] | 2023-02-13 | 10 Mar 23 | 10 Mar 23 | 2023-03-15 | 2023-03-15 | MOOE | 10000 | 10000 |  | 9990 | 9990
77 | 5-02-99-030-00 | Representation Expenses | HHSC | Negotiated 53.9 | [17 empty] | HHSC | [10 empty] | 2023-02-13 | 17 Mar 23 | 17 Mar 23 | 2023-03-21 | 2023-03-21 | MOOE | 33500 | 33500 |  | 33464 | 33464
78 | 5-02-03-210-10 | Semi-Expendable Medical Equipment Expenses | CEASH | Negotiated 53.9 | [17 empty] | CEASH | [10 empty] | 2023-02-13 | 08 Mar 23 | 08 Mar 23 | 2023-03-14 | 2023-03-14 | MOOE | 154500 | 154500 |  | 154400 | 154400
79 | 5-02-03-070-00 | Drugs & Medicines Expenses | CEASH | Negotiated 53.9 | [17 empty] | CEASH | [10 empty] | 2023-02-14 | 08 Mar 23 | 08 Mar 23 | 2023-03-14 | 2023-03-14 | MOOE | 244500 | 244500 |  | 244387 | 244387
80 | 5-02-13-060-01 | R & M Motor Vehicle Expenses | CEASH | Negotiated 53.9 | [17 empty] | CEASH | [10 empty] | 2023-02-14 | 08 Mar 23 | 08 Mar 23 | 2023-03-14 | 2023-03-14 | MOOE | 137500 | 137500 |  | 137400 | 137400
81 | 5-02-13-040-99 | R & M Other Building Expenses | CEASH | Negotiated 53.9 | [17 empty] | CEASH | [10 empty] | 2023-02-14 | 17 Mar 23 | 17 Mar 23 | 2023-03-21 | 2023-03-21 | MOOE | 98000 | 98000 |  | 97910 | 97910
82 | 5-02-03-210-03 | Semi-Expendable ICT Equipment Expenses | 903BDE | Negotiated 53.9 | [17 empty] | 903BDE | [10 empty] | 2023-02-14 | 08 Mar 23 | 08 Mar 23 | 2023-03-14 | 2023-03-14 | MOOE | 112700 | 112700 |  | 112600 | 112600
83 | 5-02-13-040-01 | R & M Building Expenses | 903BDE | Negotiated 53.9 | [17 empty] | 903BDE | [10 empty] | 2023-02-14 | 08 Mar 23 | 08 Mar 23 | 2023-03-14 | 2023-03-14 | MOOE | 103000 | 103000 |  | 102900 | 102900
84 | 5-02-13-060-01 | R & M Motor Vehicle Expenses | 903BDE | Negotiated 53.9 | [17 empty] | 903BDE | [10 empty] | 2023-02-14 | 2023-04-17 | 2023-04-17 | 2023-03-21 | 2023-03-21 | MOOE | 88150 | 88150 |  | 88070 | 88070
85 | 5-02-13-060-01 | R & M Motor Vehicle Expenses | OG4 | Negotiated 53.9 | [17 empty] | OG4 | [10 empty] | 2023-02-14 | 2023-03-30 | 2023-03-30 | 2023-04-04 | 2023-04-04 | MOOE | 612000 | 612000 |  | 611900 | 611900
86 | 5-02-05-030-00 | Internet Subscription Expenses | 22IB | Negotiated 53.9 | [17 empty] | 22IB | [10 empty] | 2023-02-20 | 08 Mar 23 | 08 Mar 23 | 2023-03-14 | 2023-03-14 | MOOE | 13500 | 13500 |  | 13500 | 13500
87 | 5-02-13-060-01 | R & M Motor Vehicle Expenses | 902BDE | Negotiated 53.9 | [17 empty] | 902BDE | [10 empty] | 2023-02-20 | 2023-03-14 | 2023-03-14 | 2023-03-17 | 2023-03-17 | MOOE | 188400 | 188400 |  | 188304 | 188304
88 | 5-02-13-040-01 | R & M Building Expenses | 9DTS | Negotiated 53.9 | [17 empty] | 9DTS | [10 empty] | 2023-02-20 | 2023-04-17 | 2023-04-17 | 2023-03-21 | 2023-03-21 | MOOE | 74000 | 74000 |  | 73900 | 73900
89 | 5-02-99-030-00 | Representation Expenses | 22IB | Negotiated 53.9 | [17 empty] | 22IB | [10 empty] | 2023-02-20 | 10 Mar 23 | 10 Mar 23 | 2023-03-15 | 2023-03-15 | MOOE | 60000 | 60000 |  | 59975 | 59975
90 | 5-02-13-040-01 | R & M Building Expenses | OG2 | Negotiated 53.9 | [17 empty] | OG2 | [10 empty] | 2023-02-20 | 14 Mar 23 | 14 Mar 23 | 2023-03-17 | 2023-03-17 | MOOE | 30000 | 30000 |  | 29950 | 29950
91 | 5-02-13-040-01 | R & M Building Expenses | 9DTS | Negotiated 53.9 | [17 empty] | 9DTS | [10 empty] | 2023-02-20 | 21 Mar 23 | 21 Mar 23 | 2023-03-24 | 2023-03-24 | MOOE | 6630 | 6630 |  | 6610 | 6610
92 | 5-02-13-060-01 | R & M Motor Vehicle Expenses | 9DTS | Negotiated 53.9 | [17 empty] | 9DTS | [10 empty] | 2023-02-20 | 21 Mar 23 | 21 Mar 23 | 2023-03-24 | 2023-03-24 | MOOE | 26750 | 26750 |  | 26710 | 26710
93 | 5-02-02-010-02 | Training Expenses | 9DPAO | Negotiated 53.9 | [17 empty] | 9DPAO | [10 empty] | 2023-02-23 | 2023-04-17 | 2023-04-17 | 2023-03-21 | 2023-03-21 | MOOE | 10000 | 10000 |  | 9980 | 9980
94 | 5-02-03-990-00 | Other Supplies & Materials Expenses | 22IB | Negotiated 53.9 | [17 empty] | 22IB | [10 empty] | 2023-02-27 | 14 Mar 23 | 14 Mar 23 | 2023-03-17 | 2023-03-17 | MOOE | 47200 | 47200 |  | 47134 | 47134
95 | 5-02-05-020-01 | Mobile Expenses | OG10 | Negotiated 53.9 | [17 empty] | OG10 | [10 empty] | 2023-02-27 | 21 Mar 23 | 21 Mar 23 | 2023-03-24 | 2023-03-24 | MOOE | 129400 | 129400 |  | 129400 | 129400
96 | 5-02-03-080-00 | Medical, Dental & Lab Expenses | HHSC | Negotiated 53.9 | [17 empty] | HHSC | [10 empty] | 2023-02-27 | 30 Mar 23 | 30 Mar 23 | 2023-04-04 | 2023-04-04 | MOOE | 12000 | 12000 |  | 11980 | 11980
97 | 5-02-03-070-00 | Drugs & Medicines Expenses | 903BDE | Negotiated 53.9 | [17 empty] | 903BDE | [10 empty] | 2023-03-13 | 30 Mar 23 | 30 Mar 23 | 2023-04-04 | 2023-04-04 | MOOE | 7500 | 7500 |  | 7491 | 7491
98 | 5-02-03-080-00 | Medical, Dental & Lab Expenses | 903BDE | Negotiated 53.9 | [17 empty] | 903BDE | [10 empty] | 2023-03-13 | 30 Mar 23 | 30 Mar 23 | 2023-04-04 | 2023-04-04 | MOOE | 32500 | 32500 |  | 32475 | 32475
99 | 5-02-03-990-00 | Other Supplies & Materials Expenses | 49IB | Negotiated 53.9 | [17 empty] | 49IB | [10 empty] | 2023-03-16 | 31 Mar 23 | 31 Mar 23 | 2023-04-05 | 2023-04-05 | MOOE | 10000 | 10000 |  | 9980 | 9980
100 | 5-02-03-070-00 | Drugs & Medicines Expenses | 49IB | Negotiated 53.9 | [17 empty] | 49IB | [10 empty] | 2023-03-16 | 31 Mar 23 | 31 Mar 23 | 2023-04-05 | 2023-04-05 | MOOE | 3910 | 3910 |  | 3900 | 3900
101 | 5-02-02-010-02 | Training Expenses | 903BDE | Negotiated 53.9 | [17 empty] | 903BDE | [10 empty] | 2023-02-13 | 2023-03-17 | 2023-03-17 | 2023-03-21 | 2023-03-21 | MOOE | 40000 | 40000 |  | 39932 | 39932
102 | 5-02-03-990-00 | Other Supplies & Materials Expenses | 91DRC | Negotiated 53.9 | [17 empty] | 91DRC | [10 empty] | 2023-03-13 | 2023-03-30 | 2023-03-30 | 2023-04-04 | 2023-04-04 | MOOE | 1500 | 1500 |  | 1494 | 1494
103 | 5-02-05-030-00 | Internet Subscription Expenses | 83IB | Negotiated 53.9 | [17 empty] | 83IB | [10 empty] | 2023-03-13 | 31 Mar 23 | 31 Mar 23 | 2023-04-05 | 2023-04-05 | MOOE | 13500 | 13500 |  | 13500 | 13500
104 | 5-02-03-080-00 | Medical, Dental & Lab Expenses | 49IB | Negotiated 53.9 | [17 empty] | 49IB | [10 empty] | 2023-03-16 | 2023-03-31 | 2023-03-31 | 2023-04-05 | 2023-04-05 | MOOE | 2090 | 2090 |  | 2080 | 2080
105 | 5-02-03-210-10 | Semi-Expendable Medical Equipment Expenses | SSBN | Negotiated 53.9 | [17 empty] | SSBN | [10 empty] | 2023-03-16 | 30 Mar 23 | 30 Mar 23 | 2023-04-04 | 2023-04-04 | MOOE | 4500 | 4500 |  | 4490 | 4490
106 | 5-02-03-990-00 | Other Supplies & Materials Expenses | SSBN | Negotiated 53.9 | [17 empty] | SSBN | [10 empty] | 2023-03-16 | 30 Mar 23 | 30 Mar 23 | 2023-04-04 | 2023-04-04 | MOOE | 20000 | 20000 |  | 19984 | 19984
107 | 5-02-02-010-02 | Training Expenses | 9MIB | Negotiated 53.9 | [17 empty] | 9MIB | [10 empty] | 2023-02-09 | 2023-03-17 | 2023-03-17 | 2023-03-21 | 2023-03-21 | MOOE | 70000 | 70000 |  | 69967 | 69967
108 | 5-02-02-010-02 | Training Expenses | 92DRC | Negotiated 53.9 | [17 empty] | 92DRC | [10 empty] | 2023-02-27 | 31 Mar 23 | 31 Mar 23 | 2023-04-05 | 2023-04-05 | MOOE | 3250 | 3250 |  | 3240 | 3240
109 | 5-02-03-080-00 | Cable, Sat, Tel, Radio & Expenses | 31IB | Negotiated 53.9 | [17 empty] | 31IB | [10 empty] | 2023-03-10 | 30 Mar 23 | 30 Mar 23 | 2023-04-04 | 2023-04-04 | MOOE | 4000 | 4000 |  | 4000 | 4000
110 | 5-02-03-080-00 | Cable, Sat, Tel, Radio & Expenses | 83IB | Negotiated 53.9 | [17 empty] | 83IB | [10 empty] | 2023-03-10 | 30 Mar 23 | 30 Mar 23 | 2023-04-04 | 2023-04-04 | MOOE | 6000 | 6000 |  | 6000 | 6000
111 | 5-02-03-080-00 | Medical, Dental & Lab Expenses | 91DRC | Negotiated 53.9 | [17 empty] | 91DRC | [10 empty] | 2023-03-13 | 30 Mar 23 | 30 Mar 23 | 2023-04-04 | 2023-04-04 | MOOE | 7500 | 7500 |  | 7450 | 7450
112 | 5-02-03-210-08 | Semi-Expendable DRRE Expenses | 902BDE | Negotiated 53.9 | [17 empty] | 902BDE | [10 empty] | 2023-03-13 | 31 Mar 23 | 31 Mar 23 | 2023-04-05 | 2023-04-05 | MOOE | 37500 | 37500 |  | 37425 | 37425
113 | 5-02-02-010-02 | Training Expenses | 902BDE | Negotiated 53.9 | [17 empty] | 902BDE | [10 empty] | 2023-03-13 | 31 Mar 23 | 31 Mar 23 | 2023-04-05 | 2023-04-05 | MOOE | 31000 | 31000 |  | 30970 | 30970
114 | 5-02-02-010-02 | Training Expenses | SSBN | Negotiated 53.9 | [17 empty] | SSBN | [10 empty] | 2023-03-16 | 2023-03-30 | 2023-03-30 | 2023-04-04 | 2023-04-04 | MOOE | 15000 | 15000 |  | 14970 | 14970
115 | 5-02-03-080-00 | Medical, Dental & Lab Expenses | SSBN | Negotiated 53.9 | [17 empty] | SSBN | [10 empty] | 2023-03-20 | 2023-04-17 | 2023-04-17 | 2023-04-20 | 2023-04-20 | MOOE | 15000 | 15000 |  | 14938 | 14938
116 | 5-02-05-030-00 | Internet Subscription Expenses | 31IB | Negotiated 53.9 | [17 empty] | 31IB | [10 empty] | 2023-03-20 | 2023-04-17 | 2023-04-17 | 2023-04-20 | 2023-04-20 | MOOE | 22499 | 22499 |  | 22468 | 22468
117 | 5-02-13-040-01 | R & M Building Expenses | 9DCAU | Negotiated 53.9 | [17 empty] | 9DCAU | [10 empty] | 2023-03-23 | 2023-04-19 | 2023-04-19 | 2023-04-25 | 2023-04-25 | MOOE | 61500 | 61500 |  | 61395 | 61395
118 | 5-02-13-040-01 | R & M Building Expenses | OG10 | Negotiated 53.9 | [17 empty] | OG10 | [10 empty] | 2023-03-27 | 2023-04-14 | 2023-04-14 | 2023-04-20 | 2023-04-20 | MOOE | 250000 | 250000 |  | 249856 | 249856
119 | 5-02-13-040-01 | R & M Building Expenses | OG10 | Negotiated 53.9 | [17 empty] | OG10 | [10 empty] | 2023-03-27 | 2023-04-14 | 2023-04-14 | 2023-04-20 | 2023-04-20 | MOOE | 160840 | 160840 |  | 160722 | 160722
120 | 5-02-13-040-01 | R & M Building Expenses | OG10 | Negotiated 53.9 | [17 empty] | OG10 | [10 empty] | 2023-03-27 | 2023-04-14 | 2023-04-14 | 2023-04-20 | 2023-04-20 | MOOE | 90840 | 90840 |  | 90750 | 90750
121 |  | RM Other Land Improvements Expenses | 83IB | Negotiated 53.9 | [17 empty] | 83IB | [10 empty] | 2023-03-13 | 11 Apr 23 | 11 Apr 23 | 2023-04-14 | 2023-04-14 | MOOE | 40000 | 40000 |  | 39970 | 39970
122 | 5-02-99-030-00 | Representation Expenses | SSBN | Negotiated 53.9 | [17 empty] | SSBN | [10 empty] | 2023-03-16 | 2023-04-11 | 2023-04-11 | 2023-04-14 | 2023-04-14 | MOOE | 25000 | 25000 |  | 24980 | 24980
123 | 5-02-13-060-01 | RM Motor Vehicle Expenses | SSBN | Negotiated 53.9 | [17 empty] | SSBN | [10 empty] | 2023-03-16 | 2023-04-17 | 2023-04-17 | 2023-04-20 | 2023-04-20 | MOOE | 12500 | 12500 |  | 12480 | 12480
124 | 5-02-13-040-01 | R & M Building Expenses | SSBN | Negotiated 53.9 | [17 empty] | SSBN | [10 empty] | 2023-03-20 | 2023-04-17 | 2023-04-17 | 2023-04-20 | 2023-04-20 | MOOE | 25000 | 25000 |  | 24978 | 24978
125 | 5-02-03-070-00 | Drugs & Medicines Expenses | 96IB | Negotiated 53.9 | [17 empty] | 96IB | [10 empty] | 2023-03-20 | 2023-04-17 | 2023-04-17 | 2023-04-20 | 2023-04-20 | MOOE | 7500 | 7500 |  | 7478 | 7478
126 | 5-02-03-080-00 | Medical, Dental & Lab Expenses | 96IB | Negotiated 53.9 | [17 empty] | 96IB | [10 empty] | 2023-03-20 | 2023-04-17 | 2023-04-17 | 2023-04-20 | 2023-04-20 | MOOE | 15000 | 15000 |  | 14980 | 14980
127 | 5-02-03-080-00 | Medical, Dental & Lab Expenses | 92DRC | Negotiated 53.9 | [17 empty] | 92DRC | [10 empty] | 2023-03-20 | 19 Apr 23 | 19 Apr 23 | 2023-04-25 | 2023-04-25 | MOOE | 7500 | 7500 |  | 7450 | 7450
128 | 5-02-03-130-00 | Chemical & Filtering Supplies Expense | 9DCAU | Negotiated 53.9 | [17 empty] | 9DCAU | [10 empty] | 2023-03-20 | 2023-04-17 | 2023-04-17 | 2023-04-20 | 2023-04-20 | MOOE | 18600 | 18600 |  | 18530 | 18530
129 | 5-02-03-080-00 | Cable, Sat, Tel, Radio & Expenses | 31IB | Negotiated 53.9 | [17 empty] | 31IB | [10 empty] | 2023-03-20 | 2023-04-17 | 2023-04-17 | 2023-04-20 | 2023-04-20 | MOOE | 4000 | 4000 |  | 4000 | 4000
130 | 5-02-05-030-00 | Internet Subscription Expenses | 31IB | Negotiated 53.9 | [17 empty] | 31IB | [10 empty] | 2023-03-20 | 2023-04-17 | 2023-04-17 | 2023-04-20 | 2023-04-20 | MOOE | 8400 | 8400 |  | 8400 | 8400
131 | 5-02-13-060-01 | RM Motor Vehicle Expenses | 9DCAU | Negotiated 53.9 | [17 empty] | 9DCAU | [10 empty] | 2023-03-21 | 2023-04-17 | 2023-04-17 | 2023-04-20 | 2023-04-20 | MOOE | 52500 | 52500 |  | 52430 | 52430
132 | 5-02-03-210-03 | Semi-Expendable ICT Equipment Expenses | 2IB | Negotiated 53.9 | [17 empty] | 2IB | [10 empty] | 2023-03-23 | 2023-04-17 | 2023-04-17 | 2023-04-20 | 2023-04-20 | MOOE | 20000 | 20000 |  | 19980 | 19980
133 | 5-02-13-040-01 | R & M Building Expenses | OG10 | Negotiated 53.9 | [17 empty] | OG10 | [10 empty] | 2023-03-27 | 2023-04-19 | 2023-04-19 | 2023-04-25 | 2023-04-25 | MOOE | 50000 | 50000 |  | 49940 | 49940
134 | 5-02-99-030-00 | Representation Expenses | 91DRC | Negotiated 53.9 | [17 empty] | 91DRC | [10 empty] | 2023-03-27 | 17 Apr 23 | 17 Apr 23 | 2023-04-20 | 2023-04-20 | MOOE | 26000 | 26000 |  | 25995 | 25995
135 | 5-02-13-040-01 | R & M Building Expenses | HHSC | Negotiated 53.9 | [17 empty] | HHSC | [10 empty] | 2023-03-27 | 14 Apr 23 | 14 Apr 23 | 2023-04-20 | 2023-04-20 | MOOE | 20000 | 20000 |  | 19955 | 19955
136 | 5-02-03-990-00 | Other Supplies & Materials Expenses | SSBN | Negotiated 53.9 | [17 empty] | SSBN | [10 empty] | 2023-03-27 | 2023-04-17 | 2023-04-17 | 2023-04-20 | 2023-04-20 | MOOE | 5000 | 5000 |  | 4975 | 4975
137 | 5-02-13-050-03 | RM Semi-Expendable ICT Equipment Expenses | 49IB | Negotiated 53.9 | [17 empty] | 49IB | [10 empty] | 2023-03-27 | 24 Apr 23 | 24 Apr 23 | 2023-04-28 | 2023-04-28 | MOOE | 10000 | 10000 |  | 9980 | 9980
138 | 5-02-03-210-03 | Semi-Expendable ICT Equipment Expenses | 49IB | Negotiated 53.9 | [17 empty] | 49IB | [10 empty] | 2023-03-16 | 2023-04-17 | 2023-04-17 | 2023-04-20 | 2023-04-20 | MOOE | 55000 | 55000 |  | 54900 | 54900
139 | 5-02-03-070-00 | Drugs & Medicines Expenses | 9DCAU | Negotiated 53.9 | [17 empty] | 9DCAU | [10 empty] | 2023-03-20 | 2023-04-17 | 2023-04-17 | 2023-04-20 | 2023-04-20 | MOOE | 5000 | 5000 |  | 4990 | 4990
140 | 5-02-03-070-00 | Drugs & Medicines Expenses | 2IB | Negotiated 53.9 | [17 empty] | 2IB | [10 empty] | 2023-03-23 | 2023-04-17 | 2023-04-17 | 2023-04-20 | 2023-04-20 | MOOE | 30000 | 30000 |  | 29965 | 29965
141 |  | Semi-Expendable Sports Equipment Expenses | 2IB | Negotiated 53.9 | [17 empty] | 2IB | [10 empty] | 2023-03-23 | 2023-04-17 | 2023-04-17 | 2023-04-20 | 2023-04-20 | MOOE | 15000 | 15000 |  | 14980 | 14980
142 | 5-02-05-020-01 | Mobile Expenses | ODSM | Negotiated 53.9 | [17 empty] | ODSM | [10 empty] | 2023-03-27 | 2023-04-19 | 2023-04-19 | 2023-04-25 | 2023-04-25 | MOOE | 4100 | 4100 |  | 4100 | 4100
143 | 5-02-13-060-01 | RM Motor Vehicle Expenses | SSBN | Negotiated 53.9 | [17 empty] | SSBN | [10 empty] | 2023-03-27 | 27 Apr 23 | 27 Apr 23 | 2023-05-02 | 2023-05-02 | MOOE | 30000 | 30000 |  | 29960 | 29960
144 | 5-02-13-040-01 | R & M Building Expenses | SSBN | Negotiated 53.9 | [17 empty] | SSBN | [10 empty] | 2023-03-27 | 27 Apr 23 | 27 Apr 23 | 2023-05-02 | 2023-05-02 | MOOE | 40000 | 40000 |  | 39962 | 39962
145 | 5-02-02-010-02 | Training Expenses | 2IB | Negotiated 53.9 | [17 empty] | 2IB | [10 empty] | 2023-02-09 | 2 Mar 23 | 2 Mar 23 | 2023-03-06 | 2023-03-06 | MOOE | 30000 | 30000 |  | 29967 | 29967
146 | 5-02-13-210-03 | R & M Semi-Expendable ICT Equipment Expenses | OG6 | Negotiated 53.9 | [17 empty] | OG6 | [10 empty] | 2023-02-27 | 2023-03-30 | 2023-03-30 | 2023-04-04 | 2023-04-04 | MOOE | 108645 | 108645 |  | 108570 | 108570
147 | 5-02-05-030-00 | Internet Subscription Expenses | 31IB | Negotiated 53.9 | [17 empty] | 31IB | [10 empty] | 2023-03-10 | 24 Apr 23 | 24 Apr 23 | 2023-04-28 | 2023-04-28 | MOOE | 8400 | 8400 |  | 8400 | 8400
148 | 5-02-02-010-02 | Training Expenses | 91DRC | Negotiated 53.9 | [17 empty] | 91DRC | [10 empty] | 2023-03-13 | 2023-04-17 | 2023-04-17 | 2023-04-20 | 2023-04-20 | MOOE | 21000 | 21000 |  | 20962 | 20962
149 | 5-02-03-210-03 | Semi-Expendable ICT Equipment Expenses | OG6 | Negotiated 53.9 | [17 empty] | OG6 | [10 empty] | 2023-02-27 | 2023-04-17 | 2023-04-17 | 2023-04-20 | 2023-04-20 | MOOE | 250000 | 250000 |  | 249900 | 249900
150 | 5-02-99-030-00 | Representation Expenses | 92DRC | Negotiated 53.9 | [17 empty] | 92DRC | [10 empty] | 2023-03-20 | 2023-04-17 | 2023-04-17 | 2023-04-20 | 2023-04-20 | MOOE | 13000 | 13000 |  | 12980 | 12980
151 | 5-02-03-080-00 | Cable, Sat, Tel, Radio & Expenses | 9DCAU | Negotiated 53.9 | [17 empty] | 9DCAU | [10 empty] | 2023-03-20 | 2023-04-17 | 2023-04-17 | 2023-04-20 | 2023-04-20 | MOOE | 6000 | 6000 |  | 6000 | 6000
152 | 5-02-13-040-99 | RM OtherStructure Expenses | 9DCAU | Negotiated 53.9 | [17 empty] | 9DCAU | [10 empty] | 2023-03-20 | 2023-04-17 | 2023-04-17 | 2023-04-20 | 2023-04-20 | MOOE | 20000 | 20000 |  | 19980 | 19980
153 | 5-02-03-210-08 | Semi-Expendable DRRE Expenses | 83IB | Negotiated 53.9 | [17 empty] | 83IB | [10 empty] | 2023-03-21 | 2023-04-17 | 2023-04-17 | 2023-04-20 | 2023-04-20 | MOOE | 120000 | 120000 |  | 119900 | 119900
154 | 5-02-05-020-01 | Mobile Expenses | OG7 | Negotiated 53.9 | [17 empty] | OG7 | [10 empty] | 2023-03-27 | 2023-04-19 | 2023-04-19 | 2023-04-25 | 2023-04-25 | MOOE | 27500 | 27500 |  | 27500 | 27500
155 | 5-02-03-080-00 | Cable, Sat, Tel, Radio & Expenses | OG7 | Negotiated 53.9 | [17 empty] | OG7 | [10 empty] | 2023-03-27 | 2023-04-19 | 2023-04-19 | 2023-04-25 | 2023-04-25 | MOOE | 1500 | 1500 |  | 1500 | 1500
156 | 5-02-13-060-01 | RM Motor Vehicle Expenses | HHSC | Negotiated 53.9 | [17 empty] | HHSC | [10 empty] | 2023-03-27 | 2023-04-17 | 2023-04-17 | 2023-04-20 | 2023-04-20 | MOOE | 5000 | 5000 |  | 4985 | 4985
157 | 5-02-99-030-00 | Representation Expenses | SSBN | Negotiated 53.9 | [17 empty] | SSBN | [10 empty] | 2023-03-27 | 24 Apr 23 | 24 Apr 23 | 2023-04-28 | 2023-04-28 | MOOE | 85000 | 85000 |  | 84900 | 84900
158 | 5-02-13-050-03 | RM Semi-Expendable ICT Equipment Expenses | SSBN | Negotiated 53.9 | [17 empty] | SSBN | [10 empty] | 2023-03-27 | 24 Apr 23 | 24 Apr 23 | 2023-04-28 | 2023-04-28 | MOOE | 4000 | 4000 |  | 3990 | 3990
159 | 5-02-13-040-01 | R & M Building Expenses | 49IB | Negotiated 53.9 | [17 empty] | 49IB | [10 empty] | 2023-02-27 | 2023-04-19 | 2023-04-19 | 2023-04-25 | 2023-04-25 | MOOE | 155800 | 155800 |  | 155706 | 155706
160 | 5-02-03-210-03 | Semi-Expendable ICT Equipment Expenses | 902BDE | Negotiated 53.9 | [17 empty] | 902BDE | [10 empty] | 2023-03-13 | 2023-04-17 | 2023-04-17 | 2023-04-20 | 2023-04-20 | MOOE | 30000 | 30000 |  | 29960 | 29960
161 | 5-02-02-010-02 | Training Expenses | 9DCAU | Negotiated 53.9 | [17 empty] | 9DCAU | [10 empty] | 2023-03-20 | 24 Apr 23 | 24 Apr 23 | 2023-04-28 | 2023-04-28 | MOOE | 18000 | 18000 |  | 17974 | 17974
162 | 5-02-13-040-01 | RM Building Expenses | OG10 | Negotiated 53.9 | [17 empty] | OG10 | [10 empty] | 2023-03-30 | 24 Apr 23 | 24 Apr 23 | 2023-04-28 | 2023-04-28 | MOOE | 50000 | 50000 |  | 49950 | 49950
163 | 5-02-03-080-00 | Cable, Sat, Tel, Radio & Expenses | DOC | Negotiated 53.9 | [17 empty] | DOC | [10 empty] | 2023-04-03 | 2023-04-27 | 2023-04-27 | 2023-05-02 | 2023-05-02 | MOOE | 1500 | 1500 |  | 1500 | 1500
164 | 5-02-05-020-01 | Mobile Expenses | DOC | Negotiated 53.9 | [17 empty] | DOC | [10 empty] | 2023-04-03 | 27 Apr 23 | 27 Apr 23 | 2023-05-02 | 2023-05-02 | MOOE | 10500 | 10500 |  | 10500 | 10500
| Total Alloted Budget of Procurement Activities | [37 empty] | 9232594.95
| Total Contract Price of Procurement Actitvites Conducted | [40 empty] | 9221763.5
| Total Savings (Total Alloted Budget - Total Contract Price) | [37 empty] | 10831.45
0N-GOING PROCUREMENT ACTIVITIES
1 | 5-02-03-010-00 | Office Supplies Expenses | OG8 | Shopping 52.IB | [17 empty] | OG8 | [10 empty] | 2023-03-27 | 27 Apr 23 | 27 Apr 23 | 2023-05-02 | 2023-05-02 | MOOE | 27000 | 27000 |  | 26956 | 26956
2 | 5-02-03-010-00 | Office Supplies Expenses | 9DPAO | Shopping 52.IB | [17 empty] | 9DPAO | [10 empty] | 2023-04-03 | 2323-05-17 | 2323-05-17 | 2023-05-22 | 2023-05-22 | MOOE | 14865 | 14865 |  | 14846 | 14846
3 | 5-02-03-010-00 | Office Supplies Expenses | 1369DEN | Shopping 52.IB | [17 empty] | 1369DEN | [10 empty] | 2023-04-03 | 2323-05-09 | 2323-05-09 | 2023-05-12 | 2023-05-12 | MOOE | 12000 | 12000 |  | 11975 | 11975
4 | 5-02-03-010-00 | Office Supplies Expenses | 903BDE | Shopping 52.IB | [17 empty] | 903BDE | [10 empty] | 2023-04-11 | 2023-05-17 | 2023-05-17 | 2023-05-22 | 2023-05-22 | MOOE | 28000 | 28000 |  | 27970 | 27970
5 | 5-02-03-010-00 | Office Supplies Expenses | 83IB | Shopping 52.IB | [17 empty] | 83IB | [10 empty] | 2023-04-11 | 2323-05-09 | 2323-05-09 | 2023-05-12 | 2023-05-12 | MOOE | 8000 | 8000 |  | 7980 | 7980
6 | 5-02-03-010-00 | Office Supplies Expenses | OG6 | Shopping 52.IB | [17 empty] | OG6 | [10 empty] | 2023-04-11 | 09 May 23 | 09 May 23 | 2023-05-12 | 2023-05-12 | MOOE | 10000 | 10000 |  | 9994 | 9994
7 | 5-02-03-010-00 | Office Supplies Expenses | CEASH | Shopping 52.IB | [17 empty] | CEASH | [10 empty] | 2023-04-17 | 2323-05-24 | 2323-05-24 | 2023-05-29 | 2023-05-29 | MOOE | 4500 | 4500 |  | 4490 | 4490
8 | 5-02-03-010-00 | Office Supplies Expenses | CEASH | Shopping 52.IB | [17 empty] | CEASH | [10 empty] | 2023-04-17 | 11 May 23 | 11 May 23 | 2023-05-16 | 2023-05-16 | MOOE | 41000 | 41000 |  | 40975 | 40975
9 | 5-02-03-010-00 | Office Supplies Expense | OG4 | Shopping 52.IB | [17 empty] | OG4 | [10 empty] | 2023-04-17 | 02 June 23 | 02 June 23 | 2023-06-08 | 2023-06-08 | MOOE | 51100 | 51100 |  | 51024 | 51024
10 | 5-02-03-010-00 | Office Supplies Expenses | 91DGSMO | Shopping 52.IB | [17 empty] | 91DGSMO | [10 empty] | 2023-04-24 | 2323-05-17 | 2323-05-17 | 2023-05-22 | 2023-05-22 | MOOE | 12220 | 12220 |  | 12205 | 12205
11 | 5-02-03-010-00 | Office Supplies Expenses | OESPA | Shopping 52.IB | [17 empty] | OESPA | [10 empty] | 2023-04-24 | 22 May 23 | 22 May 23 | 2023-05-24 | 2023-05-24 | MOOE | 15000 | 15000 |  | 14975 | 14975
12 | 5-02-03-010-00 | Office Supplies Expenses | 93DRC | Shopping 52.IB | [17 empty] | 93DRC | [10 empty] | 2023-05-02 | 2323-05-17 | 2323-05-17 | 2023-05-22 | 2023-05-22 | MOOE | 3000 | 3000 |  | 2990 | 2990
13 | 5-02-03-010-00 | Office Supplies Expenses | ODA | Shopping 52.IB | [17 empty] | ODA | [10 empty] | 2023-05-02 | 2023-05-22 | 2023-05-22 | 2023-05-24 | 2023-05-24 | MOOE | 22000 | 22000 |  | 21920 | 21920
14 | 5-02-03-010-00 | Office Supplies Expenses | HHSC | Shopping 52.IB | [17 empty] | HHSC | [10 empty] | 2023-05-05 | 05 June 2023 | 05 June 2023 | 2023-06-09 | 2023-06-09 | MOOE | 29500 | 29500 |  | 29475 | 29475
15 | 5-02-03-010-00 | Office Supplies Expenses | OG2 | Shopping 52.IB | [17 empty] | OG2 | [10 empty] | 2023-05-08 | 2323-05-24 | 2323-05-24 | 2023-05-29 | 2023-05-29 | MOOE | 15850 | 15850 |  | 15815 | 15815
16 | 5-02-03-010-00 | Office Supplies Expenses | 96IB | Shopping 52.IB | [17 empty] | 96IB | [10 empty] | 2023-05-15 | 02 June 2023 | 02 June 2023 | 2023-06-07 | 2023-06-07 | MOOE | 5000 | 5000 |  | 4986 | 4986
17 | 5-02-03-010-00 | Office Supplies Expenses | 9DTS | Shopping 52.IB | [17 empty] | 9DTS | [10 empty] | 2023-05-15 | 15 June 2023 | 15 June 2023 | 2023-06-22 | 2023-06-22 | MOOE | 42645 | 42645 |  | 42286 | 42286
18 | 5-02-02-010-02 | Training Expenses | OG8 | Negotiated 53.9 | [17 empty] | OG8 | [10 empty] | 2023-02-20 | 2023-03-30 | 2023-03-30 | 2023-04-04 | 2023-04-04 | MOOE | 25000 | 25000 |  | 24950 | 24950
19 | 5-02-13-040-01 | R & M Building Expenses | OG3 | Negotiated 53.9 | [17 empty] | OG3 | [10 empty] | 2023-02-27 | 30 Mar 23 | 30 Mar 23 | 2023-04-04 | 2023-04-04 | MOOE | 10000 | 10000 |  | 9988 | 9988
20 | 5-02-99-030-00 | Representation Expenses | 96IB | Negotiated 53.9 | [17 empty] | 96IB | [10 empty] | 2023-03-20 | 2023-04-17 | 2023-04-17 | 2023-04-20 | 2023-04-20 | MOOE | 50000 | 50000 |  | 49951 | 49951
21 | 5-02-03-210-03 | Semi-Expendable ICT Equipment Expenses | OG6 | Negotiated 53.9 | [17 empty] | OG6 | [10 empty] | 2023-02-27 | 2023-04-17 | 2023-04-17 | 2023-04-20 | 2023-04-20 | MOOE | 55000 | 55000 |  | 54900 | 54900
22 | 5-02-02-010-02 | Training Expenses | 92DRC | Negotiated 53.9 | [17 empty] | 92DRC | [10 empty] | 2023-03-20 | 2023-04-17 | 2023-04-17 | 2023-04-20 | 2023-04-20 | MOOE | 10000 | 10000 |  | 9990 | 9990
23 | 5-02-02-010-02 | Training Expenses | 92DRC | Negotiated 53.9 | [17 empty] | 92DRC | [10 empty] | 2023-03-20 | 2023-04-17 | 2023-04-17 | 2023-04-20 | 2023-04-20 | MOOE | 20750 | 20750 |  | 20719 | 20719
24 | 5-02-05-020-01 | Mobile Expenses | 9DCAU | Negotiated 53.9 | [17 empty] | 9DCAU | [10 empty] | 2023-03-20 | 2023-05-24 | 2023-05-24 | 2023-05-29 | 2023-05-29 | MOOE | 1000 | 1000 |  | 1000 | 1000
25 | 5-02-05-030-00 | Internet Subscription Expenses | 9DCAU | Negotiated 53.9 | [17 empty] | 9DCAU | [10 empty] | 2023-03-20 | 11 May 23 | 11 May 23 | 2023-05-16 | 2023-05-16 | MOOE | 26000 | 26000 |  | 26000 | 26000
26 | 5-02-02-010-02 | Training Expenses | 96IB | Negotiated 53.9 | [17 empty] | 96IB | [10 empty] | 2023-03-20 | 2023-04-24 | 2023-04-24 | 2023-04-28 | 2023-04-28 | MOOE | 18500 | 18500 |  | 18476 | 18476
27 | 5-02-99-030-00 | Representation Expenses | 31IB | Negotiated 53.9 | [17 empty] | 31IB | [10 empty] | 2023-03-21 | 2023-04-17 | 2023-04-17 | 2023-04-20 | 2023-04-20 | MOOE | 119499.92 | 119499.92 |  | 119442 | 119442
28 | 5-02-02-010-02 | Training Expenses | OG7 | Negotiated 53.9 | [17 empty] | OG7 | [10 empty] | 2023-03-27 | 2023-04-24 | 2023-04-24 | 2023-04-28 | 2023-04-28 | MOOE | 100000 | 100000 |  | 99890 | 99890
29 | 5-02-13-040-01 | R & M Building Expenses | OG10 | Negotiated 53.9 | [17 empty] | OG10 | [10 empty] | 2023-03-27 | 14 Apr 23 | 14 Apr 23 | 2023-04-20 | 2023-04-20 | MOOE | 300000 | 300000 |  | 299881 | 299881
30 | 5-02-05-030-00 | Internet Subscription Expenses | OG4 | Negotiated 53.9 | [17 empty] | OG4 | [10 empty] | 2023-03-27 | 2023-04-19 | 2023-04-19 | 2023-04-25 | 2023-04-25 | MOOE | 6000 | 6000 |  | 6000 | 6000
31 | 5-02-05-030-00 | Internet Subscription Expenses | OG7 | Negotiated 53.9 | [17 empty] | OG7 | [10 empty] | 2023-03-27 | 2023-04-19 | 2023-04-19 | 2023-04-25 | 2023-04-25 | MOOE | 6000 | 6000 |  | 6000 | 6000
32 | 5-02-02-010-02 | Training Expenses | SSBN | Negotiated 53.9 | [17 empty] | SSBN | [10 empty] | 2023-03-27 | 24 Apr 23 | 24 Apr 23 | 2023-04-28 | 2023-04-28 | MOOE | 15000 | 15000 |  | 14980 | 14980
33 | 5-02-02-010-02 | Training Expenses | 2IB | Negotiated 53.9 | [17 empty] | 2IB | [10 empty] | 2023-03-27 | 2023-05-08 | 2023-05-08 | 2023-05-11 | 2023-05-11 | MOOE | 25000 | 25000 |  | 24968 | 24968
34 | 5-02-99-030-00 | Representation Expenses | 49IB | Negotiated 53.9 | [17 empty] | 49IB | [10 empty] | 2023-03-27 | 2023-04-17 | 2023-04-17 | 2023-04-20 | 2023-04-20 | MOOE | 34760 | 34760 |  | 34742 | 34742
35 | 5-02-02-010-02 | Training Expenses | 49IB | Negotiated 53.9 | [17 empty] | 49IB | [10 empty] | 2023-03-27 | 24 Apr 23 | 24 Apr 23 | 2023-04-28 | 2023-04-28 | MOOE | 40000 | 40000 |  | 39950 | 39950
36 | 5-02-02-010-02 | Training Expenses | OG6 | Negotiated 53.9 | [17 empty] | OG6 | [10 empty] | 2023-03-30 | 2023-06-02 | 2023-06-02 | 2023-06-07 | 2023-06-07 | MOOE | 45833 | 45833 |  | 45793 | 45793
37 | 5-02-05-030-00 | Internet Subscription Expenses | OG8 | Negotiated 53.9 | [17 empty] | OG8 | [10 empty] | 2023-03-30 | 09 May 23 | 09 May 23 | 2023-05-12 | 2023-05-12 | MOOE | 6000 | 6000 |  | 6000 | 6000
38 | 5-02-03-080-00 | Cable, Sat, Tel, Radio & Expenses | OG8 | Negotiated 53.9 | [17 empty] | OG8 | [10 empty] | 2023-03-30 | 09 May 23 | 09 May 23 | 2023-05-12 | 2023-05-12 | MOOE | 1500 | 1500 |  | 1500 | 1500
39 | 5-02-05-020-01 | Mobile Expenses | OG8 | Negotiated 53.9 | [17 empty] | OG8 | [10 empty] | 2023-03-30 | 27 Apr 23 | 27 Apr 23 | 2023-05-02 | 2023-05-02 | MOOE | 4500 | 4500 |  | 4500 | 4500
40 | 5-02-02-010-02 | Training Expenses | 9DTS | Negotiated 53.9 | [17 empty] | 9DTS | [10 empty] | 2023-03-30 | 24 May 23 | 24 May 23 | 2023-05-29 | 2023-05-29 | MOOE | 37065 | 37065 |  | 37030 | 37030
41 | 5-02-13-040-01 | R & M Building Expenses | 9DTS | Negotiated 53.9 | [17 empty] | 9DTS | [10 empty] | 2023-04-04 | 02 June 23 | 02 June 23 | 2023-07-03 | 2023-07-03 | MOOE | 500000 | 500000 |  | 498800 | 498800
42 | 5-02-13-040-01 | Support for the Enhancement of Ceiling of Coy Barracks (160 Bed Capacity) | 9DTS | Negotiated 53.9 | [17 empty] | 9DTS | [10 empty] | 2023-04-04 | 11 May 23 | 11 May 23 | 2023-06-09 | 2023-06-09 | MOOE | 500000 | 500000 |  | 498800 | 498800
43 | 5-02-13-040-01 | Support for the Enhancement of Mess Hall (Building # 51) | 9DTS | Negotiated 53.9 | [17 empty] | 9DTS | [10 empty] | 2023-04-04 |  |  |  |  | MOOE | 369118 | 369118 |  | 368000 | 368000
44 | 5-02-05-020-01 | Mobile Expenses | 9DPAO | Negotiated 53.9 | [17 empty] | 9DPAO | [10 empty] | 2023-04-03 | 09 May 2323 | 09 May 2323 | 2023-05-12 | 2023-05-12 | MOOE | 24000 | 24000 |  | 24000 | 24000
45 | 5-02-02-010-02 | Training Expenses | OG8 | Negotiated 53.9 | [17 empty] | OG8 | [10 empty] | 2023-04-03 | 2023-06-02 | 2023-06-02 | 2023-06-07 | 2023-06-07 | MOOE | 25000 | 25000 |  | 24950 | 24950
46 | 5-02-02-010-02 | Training Expenses | OG8 | Negotiated 53.9 | [17 empty] | OG8 | [10 empty] | 2023-04-03 | 09 May 2323 | 09 May 2323 | 2023-05-12 | 2023-05-12 | MOOE | 42900 | 42900 |  | 42836 | 42836
47 | 5-02-03-070-00 | Drugs & Medicines Expenses | 9IB | Negotiated 53.9 | [17 empty] | 9IB | [10 empty] | 2023-04-03 | 2323-05-09 | 2323-05-09 | 2023-05-12 | 2023-05-12 | MOOE | 50000 | 50000 |  | 49920 | 49920
48 | 5-02-02-010-02 | Training Expenses | 9IB | Negotiated 53.9 | [17 empty] | 9IB | [10 empty] | 2023-04-03 | 2023-06-02 | 2023-06-02 | 2023-06-07 | 2023-06-07 | MOOE | 18000 | 18000 |  | 17976 | 17976
49 | 5-02-02-010-02 | Training Expenses | 9IB | Negotiated 53.9 | [17 empty] | 9IB | [10 empty] | 2023-04-04 |  |  |  |  | MOOE | 85000 | 85000 |  | 84959 | 84959
50 | 5-02-13-040-01 | RM Building Expenses | 31IB | Negotiated 53.9 | [17 empty] | 31IB | [10 empty] | 2023-04-04 | 2023-04-27 | 2023-04-27 | 2023-05-02 | 2023-05-02 | MOOE | 80000 | 80000 |  | 79904 | 79904
51 | 5-02-03-070-00 | Drugs & Medicines Expenses | 1369DEN | Negotiated 53.9 | [17 empty] | 1369DEN | [10 empty] | 2023-04-03 | 2323-05-09 | 2323-05-09 | 2023-05-12 | 2023-05-12 | MOOE | 23000 | 23000 |  | 22940 | 22940
52 | 5-02-02-010-02 | Training Expenses | 1369DEN | Negotiated 53.9 | [17 empty] | 1369DEN | [10 empty] | 2023-04-03 | 11 May 23 | 11 May 23 | 2023-05-16 | 2023-05-16 | MOOE | 30000 | 30000 |  | 29972 | 29972
53 | 5-02-13-040-01 | R&M Hospital & Health Care Center | 1369DEN | Negotiated 53.9 | [17 empty] | 1369DEN | [10 empty] | 2023-04-03 | 17 May 23 | 17 May 23 | 2023-05-22 | 2023-05-22 | MOOE | 10000 | 10000 |  | 9980 | 9980
54 | 5-02-03-210-07 | Semi-Expendable Communication Equipment Expenses | 903BDE | Negotiated 53.9 | [17 empty] | 903BDE | [10 empty] | 2023-04-03 | 08 May 23 | 08 May 23 | 2023-05-11 | 2023-05-11 | MOOE | 84780 | 84780 |  | 84720 | 84720
55 | 5-02-13-210-03 | R & M Semi-Expendable ICT Equipment Expenses | 96IB | Negotiated 53.9 | [17 empty] | 96IB | [10 empty] | 2023-04-11 | 15 June 23 | 15 June 23 | 2023-06-20 | 2023-06-20 | MOOE | 51500 | 51500 |  | 51400 | 51400
56 | 5-02-05-020-01 | Mobile Expenses | JAGO | Negotiated 53.9 | [17 empty] | JAGO | [10 empty] | 2023-04-11 | 2023-05-11 | 2023-05-11 | 2023-05-16 | 2023-05-16 | MOOE | 9000 | 9000 |  | 9000 | 9000
57 | 5-02-03-070-00 | Drugs & Medicines Expenses | 903BDE | Negotiated 53.9 | [17 empty] | 903BDE | [10 empty] | 2023-04-11 | 17 May 23 | 17 May 23 | 2023-05-22 | 2023-05-22 | MOOE | 7500 | 7500 |  | 7491 | 7491
58 | 5-02-02-010-02 | Training Expenses | 903BDE | Negotiated 53.9 | [17 empty] | 903BDE | [10 empty] | 2023-04-11 | 22 May 23 | 22 May 23 | 2023-05-24 | 2023-05-24 | MOOE | 50000 | 50000 |  | 49954 | 49954
59 | 5-02-03-210-03 | Semi-Expendable ICT Equipment Expenses | 903BDE | Negotiated 53.9 | [17 empty] | 903BDE | [10 empty] | 2023-04-11 | 17 May 23 | 17 May 23 | 2023-05-16 | 2023-05-16 | MOOE | 112700 | 112700 |  | 112600 | 112600
60 | 5-02-03-210-03 | Semi-Expendable ICT Equipment Expenses | 9IB | Negotiated 53.9 | [17 empty] | 9IB | [10 empty] | 2023-04-11 | 08 May 23 | 08 May 23 | 2023-05-11 | 2023-05-11 | MOOE | 102000 | 102000 |  | 101945 | 101945
61 | 5-02-13-040-01 | R & M Building Expenses | 83IB | Negotiated 53.9 | [17 empty] | 83IB | [10 empty] | 2023-04-11 | 02 June 23 | 02 June 23 | 2023-06-07 | 2023-06-07 | MOOE | 90800 | 90800 |  | 90700 | 90700
62 | 5-02-03-210-07 | Semi-Expendable Communication Equipment Expenses | 83IB | Negotiated 53.9 | [17 empty] | 83IB | [10 empty] | 2023-04-11 | 2323-05-09 | 2323-05-09 | 2023-05-12 | 2023-05-12 | MOOE | 55000 | 55000 |  | 54900 | 54900
63 | 5-02-02-010-02 | Training Expenses | 91DGSMO | Negotiated 53.9 | [17 empty] | 91DGSMO | [10 empty] | 2023-04-11 | 24 May 23 | 24 May 23 | 2023-05-29 | 2023-05-29 | MOOE | 5000 | 5000 |  | 4985 | 4985
64 | 5-02-05-030-00 | Internet Subscription Expenses | OG6 | Negotiated 53.9 | [17 empty] | OG6 | [10 empty] | 2023-04-11 | 08 May 23 | 08 May 23 | 2023-05-11 | 2023-05-11 | MOOE | 19000 | 19000 |  | 19000 | 19000
65 | 5-02-03-210-03 | Semi-Expendable ICT Equipment Expenses | OG6 | Negotiated 53.9 | [17 empty] | OG6 | [10 empty] | 2023-04-11 | 09 May 23 | 09 May 23 | 2023-05-12 | 2023-05-12 | MOOE | 41000 | 41000 |  | 40900 | 40900
66 | 5-02-99-030-00 | Representation Expenses | 9CMOBN | Negotiated 53.9 | [17 empty] | 9CMOBN | [10 empty] | 2023-04-11 | 2023-05-11 | 2023-05-11 | 2023-05-16 | 2023-05-16 | MOOE | 17750 | 17750 |  | 17725 | 17725
67 | 5-02-02-010-02 | Training Expenses | 9CMOBN | Negotiated 53.9 | [17 empty] | 9CMOBN | [10 empty] | 2023-04-11 | 2023-05-11 | 2023-05-11 | 2023-05-16 | 2023-05-16 | MOOE | 60000 | 60000 |  | 59928 | 59928
68 | 5-02-02-010-02 | Training Expenses | CEASH | Negotiated 53.9 | [17 empty] | CEASH | [10 empty] | 2023-04-17 | 2023-06-02 | 2023-06-02 | 2023-06-08 | 2023-06-08 | MOOE | 10000 | 10000 |  | 9982 | 9982
69 |  | RM Medical Equipment Expenses | CEASH | Negotiated 53.9 | [17 empty] | CEASH | [10 empty] | 2023-04-17 | 2023-06-02 | 2023-06-02 | 2023-06-08 | 2023-06-08 | MOOE | 40000 | 40000 |  | 39900 | 39900
70 | 5-02-03-210-10 | Semi-Expendable Medical Equipment Expenses | CEASH | Negotiated 53.9 | [17 empty] | CEASH | [10 empty] | 2023-04-17 | 2023-05-11 | 2023-05-11 | 2023-05-16 | 2023-05-16 | MOOE | 35000 | 35000 |  | 34900 | 34900
71 | 5-02-03-080-00 | Medical, Dental & Lab Expenses | CEASH | Negotiated 53.9 | [17 empty] | CEASH | [10 empty] | 2023-04-17 | 17 May 23 | 17 May 23 | 2023-05-22 | 2023-05-22 | MOOE | 168897 | 168897 |  | 168792 | 168792
72 | 5-02-03-210-03 | Semi-Expendable ICT Equipment Expenses | 9DTS | Negotiated 53.9 | [17 empty] | 9DTS | [10 empty] | 2023-04-17 | 22 May 23 | 22 May 23 | 2023-05-24 | 2023-05-24 | MOOE | 37400 | 37400 |  | 37360 | 37360
73 | 5-02-03-210-03 | Semi-Expendable ICT Equipment Expenses | CEASH | Negotiated 53.9 | [17 empty] | CEASH | [10 empty] | 2023-04-17 | 2323-05-22 | 2323-05-22 | 2023-05-24 | 2023-05-24 | MOOE | 54500 | 54500 |  | 54400 | 54400
74 | 5-02-13-040-01 | RM Hospitals & Health Centers Expenses | CEASH | Negotiated 53.9 | [17 empty] | CEASH | [10 empty] | 2023-04-17 | 02 June 23 | 02 June 23 | 2023-06-08 | 2023-06-08 | MOOE | 214000 | 214000 |  | 213900 | 213900
75 | 5-02-99-030-00 | Representation Expenses | 22IB | Negotiated 53.9 | [17 empty] | 22IB | [10 empty] | 2023-04-17 | 17 May 23 | 17 May 23 | 2023-05-22 | 2023-05-22 | MOOE | 75000 | 75000 |  | 74900 | 74900
76 | 5-02-99-030-00 | Representation Expenses | 22IB | Negotiated 53.9 | [17 empty] | 22IB | [10 empty] | 2023-04-17 | 11 May 23 | 11 May 23 | 2023-05-16 | 2023-05-16 | MOOE | 6000 | 6000 |  | 6000 | 6000
77 | 5-02-05-030-00 | Internet Subscription Expenses | 22IB | Negotiated 53.9 | [17 empty] | 22IB | [10 empty] | 2023-04-17 | 11 May 23 | 11 May 23 | 2023-05-16 | 2023-05-16 | MOOE | 13500 | 13500 |  | 13500 | 13500
78 | 5-02-13-040-01 | R & M Building Expenses | 9CMOBN | Negotiated 53.9 | [17 empty] | 9CMOBN | [10 empty] | 2023-04-17 | 11 May 23 | 11 May 23 | 2023-05-16 | 2023-05-16 | MOOE | 55000 | 55000 |  | 54917 | 54917
79 | 5-02-03-990-00 | Other Supplies & Materials Expenses | SSBN | Negotiated 53.9 | [17 empty] | SSBN | [10 empty] | 2023-04-17 | 17 May 23 | 17 May 23 | 2023-05-22 | 2023-05-22 | MOOE | 169400 | 169400 |  | 169200 | 169200
80 | 5-02-13-050-03 | RM Semi-Expendable ICT Equipment Expenses | OG6 | Negotiated 53.9 | [17 empty] | OG6 | [10 empty] | 2023-04-17 | On-Track | On-Track |  |  | MOOE | 24000 | 24000 |  | 23930 | 23930
81 | 5-02-03-210-07 | Semi-Expendable Communication Equipment Expenses | OG6 | Negotiated 53.9 | [17 empty] | OG6 | [10 empty] | 2023-04-17 | 17 May 23 | 17 May 23 | 2023-05-22 | 2023-05-22 | MOOE | 164000 | 164000 |  | 163890 | 163890
82 | 5-02-03-210-03 | Semi-Expendable ICT Equipment Expenses | OG6 | Negotiated 53.9 | [17 empty] | OG6 | [10 empty] | 2023-04-17 | 2023-05-22 | 2023-05-22 | 2023-05-24 | 2023-05-24 | MOOE | 248200 | 248200 |  | 248050 | 248050
83 | 5-02-03-070-00 | Drugs & Medicines Expenses | CEASH | Negotiated 53.9 | [17 empty] | CEASH | [10 empty] | 2023-04-18 | 17 May 23 | 17 May 23 | 2023-05-22 | 2023-05-22 | MOOE | 192000 | 192000 |  | 191912 | 191912
84 | 5-02-03-990-00 | Other Supplies & Materials Expense | 22IB | Negotiated 53.9 | [17 empty] | 22IB | [10 empty] | 2023-04-18 | 17 May 23 | 17 May 23 | 2023-05-22 | 2023-05-22 | MOOE | 76000 | 76000 |  | 75894 | 75894
85 | 5-02-99-030-00 | Representation Expenses | 83IB | Negotiated 53.9 | [17 empty] | 83IB | [10 empty] | 2023-04-20 | 02 June 23 | 02 June 23 | 2023-06-07 | 2023-06-07 | MOOE | 18000 | 18000 |  | 17976 | 17976
86 | 5-02-02-010-02 | Training Expenses | 83IB | Negotiated 53.9 | [17 empty] | 83IB | [10 empty] | 2023-04-20 | 02 June 23 | 02 June 23 | 2023-06-07 | 2023-06-07 | MOOE | 14000 | 14000 |  | 13980 | 13980
87 | 5-02-13-040-01 | R & M Building Expenses | 22IB | Negotiated 53.9 | [17 empty] | 22IB | [10 empty] | 2023-04-20 | 2023-06-14 | 2023-06-14 | 2023-06-19 | 2023-06-19 | MOOE | 30000 | 30000 |  | 29980 | 29980
88 | 5-02-03-210-07 | Semi-Expendable Communication Equipment Expenses | 22IB | Negotiated 53.9 | [17 empty] | 22IB | [10 empty] | 2023-04-20 | 02 June 23 | 02 June 23 | 2023-06-07 | 2023-06-07 | MOOE | 6000 | 6000 |  | 5985 | 5985
89 | 5-02-02-010-02 | Training Expenses | 22IB | Negotiated 53.9 | [17 empty] | 22IB | [10 empty] | 2023-04-20 | 17 May 23 | 17 May 23 | 2023-05-22 | 2023-05-22 | MOOE | 40000 | 40000 |  | 39965 | 39965
90 | 5-02-03-210-03 | Semi-Expendable ICT Equipment Expenses | HHSC | Negotiated 53.9 | [17 empty] | HHSC | [10 empty] | 2023-04-20 | 2023-06-05 | 2023-06-05 | 2023-06-09 | 2023-06-09 | MOOE | 25000 | 25000 |  | 24980 | 24980
91 | 5-02-03-210-07 | RM Communication Equipment Expenses | 903BDE | Negotiated 53.9 | [17 empty] | 903BDE | [10 empty] | 2023-04-20 | 2023-06-02 | 2023-06-02 | 2023-06-07 | 2023-06-07 | MOOE | 5000 | 5000 |  | 4990 | 4990
92 | 5-02-13-040-01 | R & M Building Expenses | OG6 | Negotiated 53.9 | [17 empty] | OG6 | [10 empty] | 2023-04-20 | 2023-05-22 | 2023-05-22 | 2023-05-24 | 2023-05-24 | MOOE | 30000 | 30000 |  | 29977 | 29977
93 | 5-02-03-210-03 | Semi-Expendable ICT Equipment Expenses | OG6 | Negotiated 53.9 | [17 empty] | OG6 | [10 empty] | 2023-04-20 | 2023-06-02 | 2023-06-02 | 2023-06-08 | 2023-06-08 | MOOE | 28000 | 28000 |  | 27980 | 27980
94 | 5-02-05-020-01 | Mobile Expenses | HHSC | Negotiated 53.9 | [17 empty] | HHSC | [10 empty] | 2023-04-20 | 24 May 23 | 24 May 23 | 2023-05-29 | 2023-05-29 | MOOE | 14500 | 14500 |  | 14500 | 14500
95 | 5-02-03-990-00 | Other Supplies and Materials Expenses | HHSC | Negotiated 53.9 | [17 empty] | HHSC | [10 empty] | 2023-04-24 | 2023-05-22 | 2023-05-22 | 2023-05-24 | 2023-05-24 | MOOE | 10000 | 10000 |  | 9984 | 9984
96 | 5-02-05-030-00 | Internet Subscription Expenses | OG4 | Negotiated 53.9 | [17 empty] | OG4 | [10 empty] | 2023-04-24 | 17 May 23 | 17 May 23 | 2023-05-22 | 2023-05-22 | MOOE | 6000 | 6000 |  | 6000 | 6000
97 | 5-02-03-210-07 | RM Communication Equipment Expenses | 902BDE | Negotiated 53.9 | [17 empty] | 902BDE | [10 empty] | 2023-04-24 | 14 June 23 | 14 June 23 | 2023-06-19 | 2023-06-19 | MOOE | 9000 | 9000 |  | 8950 | 8950
98 | 5-02-13-050-03 | RM ICT Equipment Expenses | 902BDE | Negotiated 53.9 | [17 empty] | 902BDE | [10 empty] | 2023-04-24 |  |  |  |  | MOOE | 6500 | 6500 |  | 6450 | 6450
99 | 5-02-13-040-99 | RM Other Structure Expenses | 902BDE | Negotiated 53.9 | [17 empty] | 902BDE | [10 empty] | 2023-04-24 | 2023-06-05 | 2023-06-05 | 2023-06-09 | 2023-06-09 | MOOE | 15000 | 15000 |  | 14977 | 14977
100 | 5-02-03-210-99 | Semi-Expendable Other Machinery & Equipment Expenses | 902BDE | Negotiated 53.9 | [17 empty] | 902BDE | [10 empty] | 2023-04-24 | 2023-06-05 | 2023-06-05 | 2023-06-09 | 2023-06-09 | MOOE | 117000 | 117000 |  | 116850 | 116850
101 | 5-02-03-210-08 | Semi-Expendable DRRE Expenses | 22IB | Negotiated 53.9 | [17 empty] | 22IB | [10 empty] | 2023-04-24 | 17 May 23 | 17 May 23 | 2023-05-22 | 2023-05-22 | MOOE | 55000 | 55000 |  | 54950 | 54950
102 | 5-02-03-210-03 | Semi-Expendable ICT Equipment Expenses | 22IB | Negotiated 53.9 | [17 empty] | 22IB | [10 empty] | 2023-04-24 | 2023-06-05 | 2023-06-05 | 2023-06-09 | 2023-06-09 | MOOE | 67500 | 67500 |  | 67440 | 67440
103 | 5-02-03-210-99 | Semi-Expendable Other Machinery & Equipment Expenses | 83IB | Negotiated 53.9 | [17 empty] | 83IB | [10 empty] | 2023-04-24 | 2023-06-02 | 2023-06-02 | 2023-06-07 | 2023-06-07 | MOOE | 179325 | 179325 |  | 179270 | 179270
104 | 5-02-13-040-01 | R & M Building Expenses | 903BDE | Negotiated 53.9 | [17 empty] | 903BDE | [10 empty] | 2023-04-24 | 22 May 23 | 22 May 23 | 2023-05-24 | 2023-05-24 | MOOE | 120000 | 120000 |  | 119928 | 119928
105 | 5-02-03-210-07 | Semi-Expendable Communication Equipment Expenses | 903BDE | Negotiated 53.9 | [17 empty] | 903BDE | [10 empty] | 2023-04-24 | 17 May 23 | 17 May 23 | 2023-05-22 | 2023-05-22 | MOOE | 83478 | 83478 |  | 83418 | 83418
106 | 5-02-13-040-01 | R & M Building Expenses | OGAD | Negotiated 53.9 | [17 empty] | OGAD | [10 empty] | 2023-04-24 | 02 June 23 | 02 June 23 | 2023-06-08 | 2023-06-08 | MOOE | 95230 | 95230 |  | 95130 | 95130
107 | 5-02-13-040-01 | R & M Building Expenses | OESPA | Negotiated 53.9 | [17 empty] | OESPA | [10 empty] | 2023-04-24 | 2023-05-22 | 2023-05-22 | 2023-05-24 | 2023-05-24 | MOOE | 10000 | 10000 |  | 9984 | 9984
108 | 5-02-02-010-02 | Training Expenses | OESPA | Negotiated 53.9 | [17 empty] | OESPA | [10 empty] | 2023-04-24 | 22 May 23 | 22 May 23 | 2023-05-24 | 2023-05-24 | MOOE | 10000 | 10000 |  | 9964 | 9964
109 | 5-02-13-040-01 | R & M Building Expenses | OGAD | Negotiated 53.9 | [17 empty] | OGAD | [10 empty] | 2023-04-24 |  |  |  |  | MOOE | 95720 | 95720 |  | 95630 | 95630
110 | 5-02-05-030-00 | Internet Subscription Expenses | ODPM | Negotiated 53.9 | [17 empty] | ODPM | [10 empty] | 2023-04-24 | 2023-05-22 | 2023-05-22 | 2023-05-24 | 2023-05-24 | MOOE | 2500 | 2500 |  | 2500 | 2500
111 | 5-02-03-990-00 | Other Supplies & Materials Expenses | 83IB | Negotiated 53.9 | [17 empty] | 83IB | [10 empty] | 2023-04-28 | 22 May 23 | 22 May 23 | 2023-05-24 | 2023-05-24 | MOOE | 50000 | 50000 |  | 49945 | 49945
112 | 5-02-02-010-02 | Training Expenses | CEASH | Negotiated 53.9 | [17 empty] | CEASH | [10 empty] | 2023-04-28 | 02 June 23 | 02 June 23 | 2023-06-08 | 2023-06-08 | MOOE | 70500 | 70500 |  | 70426 | 70426
113 | 5-02-13-040-01 | R & M Building Expenses | OGAD | Negotiated 53.9 | [17 empty] | OGAD | [10 empty] | 2023-04-28 |  |  |  |  | MOOE | 127140 | 127140 |  | 127052 | 127052
114 | 5-02-03-210-03 | Semi-Expendable ICT Equipment Expenses | 9DTS | Negotiated 53.9 | [17 empty] | 9DTS | [10 empty] | 2023-04-28 | 22 May 23 | 22 May 23 | 2023-05-24 | 2023-05-24 | MOOE | 88271 | 88271 |  | 88180 | 88180
115 | 5-02-03-210-03 | Semi-Expendable ICT Equipment Expenses | OG6 | Negotiated 53.9 | [17 empty] | OG6 | [10 empty] | 2023-04-28 | 02 June 23 | 02 June 23 | 2023-06-08 | 2023-06-08 | MOOE | 135000 | 135000 |  | 134900 | 134900
116 | 5-02-13-050-03 | RM Semi-Expendable ICT Equipment Expenses | OG6 | Negotiated 53.9 | [17 empty] | OG6 | [10 empty] | 2023-04-28 | 02 June 23 | 02 June 23 | 2023-06-07 | 2023-06-07 | MOOE | 59500 | 59500 |  | 59410 | 59410
117 | 5-02-02-010-02 | Training Expenses | OG2 | Negotiated 53.9 | [17 empty] | OG2 | [10 empty] | 2023-04-28 | 02 June 23 | 02 June 23 | 2023-06-08 | 2023-06-08 | MOOE | 50000 | 50000 |  | 49980 | 49980
118 | 5-02-02-010-02 | Training Expenses | OG2 | Negotiated 53.9 | [17 empty] | OG2 | [10 empty] | 2023-04-28 | 02 June 23 | 02 June 23 | 2023-06-08 | 2023-06-08 | MOOE | 25000 | 25000 |  | 24985 | 24985
119 | 5-02-02-010-02 | Training Expenses | OG2 | Negotiated 53.9 | [17 empty] | OG2 | [10 empty] | 2023-04-28 | 02 June 23 | 02 June 23 | 2023-06-08 | 2023-06-08 | MOOE | 50000 | 50000 |  | 49980 | 49980
120 | 5-02-99-030-00 | Representation Expenses | 93DRC | Negotiated 53.9 | [17 empty] | 93DRC | [10 empty] | 2023-05-02 | 17 May 23 | 17 May 23 | 2023-05-22 | 2023-05-22 | MOOE | 14500 | 14500 |  | 14486 | 14486
121 | 5-02-03-990-00 | Other Supplies & Materials Expense | 93DRC | Negotiated 53.9 | [17 empty] | 93DRC | [10 empty] | 2023-05-02 | 17 May 23 | 17 May 23 | 2023-05-22 | 2023-05-22 | MOOE | 4500 | 4500 |  | 4490 | 4490
122 | 5-02-02-010-02 | Training Expenses | 93DRC | Negotiated 53.9 | [17 empty] | 93DRC | [10 empty] | 2023-05-02 | 17 May 23 | 17 May 23 | 2023-05-22 | 2023-05-22 | MOOE | 27000 | 27000 |  | 26980 | 26980
123 | 5-02-13-060-01 | RM Motor Vehicle Expenses | 902BDE | Negotiated 53.9 | [17 empty] | 902BDE | [10 empty] | 2023-05-02 | 24 May 23 | 24 May 23 | 2023-05-29 | 2023-05-29 | MOOE | 119500 | 119500 |  | 119400 | 119400
124 | 5-02-13-040-01 | R & M Building Expenses | 902BDE | Negotiated 53.9 | [17 empty] | 902BDE | [10 empty] | 2023-05-02 | 05 June 23 | 05 June 23 | 2023-06-09 | 2023-06-09 | MOOE | 245000 | 245000 |  | 244891 | 244891
125 | 5-02-03-080-00 | Medical, Dental & Laboratory Supplies | 9DTS | Negotiated 53.9 | [17 empty] | 9DTS | [10 empty] | 2023-05-02 | 17 May 23 | 17 May 23 | 2023-05-22 | 2023-05-22 | MOOE | 7825 | 7825 |  | 7750 | 7750
126 | 5-02-13-060-01 | RM Motor Vehicle Expenses | 9DTS | Negotiated 53.9 | [17 empty] | 9DTS | [10 empty] | 2023-05-02 | 2023-06-15 | 2023-06-15 | 2023-06-20 | 2023-06-20 | MOOE | 24620 | 24620 |  | 24590 | 24590
127 | 5-02-13-040-01 | R & M Building Expenses | 9DTS | Negotiated 53.9 | [17 empty] | 9DTS | [10 empty] | 2023-05-02 | 2023-06-02 | 2023-06-02 | 2023-06-08 | 2023-06-08 | MOOE | 129550 | 129550 |  | 129440 | 129440
128 | 5-02-13-040-01 | RM Building Expenses (CS Barracks) | 9DTS | Negotiated 53.9 | [17 empty] | 9DTS | [10 empty] | 2023-05-02 | 2023-06-15 | 2023-06-15 | 2023-06-20 | 2023-06-20 | MOOE | 990000 | 990000 |  | 989838 | 989838
129 | 5-02-13-060-01 | RM Motor Vehicle Expenses | 903BDE | Negotiated 53.9 | [17 empty] | 903BDE | [10 empty] | 2023-05-02 | 2023-06-14 | 2023-06-14 | 2023-06-19 | 2023-06-19 | MOOE | 83850 | 83850 |  | 83750 | 83750
130 | 5-02-13-040-01 | R & M Building Expenses | 9DTS | Negotiated 53.9 | [17 empty] | 9DTS | [10 empty] | 2023-05-08 | 2023-06-15 | 2023-06-15 | 2023-06-20 | 2023-06-20 | MOOE | 630882 | 630882 |  | 630687 | 630687
131 | 5-02-02-010-02 | Training Expenses | 9DTS | Negotiated 53.9 | [17 empty] | 9DTS | [10 empty] | 2023-05-05 | 02 June 23 | 02 June 23 | 2023-06-08 | 2023-06-08 | MOOE | 42130 | 42130 |  | 42095 | 42095
132 | 5-02-13-050-00 | RM Machinery Equipment Expenses | 9DTS | Negotiated 53.9 | [17 empty] | 9DTS | [10 empty] | 2023-05-05 |  |  |  |  | MOOE | 3485 | 3485 |  | 3475 | 3475
133 | 5-02-05-020-01 | Mobile Expenses | OG3 | Negotiated 53.9 | [17 empty] | OG3 | [10 empty] | 2023-05-05 | 2023-06-02 | 2023-06-02 | 2023-06-08 | 2023-06-08 | MOOE | 12500 | 12500 |  | 12500 | 12500
134 | 5-02-03-080-00 | Cable, Sat, Tel, Radio & Expenses | OG3 | Negotiated 53.9 | [17 empty] | OG3 | [10 empty] | 2023-05-05 | 02 June 2023 | 02 June 2023 | 2023-06-08 | 2023-06-08 | MOOE | 3000 | 3000 |  | 3000 | 3000
135 | 5-02-05-030-00 | Internet Subscription Expenses | OG3 | Negotiated 53.9 | [17 empty] | OG3 | [10 empty] | 2023-05-05 | 02 June 2023 | 02 June 2023 | 2023-06-08 | 2023-06-08 | MOOE | 3000 | 3000 |  | 3000 | 3000
136 | 5-02-13-040-01 | R & M Building Expenses | OG3 | Negotiated 53.9 | [17 empty] | OG3 | [10 empty] | 2023-05-05 |  |  |  |  | MOOE | 10000 | 10000 |  | 9988 | 9988
137 | 5-02-03-080-00 | Medical, Dental & Laboratory Supplies | HHSC | Negotiated 53.9 | [17 empty] | HHSC | [10 empty] | 2023-05-05 | 05 June 2023 | 05 June 2023 | 2023-06-09 | 2023-06-09 | MOOE | 13000 | 13000 |  | 12950 | 12950
138 | 5-02-03-990-00 | Other Supplies & Materials Expense | CEASH | Negotiated 53.9 | [17 empty] | CEASH | [10 empty] | 2023-05-08 |  |  |  |  | MOOE | 411060 | 411060 |  | 410910 | 410910
139 | 5-02-13-060-01 | RM Motor Vehicles | CEASH | Negotiated 53.9 | [17 empty] | CEASH | [10 empty] | 2023-05-08 | 15 June 2023 | 15 June 2023 | 2023-06-20 | 2023-06-20 | MOOE | 132500 | 132500 |  | 132380 | 132380
140 | 5-02-13-040-01 | R & M Building Expenses | 9DTS | Negotiated 53.9 | [17 empty] | 9DTS | [10 empty] | 2023-05-08 | 02 June 2023 | 02 June 2023 | 2023-06-07 | 2023-06-07 | MOOE | 450000 | 450000 |  | 449863 | 449863
141 | 5-02-13-040-01 | R & M Building Expenses | 9DTS | Negotiated 53.9 | [17 empty] | 9DTS | [10 empty] | 2023-05-08 |  |  |  |  | MOOE | 480000 | 480000 |  | 479885 | 479885
142 | 5-02-03-210-01 | Semi-Expendable Machinery Expenses | 9MIB | Negotiated 53.9 | [17 empty] | 9MIB | [10 empty] | 2023-05-08 | 05 June 2023 | 05 June 2023 | 2023-06-09 | 2023-06-09 | MOOE | 10000 | 10000 |  | 9950 | 9950
143 | 5-02-13-050-03 | RM Semi-Expendable ICT Equipment | 9MIB | Negotiated 53.9 | [17 empty] | 9MIB | [10 empty] | 2023-05-08 | 2023-06-05 | 2023-06-05 | 2023-06-09 | 2023-06-09 | MOOE | 107095 | 107095 |  | 106995 | 106995
144 | 5-02-02-010-02 | Training Expenses | 9MIB | Negotiated 53.9 | [17 empty] | 9MIB | [10 empty] | 2023-05-08 | 2023-06-02 | 2023-06-02 | 2023-06-07 | 2023-06-07 | MOOE | 70000 | 70000 |  | 69960 | 69960
145 | 5-02-02-010-02 | Training Expenses | OG2 | Negotiated 53.9 | [17 empty] | OG2 | [10 empty] | 2023-05-08 | 15 June 2023 | 15 June 2023 | 2023-06-20 | 2023-06-20 | MOOE | 10000 | 10000 |  | 9940 | 9940
146 | 5-02-02-010-02 | Training Expenses | OG2 | Negotiated 53.9 | [17 empty] | OG2 | [10 empty] | 2023-05-08 | 15 June 2023 | 15 June 2023 | 2023-06-20 | 2023-06-20 | MOOE | 10000 | 10000 |  | 9988 | 9988
147 | 5-02-02-010-02 | Training Expenses | OG2 | Negotiated 53.9 | [17 empty] | OG2 | [10 empty] | 2023-05-08 | 15 June 2023 | 15 June 2023 | 2023-06-20 | 2023-06-20 | MOOE | 15000 | 15000 |  | 14945 | 14945
148 | 5-02-13-040-01 | RM Building Expenses | 9DTS | Negotiated 53.9 | [17 empty] | 9DTS | [10 empty] | 2023-05-09 | 2023-06-02 | 2023-06-02 | 2023-06-07 | 2023-06-07 | MOOE | 849000 | 849000 |  | 848828 | 848828
149 | 5-02-03-990-00 | Other Supplies & Materials Expense | ODA | Negotiated 53.9 | [17 empty] | ODA | [10 empty] | 2023-05-12 | 15 June 2023 | 15 June 2023 | 2023-06-22 | 2023-06-22 | MOOE | 51974 | 51974 |  | 47976 | 47976
150 | 5-02-03-070-00 | Drugs & Medicines Expenses | ODA | Negotiated 53.9 | [17 empty] | ODA | [10 empty] | 2023-05-15 | 02 June 2023 | 02 June 2023 | 2023-06-07 | 2023-06-07 | MOOE | 88900 | 88900 |  | 88785 | 88785
151 | 5-02-13-060-01 | RM Motor Vehicles | SSBN | Negotiated 53.9 | [17 empty] | SSBN | [10 empty] | 2023-05-15 |  |  |  |  | MOOE | 186360 | 186360 |  | 186250 | 186250
152 | 5-02-13-060-01 | RM Motor Vehicles | SSBN | Negotiated 53.9 | [17 empty] | SSBN | [10 empty] | 2023-05-15 |  |  | 2023-06-20 | 2023-06-20 | MOOE | 72051 | 72051 |  | 71942 | 71942
153 | 5-02-13-060-01 | RM Motor Vehicles | OG4 | Negotiated 53.9 | [17 empty] | OG4 | [10 empty] | 2023-05-15 | 2023-06-02 | 2023-06-02 | 2023-06-07 | 2023-06-07 | MOOE | 587000 | 587000 |  | 586800 | 586800
154 | 5-02-03-210-07 | Semi-Expendable Communication Equipment Expenses | 83IB | Negotiated 53.9 | [17 empty] | 83IB | [10 empty] | 2023-05-15 |  |  |  |  | MOOE | 16700 | 16700 |  | 16660 | 16660
155 | 5-02-03-070-00 | Drugs & Medicines Expenses | 96IB | Negotiated 53.9 | [17 empty] | 96IB | [10 empty] | 2023-05-15 | 2023-06-02 | 2023-06-02 | 2023-06-07 | 2023-06-07 | MOOE | 88900 | 88900 |  | 88785 | 88785
156 | 5-02-03-210-03 | Semi-Expendable ICT Equipment Expenses | 9DTS | Negotiated 53.9 | [17 empty] | 9DTS | [10 empty] | 2023-05-15 | 02 June 2023 | 02 June 2023 | 2023-06-07 | 2023-06-07 | MOOE | 77025 | 77025 |  | 76895 | 76895
157 | 5-02-02-010-02 | Training Expenses | HHSC | Negotiated 53.9 | [17 empty] | HHSC | [10 empty] | 2023-05-15 | 2023-06-02 | 2023-06-02 | 2023-06-08 | 2023-06-08 | MOOE | 26000 | 26000 |  | 25940 | 25940
158 | 5-02-99-030-00 | Representation Expenses | HHSC | Negotiated 53.9 | [17 empty] | HHSC | [10 empty] | 2023-05-19 |  |  |  |  | MOOE | 52500 | 52500 |  | 52446 | 52446
159 | 5-02-13-040-01 | R & M Building Expenses | OG4 | Negotiated 53.9 | [17 empty] | OG4 | [10 empty] | 2023-05-19 |  |  |  |  | MOOE | 858250 | 858250 |  | 858132 | 858132
160 | 5-02-13-040-01 | R & M Building Expenses | 49IB | Negotiated 53.9 | [17 empty] | 49IB | [10 empty] | 2023-05-22 |  |  | 2023-06-20 | 2023-06-20 | MOOE | 139000 | 139000 |  | 138904 | 138904
161 | 5-02-13-040-01 | R & M Building Expenses | OG4 | Negotiated 53.9 | [17 empty] | OG4 | [10 empty] | 2023-05-23 |  |  |  |  | MOOE | 999506 | 999506 |  | 999312.5 | 999312.5
162 | 5-02-03-210-03 | Semi-Expendable ICT Equipment | 9MIB | Negotiated 53.9 | [17 empty] | 9MIB | [10 empty] | 2023-05-25 |  |  |  |  | MOOE | 21920 | 21920 |  | 21870 | 21870
163 | 5-02-13-040-01 | R & M Building Expenses | 9MIB | Negotiated 53.9 | [17 empty] | 9MIB | [10 empty] | 2023-05-26 |  |  |  |  | MOOE | 99290 | 99290 |  | 99191 | 99191
164 | 5-02-13-040-01 | R & M Building Expenses | 9MIB | Negotiated 53.9 | [17 empty] | 9MIB | [10 empty] | 2023-05-29 |  |  |  |  | MOOE | 54635 | 54635 |  | 54538 | 54538
165 | 5-02-03-210-03 | Semi-Expendable ICT Equipment | OG6 | Negotiated 53.9 | [17 empty] | OG6 | [10 empty] | 2023-05-30 |  |  |  |  | MOOE | 400000 | 400000 |  | 399200 | 399200
166 | 5-02-02-010-02 | Training Expenses | OG2 | Negotiated 53.9 | [17 empty] | OG2 | [10 empty] | 2023-06-02 |  |  |  |  | MOOE | 134344 | 134344 |  | 134194.36 | 134194.36
167 | 5-02-03-210-03 | Semi-Expendable ICT Equipment | 96IB | Negotiated 53.9 | [17 empty] | 96IB | [10 empty] | 2023-06-02 |  |  |  |  | MOOE | 100000 | 100000 |  | 99920 | 99920
168 | 5-02-13-040-01 | R & M Building Expenses | OG2 | Negotiated 53.9 | [17 empty] | OG2 | [10 empty] | 2023-06-02 |  |  |  |  | MOOE | 30000 | 30000 |  | 29950 | 29950
169 | 5-02-03-210-99 | Semi- Expendable Other Machinery and Equipment | CEASH | Negotiated 53.9 | [17 empty] | CEASH | [10 empty] | 2023-06-05 |  |  |  |  | MOOE | 57000 | 57000 |  | 56900 | 56900
170 | 5-02-03-080-00 | Medical, Dental & Laboratory Supplies | OG1 | Negotiated 53.9 | [17 empty] | OG1 | [10 empty] | 2023-06-05 |  |  |  |  | MOOE | 344528.84 | 344528.84 |  | 344524.35 | 344524.35
| Total Alloted Budget of Procurement Activities | [37 empty] | 16488077.76
| Total Contract Price of Procurement Actitvites Conducted | [40 empty] | 16469889.21
| Total Savings (Total Alloted Budget - Total Contract Price) | [37 empty] | 18188.55
|  | Prepared by: | [17 empty] | Noted by: | [9 empty] | Noted by:
|  |  | Leony E Rojo | [17 empty] | ELMER O LUNAS | [9 empty] | ELMER O LUNAS
|  |  | SSg PAF | [17 empty] | CDR PN | [9 empty] | CDR PN
|  |  | Operations NCO | [17 empty] | Commanding Officer | [9 empty] | Commanding Officer