## FCPA
|  | ANNEX A | [18 empty] | ANNEX B
|  | Department of Budget and Management Annual Procurement Plan for FY 2006 | [18 empty] | FCPA Procurement Monitoring Report (1st Semester) as of June 30, 2023
Code (PAP) | Procurement Project | PMO/ End-User | Mode of Procurement | Schedule for Each Procurement Activity | [11 empty] | Source of Funds | ABC (PhP) |  |  | Remarks (brief description of Program/Project) | PMO/ End-User | Is this an Early Procurement Activity? | Mode of Procurement | Actual Procurement Activity | [12 empty] | Source of Funds | ABC (PhP) |  |  | Contract Cost (PhP) |  |  | List of Invited Observers | Date of Receipt of Invitation | [5 empty] | Remarks (Explaining changes from the APP)
|  |  |  | Pre-Proc Conference | Ads/Post of IAEB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Contract Award | Contract Signing | Notice to Proceed | Delivery/ Accept | Payment Process |  | Total | MOOE | CO |  |  |  |  | Pre-Proc Conference | Ads/Post of IB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Date of BAC Resolution Recommending Award | Notice of Award | Contract Signing | Notice to Proceed | Delivery/ Completion | Inspection & Acceptance |  | Total | MOOE | CO | Total | MOOE | CO |  | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Delivery/ Completion/ Acceptance (If applicable)
COMPLETED PROCUREMENT ACTIVITIES
| SD of 209 Boxes Continuous Form 11x14 7/8 (4PLY) Carboneless and 5 others | [19 empty] | FCPA | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2023-02-10 | 2023-02-10 | 2023-03-13 | 2023-03-15 | 2023-03-15 | GoP | 999330 | 999330 | 0 | 999270 | 999270 | 0 | [7 empty] | N/A
| SD of 20 pcs Office Chair, Alloy Metal 54 x 54 x 80cm & 3 others | [19 empty] | FCPA | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2023-02-10 | 2023-02-10 | 2023-03-10 | 2023-03-23 | 2023-03-23 | GoP | 370000 | 370000 | 0 | 365000 | 365000 | 0 | [7 empty] | N/A
| SD of 2 units Split Type Aircon (Inverter) 2.5hp & 2 others. | [19 empty] | FCPA | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2023-02-10 | 2023-02-10 | 2023-03-13 | 2023-03-23 | 2023-03-23 | GoP | 299200 | 299200 | 0 | 298000 | 298000 | 0 | [7 empty] | N/A
| SD of 4 sets Computer Set Core i3/10 Gen/16GB RAM/DDR4/256GB/24" IPS Monitor & 1 other | [19 empty] | FCPA | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2023-02-10 | 2023-02-10 | 2023-03-13 | 2023-03-23 | 2023-03-23 | GoP | 261000 | 261000 | 0 | 260000 | 260000 | 0 | [7 empty] | N/A
| SD of 105 pcs Engine Oil (1ltr) Diesel (Foton,H100,Innova,Montero,Ford) and 36 Others. | [19 empty] | FCPA | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2023-03-23 | 2023-03-23 | 2023-05-04 | 2024-05-29 | 2024-05-29 | GoP | 570390 | 570390 | 0 | 570040 | 570040 | 0 | [7 empty] | N/A
| SD of 40 bags Cement and 25 others. | [19 empty] | FCPA | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2023-03-07 | 2023-03-07 | 2023-04-24 | 2023-05-02 | 2023-05-02 | GoP | 82300 | 82300 | 0 | 82000 | 82000 | 0 | [7 empty] | N/A
| SD of 82 bags Cement and 36 others. | [19 empty] | FCPA | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2023-03-14 | 2023-03-14 | 2023-04-24 | 2023-05-02 | 2023-05-02 | GoP | 400999 | 400999 | 0 | 400178 | 400178 | 0 | [7 empty] | N/A
| SD of 19 pcs Power Supply 600w and 5 others | [19 empty] | FCPA | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2023-03-14 | 2023-03-14 | 2023-05-29 | 2023-06-06 | 2023-06-06 | GoP | 166000 | 166000 | 0 | 165673 | 165673 | 0 | [7 empty] | N/A
| SD of 230 Boxes Continuous Form 11 x 14 7/8 (4PLY 500 sheets) Carbonless & 5 others | [19 empty] | FCPA | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2023-04-24 | 2023-04-24 | 2023-05-29 | 2023-06-06 | 2023-06-06 | GoP | 999330 | 999330 | 0 | 991980 | 991980 | 0 | [7 empty] | N/A
| SD of 18 Sets Computer Set Core i7 11th Gen with Window 10 Pro & 2 others | [19 empty] | FCPA | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2023-04-24 | 2023-04-24 | 2023-05-29 | 2023-06-06 | 2023-06-06 | GoP | 900000 | 900000 | 0 | 851580 | 851580 | 0 | [7 empty] | N/A
| Procurement of 3 Units Window Type Aircon 2.5hp & 2 Others | [19 empty] | FCPA | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2023-04-24 | 2023-04-24 | 2023-05-29 | 2023-06-06 | 2023-06-06 | GoP | 452159.99 | 452159.99 | 0 | 450862 | 450862 | 0 | [7 empty] | N/A
| SD of 150 Boxes Continuous Form 11x14 7/8 (4ply 500 sheets) Carbonless and 2 others. | [19 empty] | FCPA | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2023-04-28 | 2023-04-28 | 2023-05-29 | 2023-06-06 | 2023-06-06 | GoP | 652000 | 652000 | 0 | 649800 | 649800 | 0 | [7 empty] | N/A
| 1 pc Ficem Board 1/4 x 4 x 8 and 56 others | [19 empty] | FCPA | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2023-05-05 | 2023-05-05 |  |  |  | GoP | 320205 | 320205 | 0 | 319785 | 319785 | 0 | [7 empty] | N/A
| 1 pc Oil filter (Innova ZHB-615) and 43 other | [19 empty] | FCPA | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2023-05-05 | 2023-05-05 |  |  |  | GoP | 134480 | 134480 | 0 | 134210 | 134210 | 0 | [7 empty] | N/A
| Procurement of 1 unit Television 55 inch 4k, ultra HD Smart TV Quantum HDR & 1 other LI | [19 empty] | 1FSFO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2023-05-23 | 2023-05-23 |  |  |  | GoP | 60000 | 60000 | 0 | 55000 | 55000 | 0 | [7 empty] | N/A
| Procurement of One (1) unit Facsimile Machine KX-FT981CX-W & 1 Other LI | [19 empty] | 1FSFO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2023-05-23 | 2023-05-23 |  |  |  | GoP | 94000 | 94000 | 0 | 88000 | 88000 | 0 | [7 empty] | N/A
| Vehicle Parts & Accessories | [19 empty] | 2FSFO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2023-02-03 | 2023-03-28 | 2023-03-28 | 2023-03-30 | 2023-03-30 | GoP | 37500 | 37000 | 0 | 37500 | 37000 | 0 | [7 empty] | N/A
| R&M-Buildings | [19 empty] | 2FSFO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2023-03-27 | 2023-03-31 | 2023-03-31 | 2023-04-04 | 2023-04-04 | Special Release | 374999.5 | 373840 | 0 | 374999.5 | 373840 | 0 | [7 empty] | N/A
| R&M-Buildings | [19 empty] | 2FSFO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2023-03-20 | 2023-03-28 | 2023-03-28 | 2023-03-30 | 2023-03-30 | Special Release | 350772 | 350371 | 0 | 350772 | 350371 | 0 | [7 empty] | N/A
| Chemical and Filtering Supplies Expenses | [19 empty] | 7FSFO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2023-02-20 | 2023-03-08 | 2023-03-08 | 2023-03-16 | 2023-03-16 | GoP | 8024 | 8024 | 0 | 8000 | 8000 | 0 | [7 empty] | N/A
| Other Supplies and Materials Expenses | [19 empty] | 7FSFO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2023-02-20 | 2023-03-08 | 2023-03-08 | 2023-03-16 | 2023-03-16 | GoP | 102000 | 102000 | 0 | 100200 | 100200 | 0 | [7 empty] | N/A
| Semi-Expendable Furniture & Fixture | [19 empty] | 7FSFO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2023-02-20 | 2023-03-08 | 2023-03-08 | 2023-03-16 | 2023-03-16 | GoP | 72000 | 72000 | 0 | 70200 | 70200 | 0 | [7 empty] | N/A
| Semi-Expendable ICT Equipment | [19 empty] | 7FSFO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2023-02-28 | 2023-03-21 | 2023-03-21 | 2023-03-29 | 2023-03-29 | GoP | 40000 | 40000 | 0 | 39000 | 39000 | 0 | [7 empty] | N/A
| Communication Expenses-Mobile | [19 empty] | 7FSFO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2023-02-20 | 2023-05-02 | 2023-05-02 | 2023-05-11 | 2023-05-11 | GoP | 27000 | 27000 | 0 | 27000 | 27000 | 0 | [7 empty] | N/A
| Communication Expenses-Mobile | [19 empty] | 7FSFO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2023-03-28 | 2023-05-10 | 2023-05-10 | 2023-05-17 | 2023-05-17 | GoP | 27000 | 27000 | 0 | 27000 | 27000 | 0 | [7 empty] | N/A
| Office Supplies Expenses | [19 empty] | 7FSFO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2023-04-04 | 2023-06-06 | 2023-06-06 | 2023-06-14 | 2023-06-14 | GoP | 125000 | 125000 | 0 | 123440 | 123440 | 0 | [7 empty] | N/A
| R&M Motor Veh | [19 empty] | 7FSFO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2023-04-17 | 2023-05-15 | 2023-05-15 | 2023-05-23 | 2023-05-23 | GoP | 16500 | 16500 | 0 | 16100 | 16100 | 0 | [7 empty] | N/A
| R&M Building | [19 empty] | 7FSFO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2023-04-17 | 2023-05-11 | 2023-05-11 | 2023-05-12 | 2023-05-12 | GoP | 25000 | 25000 | 0 | 24800 | 24800 | 0 | [7 empty] | N/A
| ICT equipment | [19 empty] | 7FSFO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2023-04-17 | 2023-05-02 | 2023-05-02 | 2023-03-12 | 2023-03-12 | GoP | 10000 | 10000 | 0 | 9800 | 9800 | 0 | [7 empty] | N/A
| Semi-Expendable ICT equipment | [19 empty] | 7FSFO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2023-04-17 | 2023-05-02 | 2023-05-02 | 2023-03-12 | 2023-03-12 | GoP | 48000 | 48000 | 0 | 47500 | 47500 | 0 | [7 empty] | N/A
| R&M Motor Veh | [19 empty] | 7FSFO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2023-04-28 | 2023-05-15 | 2023-05-15 | 2023-05-23 | 2023-05-23 | GoP | 16500 | 16500 | 0 | 15800 | 15800 | 0 | [7 empty] | N/A
| Medical, Dental & Laboratory Supplies Expenses | [19 empty] | 7FSFO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2023-04-28 |  |  |  |  | GoP | 40000 | 40000 | 0 | 39290 | 39290 | 0 | [7 empty] | N/A
| Semi-Expendable Office Equipment | [19 empty] | 7FSFO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2023-05-09 | 2023-06-06 | 2023-06-06 | 2023-06-14 | 2023-06-14 | GoP | 50000 | 50000 | 0 | 48950 | 48950 | 0 | [7 empty] | N/A
| Other Supplies and Materials Expenses | [19 empty] | 7FSFO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2023-05-09 | 2023-06-06 | 2023-06-06 | 2023-06-14 | 2023-06-14 | GoP | 20000 | 20000 | 0 | 19600 | 19600 | 0 | [7 empty] | N/A
| Repair and Maintenance Building-Enhancement of Building | [19 empty] | 7FSFO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2023-05-09 | 2023-05-29 | 2023-05-29 | 2023-06-07 | 2023-06-07 | Special Release | 564905.2 | 564905.2 | 0 | 559700.2 | 559700.2 | 0 | [7 empty] | N/A
| Repair and Maintenance Building-Enhancement of Visitors, Civilian HR and EW Quarters | [19 empty] | 7FSFO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2023-05-09 | 2023-05-29 | 2023-05-29 | 2023-06-07 | 2023-06-07 | Special Release | 725862.83 | 725862.83 | 0 | 719052.83 | 719052.83 | 0 | [7 empty] | N/A
| Repair and Maintenance Building-Enhancement of Kitchen and Service Area | [19 empty] | 7FSFO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2023-05-09 | 2023-05-29 | 2023-05-29 | 2023-06-07 | 2023-06-07 | Special Release | 767436.62 | 767436.62 | 0 | 762436.62 | 762436.62 | 0 | [7 empty] | N/A
| Internet Expenses | [19 empty] | 8FSFO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2023-06-27 |  |  |  |  | GoP | 6000 | 6000 | 0 | 5988 | 5988 | 0 | [7 empty] | N/A
| ICT Subscription | [19 empty] | 8FSFO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2023-06-27 |  |  |  |  | GoP | 7400 | 7400 | 0 | 7250 | 7250 | 0 | [7 empty] | N/A
| 6 pcs Cell Cards (P300.00) & ! other | [19 empty] | 9FSFO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2023-01-27 | 2023-01-27 | 2023-02-03 | 2023-02-07 | 2023-02-07 | GoP | 7800 | 7800 | 0 | 7770 | 7770 | 0 | [7 empty] | N/A
| 1 box Carbon Film & 19 others | [19 empty] | 9FSFO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2023-01-27 | 2023-01-27 | 2023-02-03 | 2023-02-07 | 2023-02-07 | GoP | 45625 | 45625 | 0 | 45545 | 45545 | 0 | [7 empty] | N/A
| 5 reams A4 Multicopy bondpaper & 10 others | [19 empty] | 9FSFO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2023-01-27 | 2023-01-27 | 2023-02-03 | 2023-02-07 | 2023-02-07 | GoP | 24125 | 24125 | 0 | 24065 | 24065 | 0 | [7 empty] | N/A
| 10 ltrs Wood Putty & 9 others | [19 empty] | 9FSFO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2023-01-30 | 2023-01-30 | 2023-02-03 | 2023-02-07 | 2023-02-07 | GoP | 64910 | 64910 | 0 | 64850 | 64850 | 0 | [7 empty] | N/A
| 50 pcs Ordinary Plywood & 9 others | [19 empty] | 9FSFO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2023-01-30 | 2023-01-30 | 2023-02-03 | 2023-02-07 | 2023-02-07 | GoP | 61310 | 61310 | 0 | 61190 | 61190 | 0 | [7 empty] | N/A
| 20 packs Bicuits & 9 others | [19 empty] | 9FSFO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2023-01-27 | 2023-01-27 | 2023-02-03 | 2023-02-07 | 2023-02-07 | GoP | 36525 | 36525 | 0 | 36450 | 36450 | 0 | [7 empty] | N/A
| 100 box medica mask & 1 other | [19 empty] | 9FSFO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2023-01-27 | 2023-01-27 | 2023-02-03 | 2023-02-07 | 2023-02-07 | GoP | 27000 | 27000 | 0 | 26960 | 26960 | 0 | [7 empty] | N/A
| 1 unit hot & cold water dispenser | [19 empty] | 9FSFO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2023-01-27 | 2023-01-27 | 2023-02-03 | 2023-02-07 | 2023-02-07 | GoP | 15000 | 15000 | 0 | 14970 | 14970 | 0 | [7 empty] | N/A
| 1 unit 2 stroke grascutter | [19 empty] | 9FSFO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2023-01-27 | 2023-01-27 | 2023-02-03 | 2023-02-07 | 2023-02-07 | GoP | 18000 | 18000 | 0 | 17960 | 17960 | 0 | [7 empty] | N/A
| 1 unit document scanner & 2 others | [19 empty] | 9FSFO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2023-01-30 | 2023-01-30 | 2023-02-03 | 2023-02-07 | 2023-02-07 | GoP | 165000 | 165000 | 0 | 164745 | 164745 | 0 | [7 empty] | N/A
| 1 set gang swish flash type & 93 others | [19 empty] | 9FSFO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2023-03-13 | 2023-03-13 | 2023-03-21 | 2023-03-24 | 2023-03-24 | Special Release | 439476 | 439476 | 0 | 438826 | 438826 | 0 | [7 empty] | N/A
| 1 set Video Conferencing System | [19 empty] | 9FSFO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2023-02-17 | 2023-02-17 | 2023-04-03 | 2023-04-11 | 2023-04-11 | GoP | 36540 | 36540 | 0 | 36470 | 36470 | 0 | [7 empty] | N/A
| 5 bottle toilet cleaner & 19 others | [19 empty] | 9FSFO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2023-02-17 | 2023-02-17 | 2023-04-03 | 2023-04-11 | 2023-04-11 | GoP | 45625 | 45625 | 0 | 45535 | 45535 | 0 | [7 empty] | N/A
| 50 packs Candies, Chewy Mint, 300pcs and 8 others | [19 empty] | 9FSFO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2023-02-17 | 2023-02-17 | 2023-04-03 | 2023-04-11 | 2023-04-11 | GoP | 47400 | 47400 | 0 | 47300 | 47300 | 0 | [7 empty] | N/A
| 1 piece Multifunctional Folding Fabric Sofa & 1 other | [19 empty] | 9FSFO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2023-02-17 | 2023-02-17 | 2023-04-03 | 2023-04-11 | 2023-04-11 | GoP | 28000 | 28000 | 0 | 27920 | 27920 | 0 | [7 empty] | N/A
| 6 pieces Cell cards (P300) and 1 others | [19 empty] | 9FSFO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2023-02-17 | 2023-02-17 | 2023-04-03 | 2023-04-11 | 2023-04-11 | GoP | 7800 | 7800 | 0 | 7782 | 7782 | 0 | [7 empty] | N/A
| 30 pieces Ordinary Plywood (1/4"x4"x8") and 16 others | [19 empty] | 9FSFO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2023-02-17 | 2023-02-17 | 2023-04-03 | 2023-04-11 | 2023-04-11 | GoP | 94370 | 94370 | 0 | 94180 | 94180 | 0 | [7 empty] | N/A
| 1 piece Multifunctional Folding Fabric Sofa and 1 other | [19 empty] | 9FSFO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2023-02-17 | 2023-02-17 | 2023-04-03 | 2023-04-11 | 2023-04-11 | GoP | 97000 | 97000 | 0 | 96815 | 96815 | 0 | [7 empty] | N/A
| Repair and Maintenance of Vehicle | [19 empty] | 10FSFO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2023-02-27 | 2023-02-28 | 2023-03-13 | 2023-03-15 | 2023-03-15 | GoP | 55000 | 55000 | 0 | 54700 | 54700 | 0 | [7 empty] | N/A
| Repair and Maintenance of Building | [19 empty] | 10FSFO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2023-02-22 | 2023-02-23 | 2023-03-13 | 2023-03-15 | 2023-03-15 | GoP | 75300 | 75300 | 0 | 75000 | 75000 | 0 | [7 empty] | N/A
| Subscription Expenses | [19 empty] | 10FSFO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2023-02-28 | 2023-03-01 | 2023-03-14 | 2023-03-16 | 2023-03-16 | GoP | 5000 | 5000 | 0 | 4890 | 4890 | 0 | [7 empty] | N/A
| Repair and Maintenance of Office Equipment | [19 empty] | 10FSFO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2023-02-28 | 2023-03-01 | 2023-03-17 | 2023-03-20 | 2023-03-20 | GoP | 15250 | 15250 | 0 | 15060 | 15060 | 0 | [7 empty] | N/A
| Semi Expendable of ICT | [19 empty] | 10FSFO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2023-02-28 | 2023-03-01 | 2023-03-14 | 2023-03-16 | 2023-03-16 | GoP | 48500 | 48500 | 0 | 48200 | 48200 | 0 | [7 empty] | N/A
| Repair and Maintenance Military Pol & Security Equipment | [19 empty] | 10FSFO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2023-02-28 | 2023-03-01 | 2023-03-17 | 2023-03-20 | 2023-03-20 | GoP | 9500 | 9500 | 0 | 9300 | 9300 | 0 | [7 empty] | N/A
| Repair and Maintenance of ICT | [19 empty] | 10FSFO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2023-03-06 | 2023-03-07 | 2023-03-24 | 2023-03-27 | 2023-03-27 | GoP | 31250 | 31250 | 0 | 31110 | 31110 | 0 | [7 empty] | N/A
| Office Supplies | [19 empty] | 10FSFO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2023-03-06 | 2023-03-07 | 2023-03-27 | 2023-03-29 | 2023-03-29 | GoP | 54000 | 54000 | 0 | 53760 | 53760 | 0 | [7 empty] | N/A
| Repair and Maintenance of Furniture and Fixture | [19 empty] | 10FSFO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2023-03-06 | 2023-03-07 | 2023-03-29 | 2023-03-31 | 2023-03-31 | GoP | 45000 | 45000 | 0 | 44850 | 44850 | 0 | [7 empty] | N/A
| Office Supplies - ICT | [19 empty] | 11FSFO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2023-05-05 | 2023-05-08 | 2023-05-25 | 2023-06-02 | 2023-06-02 | GoP | 40000 | 40000 | 0 | 37445 | 37445 | 1 | [7 empty] | N/A
| R&M ICT | [19 empty] | 11FSFO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2023-05-05 | 2023-05-08 | 2023-05-25 | 2023-06-02 | 2023-06-02 | GoP | 25000 | 25000 | 0 | 24776 | 24776 | 0 | [7 empty] | N/A
| R/M BUILDINGS | [19 empty] | 12FSFO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2023-03-19 | 2023-03-19 | 2023-05-15 | 2023-05-17 | 2023-05-17 | GoP | 100000 | 100000 | 0 | 99300 | 99300 | 0 | [7 empty] | N/A
| Office Supplies Expenses | [19 empty] | 14FSFO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2023-04-04 | 2023-04-05 | 2023-03-15 | 2023-03-22 | 2023-03-22 | GoP | 50988.08 | 50988.08 | 0 | 50913 | 50913 | 0 | [7 empty] | N/A
| Repair and Maintenance of Building | [19 empty] | 14FSFO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2023-04-04 | 2023-04-05 | 2023-04-11 | 2023-03-17 | 2023-03-17 | GoP | 212810 | 212810 | 0 | 211960 | 211960 | 0 | [7 empty] | N/A
| Semi Expendable Machinery | [19 empty] | 14FSFO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2023-04-25 | 2023-04-26 | 2023-05-08 | 2023-05-08 | 2023-05-08 | GoP | 48214 | 48214 | 0 | 46800 | 46800 | 0 | [7 empty] | N/A
| Semi Expendable Office Equipment | [19 empty] | 14FSFO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2023-04-25 | 2023-04-26 | 2023-05-15 | 2023-05-18 | 2023-05-18 | GoP | 12721.79 | 12721.79 | 0 | 10550 | 10550 | 0 | [7 empty] | N/A
| Repair and Maintenance of Motor Vehicle | [19 empty] | 14FSFO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2023-05-02 | 2023-05-03 | 2023-05-16 | 2023-05-23 | 2023-05-23 | GoP | 61000 | 61000 | 0 | 60800 | 60800 | 0 | [7 empty] | N/A
| Representation Expenses | [19 empty] | 14FSFO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2023-05-02 | 2023-05-03 | 2023-05-18 | 2023-05-25 | 2023-05-25 | GoP | 27998.9 | 27998.9 | 0 | 27748 | 27748 | 0 | [7 empty] | N/A
| Office Supplies Expenses | [19 empty] | 14FSFO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2023-05-02 | 2023-05-03 | 2023-05-16 | 2023-05-22 | 2023-05-22 | GoP | 57014.48 | 57014.48 | 0 | 56866 | 56866 | 0 | [7 empty] | N/A
| Training Expenses | [19 empty] | 14FSFO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2023-05-02 | 2023-05-03 | 2023-05-16 | 2023-05-22 | 2023-05-22 | GoP | 42000 | 42000 | 0 | 41871.5 | 41871.5 | 0 | [7 empty] | N/A
| Other Supplies and Materials Expenses | [19 empty] | 14FSFO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2023-05-02 | 2023-05-03 | 2023-05-18 | 2023-05-25 | 2023-05-25 | GoP | 40000 | 40000 | 0 | 39800 | 39800 | 0 | [7 empty] | N/A
| Mobile Expenses | [19 empty] | 14FSFO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2023-05-02 | 2023-05-03 | 2023-05-18 | 2023-05-25 | 2023-05-25 | GoP | 21000 | 21000 | 0 | 20974 | 20974 | 0 | [7 empty] | N/A
| Office Supplies Expenses | [19 empty] | 14FSFO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2023-05-02 | 2023-05-03 | 2023-05-16 | 2023-05-23 | 2023-05-23 | GoP | 7000 | 7000 | 0 | 6960 | 6960 | 0 | [7 empty] | N/A
| Representation Expenses | [19 empty] | 14FSFO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2023-05-02 | 2023-05-03 | 2023-05-16 | 2023-05-23 | 2023-05-23 | GoP | 16200 | 16200 | 0 | 16130 | 16130 | 0 | [7 empty] | N/A
| Representation Expenses | [19 empty] | 14FSFO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2023-05-02 | 2023-05-03 | 2023-05-16 | 2023-05-23 | 2023-05-23 | GoP | 19000 | 19000 | 0 | 18949 | 18949 | 0 | [7 empty] | N/A
| Semi-Expendable Furniture and Fixture | [19 empty] | 14FSFO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2023-05-09 | 2023-05-10 | 2023-05-16 | 2023-05-22 | 2023-05-22 | GoP | 10000 | 10000 | 0 | 9999 | 9999 | 0 | [7 empty] | N/A
| Repair and Maintenance of Office Equipment | [19 empty] | 14FSFO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2023-05-23 | 2023-05-24 |  |  |  | GoP | 8800 | 8800 | 0 | 8740 | 8740 | 0 | [7 empty] | N/A
| SD of 8 pcs Door Knob & 21 others | [19 empty] | 15FSFO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2023-03-30 | 2023-03-30 | 2023-05-02 | 2023-05-12 | 2023-05-12 | GoP | 106000 | 106000 | 0 | 105280 | 105280 | 0 | [7 empty] | N/A
| SD of 150 pcs C-channel and 38 others | [19 empty] | 15FSFO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2023-03-30 | 2023-03-30 | 2023-05-02 | 2023-05-12 | 2023-05-12 | GoP | 400170 | 400170 | 0 | 398670 | 398670 | 0 | [7 empty] | N/A
| R/M EP Barraks | [19 empty] | 16FSFO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2023-03-17 | N/A | 2023-04-03 | 2023-04-13 | 2023-04-13 | Special Release | 149900 | 149900 | 0 | 149772 | 149772 | 0 | [7 empty] | N/A
| R/M Building | [19 empty] | 16FSFO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2023-03-28 | N/A | 2023-04-17 | 2023-04-19 | 2023-04-19 | Special Release | 260000 | 260000 | 0 | 259763.75 | 259763.75 | 0 | [7 empty] | N/A
| Construction Material & Supplies | [19 empty] | 17FSFO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2023-01-31 | 2023-01-31 | 2023-03-02 | 2023-03-07 | 2023-03-07 | GoP | 180950 | 180950 | 0 | 180340 | 180340 | 0 | [7 empty] | N/A
| Training Supplies | [19 empty] | 17FSFO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2023-02-13 | 2023-02-13 | 2023-03-07 | 2023-03-13 | 2023-03-13 | GoP | 30000 | 30000 | 0 | 29685 | 29685 | 0 | [7 empty] | N/A
| Vehicle Parts & Acc | [19 empty] | 17FSFO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2023-02-07 | 2023-02-07 | 2023-03-07 | 2023-03-13 | 2023-03-13 | GoP | 40000 | 40000 | 0 | 39600 | 39600 | 0 | [7 empty] | N/A
| Grocery Items | [19 empty] | 17FSFO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2023-02-14 | 2023-02-14 | 2023-03-07 | 2023-03-13 | 2023-03-13 | GoP | 58000 | 58000 | 0 | 57694 | 57694 | 0 | [7 empty] | N/A
| Grocery Items | [19 empty] | 17FSFO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2023-04-18 | 2023-04-18 | 2023-05-04 | 2023-05-11 | 2023-05-11 | GoP | 4250 | 4250 | 0 | 4115 | 4115 | 0 | [7 empty] | N/A
| Grocery Items | [19 empty] | 17FSFO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2023-04-20 | 2023-04-20 | 2023-05-17 | 2023-05-25 | 2023-05-25 | GoP | 77000 | 77000 | 0 | 76600 | 76600 | 0 | [7 empty] | N/A
| Training Supplies | [19 empty] | 17FSFO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2023-04-20 | 2023-04-20 | 2023-05-23 | 2023-05-30 | 2023-05-30 | GoP | 90000 | 90000 | 0 | 89450 | 89450 | 0 | [7 empty] | N/A
| Other Supplies | [19 empty] | 17FSFO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2023-04-24 | 2023-04-24 | 2023-05-22 | 2023-05-30 | 2023-05-30 | GoP | 4250 | 4250 | 0 | 4199 | 4199 | 0 | [7 empty] | N/A
Total Alloted Budget of Procurement Activities | [37 empty] | 14023867.39
Total Contract Price of Procurement Actitvites Conducted | [40 empty] | 13897710.4
Total Savings (Total Alloted Budget - Total Contract Price) | [37 empty] | 126156.99
0N-GOING PROCUREMENT ACTIVITIES
Total Alloted Budget of On-going Procurement Activities | [37 empty] | #REF!
| Prepared by: | [32 empty] | Certified Correct By | [6 empty] | Noted By
| Jojiemae G Collado | [32 empty] | JESUS B BINARAO | [6 empty] | SEIGFRED C TUBALADO
| MSg (FS) PA | [32 empty] | Major (FS) PA | [6 empty] | Colonel (MNSA) INF PA
| Logistics, NCO | [32 empty] | Logistics, Officer | [6 empty] | Director, FCPA

## Sheet1 (hidden)
Competitive Bidding | GoP | YES
Limited Source Bidding | Foreign | NO
Direct Contracting | Special Purpose Fund
Repeat Order | Corporate Budget
Shopping | Income
NP-53.1 Two Failed Biddings | Others
NP-53.2 Emergency Cases
NP-53.3 Take-Over of Contracts
NP-53.4 Adjacent or Contiguous
NP-53.5 Agency-to-Agency
NP-53.6 Scientific, Scholarly, Artistic Work, Exclusive Technology and Media Services
NP-53.7 Highly Technical Consultants
NP-53.8 Defense Cooperation Agreement
NP-53.9 - Small Value Procurement
NP-53.10 Lease of Real Property and Venue
NP-53.11 NGO Participation
NP-53.12 Community Participation
NP-53.13 UN Agencies, Int'l Organizations or International Financing Institutions
Others - Foreign-funded procurement