## pmr
|  | ANNEX A | [14 empty] | ANNEX B
|  | Department of Budget and Management Annual Procurement Plan for FY 2006 | [14 empty] | 11ID, PA |  |  |  | Procurement Monitoring Report from 01 July - 31 December 2022
Code (PAP) | Procurement Project | PMO/ End-User | Mode of Procurement | Schedule for Each Procurement Activity | [11 empty] | Source of Funds | PMO/ End-User | Is this an Early Procurement Activity? | Mode of Procurement | Actual Procurement Activity | [12 empty] | Source of Funds | ABC (PhP) |  |  | Contract Cost (PhP) |  |  | List of Invited Observers | Date of Receipt of Invitation | [5 empty] | Remarks (Explaining changes from the APP)
|  |  |  | Pre-Proc Conference | Ads/Post of IAEB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Contract Award | Contract Signing | Notice to Proceed | Delivery/ Accept | Payment Process |  |  |  |  | Pre-Proc Conference | Ads/Post of IB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Date of BAC Resolution Recommending Award | Notice of Award | Contract Signing | Notice to Proceed | Delivery/ Completion | Inspection & Acceptance |  | Total | MOOE | CO | Total | MOOE | CO |  | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Delivery/ Completion/ Acceptance (If applicable)
COMPLETED PROCUREMENT ACTIVITIES
08-593 | R/M Bldg | [15 empty] | 11DTS | NO | Negotiated 53.11 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-04 | 2022-08-04 | 2022-08-16 | 2022-08-26 | 2022-08-26 | MOOE | 20000 | 20000 |  | 19730 | 19730 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
08-598 | Med,Den & Lab Sup Exp | [15 empty] | 11DCAU | NO | Negotiated 53.14 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-04 | 2022-08-04 | 2022-08-16 | 2022-08-26 | 2022-08-26 | MOOE | 22000 | 22000 |  | 21700 | 21700 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
08-603 | Training Expenses | [15 empty] | 11SSBn | NO | Negotiated 53.16 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-04 | 2022-08-04 | 2022-08-16 | 2022-08-26 | 2022-08-26 | MOOE | 32000 | 32000 |  | 31600 | 31600 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
08-604 | Semi-Exp Other Mach & Eqpmt | [15 empty] | 11SSBn | NO | Negotiated 53.17 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-04 | 2022-08-04 | 2022-08-17 | 2022-08-26 | 2022-08-26 | MOOE | 20000 | 20000 |  | 19700 | 19700 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
08-605 | Office Supplies | [15 empty] | 11SSBn | NO | Negotiated 53.18 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-04 | 2022-08-04 | 2022-08-17 | 2022-08-26 | 2022-08-26 | MOOE | 14000 | 14000 |  | 13680 | 13680 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
08-606 | Training Expenses | [15 empty] | 1102Bde | NO | Negotiated 53.19 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-05 | 2022-08-05 | 2022-08-17 | 2022-08-25 | 2022-08-25 | MOOE | 122000 | 122000 |  | 121525 | 121525 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
08-607 | Office Supplies | [15 empty] | 1102Bde | NO | Negotiated 53.20 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-05 | 2022-08-05 | 2022-08-17 | 2022-08-25 | 2022-08-25 | MOOE | 50000 | 50000 |  | 49700 | 49700 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
08-608 | Training Expenses | [15 empty] | 11DTS | NO | Negotiated 53.21 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-05 | 2022-08-05 | 2022-08-17 | 2022-08-25 | 2022-08-25 | MOOE | 123630 | 123630 |  | 123050 | 123050 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
08-609 | R/M Other Mach & Eqpmt | [15 empty] | 1103Bde | NO | Negotiated 53.22 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-05 | 2022-08-05 | 2022-08-17 | 2022-08-26 | 2022-08-26 | MOOE | 60000 | 60000 |  | 59670 | 59670 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
08-610 | R/M Bldg | [15 empty] | 1103Bde | NO | Negotiated 53.23 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-05 | 2022-08-05 | 2022-08-17 | 2022-08-26 | 2022-08-26 | MOOE | 50000 | 50000 |  | 49626 | 49626 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
08-611 | Representation Expenses | [15 empty] | 15CMO | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-05 | 2022-08-05 | 2022-08-17 | 2022-08-25 | 2022-08-25 | MOOE | 59250 | 59250 |  | 58920 | 58920 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
08-613 | Representation Expenses | [15 empty] | 11DCAU | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-05 | 2022-08-05 | 2022-08-17 | 2022-08-26 | 2022-08-26 | MOOE | 100000 | 100000 |  | 99350 | 99350 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
08-614 | Training Expenses | [15 empty] | 11DCAU | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-05 | 2022-08-05 | 2022-08-17 | 2022-08-26 | 2022-08-26 | MOOE | 87050 | 87050 |  | 86640 | 86640 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
08-619 | Representation Expenses | [15 empty] | 11SSBn | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-05 | 2022-08-05 | 2022-08-17 | 2022-08-26 | 2022-08-26 | MOOE | 116500 | 116500 |  | 116015 | 116015 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
08-628 | Semi-Exp ICT Eqpmt | [15 empty] | 11ID | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-12 | 2022-08-12 | 2022-08-31 | 2022-09-08 | 2022-09-08 | MOOE | 84530 | 84530 |  | 84180 | 84180 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
08-631 | R/M Motor Vehicles | [15 empty] | 11DTS | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-12 | 2022-08-12 | 2022-08-31 | 2022-09-08 | 2022-09-08 | MOOE | 75000 | 75000 |  | 74600 | 74600 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
08-632 | Training Expenses | [15 empty] | 32IB | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-12 | 2022-08-12 | 2022-08-31 | 2022-09-08 | 2022-09-08 | MOOE | 118000 | 118000 |  | 117036 | 117036 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
08-633 | Training Expenses | [15 empty] | 1103Bde | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-12 | 2022-08-12 | 2022-08-31 | 2022-09-08 | 2022-09-08 | MOOE | 222000 | 222000 |  | 220750 | 220750 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
08-634 | Representation Expenses | [15 empty] | 1103Bde | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-12 | 2022-08-12 | 2022-08-31 | 2022-09-08 | 2022-09-08 | MOOE | 190000 | 190000 |  | 189050 | 189050 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
08-636 | Semi-Exp ICT Eqpmt | [15 empty] | 11MIB | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-19 | 2022-08-19 | 2022-08-31 | 2022-09-08 | 2022-09-08 | MOOE | 35000 | 35000 |  | 34580 | 34580 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
08-637 | R/M Bldg | [15 empty] | 11MIB | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-19 | 2022-08-19 | 2022-08-31 | 2022-09-08 | 2022-09-08 | MOOE | 36500 | 36500 |  | 36350 | 36350 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
09-642 | R/M Bldg | [15 empty] | HHSBn | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-01 | 2022-09-01 | 2022-09-16 | 2022-09-21 | 2022-09-21 | MOOE | 40585 | 40585 |  | 40285 | 40285 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
09-643 | Semi-Exp Other Mach | [15 empty] | HHSBn | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-01 | 2022-09-01 | 2022-09-16 | 2022-09-21 | 2022-09-21 | MOOE | 30000 | 30000 |  | 29750 | 29750 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
09-644 | Semi-Exp ICT Eqpmt | [15 empty] | HHSBn | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-01 | 2022-09-01 | 2022-09-16 | 2022-09-21 | 2022-09-21 | MOOE | 37500 | 37500 |  | 37100 | 37100 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
09-645 | Training Expenses | [15 empty] | 11MIB | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-01 | 2022-09-01 | 2022-09-16 | 2022-09-21 | 2022-09-21 | MOOE | 30000 | 30000 |  | 29800 | 29800 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
09-646 | Representation Expenses | [15 empty] | 45IB | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-01 | 2022-09-01 | 2022-09-16 | 2022-09-21 | 2022-09-21 | MOOE | 11250 | 11250 |  | 11190 | 11190 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
09-647 | Office Supplies | [15 empty] | 45IB | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-01 | 2022-09-01 | 2022-09-16 | 2022-09-21 | 2022-09-21 | MOOE | 45000 | 45000 |  | 44776 | 44776 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
09-650 | Cell Card | [15 empty] | 45IB | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-01 | 2022-09-01 | 2022-09-16 | 2022-09-21 | 2022-09-21 | MOOE | 5000 | 5000 |  | 4950 | 4950 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
09-652 | R/M Motor Vehicles | [15 empty] | 1102Bde | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-05 | 2022-09-05 | 2022-09-23 | 24/10/20222 | 2022-11-07 | MOOE | 297700 | 297700 |  | 295900 | 295900 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
09-654 | R/M ICT Eqpmt | [15 empty] | 11DTS | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-05 | 2022-09-05 | 2022-09-23 | 2022-11-07 | 2022-11-23 | MOOE | 60000 | 60000 |  | 59600 | 59600 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
09-655 | Training Expenses | [15 empty] | 45IB | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-05 | 2022-09-05 | 2022-09-23 | 2022-11-07 | 2022-11-23 | MOOE | 125500 | 125500 |  | 124170 | 124170 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
09-656 | Other Supplies | [15 empty] | 45IB | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-05 | 2022-09-05 | 2022-09-23 | 2022-09-29 | 2022-09-29 | MOOE | 81000 | 81000 |  | 80655 | 80655 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
09-659 | R/M Motor Vehicles | [15 empty] | 1103Bde | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-05 | 2022-09-05 | 2022-09-23 | 2022-09-29 | 2022-09-29 | MOOE | 110000 | 110000 |  | 109200 | 109200 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
09-661 | R/M Motor Vehicles | [15 empty] | HHSBn | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-05 | 2022-09-05 | 2022-09-23 | 2022-09-29 | 2022-09-29 | MOOE | 150850 | 150850 |  | 149850 | 149850 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
09-662 | Semi-Exp Machinery | [15 empty] | 11DCAU | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-05 | 2022-09-05 | 2022-09-23 | 2022-09-29 | 2022-09-29 | MOOE | 80000 | 80000 |  | 79150 | 79150 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
09-663 | R/M Motor Vehicles | [15 empty] | 11DCAU | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-05 | 2022-09-05 | 2022-09-23 | 2022-09-29 | 2022-09-29 | MOOE | 60000 | 60000 |  | 59500 | 59500 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
09-668 | R/M Bldg | [15 empty] | 11MIB | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-15 | 2022-09-15 | 2022-09-30 | 2022-09-29 | 2022-09-29 | MOOE | 28750 | 28750 |  | 28350 | 28350 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
09-669 | Semi-Exp DRRO | [15 empty] | 41IB | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-15 | 2022-09-15 | 2022-09-30 | 2022-09-29 | 2022-09-29 | MOOE | 20000 | 20000 |  | 19700 | 19700 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
09-670 | Mobile Exp | [15 empty] | HHSBn | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-15 | 2022-09-15 | 2022-09-30 | 2022-09-29 | 2022-09-29 | MOOE | 20000 | 20000 |  | 19920 | 19920 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
09-671 | Drugs and Med Exp | [15 empty] | 45IB | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-15 | 2022-09-15 | 2022-09-30 | 2022-09-29 | 2022-09-29 | MOOE | 23000 | 23000 |  | 22700 | 22700 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
09-672 | Mobile Exp | [15 empty] | 45IB | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-15 | 2022-09-15 | 2022-09-30 | 2022-09-29 | 2022-09-29 | MOOE | 10000 | 10000 |  | 9800 | 9800 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
09-673 | R/M ICT Eqpmt | [15 empty] | 45IB | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-15 | 2022-09-15 | 2022-09-30 | 2022-09-29 | 2022-09-29 | MOOE | 30000 | 30000 |  | 29850 | 29850 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
09-674 | Office Supplies | [15 empty] | 101IB | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-15 | 2022-09-15 | 2022-09-30 | 2022-09-29 | 2022-09-29 | MOOE | 35000 | 35000 |  | 34600 | 34600 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
09-675 | Other Supplies | [15 empty] | 101IB | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-15 | 2022-09-15 | 2022-09-30 | 2022-09-29 | 2022-09-29 | MOOE | 28385 | 28385 |  | 28095 | 28095 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
09-676 | Mobile Exp | [15 empty] | 101IB | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-15 | 2022-09-15 | 2022-09-30 | 2022-09-29 | 2022-09-29 | MOOE | 17000 | 17000 |  | 16920 | 16920 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
09-677 | Training Expenses | [15 empty] | 101IB | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-15 | 2022-09-15 | 2022-09-30 | 2022-09-29 | 2022-09-29 | MOOE | 10000 | 10000 |  | 9800 | 9800 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
09-679 | R/M ICT Eqpmt | [15 empty] | 15CMO | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-16 | 2022-09-16 | 2022-10-27 | 2022-11-07 | 2022-11-07 | MOOE | 50000 | 50000 |  | 49600 | 49600 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
09-680 | Training Expenses | [15 empty] | 15CMO | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-16 | 2022-09-16 | 2022-10-27 | 2022-11-07 | 2022-11-07 | MOOE | 150000 | 150000 |  | 149350 | 149350 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
09-684 | R/M Other Structures | [15 empty] | 1103Bde | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-16 | 2022-09-16 | 2022-10-27 | 2022-11-07 | 2022-11-07 | MOOE | 100000 | 100000 |  | 99550 | 99550 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
09-687 | Med,Den & Lab Sup Exp | [15 empty] | 45IB | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-16 | 2022-09-16 | 2022-10-27 | 2022-11-07 | 2022-11-07 | MOOE | 100000 | 100000 |  | 99308 | 99308 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
09-691 | Training Expenses | [15 empty] | 101IB | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-16 | 2022-09-16 | 2022-10-27 | 2022-11-07 | 2022-11-07 | MOOE | 141500 | 141500 |  | 140920 | 140920 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
09-692 | Semi-Exp ICT Eqpmt | [15 empty] | 11ID | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-16 | 2022-09-16 | 2022-10-27 | 2022-11-07 | 2022-11-07 | MOOE | 377747 | 377747 |  | 376640 | 376640 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
09-694 | Other Supplies | [15 empty] | 100IB | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-21 | 2022-09-21 | 2022-10-27 | 2022-11-07 | 2022-11-07 | MOOE | 28500 | 28500 |  | 28185 | 28185 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
09-695 | Representation Expenses | [15 empty] | 100IB | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-21 | 2022-09-21 | 2022-10-27 | 2022-11-07 | 2022-11-07 | MOOE | 22800 | 22800 |  | 22400 | 22400 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
09-696 | Mobile Exp | [15 empty] | 35IB | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-21 | 2022-09-21 | 2022-10-27 | 2022-11-07 | 2022-11-07 | MOOE | 15000 | 15000 |  | 14940 | 14940 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
09-697 | Cable Expenses | [15 empty] | 1101Bde | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-21 | 2022-09-21 | 2022-10-27 | 2022-11-07 | 2022-11-07 | MOOE | 4400 | 4400 |  | 4300 | 4300 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
09-698 | R/M Commo Eqpmt | [15 empty] | 1101Bde | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-21 | 2022-09-21 | 2022-10-27 | 2022-11-07 | 2022-11-07 | MOOE | 40000 | 40000 |  | 39680 | 39680 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
09-699 | Med,Den & Lab Sup Exp | [15 empty] | 1101Bde | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-21 | 2022-09-21 | 2022-10-27 | 2022-11-07 | 2022-11-07 | MOOE | 42700 | 42700 |  | 42220 | 42220 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
09-700 | Semi-Exp ICT Eqpmt | [15 empty] | 1101Bde | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-21 | 2022-09-21 | 2022-10-27 | 2022-11-07 | 2022-11-07 | MOOE | 7000 | 7000 |  | 6850 | 6850 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
09-702 | R/M Other Structures | [15 empty] | 1101Bde | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-23 | 2022-09-23 | 2022-10-27 | 2022-11-07 | 2022-11-07 | MOOE | 100000 | 100000 |  | 99475 | 99475 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
09-703 | R/M Motor Vehicles | [15 empty] | 45IB | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-23 | 2022-09-23 | 2022-10-27 | 2022-11-07 | 2022-11-07 | MOOE | 90000 | 90000 |  | 89540 | 89540 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
09-704 | Representation Expenses | [15 empty] | 41IB | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-23 | 2022-09-23 | 2022-10-27 | 2022-11-07 | 2022-11-07 | MOOE | 108000 | 108000 |  | 107450 | 107450 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
09-705 | R/M Bldg | [15 empty] | 41IB | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-23 | 2022-09-23 | 2022-10-27 | 2022-11-07 | 2022-11-07 | MOOE | 205000 | 205000 |  | 204200 | 204200 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
09-706 | Training Expenses | [15 empty] | 41IB | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-23 | 2022-09-23 | 2022-10-27 | 2022-11-07 | 2022-11-07 | MOOE | 72000 | 72000 |  | 71520 | 71520 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
09-710 | Med,Den & Lab Sup Exp | [15 empty] | 100IB | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-23 | 2022-09-23 | 2022-10-27 | 2022-11-07 | 2022-11-07 | MOOE | 80000 | 80000 |  | 79460 | 79460 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
09-711 | Training Expenses | [15 empty] | 100IB | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-23 | 2022-09-23 | 2022-10-27 | 2022-11-07 | 2022-11-07 | MOOE | 141500 | 141500 |  | 140972 | 140972 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
09-713 | Training Expenses | [15 empty] | 35IB | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-23 | 2022-09-23 | 2022-10-27 | 2022-11-07 | 2022-11-07 | MOOE | 66350 | 66350 |  | 65840 | 65840 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
09-714 | Representation Expenses | [15 empty] | 35IB | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-23 | 2022-09-23 | 2022-10-27 | 2022-11-07 | 2022-11-07 | MOOE | 112800 | 112800 |  | 112232 | 112232 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
09-719 | Semi-Exp ICT Eqpmt | [15 empty] | 11ID | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-12 | 2022-08-12 | 2022-08-31 | 2022-09-08 | 2022-09-08 | MOOE | 84530 | 84530 |  | 84180 | 84180 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
09-721 | R/M Motor Vehicles | [15 empty] | 11DTS | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-12 | 2022-08-12 | 2022-08-31 | 2022-09-08 | 2022-09-08 | MOOE | 75000 | 75000 |  | 74600 | 74600 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
09-722 | Training Expenses | [15 empty] | 32IB | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-12 | 2022-08-12 | 2022-08-31 | 2022-09-08 | 2022-09-08 | MOOE | 118000 | 118000 |  | 117036 | 117036 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
09-723 | Training Expenses | [15 empty] | 1103Bde | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-12 | 2022-08-12 | 2022-08-31 | 2022-09-08 | 2022-09-08 | MOOE | 222000 | 222000 |  | 220750 | 220750 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
09-724 | Representation Expenses | [15 empty] | 1103Bde | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-12 | 2022-08-12 | 2022-08-31 | 2022-09-08 | 2022-09-08 | MOOE | 190000 | 190000 |  | 189050 | 189050 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
09-726 | Semi-Exp ICT Eqpmt | [15 empty] | 11MIB | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-19 | 2022-08-19 | 2022-08-31 | 2022-09-08 | 2022-09-08 | MOOE | 35000 | 35000 |  | 34580 | 34580 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
09-727 | R/M Bldg | [15 empty] | 11MIB | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-19 | 2022-08-19 | 2022-08-31 | 2022-09-08 | 2022-09-08 | MOOE | 36500 | 36500 |  | 36350 | 36350 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
09-736 | R/M Bldg | [15 empty] | HHSBn | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-01 | 2022-09-01 | 2022-09-16 | 2022-09-21 | 2022-09-21 | MOOE | 40585 | 40585 |  | 40285 | 40285 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
09-737 | Semi-Exp Other Mach | [15 empty] | HHSBn | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-01 | 2022-09-01 | 2022-09-16 | 2022-09-21 | 2022-09-21 | MOOE | 30000 | 30000 |  | 29750 | 29750 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
09-738 | Semi-Exp ICT Eqpmt | [15 empty] | HHSBn | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-01 | 2022-09-01 | 2022-09-16 | 2022-09-21 | 2022-09-21 | MOOE | 37500 | 37500 |  | 37100 | 37100 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
09-739 | Training Expenses | [15 empty] | 11MIB | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-01 | 2022-09-01 | 2022-09-16 | 2022-09-21 | 2022-09-21 | MOOE | 30000 | 30000 |  | 29800 | 29800 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
09-740 | Representation Expenses | [15 empty] | 45IB | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-01 | 2022-09-01 | 2022-09-16 | 2022-09-21 | 2022-09-21 | MOOE | 11250 | 11250 |  | 11190 | 11190 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
09-741 | Office Supplies | [15 empty] | 45IB | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-01 | 2022-09-01 | 2022-09-16 | 2022-09-21 | 2022-09-21 | MOOE | 45000 | 45000 |  | 44776 | 44776 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
10-744 | Cell Card | [15 empty] | 45IB | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-01 | 2022-09-01 | 2022-09-16 | 2022-09-21 | 2022-09-21 | MOOE | 5000 | 5000 |  | 4950 | 4950 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
10-745 | R/M Motor Vehicles | [15 empty] | 1102Bde | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-05 | 2022-09-05 | 2022-09-23 | 2022-11-25 | 2023-12-09 | MOOE | 297700 | 297700 |  | 295900 | 295900 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
10-747 | R/M ICT Eqpmt | [15 empty] | 11DTS | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-05 | 2022-09-05 | 2022-09-23 | 2022-11-25 | 2023-12-09 | MOOE | 60000 | 60000 |  | 59600 | 59600 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
10-749 | Training Expenses | [15 empty] | 45IB | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-05 | 2022-09-05 | 2022-09-23 | 2022-11-25 | 2023-12-09 | MOOE | 125500 | 125500 |  | 124170 | 124170 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
10-750 | Other Supplies | [15 empty] | 45IB | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-05 | 2022-09-05 | 2022-09-23 | 2022-09-29 | 2022-09-29 | MOOE | 81000 | 81000 |  | 80655 | 80655 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
10-754 | R/M Motor Vehicles | [15 empty] | 1103Bde | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-05 | 2022-09-05 | 2022-09-23 | 2022-09-29 | 2022-09-29 | MOOE | 110000 | 110000 |  | 109200 | 109200 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
10-759 | R/M Motor Vehicles | [15 empty] | HHSBn | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-05 | 2022-09-05 | 2022-09-23 | 2022-09-29 | 2022-09-29 | MOOE | 150850 | 150850 |  | 149850 | 149850 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
10-760 | Semi-Exp Machinery | [15 empty] | 11DCAU | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-05 | 2022-09-05 | 2022-09-23 | 2022-09-29 | 2022-09-29 | MOOE | 80000 | 80000 |  | 79150 | 79150 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
10-761 | R/M Motor Vehicles | [15 empty] | 11DCAU | NO | Negotiated 53.10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-05 | 2022-09-05 | 2022-09-23 | 2022-09-29 | 2022-09-29 | MOOE | 60000 | 60000 |  | 59500 | 59500 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
09-762 | R/M Bldg | [15 empty] | 11ID | NO | Negotiated 53.11 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-05 | 2022-09-05 | 2022-09-23 | 2022-09-29 | 2022-09-29 | MOOE | 417000 | 417000 |  | 415810 | 415810 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
10-764 | ICT Software Subscription | [15 empty] | 101IB | NO | Negotiated 53.12 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-05 | 2022-09-05 | 2022-09-23 | 2022-09-29 | 2022-09-29 | MOOE | 3050 | 3050 |  | 3000 | 3000 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
10-765 | Mobile Exp | [15 empty] | 1103Bde | NO | Negotiated 53.13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-05 | 2022-09-05 | 2022-09-23 | 2022-12-07 | 2022-12-07 | MOOE | 36000 | 36000 |  | 35784 | 35784 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
10-766 | R/M Bldg | [15 empty] | 11MIB | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-15 | 2022-09-15 | 2022-09-30 | 2022-12-07 | 2022-12-07 | MOOE | 28750 | 28750 |  | 28350 | 28350 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
10-767 | Semi-Exp DRRO | [15 empty] | 41IB | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-15 | 2022-09-15 | 2022-09-30 | 2022-12-07 | 2022-12-07 | MOOE | 20000 | 20000 |  | 19700 | 19700 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
10-768 | Mobile Exp | [15 empty] | HHSBn | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-15 | 2022-09-15 | 2022-09-30 | 2022-12-07 | 2022-12-07 | MOOE | 20000 | 20000 |  | 19920 | 19920 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
10-769 | Drugs and Med Exp | [15 empty] | 45IB | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-15 | 2022-09-15 | 2022-09-30 | 2022-12-07 | 2022-12-07 | MOOE | 23000 | 23000 |  | 22700 | 22700 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
10-770 | Mobile Exp | [15 empty] | 45IB | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-15 | 2022-09-15 | 2022-09-30 | 2022-12-07 | 2022-12-07 | MOOE | 10000 | 10000 |  | 9800 | 9800 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
10-771 | R/M ICT Eqpmt | [15 empty] | 45IB | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-15 | 2022-09-15 | 2022-09-30 | 2022-12-07 | 2022-12-07 | MOOE | 30000 | 30000 |  | 29850 | 29850 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
10-775 | Office Supplies | [15 empty] | 101IB | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-15 | 2022-09-15 | 2022-09-30 | 2022-12-07 | 2022-12-07 | MOOE | 35000 | 35000 |  | 34600 | 34600 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
10-776 | Other Supplies | [15 empty] | 101IB | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-15 | 2022-09-15 | 2022-09-30 | 2022-12-07 | 2022-12-07 | MOOE | 28385 | 28385 |  | 28095 | 28095 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
10-777 | Mobile Exp | [15 empty] | 101IB | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-15 | 2022-09-15 | 2022-09-30 | 2022-12-07 | 2022-12-07 | MOOE | 17000 | 17000 |  | 16920 | 16920 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
10-778 | Training Expenses | [15 empty] | 101IB | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-15 | 2022-09-15 | 2022-09-30 | 2022-12-07 | 2022-12-07 | MOOE | 10000 | 10000 |  | 9800 | 9800 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
10-782 | R/M ICT Eqpmt | [15 empty] | 15CMO | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-16 | 2022-09-16 | 2022-09-30 | 2022-12-07 | 2022-12-07 | MOOE | 50000 | 50000 |  | 49600 | 49600 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
10-783 | Training Expenses | [15 empty] | 15CMO | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-16 | 2022-09-16 | 2022-11-25 | 2022-12-09 | 2022-12-09 | MOOE | 150000 | 150000 |  | 149350 | 149350 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
10-794 | R/M Other Structures | [15 empty] | 1103Bde | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-16 | 2022-09-16 | 2022-11-25 | 2022-12-09 | 2022-12-09 | MOOE | 100000 | 100000 |  | 99550 | 99550 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
10-798 | Med,Den & Lab Sup Exp | [15 empty] | 45IB | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-16 | 2022-09-16 | 2022-11-25 | 2022-12-09 | 2022-12-09 | MOOE | 100000 | 100000 |  | 99308 | 99308 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
10-806 | Training Expenses | [15 empty] | 101IB | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-16 | 2022-09-16 | 2022-11-25 | 2022-12-09 | 2022-12-09 | MOOE | 141500 | 141500 |  | 140920 | 140920 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
10-807 | Semi-Exp ICT Eqpmt | [15 empty] | 11ID | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-16 | 2022-09-16 | 2022-11-25 | 2022-12-09 | 2022-12-09 | MOOE | 377747 | 377747 |  | 376640 | 376640 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
10-809 | Other Supplies | [15 empty] | 100IB | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-21 | 2022-09-21 | 2022-11-25 | 2022-12-09 | 2022-12-09 | MOOE | 28500 | 28500 |  | 28185 | 28185 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
10-810 | Representation Expenses | [15 empty] | 100IB | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-21 | 2022-09-21 | 2022-11-25 | 2022-12-09 | 2022-12-09 | MOOE | 22800 | 22800 |  | 22400 | 22400 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
10-811 | Mobile Exp | [15 empty] | 35IB | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-21 | 2022-09-21 | 2022-11-25 | 2022-12-09 | 2022-12-09 | MOOE | 15000 | 15000 |  | 14940 | 14940 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
10-814 | Cable Expenses | [15 empty] | 1101Bde | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-21 | 2022-09-21 | 2022-11-25 | 2022-12-09 | 2022-12-09 | MOOE | 4400 | 4400 |  | 4300 | 4300 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
10-815 | R/M Commo Eqpmt | [15 empty] | 1101Bde | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-21 | 2022-09-21 | 2022-11-25 | 2022-12-09 | 2022-12-09 | MOOE | 40000 | 40000 |  | 39680 | 39680 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
10-815 | Med,Den & Lab Sup Exp | [15 empty] | 1101Bde | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-21 | 2022-09-21 | 2022-11-25 | 2022-12-09 | 2022-12-09 | MOOE | 42700 | 42700 |  | 42220 | 42220 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
10-818 | Semi-Exp ICT Eqpmt | [15 empty] | 1101Bde | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-21 | 2022-09-21 | 2022-11-25 | 2022-12-09 | 2022-12-09 | MOOE | 7000 | 7000 |  | 6850 | 6850 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
10-821 | R/M Other Structures | [15 empty] | 1101Bde | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-23 | 2022-09-23 | 2022-11-25 | 2022-12-09 | 2022-12-09 | MOOE | 100000 | 100000 |  | 99475 | 99475 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
10-822 | R/M Motor Vehicles | [15 empty] | 45IB | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-23 | 2022-09-23 | 2022-11-25 | 2022-12-09 | 2022-12-09 | MOOE | 90000 | 90000 |  | 89540 | 89540 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
10-822 | Representation Expenses | [15 empty] | 41IB | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-23 | 2022-09-23 | 2022-11-25 | 2022-12-09 | 2022-12-09 | MOOE | 108000 | 108000 |  | 107450 | 107450 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
10-823 | R/M Bldg | [15 empty] | 41IB | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-23 | 2022-09-23 | 2022-11-25 | 2022-12-09 | 2022-12-09 | MOOE | 205000 | 205000 |  | 204200 | 204200 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
10-825 | Training Expenses | [15 empty] | 41IB | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-23 | 2022-09-23 | 2022-11-25 | 2022-12-09 | 2022-12-09 | MOOE | 72000 | 72000 |  | 71520 | 71520 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
10-831 | Med,Den & Lab Sup Exp | [15 empty] | 100IB | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-23 | 2022-09-23 | 2022-11-25 | 2022-12-09 | 2022-12-09 | MOOE | 80000 | 80000 |  | 79460 | 79460 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
10-838 | Training Expenses | [15 empty] | 100IB | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-23 | 2022-09-23 | 2022-11-25 | 2022-12-09 | 2022-12-09 | MOOE | 141500 | 141500 |  | 140972 | 140972 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
10-850 | Representation Expenses | [15 empty] | 11SSBn | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-11 | 2022-11-11 | 2022-12-14 | 2022-12-15 | 2022-12-15 | MOOE | 127250 | 127250 |  | 22835 | 22835 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
11-856 | R/M ICT Eqpmt | [15 empty] | 11DCAU | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-15 | 2022-11-15 | 2022-12-14 | 2022-12-15 | 2022-12-15 | MOOE | 23000 | 23000 |  | 22835 | 22835 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
11-857 | Training Expenses | [15 empty] | 101IB | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-15 | 2022-11-15 | 2022-12-14 | 2022-12-15 | 2022-12-15 | MOOE | 50000 | 50000 |  | 49600 | 49600 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
11-863 | Representation Expenses | [15 empty] | 41IB | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-15 | 2022-11-15 | 2022-12-14 | 2022-12-15 | 2022-12-15 | MOOE | 72000 | 72000 |  | 71650 | 71650 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
11-866 | Semi-Exp ICT Eqpmt | [15 empty] | 11ID | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-15 | 2022-11-15 | 2022-12-14 | 2022-12-15 | 2022-12-15 | MOOE | 296250 | 296250 |  | 295500 | 295500 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
11-867 | Mil Pol & Traf Supplies | [15 empty] | 11ID | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-15 | 2022-11-15 | 2022-12-14 | 2022-12-15 | 2022-12-15 | MOOE | 75000 | 75000 |  | 74600 | 74600 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
11-868 | Semi-Exp ICT Eqpmt | [15 empty] | 11ID | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-15 | 2022-11-15 | 2022-12-14 | 2022-12-15 | 2022-12-15 | MOOE | 250147.4 | 250147.4 |  | 249500 | 249500 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
11-869 | Semi-Exp Commo Eqpmt | [15 empty] | 11ID | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-15 | 2022-11-15 | 2022-12-14 | 2022-12-15 | 2022-12-15 | MOOE | 90000 | 90000 |  | 89500 | 89500 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
11-871 | Semi-Exp ICT Eqpmt | [15 empty] | 15CMO | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-15 | 2022-11-15 | 2022-12-14 | 2022-12-15 | 2022-12-15 | MOOE | 147510 | 147510 |  | 146900 | 146900 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
11-872 | Med,Den & Lab Sup Exp | [15 empty] | 45IB | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-15 | 2022-11-15 | 2022-12-14 | 2022-12-15 | 2022-12-15 | MOOE | 50000 | 50000 |  | 49500 | 49500 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
11-873 | Med,Den & Lab Sup Exp | [15 empty] | 41IB | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-15 | 2022-11-15 | 2022-12-14 | 2022-12-15 | 2022-12-15 | MOOE | 50000 | 50000 |  | 49600 | 49600 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
11-880 | Semi-Exp ICT Eqpmt | [15 empty] | 101IB | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-22 | 2022-11-22 | 2022-12-14 | 2022-12-15 | 2022-12-15 | MOOE | 40000 | 40000 |  | 39500 | 39500 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
11-881 | Semi-Exp ICT Eqpmt | [15 empty] | 11ID | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-22 | 2022-11-22 | 2022-12-14 | 2022-12-15 | 2022-12-15 | MOOE | 40290 | 40290 |  | 40000 | 40000 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
11-885 | Med,Den & Lab Sup Exp | [15 empty] | 101IB | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-22 | 2022-11-22 | 2022-12-14 | 2022-12-15 | 2022-12-15 | MOOE | 35000 | 35000 |  | 34500 | 34500 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
11-900 | R/M Bldg | [15 empty] | 11DTS | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-22 | 2022-11-22 | 2022-12-14 | 2022-12-15 | 2022-12-15 | MOOE | 45000 | 45000 |  | 44730 | 44730 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
12-921 | OE-SE | [15 empty] | 11ID | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-29 | 2022-11-29 | 2023-12-23 | 2023-12-29 | 2023-12-29 | MOOE | 737437 | 737437 |  | 736442 | 736442 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
12-924 | RMB | [15 empty] | 21IB | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-29 | 2022-11-29 | 2023-12-23 | 2023-12-29 | 2023-12-29 | MOOE | 203500 | 203500 |  | 202850 | 202850 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
12-927 | RMOLI | [15 empty] | 11ID | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-29 | 2022-11-29 | 2023-12-23 | 2023-12-29 | 2023-12-29 | MOOE | 984643.29 | 984643.29 |  | 983613.29 | 983613.29 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
12-930 | RMB | [15 empty] | 11SSBn | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-29 | 2022-11-29 | 2023-12-23 | 2023-12-29 | 2023-12-29 | MOOE | 100000 | 100000 |  | 99466 | 99466 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
12-932 | ICT-SE | [15 empty] | 1101Bde | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-06 | 2022-12-06 | 2023-12-23 | 2023-12-29 | 2023-12-29 | MOOE | 55000 | 55000 |  | 54650 | 54650 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
12-933 | RMB | [15 empty] | 1101Bde | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-06 | 2022-12-06 | 2023-12-23 | 2023-12-29 | 2023-12-29 | MOOE | 100000 | 100000 |  | 99520 | 99520 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
12-934 | RMOME | [15 empty] | 1103Bde | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-06 | 2022-12-06 | 2023-12-23 | 2023-12-29 | 2023-12-29 | MOOE | 60000 | 60000 |  | 59760 | 59760 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
12-935 | RMICT | [15 empty] | 45IB | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-06 | 2022-12-06 | 2023-12-23 | 2023-12-29 | 2023-12-29 | MOOE | 30000 | 30000 |  | 29750 | 29750 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
12-940 | Representation Expenses | [15 empty] | 32IB | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-07 | 2022-12-07 | 2023-12-23 | 2023-12-29 | 2023-12-29 | MOOE | 22000 | 22000 |  | 21685 | 21685 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
12-941 | ICT-SE | [15 empty] | 11ID | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-07 | 2022-12-07 | 2023-12-23 | 2023-12-29 | 2023-12-29 | MOOE | 35000 | 35000 |  | 34750 | 34750 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
12-942 | RMICT | [15 empty] | 32IB | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-07 | 2022-12-07 | 2023-12-23 | 2023-12-29 | 2023-12-29 | MOOE | 30000 | 30000 |  | 29720 | 29720 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
12-947 | ICT-SE | [15 empty] | 11ID | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-07 | 2022-12-07 | 2023-12-23 | 2023-12-29 | 2023-12-29 | MOOE | 14999 | 14999 |  | 14900 | 14900 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
12-949 | RMICT | [15 empty] | 15CMO | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-07 | 2022-12-07 | 2023-12-23 | 2023-12-29 | 2023-12-29 | MOOE | 50000 | 50000 |  | 49680 | 49680 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
12-950 | Representation Expenses | [15 empty] | 1101Bde | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-07 | 2022-12-07 | 2023-12-23 | 2023-12-29 | 2023-12-29 | MOOE | 35000 | 35000 |  | 34685 | 34685 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
12-952 | ICT-SE | [15 empty] | 11MIB | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-07 | 2022-12-07 | 2023-12-23 | 2023-12-29 | 2023-12-29 | MOOE | 35000 | 35000 |  | 34720 | 34720 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
12-957 | OS | [15 empty] | 11ID | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-09 | 2022-12-09 | 2023-12-23 | 2023-12-29 | 2023-12-29 | MOOE | 197150 | 197150 |  | 196380 | 196380 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
12-958 | TE-M | [15 empty] | 11ID | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-09 | 2022-12-09 | 2023-12-23 | 2023-12-29 | 2023-12-29 | MOOE | 185000 | 185000 |  | 184380 | 184380 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
12-961 | RMOS | [15 empty] | 1101Bde | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-09 | 2022-12-09 | 2023-12-23 | 2023-12-29 | 2023-12-29 | MOOE | 145000 | 145000 |  | 144200 | 144200 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
[34 empty] | 13970200.69 | 13970200.69 |  | 13792907.29 | 13792907.29
Total Alloted Budget of Procurement Activities | [33 empty] | 13970200.69
Total Contract Price of Procurement Actitvites Conducted | [36 empty] | 13792907.29
Total Savings (Total Alloted Budget - Total Contract Price) | [33 empty] | 177293.4
0N-GOING PROCUREMENT ACTIVITIES
Total Alloted Budget of On-going Procurement Activities
| Prepared By: | [18 empty] | Certified Correct By: | [6 empty] | Noted By: | [11 empty] | APPROVED:
| Sgt Christian Junn G Mauro (OS) PA | [19 empty] | MSg Antonieto J Igmen (QMS) PA | [6 empty] | MAJ MICHAEL B DE GUIA (CE) PA | [10 empty] | Head of the Procuring Entity
| Operation, NCO | [19 empty] | First Seargent | [6 empty] | Commanding Officer
Formulas:
Contract Signing = [Notice of Award]

## Sheet1 (hidden)
Competitive Bidding | GoP | YES
Limited Source Bidding | Foreign | NO
Direct Contracting | Special Purpose Fund
Repeat Order | Corporate Budget
Shopping | Income
NP-53.1 Two Failed Biddings | Others
NP-53.2 Emergency Cases
NP-53.3 Take-Over of Contracts
NP-53.4 Adjacent or Contiguous
NP-53.5 Agency-to-Agency
NP-53.6 Scientific, Scholarly, Artistic Work, Exclusive Technology and Media Services
NP-53.7 Highly Technical Consultants
NP-53.8 Defense Cooperation Agreement
NP-53.9 - Small Value Procurement
NP-53.10 Lease of Real Property and Venue
NP-53.11 NGO Participation
NP-53.12 Community Participation
NP-53.13 UN Agencies, Int'l Organizations or International Financing Institutions
Others - Foreign-funded procurement