## Sheet1
ANNEX B
54EBDE,PA
114th CO, AFPPS Procurement Monitoring Report as of 19 December 2022
Code (PAP) | Procurement Project | PMO/ End-User | Is this an Early Procurement Activity? | Mode of Procurement | Actual Procurement Activity | [12 empty] | Source of Funds | ABC (PhP) |  |  | Contract Cost (PhP) |  |  | List of Invited Observers | Date of Receipt of Invitation | [5 empty] | Remarks (Explaining changes from the APP)
[5 empty] | Pre-Proc Conference | Ads/Post of IB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Date of BAC Resolution Recommending Award | Notice of Award | Contract Signing | Notice to Proceed | Delivery/ Completion | Inspection & Acceptance |  | Total | MOOE | CO | Total | MOOE | CO |  | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Delivery/ Completion/ Acceptance (If applicable)
COMPLETED PROCUREMENT ACTIVITIES
09-426 | R/M of Communication Eqpt | 54EBde,PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | 2022-09-30 | N/A | N/A | N/A | 2022-09-30 | N/A | 2022-10-13 | 2022-10-24 | 2022-10-24 | MOOE | 36861 | 36861 |  | 36734 | 36734 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
10-442 | R/M of Motor Vehicles | 545ECB, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | 2022-10-07 | N/A | N/A | N/A | 2022-10-07 | N/A | 2022-10-19 | 2027-10-25 | 2027-10-25 | MOOE | 30570 | 30570 |  | 30484 | 30484 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
10-449 | R/M of ICT Equipment | 54EBde,PA | NO | Negotiated 53.9 | N/A | 2022-10-11 | N/A | N/A | 2022-10-14 | N/A | N/A | N/A | 2022-10-14 | N/A | 2022-11-03 | 2022-11-07 | 2022-11-07 | MOOE | 100000 | 100000 |  | 99830 | 99830 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
10-451 | SEmi-Expendable Furnitures & Fixtures | 54EBde,PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | 2022-10-14 | N/A | N/A | N/A | 2022-10-14 | N/A | 2022-11-09 | 2022-11-11 | 2022-11-11 | MOOE | 13806 | 13806 |  | 13745 | 13745 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
10-452 | Training Expenses | 547EB, PA | NO | Negotiated 53.9 | N/A | 2022-10-15 | N/A | N/A | 2022-10-18 | N/A | N/A | N/A | 2022-10-18 | N/A | 2022-11-03 | 2022-11-07 | 2022-11-07 | MOOE | 80114 | 80114 |  | 80037 | 80037 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
10-454 | Office Supplies Expns | ESC, 54EBde,PA | NO | Shopping 52.1b | N/A | N/A | N/A | N/A | 2022-10-18 | N/A | N/A | N/A | 2022-10-18 | N/A | 2022-11-03 | 2022-11-07 | 2022-11-07 | MOOE | 3068.54 | 3068.54 |  | 3038.5 | 3038.5 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
10-458 | Printing and publication exp | 54EBde,PA | NO | Negotiated 53.9 | N/A | 2022-10-15 | N/A | N/A | 2022-10-18 | N/A | N/A | N/A | 2022-10-18 | N/A | 2022-11-03 | 2022-11-07 | 2022-11-07 | MOOE | 67872 | 67872 |  | 67757 | 67757 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
10-463 | Representation Expenses | 547EB, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | 2022-10-25 | N/A | N/A | N/A | 2022-10-25 | N/A | 2022-11-09 | 2022-11-11 | 2022-11-11 | MOOE | 20000 | 20000 |  | 19943 | 19943 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
10-464 | Representation Expenses | 549ECBn, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | 2022-10-25 | N/A | N/A | N/A | 2022-10-25 | N/A | 2022-11-09 | 2022-11-11 | 2022-11-11 | MOOE | 20000 | 20000 |  | 19933 | 19933 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
10-465 | Other Supplies & Material Expns | ESC, 54EBde,PA | NO | Negotiated 53.9 | N/A | 2022-10-21 | N/A | N/A | 2022-10-25 | N/A | N/A | N/A | 2022-10-25 | N/A | 2022-11-09 | 2022-11-11 | 2022-11-11 | MOOE | 90000 | 90000 |  | 89884 | 89884 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
10-467 | R/M of Motor Vehicles | 54EBde,PA | NO | Negotiated 53.9 | N/A | 2022-10-21 | N/A | N/A | 2022-10-25 | N/A | N/A | N/A | 2022-10-25 | N/A | 2022-11-09 | 2022-11-11 | 2022-11-11 | MOOE | 153510 | 153510 |  | 153348 | 153348 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
10-469 | Other Supplies & Material Expns | 54EBde,PA | NO | Negotiated 53.9 | N/A | 2022-10-21 | N/A | N/A | 2022-10-25 | N/A | N/A | N/A | 2022-10-25 | N/A | 2022-11-09 | 2022-11-11 | 2022-11-11 | Special Release | 100000 | 100000 |  | 99857.5 | 99857.5 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
10-471 | Drugs and Medicines Expns | 54EBde,PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | 2022-10-25 | N/A | N/A | N/A | 2022-10-25 | N/A | 2022-11-09 | 2022-11-11 | 2022-11-11 | MOOE | 46675 | 46675 |  | 46615 | 46615 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
10-472 | Admin & Operational Support | 545ECB, PA | NO | Negotiated 53.9 | N/A | 2022-10-21 | N/A | N/A | 2022-10-25 | N/A | N/A | N/A | 2022-10-25 | N/A | 2022-11-09 | 2022-11-16 | 2022-11-16 | Special Release | 175000 | 175000 |  | 174829 | 174829 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
10-473 | Representation Expenses | 545ECB, PA | NO | Negotiated 53.9 | N/A | 2022-10-21 | N/A | N/A | 2022-10-25 | N/A | N/A | N/A | 2022-10-25 | N/A | 2022-11-09 | 2022-11-21 | 2022-11-21 | MOOE | 159662 | 159662 |  | 159588 | 159588 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
10-488 | Representation Expenses | 545ECB, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | 2022-10-28 | N/A | N/A | N/A | 2022-10-28 | N/A | 2022-11-09 | 2022-11-16 | 2022-11-16 | Special Release | 20000 | 20000 |  | 19927.5 | 19927.5 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
[19 empty] | 1117138.54 | 1117138.54 |  | 1115550.5 | 1115550.5
Total Alloted Budget of Procurement Activities | [18 empty] | 1117138.54
Total Contract Price of Procurement Actitvites Conducted | [21 empty] | 1115550.5
Total Savings (Total Alloted Budget - Total Contract Price) | [18 empty] | 1588.04
0N-GOING PROCUREMENT ACTIVITIES
09-368 | R/M of Motor Vehicles | 547EB, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | 2022-09-06 | N/A | N/A | N/A | 2022-09-06 | N/A | 2022-09-16 | 2022-09-20 | 2022-09-20 | MOOE | 25160 | 25160 |  | 24990 | 24990 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | For Payment 08 Dec 22
10-450 | Semi-Expendable Office Equipment | 54EBde,PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | 2022-10-14 | N/A | N/A | N/A | 2022-10-14 | N/A | 2022-11-23 | 2022-11-25 | 2022-11-25 | MOOE | 8700 | 8700 |  | 8653 | 8653 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | For Payment 08 Dec 22
10-457 | Semi-Expendable ICT | 54EBde,PA | NO | Negotiated 53.9 | N/A | 2022-10-15 | N/A | N/A | 2022-10-18 | N/A | N/A | N/A | 2022-10-18 | N/A | 2022-11-09 | 2022-11-11 | 2022-11-11 | Special Release | 50000 | 50000 |  | 49861 | 49861 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | For CAC 12 Dec 22
11-489 | Office Supplies Expns | 54EBde,PA | NO | Shopping 52.1b | N/A | 2022-11-08 | N/A | N/A | 2022-11-11 | N/A | N/A | N/A | 2022-11-11 | N/A | N/A | N/A | N/A | MOOE | 76251 | 76251 |  | 76125.5 | 76125.5 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | For CAC 12 Dec 22
11-493 | R/M of Motor Vehicles | 54EBde,PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | 2022-11-11 | N/A | N/A | N/A | 2022-11-11 | N/A | N/A | N/A | N/A | MOOE | 14250 | 14250 |  | 14190 | 14190 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | For CAC 12 Dec 22
11-494 | Medical, Dental & LAB SUPPLIES Expns | 54EBde,PA | NO | Negotiated 53.9 | N/A | 2022-11-11 | N/A | N/A | 2022-11-14 | N/A | N/A | N/A | 2022-11-14 | N/A | N/A | N/A | N/A | Special Release | 492000 | 492000 |  | 491685 | 491685 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | For CAC 12 Dec 22
11-495 | R/M of Other Structures Expns | 54EBde,PA | NO | Negotiated 53.9 | N/A | 2022-11-11 | N/A | N/A | 2022-11-14 | N/A | N/A | N/A | 2022-11-14 | N/A | N/A | N/A | N/A | Special Release | 908600 | 908600 |  | 907948 | 907948 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | For CAC 12 Dec 22
11-496 | Other Supplies & Material Expns | 54EBde,PA | NO | Negotiated 53.9 | N/A | 2022-11-11 | N/A | N/A | 2022-11-14 | N/A | N/A | N/A | 2022-11-14 | N/A | N/A | N/A | N/A | Special Release | 80642 | 80642 |  | 80534 | 80534 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | For CAC 12 Dec 22
11-497 | Office Supplies Expns | 54EBde,PA | NO | Negotiated 53.9 | N/A | 2022-11-11 | N/A | N/A | 2022-11-14 | N/A | N/A | N/A | 2022-11-14 | N/A | N/A | N/A | N/A | MOOE | 92613 | 92613 |  | 92520.25 | 92520.25 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | For CAC 12 Dec 22
11-498 | Office Supplies Expns | 54EBde,PA | NO | Negotiated 53.9 | N/A | 2022-11-11 | N/A | N/A | 2022-11-14 | N/A | N/A | N/A | 2022-11-14 | N/A | N/A | N/A | N/A | Special Release | 50000 | 50000 |  | 49941.5 | 49941.5 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | For CAC 12 Dec 22
11-499 | Training Expenses | 54EBde,PA | NO | Negotiated 53.9 | N/A | 2022-11-11 | N/A | N/A | 2022-11-14 | N/A | N/A | N/A | 2022-11-14 | N/A | N/A | N/A | N/A | MOOE | 172510 | 172510 |  | 172365.75 | 172365.75 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | For CAC 12 Dec 22
11-500 | Other Supplies & Material Expns | 54EBde,PA | NO | Negotiated 53.9 | N/A | 2022-11-11 | N/A | N/A | 2022-11-14 | N/A | N/A | N/A | 2022-11-14 | N/A | N/A | N/A | N/A | MOOE | 76283 | 76283 |  | 76055 | 76055 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | For CAC 12 Dec 22
11-501 | Representation Expenses | 54EBde,PA | NO | Negotiated 53.9 | N/A | 2022-11-11 | N/A | N/A | 2022-11-14 | N/A | N/A | N/A | 2022-11-14 | N/A | N/A | N/A | N/A | MOOE | 380409.5 | 380409.5 |  | 380167.5 | 380167.5 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | For CAC 12 Dec 22
11-502 | R/M Building | 54EBde,PA | NO | Negotiated 53.9 | N/A | 2022-11-11 | N/A | N/A | 2022-11-14 | N/A | N/A | N/A | 2022-11-14 | N/A | N/A | N/A | N/A | MOOE | 100000 | 100000 |  | 99877 | 99877 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | For CAC 12 Dec 22
11-503 | Representation Expenses | 54EBde,PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | 2022-11-15 | N/A | N/A | N/A | 2022-11-15 | N/A | N/A | N/A | N/A | MOOE | 36745.6 | 36745.6 |  | 36622 | 36622 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | For CAC 12 Dec 22
11-504 | R/M of ICT Equipment | 54EBde,PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | 2022-11-15 | N/A | N/A | N/A | 2022-11-15 | N/A | N/A | N/A | N/A | MOOE | 15500 | 15500 |  | 15423 | 15423 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | For CAF 12 Dec 22
11-505 | R/M of Motor Vehicles | 545ECB, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | 2022-11-23 | N/A | N/A | N/A | 2022-11-23 | N/A | N/A | N/A | N/A | MOOE | 15000 | 15000 |  | 14923 | 14923 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | For CAF 12 Dec 22
11-506 | Other Supplies & Material Expns | 545ECB, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | 2022-11-23 | N/A | N/A | N/A | 2022-11-23 | N/A | N/A | N/A | N/A | MOOE | 21250 | 21250 |  | 21160 | 21160 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | For CAF 12 Dec 22
11-507 | Drugs and Medicines Expns | 545ECB, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | 2022-11-23 | N/A | N/A | N/A | 2022-11-23 | N/A | N/A | N/A | N/A | MOOE | 21250 | 21250 |  | 21213 | 21213 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | For CAF 12 Dec 22
11-508 | R/M of Motor Vehicles | 549ECBn, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | 2022-11-23 | N/A | N/A | N/A | 2022-11-23 | N/A | N/A | N/A | N/A | MOOE | 25000 | 25000 |  | 24934 | 24934 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | For CAF 12 Dec 22
11-509 | Medical, Dental & LAB SUPPLIES Expns | 549ECBn, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | 2022-11-23 | N/A | N/A | N/A | 2022-11-23 | N/A | N/A | N/A | N/A | MOOE | 42600 | 42600 |  | 42531 | 42531 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | For CAF 12 Dec 22
11-510 | R/M of Motor Vehicles | 547EB, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | 2022-11-23 | N/A | N/A | N/A | 2022-11-23 | N/A | N/A | N/A | N/A | MOOE | 10000 | 10000 |  | 9949 | 9949 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | For CAF 12 Dec 22
11-515 | R/M of Motor Vehicles | 54EBde,PA | NO | Negotiated 53.9 | N/A | 2022-11-22 | N/A | N/A | 2022-11-25 | N/A | N/A | N/A | 2022-11-25 | N/A | N/A | N/A | N/A | Special Release | 79861.6 | 79861.6 |  | 79735 | 79735 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | For CAF 12 Dec 22
11-517 | Representation Expenses | 545ECB, PA | NO | Negotiated 53.9 | N/A | 2022-11-22 | N/A | N/A | 2022-11-25 | N/A | N/A | N/A | 2022-11-25 | N/A | N/A | N/A | N/A | Special Release | 175000 | 175000 |  | 174873.5 | 174873.5 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | For CAF 12 Dec 22
11-518 | R/M of Const & Heavy Eqpt | 547EB, PA | NO | Negotiated 53.9 | N/A | 2022-11-22 | N/A | N/A | 2022-11-25 | N/A | N/A | N/A | 2022-11-25 | N/A | N/A | N/A | N/A | MOOE | 95000 | 95000 |  | 94887 | 94887 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | For CAF 12 Dec 22
11-519 | Medical, Dental & LAB SUPPLIES Expns | 547EB, PA | NO | Negotiated 53.9 | N/A | 2022-11-22 | N/A | N/A | 2022-11-25 | N/A | N/A | N/A | 2022-11-25 | N/A | N/A | N/A | N/A | MOOE | 85200 | 85200 |  | 85110 | 85110 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | For CAF 12 Dec 22
11-520 | R/M of Const & Heavy Eqpt | 547EB, PA | NO | Negotiated 53.9 | N/A | 2022-11-22 | N/A | N/A | 2022-11-25 | N/A | N/A | N/A | 2022-11-25 | N/A | N/A | N/A | N/A | MOOE | 150000 | 150000 |  | 149935 | 149935 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | For CAF 12 Dec 22
11-521 | R/M of ICT Equipment | 545ECB, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | 2022-11-25 | N/A | N/A | N/A | 2022-11-25 | N/A | N/A | N/A | N/A | MOOE | 21378 | 21378 |  | 21281 | 21281 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | For CAF 13 Dec 22
11-522 | R/M of Motor Vehicles | ESC, 54EBde,PA | NO | Negotiated 53.9 | N/A | 2022-11-29 | N/A | N/A | 2022-12-02 | N/A | N/A | N/A | 2022-12-02 | N/A | N/A | N/A | N/A | MOOE | 125000 | 125000 |  | 124862 | 124862 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | For funding MFO 07 Dec 22
12-526 | R/M of Motor Vehicles | 54EBde,PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | 2022-12-07 | N/A | N/A | N/A | 2022-12-07 | N/A | N/A | N/A | N/A | Special Release | 14250 | 14250 |  | 14121 | 14121 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | For funding MFO 07 Dec 22
12-527 | Other Supplies & Material Expns | 549ECBn, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | 2022-12-07 | N/A | N/A | N/A | 2022-12-07 | N/A | N/A | N/A | N/A | Special Release | 20000 | 20000 |  | 19931 | 19931 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | For funding MFO 07 Dec 22
12-529 | Training Expenses | 54EBde,PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | 2022-12-07 | N/A | N/A | N/A | 2022-12-07 | N/A | N/A | N/A | N/A | Special Release | 30000 | 30000 |  | 29932.5 | 29932.5 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | For funding MFO 07 Dec 22
12-530 | Other Supplies & Material Expns | 54EBde,PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | 2022-12-07 | N/A | N/A | N/A | 2022-12-07 | N/A | N/A | N/A | N/A | Special Release | 30000 | 30000 |  | 29945 | 29945 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | For funding MFO 09 Dec 22
12-535 | Other Supplies & Material Expns | 545ECB, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | 2022-12-09 | N/A | N/A | N/A | 2022-12-09 | N/A | N/A | N/A | N/A | Special Release | 20000 | 20000 |  | 19892.5 | 19892.5 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | For funding MFO 09 Dec 22
12-536 | Repair and Maintenance of Machinery and Equipment | 545ECB, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | 2022-12-09 | N/A | N/A | N/A | 2022-12-09 | N/A | N/A | N/A | N/A | MOOE | 15000 | 15000 |  | 14930 | 14930 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | For funding MFO 12 Dec 22
12-540 | R/M of Building | 549ECBn, PA | NO | Negotiated 53.9 | N/A | 2022-12-09 | N/A | N/A | 2022-12-12 | N/A | N/A | N/A | 2022-12-12 | N/A | N/A | N/A | N/A | Special Release | 150000 | 150000 |  | 149860.5 | 149860.5 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | For funding MFO 12 Dec 22
12-541 | Representation Expenses | 547EB, PA | NO | Negotiated 53.9 | N/A | 2022-12-09 | N/A | N/A | 2022-12-12 | N/A | N/A | N/A | 2022-12-12 | N/A | N/A | N/A | N/A | Special Release | 50000 | 50000 |  | 49939.5 | 49939.5 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | For funding MFO 12 Dec 22
12-542 | Representation Expenses | 549ECBn, PA | NO | Negotiated 53.9 | N/A | 2022-12-09 | N/A | N/A | 2022-12-12 | N/A | N/A | N/A | 2022-12-12 | N/A | N/A | N/A | N/A | Special Release | 50000 | 50000 |  | 49913.75 | 49913.75 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | For funding MFO 12 Dec 22
12-543 | Representation Expenses | 545ECB, PA | NO | Negotiated 53.9 | N/A | 2022-12-09 | N/A | N/A | 2022-12-12 | N/A | N/A | N/A | 2022-12-12 | N/A | N/A | N/A | N/A | Special Release | 50000 | 50000 |  | 49917.5 | 49917.5 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | For funding MFO 12 Dec 22
12-544 | Representation Expenses | 54EBde,PA | NO | Negotiated 53.9 | N/A | 2022-12-09 | N/A | N/A | 2022-12-12 | N/A | N/A | N/A | 2022-12-12 | N/A | N/A | N/A | N/A | Special Release | 100000 | 100000 |  | 99859 | 99859 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | For funding MFO 12 Dec 22
12-545 | R/M of Other Structures Expns | 54EBde,PA | NO | Negotiated 53.9 | N/A | 2022-12-09 | N/A | N/A | 2022-12-12 | N/A | N/A | N/A | 2022-12-12 | N/A | N/A | N/A | N/A | Special Release | 100000 | 100000 |  | 99841 | 99841 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | For funding MFO 12 Dec 22
12-546 | R/M of Building | 54EBde,PA | NO | Negotiated 53.9 | N/A | 2022-12-09 | N/A | N/A | 2022-12-12 | N/A | N/A | N/A | 2022-12-12 | N/A | N/A | N/A | N/A | Special Release | 140711 | 140711 |  | 140569 | 140569 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | For funding MFO 13 Dec 22
12-548 | Compaction Testing ICOW Cons of Ammunition Dump | 549ECBn, PA | NO | Negotiated 53.9 | N/A | 2022-12-09 | N/A | N/A | 2022-12-13 | N/A | N/A | N/A | 2022-12-13 | N/A | N/A | N/A | N/A | Special Release | 60000 | 60000 |  | 59944 | 59944 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | For funding MFO 13 Dec 22
12-549 | Office Supplies Expns | 54EBde,PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | 2022-12-13 | N/A | N/A | N/A | 2022-12-13 | N/A | N/A | N/A | N/A | Special Release | 49005 | 49005 |  | 48866 | 48866 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | For funding MFO 13 Dec 22
12-550 | Other Supplies & Material Expns | 54EBde,PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | 2022-12-13 | N/A | N/A | N/A | 2022-12-13 | N/A | N/A | N/A | N/A | Special Release | 48292 | 48292 |  | 48084.5 | 48084.5 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | For funding MFO 13 Dec 22
12-551 | Representation Expenses | 54EBde,PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | 2022-12-13 | N/A | N/A | N/A | 2022-12-13 | N/A | N/A | N/A | N/A | Special Release | 48900.3 | 48900.3 |  | 48758.5 | 48758.5 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | For funding MFO 13 Dec 22
[19 empty] | 4422362 |  |  | 4416657.25
Total Alloted Budget of On-going Procurement Activities | [18 empty] | 4422362