## pmr
|  | ANNEX A | [18 empty] | ANNEX B
|  | Department of Budget and Management Annual Procurement Plan for FY 2006 | [18 empty] | (ASR) Procurement Monitoring Report as of December 31, 2022
Code (PAP) | Procurement Project | PMO/ End-User | Mode of Procurement | Schedule for Each Procurement Activity | [11 empty] | Source of Funds | ABC (PhP) |  |  | Remarks (brief description of Program/Project) | PMO/ End-User | Is this an Early Procurement Activity? | Mode of Procurement | Actual Procurement Activity | [12 empty] | Source of Funds | ABC (PhP) |  |  | Contract Cost (PhP) |  |  | List of Invited Observers | Date of Receipt of Invitation | [5 empty] | Remarks (Explaining changes from the APP)
|  |  |  | Pre-Proc Conference | Ads/Post of IAEB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Contract Award | Contract Signing | Notice to Proceed | Delivery/ Accept | Payment Process |  | Total | MOOE | CO |  |  |  |  | Pre-Proc Conference | Ads/Post of IB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Date of BAC Resolution Recommending Award | Notice of Award | Contract Signing | Notice to Proceed | Delivery/ Completion | Inspection & Acceptance |  | Total | MOOE | CO | Total | MOOE | CO |  | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Delivery/ Completion/ Acceptance (If applicable)
COMPLETED PROCUREMENT ACTIVITIES
| S/D of 1 pc Front Grill & 8 others | [19 empty] | ASR | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-07-08 | 2022-07-08 | 2022-08-18 | 2022-08-25 | 2022-08-25 | GoP | 37000 | 37000 | 0 | 36000 | 36000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of 4 gals Paint QDE Green & 14 others | [19 empty] | ASR | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-07-15 | 2022-07-15 | 2022-08-15 | 2022-08-22 | 2022-08-22 | GoP | 36000 | 36000 | 0 | 35100 | 35100 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of 30 bags Cement & 19 others | [19 empty] | ASR | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-07-26 | 2022-07-26 | 2022-09-05 | 2022-09-12 | 2022-09-12 | GoP | 269250 | 269250 | 0 | 227581 | 227581 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of Z590 Motherboards & 7 Others | [19 empty] | ASR | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-07-22 | 2022-07-22 | 2022-09-12 | 2022-09-19 | 2022-09-19 | GoP | 96700 | 96700 | 0 | 96290 | 96290 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| SD of 1 set Wheel Hub (for KM250) & 8 Others | [19 empty] | ASR | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-07-26 | 2022-07-26 | 2022-09-05 | 2022-09-12 | 2022-09-12 | GoP | 60000 | 60000 | 0 | 59200 | 59200 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of 1 set Piston Ring (for Toyota Innova Freedom) White & 22 Others | [19 empty] | ASR | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-07-26 | 2022-07-26 | 2022-09-12 | 2022-09-19 | 2022-09-19 | GoP | 80000 | 80000 | 0 | 79100 | 79100 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of 1 pc Granite Tiles 0.60m x 2.00m & 75 others | [19 empty] | ASR | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-13 | 2022-09-13 | 2022-12-02 | 2022-12-09 | 2022-12-09 | GoP | 199581 | 199581 | 0 | 199081 | 199081 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of 5 pcs Laptop & 4 others | [19 empty] | ASR | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-30 | 2022-09-30 | 2022-11-16 | 2022-11-23 | 2022-11-23 | GoP | 324945 | 324945 | 0 | 322945 | 322945 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of 1 set Alternator Assembly & 11 Others | [19 empty] | ASR | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-18 | 2022-10-18 | 2022-12-02 | 2022-12-09 | 2022-12-09 | GoP | 60000 | 60000 | 0 | 59500 | 59500 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of 1 pc Processor Core i5 and 9 others | [19 empty] | ASR | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-04 | 2022-11-04 | 2022-12-02 | 2022-12-09 | 2022-12-09 | GoP | 50000 | 50000 | 0 | 49505 | 49505 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of 15 pcs IFAK Pouch and 8 others | [19 empty] | ASR | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-11-04 | 2022-11-04 | 2022-12-02 | 2022-12-09 | 2022-12-09 | GoP | 150000 | 150000 | 0 | 149775 | 149775 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of 20 pcs Printer WF-4830 Wireless All-in-One & 2 others | [19 empty] | ASR | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-08-09 | 2022-08-09 | 2022-09-07 | 2022-09-14 | 2022-09-14 | GoP | 727430 | 727430 | 0 | 726130 | 726130 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| SD of 50 pcs UPS Ballpen and 33 Others | [19 empty] | NETBN, ASR | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-07-08 | 2022-07-08 | 2022-09-07 | 2022-09-14 | 2022-09-14 | GoP | 750000 | 750000 | 0 | 748250 | 748250 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| SD of 5 pcs Printer and 7 Others | [19 empty] | NETBN, ASR | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-07-19 | 2022-07-19 | 2022-08-24 | 2022-08-31 | 2022-08-31 | GoP | 625000 | 625000 | 0 | 618500 | 618500 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| SD of 10 piece Screen Protector all in one (Screen Anti Glare Protector Cover Filter For Monitor) and 26 others | [19 empty] | NETBN, ASR | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-07-22 | 2022-07-22 | 2022-09-12 | 2022-09-19 | 2022-09-19 | GoP | 580000 | 580000 | 0 | 578500 | 578500 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| SD of 9 Wifi Access point outdoor and 10 Others | [19 empty] | NETBN, ASR | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-07-29 | 2022-07-29 | 2022-09-07 | 2022-09-14 | 2022-09-14 | GoP | 964000 | 964000 | 0 | 962525 | 962525 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| SD of 1 piece Welding Machine (32A/27V-300A/32V) and 10 Others | [19 empty] | NETBN, ASR | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-08-16 | 2022-08-16 | 2022-09-23 | 2022-09-30 | 2022-09-30 | GoP | 73960 | 73960 | 0 | 73200 | 73200 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| SD of 1 lot GIS Desktop Basic Single Use Upgrade from Version10.1 to Latest Version and 2 others | [19 empty] | NETBN, ASR | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-08-31 | 2022-08-31 | 2022-10-14 | 2022-10-21 | 2022-10-21 | GoP | 467762.5 | 467762.5 | 0 | 466762.5 | 466762.5 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| SD of 12 Wifi Access point outdoor and 10 Others | [19 empty] | NETBN, ASR | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-09-09 | 2022-09-09 | 2022-10-14 | 2022-10-21 | 2022-10-21 | GoP | 980000 | 980000 | 0 | 969800 | 969800 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| CATERING SERVICES | [19 empty] | NETBN, ASR | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-09-27 | 2022-09-27 | 2022-12-02 | 2022-12-09 | 2022-12-09 | GoP | 327600 | 327600 | 0 | 323680 | 323680 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| SD of 5 piece video card GTX1030 ( graphics) and 5 others | [19 empty] | NETBN, ASR | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-10-11 | 2022-10-11 | 2022-12-02 | 2022-12-09 | 2022-12-09 | GoP | 143100 | 143100 | 0 | 142740 | 142740 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| SD of 25 box Ballpen BS 0.7 blue and 21 Others | [19 empty] | NETBN, ASR | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-11-04 | 2022-11-04 | 2022-12-02 | 2022-12-09 | 2022-12-09 | GoP | 258500 | 258500 | 0 | 257000 | 257000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of 2 pcs 1-chip WUXGA DLP 6,700 lumen digital projector & 31 others | [19 empty] | NETBN, ASR | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-11-09 | 2022-11-09 | 2022-12-02 | 2022-12-09 | 2022-12-09 | GoP | 868174 | 868174 | 0 | 861094.4 | 861094.4 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of 2 sets Generator 3.5 KVA and 1 other | [19 empty] | SIMBN, ASR | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-07-12 | 2022-07-12 | 2022-08-10 | 2022-08-17 | 2022-08-17 | GoP | 49700 | 49700 | 0 | 45700 | 45700 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of 50 pcs Ballpen BS 0.7 blue and 33 others | [19 empty] | SIMBN, ASR | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-07-12 | 2022-07-12 | 2022-09-07 | 2022-09-14 | 2022-09-14 | GoP | 750000 | 750000 | 0 | 740400 | 740400 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of 1 pc Motorola M3688 Base Radio (UHF) and 1 other | [19 empty] | SIMBN, ASR | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-07-15 | 2022-07-15 | 2022-08-22 | 2022-08-30 | 2022-08-30 | GoP | 55625 | 55625 | 0 | 53650 | 53650 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of 1 unit LED TV 24 inch and 1 other | [19 empty] | SIMBN, ASR | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-07-19 | 2022-07-19 | 2022-08-30 | 2022-09-06 | 2022-09-06 | GoP | 66246 | 66246 | 0 | 61600 | 61600 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of 1 pc 8 Element Variloop Antenna and 48 others | [19 empty] | SIMBN, ASR | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-07-19 | 2022-07-19 | 2022-08-30 | 2022-09-06 | 2022-09-06 | GoP | 328429 | 328429 | 0 | 320579 | 320579 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of 2 unit Laptop Core-i7 10th Gen 15.6" and 5 others | [19 empty] | SIMBN, ASR | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-07-29 | 2022-07-29 | 2022-09-07 | 2022-09-14 | 2022-09-14 | GoP | 300000 | 300000 | 0 | 299100 | 299100 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Supply Delivery of 6 units Desktop Computer & 2 others | [19 empty] | TSS, ASR | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-11-04 | 2022-11-04 | 2022-12-02 | 2022-12-09 | 2022-12-09 | GoP | 391370 | 391370 | 0 | 388000 | 388000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| CATERING SERVICES | [19 empty] | CSBN, ASR | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-07-12 | 2022-07-12 | 2022-08-22 | 2022-08-29 | 2022-08-29 | GoP | 147500 | 147500 | 0 | 146420 | 146420 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| SD of 50 pcs Ballpen BS 0.7 blue and 33 others | [19 empty] | CSBN, ASR | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-07-29 | 2022-07-29 | 2022-09-12 | 2022-09-19 | 2022-09-19 | GoP | 750000 | 750000 | 0 | 742025 | 742025 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| SD of 100 box Scotch Lock & 6 others | [19 empty] | CSBN, ASR | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-08-31 | 2022-08-31 | 2022-10-06 | 2022-10-13 | 2022-10-13 | GoP | 550487 | 550487 | 0 | 545485 | 545485 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| SD of 6 pcs of passive speaker 15 & 8 others | [19 empty] | CSBN, ASR | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-08-31 | 2022-08-31 | 2022-10-10 | 2022-10-17 | 2022-10-17 | GoP | 986526 | 986526 | 0 | 981526 | 981526 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of 18 pcs Printer T720DW Ink Tank and 3 Others | [19 empty] | CYBERBN, ASR | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-07-15 | 2022-07-15 | 2022-08-10 | 2022-08-17 | 2022-08-17 | GoP | 974000 | 974000 | 0 | 972110 | 972110 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| SD of 1 lot Nessus Professional Vulnerability Scanner Version 7 | [19 empty] | CYBERBN, ASR | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-07-29 | 2022-07-29 | 2022-09-23 | 2022-09-30 | 2022-09-30 | GoP | 290000 | 290000 | 0 | 285000 | 285000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| SD of 15 pcs Printer T720DW Ink Tank and 3 Others | [19 empty] | CYBERBN, ASR | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-09-09 | 2022-09-09 | 2022-09-29 | 2022-10-06 | 2022-10-06 | GoP | 990000 | 990000 | 0 | 987825 | 987825 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of 1 lot Endpoint Security Solution | [19 empty] | CYBERBN, ASR | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-09-27 | 2022-09-27 | 2022-11-17 | 2022-11-24 | 2022-11-24 | GoP | 700000 | 700000 | 0 | 698900 | 698900 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of 1 lot Network Security Protection DMZ Firewall | [19 empty] | CYBERBN, ASR | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-09-27 | 2022-09-27 | 2022-11-04 | 2022-11-11 | 2022-11-11 | GoP | 980000 | 980000 | 0 | 979500 | 979500 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of 1 lot Endpoint Security Protection (X Advanced XDR and MTR) | [19 empty] | CYBERBN, ASR | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-09-27 | 2022-09-27 | 2022-11-11 | 2022-11-24 | 2022-11-24 | GoP | 300000 | 300000 | 0 | 299900 | 299900 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Total Alloted Budget of Procurement Activities | [37 empty] | 16738885.5
Total Contract Price of Procurement Actitvites Conducted | [40 empty] | 16589978.9
Total Savings (Total Alloted Budget - Total Contract Price) | [37 empty] | 148906.6
0N-GOING PROCUREMENT ACTIVITIES
| S/D of 1 pc 24 inch Monitor for Desktop and 1 others | [19 empty] | ASR | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-18 | 2022-11-18 | N/A | N/A | N/A | GoP | 29250 | 29250 | 0 | 28850 | 28850 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of 5 pcs Printer & 3 others | [19 empty] | ASR | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-24 | 2022-11-24 | N/A | N/A | N/A | GoP | 176863 | 176863 | 0 | 174613 | 174613 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of 2 pcs Laptop & 7 others | [19 empty] | ASR | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-24 | 2022-11-24 | N/A | N/A | N/A | GoP | 400000 | 400000 | 0 | 397000 | 397000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of 5 unit Satellite Phone XT Lite | [19 empty] | CSBN, ASR | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-24 | 2022-11-24 | N/A | N/A | N/A | GoP | 245000 | 245000 | 0 | 243750 | 243750 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of 5 pcs Prepaid Sim Card with 225 units preload & 2 others | [19 empty] | CSBN, ASR | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-24 | 2022-11-24 | N/A | N/A | N/A | GoP | 254000 | 254000 | 0 | 252000 | 252000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| SD of 2 pcs Rackmount Server and 2 others | [19 empty] | CSBN, ASR | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-24 | 2022-11-24 | N/A | N/A | N/A | GoP | 300000 | 300000 | 0 | 297000 | 297000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of 2 pc Studiomaster 16ch Mixer & 5 others | [19 empty] | CSBN, ASR | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-24 | 2022-11-24 | N/A | N/A | N/A | GoP | 702822 | 702822 | 0 | 698000 | 698000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of 2 pcs Laptop & 13 others | [19 empty] | CYBERBN, ASR | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-24 | 2022-11-24 | N/A | N/A | N/A | GoP | 997000 | 997000 | 0 | 994750 | 994750 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of 50 pcs Metal Furring 1" x 2" x 16' & 71 Others | [19 empty] | CYBERBN, ASR | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-24 | 2022-11-24 | N/A | N/A | N/A | GoP | 700000 | 700000 | 0 | 698700 | 698700 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of 1 pc VDP PWB Assembly and 3 others | [19 empty] | SIMBN | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-24 | 2022-11-24 | 2022-12-16 | 2022-12-22 | N/A | GoP | 555600 | 555600 | 0 | 553500 | 553500 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Total Alloted Budget of On-going Procurement Activities | [37 empty] | 4360535
| Prepared by: | [32 empty] | Certified Correct By | [6 empty] | Noted By
| Signed | [32 empty] | Signed | [6 empty] | Signed
| CLAIRE R AURE-REYES | [32 empty] | JOHN KENNETH D BABICA | [6 empty] | MANOLO V SANTIAGO
| Major (QMS) PA | [32 empty] | Major (INF) PA | [6 empty] | Colonel CE (GSC) PA
| Operations Officer | [32 empty] | Executive Officer | [6 empty] | Commanding Officer

## Sheet1 (hidden)
Competitive Bidding | GoP | YES
Limited Source Bidding | Foreign | NO
Direct Contracting | Special Purpose Fund
Repeat Order | Corporate Budget
Shopping | Income
NP-53.1 Two Failed Biddings | Others
NP-53.2 Emergency Cases
NP-53.3 Take-Over of Contracts
NP-53.4 Adjacent or Contiguous
NP-53.5 Agency-to-Agency
NP-53.6 Scientific, Scholarly, Artistic Work, Exclusive Technology and Media Services
NP-53.7 Highly Technical Consultants
NP-53.8 Defense Cooperation Agreement
NP-53.9 - Small Value Procurement
NP-53.10 Lease of Real Property and Venue
NP-53.11 NGO Participation
NP-53.12 Community Participation
NP-53.13 UN Agencies, Int'l Organizations or International Financing Institutions
Others - Foreign-funded procurement