## v2
ANNEX B
(Aviation Regiment,PA) Procurement Monitoring Report 2nd Sem CY 2022
Code (PAP) | Procurement Project | PMO/ End-User | Mode of Procurement | Schedule for Each Procurement Activity | [11 empty] | Source of Funds | ABC (PhP) |  |  | Remarks (brief description of Program/Project) | PMO/ End-User | Is this an Early Procurement Activity? | Mode of Procurement | Actual Procurement Activity | [12 empty] | Source of Funds | ABC (PhP) |  |  | Contract Cost (PhP) |  |  | List of Invited Observers | Date of Receipt of Invitation | [5 empty] | Remarks (Explaining changes from the APP)
|  |  |  | Pre-Proc Conference | Ads/Post of IAEB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Contract Award | Contract Signing | Notice to Proceed | Delivery/ Accept | Payment Process |  | Total | MOOE | CO |  |  |  |  | Pre-Proc Conference | Ads/Post of IB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Date of BAC Resolution Recommending Award | Notice of Award | Contract Signing | Notice to Proceed | Delivery/ Completion | Inspection & Acceptance |  | Total | MOOE | CO | Total | MOOE | CO |  | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Delivery/ Completion/ Acceptance (If applicable)
COMPLETED PROCUREMENT ACTIVITIES
| R&M of Motor Vehicle | [19 empty] | AvnR, PA | NO | NP-53.9 - Small Value Procurement |  | 2022-05-09 |  |  | 2022-05-10 |  |  |  | 2022-05-13 | 2022-06-29 | 2022-06-22 | 2022-07-21 | 2022-07-14 | MOOE-2022 | 261000 | 261000 |  | 260628 | 260628
| R&M of Buildings | [19 empty] | AvnR, PA | NO | NP-53.9 - Small Value Procurement |  | 2022-05-09 |  |  | 2022-05-10 |  |  |  | 2022-05-13 | 2022-06-29 | 2022-06-22 | 2022-07-21 | 2022-07-14 | MOOE-2022 | 258000 | 258000 |  | 257661 | 257661
| R&M of Other Structure | [19 empty] | AvnR, PA | NO | NP-53.9 - Small Value Procurement |  | 2022-05-09 |  |  | 2022-05-10 |  |  |  | 2022-05-13 | 2022-07-25 | 2022-07-18 | 2022-08-09 | 2022-08-02 | MOOE-2022 | 105000 | 105000 |  | 104679 | 104679
| R&M of (Semi-Expendable) Communication Equipment | [19 empty] | AvnR, PA | NO | NP-53.9 - Small Value Procurement |  | 2022-05-09 |  |  | 2022-05-10 |  |  |  | 2022-05-13 | 2022-07-25 | 2022-07-18 | 2022-08-09 | 2022-08-02 | MOOE-2022 | 60000 | 60000 |  | 59600 | 59600
| R&M of (Semi-Expendable) ICT Equipment | [19 empty] | AvnR, PA | NO | NP-53.9 - Small Value Procurement |  | N/A |  |  | 2022-05-13 |  |  |  | 2022-05-16 | 2022-07-04 | 2022-06-27 | 2022-07-27 | 2022-07-19 | MOOE-2022 | 50000 | 50000 |  | 49737 | 49737
| Office Supplies | [19 empty] | AvnR, PA | NO | NP-53.9 - Small Value Procurement |  | 2022-06-08 |  |  | 2022-06-09 |  |  |  | 2022-06-13 | 2022-07-04 | 2022-06-27 | 2022-07-27 | 2022-07-19 | MOOE-2022 | 233750 | 233750 |  | 233312 | 233312
| R&M (Semi-Expendable) Communication Equipment | [19 empty] | AvnR, PA | NO | NP-53.9 - Small Value Procurement |  | N/A |  |  | 2022-08-17 |  |  |  | 2022-08-18 | 2022-10-17 | 2022-10-10 | 2022-11-05 | 2023-10-28 | MOOE-2022 | 30000 | 30000 |  | 29720 | 29720
| R&M (Semi-Expendable) ICT Equipment | [19 empty] | AvnR, PA | NO | NP-53.9 - Small Value Procurement |  | 2022-08-17 |  |  | 2022-08-18 |  |  |  | 2022-08-22 | 2022-10-21 | 2022-10-14 | 2022-11-05 | 2022-10-28 | MOOE-2022 | 150000 | 150000 |  | 149600 | 149600
| R&M of Motor Vehicle | [19 empty] | AvnR, PA | NO | NP-53.9 - Small Value Procurement |  | 2022-08-17 |  |  | 2022-08-18 |  |  |  | 2022-08-22 | 2022-10-17 | 2022-10-10 | 2022-11-05 | 2022-10-28 | MOOE-2022 | 330000 | 330000 |  | 329560 | 329560
| R&M of Other Structure | [19 empty] | AvnR, PA | NO | NP-53.9 - Small Value Procurement |  | 2022-08-17 |  |  | 2022-08-18 |  |  |  | 2022-08-22 | 2022-09-19 | 2022-09-19 | 2022-09-27 | 2022-09-21 | MOOE-2022 | 60000 | 60000 |  | 59625 | 59625
| R&M of Buildings | [19 empty] | AvnR, PA | NO | NP-53.9 - Small Value Procurement |  | 2022-08-17 |  |  | 2022-08-18 |  |  |  | 2022-08-22 | 2022-10-17 | 2022-10-10 | 2022-11-05 | 2022-10-28 | MOOE-2022 | 110000 | 110000 |  | 109695 | 109695
| Semi-Expendable-ICT Equipment | [19 empty] | AvnR, PA | NO | NP-53.9 - Small Value Procurement |  | N/A |  |  | 2022-08-17 |  |  |  | 2022-08-18 | 2022-10-17 | 2022-10-10 | 2022-11-05 | 2022-10-28 | MOOE-2022 | 15000 | 15000 |  | 14850 | 14850
| R&M of Other Structure | [19 empty] | AvnR, PA | NO | NP-53.9 - Small Value Procurement |  | 2022-08-17 |  |  | 2022-08-18 |  |  |  | 2022-08-22 | 2022-10-17 | 2022-10-10 | 2022-11-05 | 2022-10-28 | MOOE-2022 | 150000 | 150000 |  | 149670 | 149670
| Office Supplies | [19 empty] | AvnR, PA | NO | NP-53.9 - Small Value Procurement |  | 2022-08-02 |  |  | 2022-08-03 |  |  |  | 2022-08-08 | 2022-09-14 | 2022-09-07 | 2022-09-27 | 2022-09-21 | MOOE-2022 | 212000 | 212000 |  | 211669 | 211669
| Aircraft Ground Equipment | [19 empty] | AvnR, PA | NO | NP-53.9 - Small Value Procurement |  | 2022-08-17 |  |  | 2022-08-18 |  |  |  | 2022-08-22 | 2022-10-17 | 2022-10-10 | 2022-11-05 | 2022-10-28 | MOOE-2022 | 120000 | 120000 |  | 119735 | 119735
| R&M of Motor Vehicle | [19 empty] | AvnR, PA | NO | NP-53.9 - Small Value Procurement |  | 2022-10-28 |  |  | 2022-10-29 |  |  |  | 2022-11-02 | 2022-11-29 | 2022-11-28 | 2022-12-13 | 2022-12-06 | MOOE-2022 | 261000 | 261000 |  | 260570 | 260570
| R&M of Other Structure | [19 empty] | AvnR, PA | NO | NP-53.9 - Small Value Procurement |  | 2022-10-28 |  |  | 2022-10-29 |  |  |  | 2022-11-02 | 2022-11-29 | 2022-11-28 | 2022-12-13 | 2022-12-06 | MOOE-2022 | 145000 | 145000 |  | 144563 | 144563
| R&M of Buildings | [19 empty] | AvnR, PA | NO | NP-53.9 - Small Value Procurement |  | 2022-10-28 |  |  | 2022-10-29 |  |  |  | 2022-11-02 | 2022-11-29 | 2022-11-28 | 2022-12-13 | 2022-12-06 | MOOE-2022 | 133000 | 133000 |  | 132567 | 132567
| R&M of (Semi-Expendable) Communication Equipment | [19 empty] | AvnR, PA | NO | NP-53.9 - Small Value Procurement |  | 2022-10-28 |  |  | 2022-10-29 |  |  |  | 2022-11-02 | 2022-11-29 | 2022-11-28 | 2022-12-13 | 2022-12-06 | MOOE-2022 | 60000 | 60000 |  | 59680 | 59680
| R&M of (Semi-Expendable) ICT Equipment | [19 empty] | AvnR, PA | NO | NP-53.9 - Small Value Procurement |  | N/A |  |  | 2022-10-26 |  |  |  | 2022-10-28 | 2022-11-29 | 2022-11-28 | 2022-12-13 | 2022-12-06 | MOOE-2022 | 20000 | 20000 |  | 19835 | 19835
| Office Supplies | [19 empty] | AvnR, PA | NO | NP-53.9 - Small Value Procurement |  | 2022-10-11 |  |  | 2022-10-12 |  |  |  | 2022-10-17 | 2022-11-11 | 2022-11-10 | 2022-12-06 | 2022-11-29 | MOOE-2022 | 186000 | 186000 |  | 185540 | 185540
| R&M of Buildings | [19 empty] | ASC AvnR, PA | NO | NP-53.9 - Small Value Procurement |  | 2022-07-11 |  |  | 2022-07-12 |  |  |  | 2022-07-15 | 2022-09-14 | 2022-09-07 | 2022-09-28 | 2022-09-21 | MOOE-2022 | 100000 | 100000 |  | 99821 | 99821
| R&M of Other Structure (R&M of Flight Simulator) | [19 empty] | ASC AvnR, PA | NO | NP-53.9 - Small Value Procurement |  | 2022-08-08 |  |  | 2022-08-09 |  |  |  | 2022-08-12 | 2022-09-19 | 2022-09-19 | 2022-09-28 | 2022-09-21 | MOOE-2022 | 80000 | 80000 |  | 79500 | 79500
| R&M Semi-Expendable (ICT Equipment) | [19 empty] | ASC AvnR, PA | NO | NP-53.9 - Small Value Procurement |  | N/A |  |  | 2022-08-10 |  |  |  | 2022-08-11 | 2022-09-19 | 2022-09-19 | 2022-09-28 | 2022-09-21 | MOOE-2022 | 30000 | 30000 |  | 29720 | 29720
| R&M of Building and Other Structure (Building) | [19 empty] | ASC AvnR, PA | NO | NP-53.9 - Small Value Procurement |  | N/A |  |  | N/A |  |  |  | 2022-07-11 | 2022-08-16 | 2022-08-16 | 2022-08-25 | 2022-08-18 | MOOE-2022 | 40000 | 40000 |  | 39850 | 39850
| R&M of buildings and Other Structure | [19 empty] | AMC AvnR, PA | NO | NP-53.9 - Small Value Procurement |  | N/A |  |  | 2022-04-05 |  |  |  | 2022-04-06 | 2022-05-18 | 2022-05-17 | 2022-06-03 | 2022-05-26 | MOOE-2022 | 45000 | 45000 |  | 44700 | 44700
| R&M of buildings and Other Structure | [19 empty] | AMC AvnR, PA | NO | NP-53.9 - Small Value Procurement |  | N/A |  |  | 2022-10-17 |  |  |  | 2022-10-18 | 2022-11-24 | 2022-11-17 | 2022-12-06 | 2022-11-29 | MOOE-2022 | 30000 | 30000 |  | 29705 | 29705
| R&M of buildings and Other Structure | [19 empty] | AMC AvnR, PA | NO | NP-53.9 - Small Value Procurement |  | N/A |  |  | 2022-10-18 |  |  |  | 2022-10-29 | 2022-11-24 | 2022-11-17 | 2022-12-06 | 2022-11-29 | MOOE-2022 | 10000 | 10000 |  | 9800 | 9800
| R&M of buildings and Other Structure | [19 empty] | AMC AvnR, PA | NO | NP-53.9 - Small Value Procurement |  | N/A |  |  | 2022-05-11 |  |  |  | 2022-05-12 | 2022-06-04 | 2022-06-27 | 2022-07-25 | 2022-07-18 | MOOE-2022 | 30000 | 30000 |  | 29800 | 29800
| R&M of buildings and Other Structure | [19 empty] | AMC AvnR, PA | NO | NP-53.9 - Small Value Procurement |  | 2022-07-19 |  |  | 2022-07-20 |  |  |  | 2022-07-25 | 2022-09-14 | 2022-09-07 | 2022-09-28 | 2022-09-21 | MOOE-2022 | 55000 | 55000 |  | 54800 | 54800
| R&M of Other Structure | [19 empty] | HHSBn AvnR, PA | NO | NP-53.9 - Small Value Procurement |  | N/A |  |  | 2022-09-21 |  |  |  | 2022-09-22 | 2022-10-21 | 2022-10-14 | 2022-11-05 | 2022-10-28 | MOOE-2022 | 50000 | 50000 |  | 49460 | 49460
| R&M of buildings and Other Structure | [19 empty] | HHSBn AvnR, PA | NO | NP-53.9 - Small Value Procurement |  | N/A |  |  | 2022-04-11 |  |  |  | 2022-04-12 | 2022-05-20 | 2022-05-19 | 2022-06-03 | 2022-05-26 | MOOE-2022 | 50000 | 50000 |  | 49800 | 49800
| Office Supplies | [19 empty] | HHSBn AvnR, PA | NO | NP-53.9 - Small Value Procurement |  | N/A |  |  | 2022-09-14 |  |  |  | 2022-09-15 | 2022-11-29 | 2022-11-28 | 2022-12-13 | 2022-12-06 | MOOE-2022 | 30000 | 30000 |  | 29337 | 29337
Total Alloted Budget of Procurement Activities | [37 empty] | 3499750
Total Contract Price of Procurement Actitvites Conducted | [40 empty] | 3488789
Total Savings (Total Alloted Budget - Total Contract Price) | [37 empty] | 10961
|  | Prepared By: | [30 empty] | Noted By:
|  | Signed | [30 empty] | Signed
|  | ARIES MASSEM T DELA CUADRA | [30 empty] | ANDRE B SANTOS
|  | MAJ (SC) PA | [30 empty] | Colonel (MNSA) PA
|  | AC of S for Logistics, G4 | [30 empty] | Commanding Officer

## Sheet1 (hidden)
Competitive Bidding | GoP | YES
Limited Source Bidding | Foreign | NO
Direct Contracting | Special Purpose Fund
Repeat Order | Corporate Budget
Shopping | Income
NP-53.1 Two Failed Biddings | Others
NP-53.2 Emergency Cases
NP-53.3 Take-Over of Contracts
NP-53.4 Adjacent or Contiguous
NP-53.5 Agency-to-Agency
NP-53.6 Scientific, Scholarly, Artistic Work, Exclusive Technology and Media Services
NP-53.7 Highly Technical Consultants
NP-53.8 Defense Cooperation Agreement
NP-53.9 - Small Value Procurement
NP-53.10 Lease of Real Property and Venue
NP-53.11 NGO Participation
NP-53.12 Community Participation
NP-53.13 UN Agencies, Int'l Organizations or International Financing Institutions
Others - Foreign-funded procurement