## 10ID
Code (PAP) | Procurement Project | PMO/ End-User | Mode of Procurement | Schedule for Each Procurement Activity | [11 empty] | Source of Funds | ABC (PhP) |  |  | Remarks (brief description of Program/Project) | PMO/ End-User | Is this an Early Procurement Activity? | Mode of Procurement | Actual Procurement Activity | [12 empty] | Source of Funds | ABC (PhP) |  |  | Contract Cost (PhP) |  |  | List of Invited Observers | Date of Receipt of Invitation | [5 empty] | Remarks (Explaining changes from the APP)
|  |  |  | Pre-Proc Conference | Ads/Post of IAEB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Contract Award | Contract Signing | Notice to Proceed | Delivery/ Accept | Payment Process |  | Total | MOOE | CO |  |  |  |  | Pre-Proc Conference | Ads/Post of IB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Date of BAC Resolution Recommending Award | Notice of Award | Contract Signing | Notice to Proceed | Delivery/ Completion | Inspection & Acceptance |  | Total | MOOE | CO | Total | MOOE | CO |  | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Delivery/ Completion/ Acceptance (If applicable)
COMPLETED PROCUREMENT ACTIVITIES
5-02-03-990-00 | Other Suppplies Expenses | 27IB | Neg 53.9 | [17 empty] | 27IB |  | MOOE | [8 empty] | 2023-03-01 | 2023-03-02 | 2023-05-10 | 2023-06-07 | 2023-06-07 | MOOE | 48180 | 48180 |  | 48100 | 48100
5-02-13-040-99 | R&M Other Structure | 27IB | Neg 53.9 | [17 empty] | 27IB |  | MOOE | [8 empty] | 2023-03-01 | 2023-03-02 | 2023-03-10 | 2023-03-28 | 2023-03-28 | MOOE | 50000 | 50000 |  | 49440 | 49440
5-02-03-040-01 | R & M Building | 39IB | Neg 53.9 | [17 empty] | 39IB |  | MOOE | [8 empty] | 2023-03-06 | 2023-03-07 | 2023-03-10 | 2023-03-28 | 2023-03-28 | MOOE | 101200 | 101200 |  | 100705 | 100705
5-02-03-010-00 | Office Supplies Expenses | OG4 | Neg 53.9 | [17 empty] | OG4 |  | MOOE | [8 empty] | 2023-03-06 | 2023-03-07 | 2023-03-21 | 2023-04-04 | 2023-04-04 | MOOE | 353899.1 | 353899.1 |  | 353762.1 | 353762.1
5-02-03-010-00 | Office Supplies Expenses | SSBN | Neg 53.9 | [17 empty] | SSBN |  | MOOE | [8 empty] | 2023-03-06 | 2023-03-07 | 2023-03-22 | 2023-04-04 | 2023-04-04 | MOOE | 35000 | 35000 |  | 34744.2 | 34744.2
5-02-03-990-00 | Other Supplies Expenses | SSBN | Neg 53.9 | [17 empty] | SSBN |  | MOOE | [8 empty] | 2023-03-06 | 2023-03-07 | 2023-03-22 | 2023-03-28 | 2023-03-28 | MOOE | 29000 | 29000 |  | 28935 | 28935
5-02-13-060-01 | R&M Motor Vehicle | SSBN | Neg 53.9 | [17 empty] | SSBN |  | MOOE | [8 empty] | 2023-03-06 | 2023-03-07 | 2023-03-22 | 2023-04-03 | 2023-04-03 | MOOE | 118000 | 118000 |  | 117890 | 117890
5-02-03-210-03 | Semi-EX ICT | 27IB | Neg 53.9 | [17 empty] | 27IB |  | MOOE | [8 empty] | 2023-03-13 | 2023-03-14 | 2023-03-22 | 2023-03-23 | 2023-03-23 | MOOE | 50000 | 50000 |  | 47830 | 47830
5-02-03-220-01 | Semi-EX - Furniture & Fixture | 10CMOBN | Neg 53.9 | [17 empty] | 10CMOBN |  | MOOE | [8 empty] | 2023-03-13 | 2023-03-14 | 2023-03-21 | 2023-03-24 | 2023-03-24 | MOOE | 76608 | 76608 |  | 69100 | 69100
5-02-13-040-01 | R&M Building | 10CMOBN | Neg 53.9 | [17 empty] | 10CMOBN |  | MOOE | [8 empty] | 2023-03-13 | 2023-03-14 | 2023-03-22 | 2023-04-04 | 2023-04-04 | MOOE | 55000 | 55000 |  | 53211 | 53211
5-02-13-040-99 | R&M Other Structure | 10CMOBN | Neg 53.9 | [17 empty] | 10CMOBN |  | MOOE | [8 empty] | 2023-03-09 | 2023-03-10 | 2023-03-22 | 2023-04-04 | 2023-04-04 | MOOE | 30000 | 30000 |  | 28500 | 28500
5-02-03-210-00 | Semi-EX Other Machinery | 25IB | Neg 53.9 | [17 empty] | 25IB |  | MOOE | [8 empty] | 2023-03-13 | 2023-03-14 | 2023-03-21 | 2023-03-24 | 2023-03-24 | MOOE | 31250 | 31250 |  | 28700 | 28700
5-02-13040-00 | R&M Building | 25IB | Neg 53.9 | [17 empty] | 25IB |  | MOOE | [8 empty] | 2023-03-13 | 2023-03-14 | 2023-03-21 | 2023-05-11 | 2023-05-11 | MOOE | 70000 | 70000 |  | 69820 | 69820
5-02-03-060-01 | R&M Motor Vehicle | TFD | Neg 53.9 | [17 empty] | TFD |  | MOOE | [8 empty] | 2023-03-13 | 2023-03-14 | 2023-03-29 | 2023-04-03 | 2023-04-03 | MOOE | 130000 | 130000 |  | 129916 | 129916
5-02-13-060-04 | R&M Watercrafts | TFD | Neg 53.9 | [17 empty] | TFD |  | MOOE | [8 empty] | 2023-03-13 | 2023-03-14 | 2023-03-27 | 2023-05-11 | 2023-05-11 | MOOE | 45000 | 45000 |  | 44980 | 44980
5-02-03-010-00 | Office Supplies Expenses | 10MIB | Neg 53.9 | [17 empty] | 10MIB |  | MOOE | [8 empty] | 2023-03-20 | 2023-03-21 | 2023-03-27 | 2023-04-04 | 2023-04-04 | MOOE | 77525 | 77525 |  | 75126.5 | 75126.5
5-02-13-060-01 | R&M Motor Vehicle | 10MIB | Neg 53.9 | [17 empty] | 10MIB |  | MOOE | [8 empty] | 2023-03-20 | 2023-03-21 | 2023-03-27 | 2023-04-03 | 2023-04-03 | MOOE | 86000 | 86000 |  | 85400 | 85400
5-02-13-040-01 | R&M Building | 60IB | Neg 53.9 | [17 empty] | 60IB |  | MOOE | [8 empty] | 2023-03-16 | 2023-03-17 | 2023-03-28 | 2023-05-11 | 2023-05-11 | MOOE | 29000 | 29000 |  | 28971 | 28971
5-02-03-010-02 | Office Supplies Expenses | 60IB | Neg 53.9 | [17 empty] | 60IB |  | MOOE | [8 empty] | 2023-03-16 | 2023-03-17 | 2023-03-27 | 2023-04-04 | 2023-04-04 | MOOE | 10000 | 10000 |  | 9906.5 | 9906.5
5-02-03-010-02 | Office Supplies Expenses | 66IB | Neg 53.9 | [17 empty] | 66IB |  | MOOE | [8 empty] | 2023-03-16 | 2023-03-17 | 2023-03-29 | 2023-04-04 | 2023-04-04 | MOOE | 15000 | 15000 |  | 14907.75 | 14907.75
5-02-03-210-00 | Semi-EX Mil, Pol & Sec Equipt | 66IB | Neg 53.9 | [17 empty] | 66IB |  | MOOE | [8 empty] | 2023-03-16 | 2023-03-17 | 2023-03-30 | 2023-04-11 | 2023-04-11 | MOOE | 20000 | 20000 |  | 18700 | 18700
5-02-03-210-03 | Semi-EX ICT | 66IB | Neg 53.9 | [17 empty] | 66IB |  | MOOE | [8 empty] | 2023-03-20 | 2023-03-21 | 2023-03-28 | 2023-04-03 | 2023-04-03 | MOOE | 103000 | 103000 |  | 99897.5 | 99897.5
5-02-03-990-00 | Other Supplies Expenses | 66IB | Neg 53.9 | [17 empty] | 66IB |  | MOOE | [8 empty] | 2023-03-16 | 2023-03-17 | 2023-03-30 | 2023-04-11 | 2023-04-11 | MOOE | 15500 | 15500 |  | 15300 | 15300
5-02-13-040-01 | R&M Building | 66IB | Neg 53.9 | [17 empty] | 66IB |  | MOOE | [8 empty] | 2023-03-20 | 2023-03-21 | 2023-03-28 | 2023-05-24 | 2023-05-24 | MOOE | 95400 | 95400 |  | 95345 | 95345
5-02-03-210-99 | Semi-EX Other Machinery | 66IB | Neg 53.9 | [17 empty] | 66IB |  | MOOE | [8 empty] | 2023-03-16 | 2023-03-17 | 2023-03-30 | 2023-04-11 | 2023-04-11 | MOOE | 45000 | 45000 |  | 44975 | 44975
5-02-03-080-00 | Med, Dent & Lab Sup Exp | 66IB | Neg 53.9 | [17 empty] | 66IB |  | MOOE | [8 empty] | 2023-03-16 | 2023-03-17 | 2023-03-29 | 2023-04-20 | 2023-04-20 | MOOE | 10000 | 10000 |  | 9970 | 9970
5-02-13-040-99 | R&M Other Structure | 28IB | Neg 53.9 | [17 empty] | 28IB |  | MOOE | [8 empty] | 2023-03-17 | 2023-03-20 | 2023-03-28 | 2023-05-11 | 2023-05-11 | MOOE | 29000 | 29000 |  | 28766 | 28766
5-02-13-040-01 | R&M Building | 28IB | Neg 53.9 | [17 empty] | 28IB |  | MOOE | [8 empty] | 2023-03-17 | 2023-03-20 | 2022-03-29 | 2023-05-11 | 2023-05-11 | MOOE | 10962 | 10962 |  | 10750 | 10750
5-02-13-210-03 | R&M ICT | 25IB | Neg 53.9 | [17 empty] | 25IB |  | MOOE | [8 empty] | 2023-03-20 | 2023-03-21 | 2023-03-29 | 2023-04-03 | 2023-04-03 | MOOE | 36000 | 36000 |  | 35121 | 35121
5-02-03-210-00 | Semi-Ex - ICT | 25IB | Neg 53.9 | [17 empty] | 25IB |  | MOOE | [8 empty] | 2023-03-21 | 2023-03-22 | 2023-03-29 | 2023-05-03 | 2023-05-03 | MOOE | 60000 | 60000 |  | 58999 | 58999
5-02-03-210-08 | Semi-Ex - DRR Equipment | 2FAB | Neg 53.9 | [17 empty] | 2FAB |  | MOOE | [8 empty] | 2023-03-20 | 2023-03-21 | 2023-03-27 | 2023-04-11 | 2023-04-11 | MOOE | 25000 | 25000 |  | 24900 | 24900
5-02-03-210-09 | Semi-EX Mil, Pol & Sec Equipt | 2FAB | Neg 53.9 | [17 empty] | 2FAB |  | MOOE | [8 empty] | 2023-03-21 | 2023-03-22 | 2023-03-30 | 2023-04-11 | 2023-04-11 | MOOE | 104000 | 104000 |  | 102370 | 102370
5-02-03-990-00 | Other Supplies Expenses | 2FAB | Neg 53.9 | [17 empty] | 2FAB |  | MOOE | [8 empty] | 2023-03-20 | 2023-03-21 | 2023-03-27 | 2023-04-11 | 2023-04-11 | MOOE | 6000 | 6000 |  | 5340 | 5340
5-02-03-210-03 | Semi-Ex - ICT | 2FAB | Neg 53.9 | [17 empty] | 2FAB |  | MOOE | [8 empty] | 2023-03-21 | 2023-03-22 | 2023-03-29 | 2023-04-03 | 2023-04-03 | MOOE | 276000 | 276000 |  | 273426 | 273426
502-03-210-07 | Semi-Ex Commo Equipt | 2FAB | Neg 53.9 | [17 empty] | 2FAB |  | MOOE | [8 empty] | 2023-03-20 | 2023-03-21 | 2023-03-30 | 2023-04-03 | 2023-04-03 | MOOE | 27000 | 27000 |  | 21600 | 21600
5-02-03-210-03 | Semi-Ex - ICT | 66IB | Neg 53.9 | [17 empty] | 66IB |  | MOOE | [8 empty] | 2022-03-21 | 2023-03-22 | 2023-03-29 | 2023-05-03 | 2023-05-03 | MOOE | 60000 | 60000 |  | 58999 | 58999
5-02-03-210-03 | Semi-Ex - ICT | 102DRC | Neg 53.9 | [17 empty] | 102DRC |  | MOOE | [8 empty] | 2023-03-24 | 2023-03-27 | 2023-03-29 | 2023-04-03 | 2023-04-03 | MOOE | 42000 | 42000 |  | 41800 | 41800
5-02-03-010-02 | Office Supplies Expenses | 10DTS | Neg 53.9 | [17 empty] | 10DTS |  | MOOE | [8 empty] | 2023-03-29 | 2023-03-30 | 2023-04-18 | 2023-04-19 | 2023-04-19 | MOOE | 25998.75 | 25998.75 |  | 25978.85 | 25978.85
5-02-13-040-01 | R&M Building | 10DTS | Neg 53.9 | [17 empty] | 10DTS |  | MOOE | [8 empty] | 2023-03-29 | 2023-03-30 | 2023-04-18 | 2023-04-26 | 2023-04-26 | MOOE | 70000 | 70000 |  | 69980.25 | 69980.25
5-02-13-040-99 | R&M Other Structure | 10DTS | Neg 53.9 | [17 empty] | 10DTS |  | MOOE | [8 empty] | 2023-03-29 | 2023-03-30 | 2023-04-18 | 2023-04-26 | 2023-04-26 | MOOE | 30000 | 30000 |  | 29982 | 29982
5-02-03-010-00 | Office Supplies Expenses | 2FAB | Neg 53.9 | [17 empty] | 2FAB |  | MOOE | [8 empty] | 2023-03-29 | 2023-03-30 | 2023-04-11 | 2023-04-19 | 2023-04-19 | MOOE | 30000 | 30000 |  | 29977.8 | 29977.8
5-02-03-990-00 | Other Supplies Expenses | 1002BDE | Neg 53.9 | [17 empty] | 1002BDE |  | MOOE | [8 empty] | 2023-03-29 | 2023-03-30 | 2023-04-11 | 2023-04-19 | 2023-04-19 | MOOE | 39000 | 39000 |  | 35649.3 | 35649.3
5-02-03-080-00 | Med, Dent & Lab Sup Exp | 1002BDE | Neg 53.9 | [17 empty] | 1002BDE |  | MOOE | [8 empty] | 2023-03-31 | 2023-04-03 | 2023-04-11 | 2023-04-20 | 2023-04-20 | MOOE | 50000 | 50000 |  | 49135 | 49135
5-02-03-010-02 | Office Supplies Expenses | 1002BDE | Neg 53.9 | [17 empty] | 1002BDE |  | SPP | [8 empty] | 2023-03-31 | 2023-04-03 | 2023-04-18 | 2023-04-19 | 2023-04-19 | MOOE | 97400 | 97400 |  | 95088.75 | 95088.75
5-02-03-210-00 | Semi-EX ICT | 1002BDE | Neg 53.9 | [17 empty] | 1002BDE |  | MOOE | [8 empty] | 2023-03-31 | 2023-04-03 | 2023-04-11 | 2023-05-18 | 2023-05-18 | MOOE | 60000 | 60000 |  | 58728 | 58728
5-02-13-060-01 | R&M Motor Vehicle | 1002BDE | Neg 53.9 | [17 empty] | 1002BDE |  | MOOE | [8 empty] | 2023-03-31 | 2023-04-03 | 2023-04-11 | 2023-04-20 | 2023-04-20 | MOOE | 167000 | 167000 |  | 164800 | 164800
5-02-13-050-03 | R&M ICT | 1002BDE | Neg 53.9 | [17 empty] | 1002BDE |  | MOOE | [8 empty] | 2023-04-03 | 2023-04-04 | 2023-04-25 | 2023-05-03 | 2023-05-03 | MOOE | 41371 | 41371 |  | 40695 | 40695
5-02-03-210-03 | Semi-Ex ICT | 73IB | Neg 53.9 | [17 empty] | 73IB |  | MOOE | [8 empty] | 2023-04-03 | 2023-04-04 | 2023-04-18 | 2023-05-18 | 2023-05-18 | MOOE | 60000 | 60000 |  | 58999 | 58999
5-02-13-040-01 | R&M Building | 73IB | Neg 53.9 | [17 empty] | 73IB |  | MOOE | [8 empty] | 2023-04-03 | 2023-04-04 | 2023-04-18 | 2023-04-26 | 2023-04-26 | MOOE | 15000 | 15000 |  | 14998.75 | 14998.75
5-02-03-010-01 | Office Supplies Exp - ICT | 10IMB | Neg 53.9 | [17 empty] | 10IMB |  | MOOE | [8 empty] | 2023-04-03 | 2023-04-04 | 2023-04-25 | 2023-05-03 | 2023-05-03 | MOOE | 10000 | 10000 |  | 9780 | 9780
5-02-03-210-03 | Semi-EX ICT | 10IMB | Neg 53.9 | [17 empty] | 10IMB |  | MOOE | [8 empty] | 2023-04-03 | 2023-04-04 | 2023-04-25 | 2023-05-03 | 2023-05-03 | MOOE | 39555 | 39555 |  | 39550 | 39550
5-02-03-010-02 | Office Supplies Expenses | 10IMB | Neg 53.9 | [17 empty] | 10IMB |  | MOOE | [8 empty] | 2023-04-04 | 2023-04-05 | 2023-04-25 | 2023-05-02 | 2023-05-02 | MOOE | 66596 | 66596 |  | 66393 | 66393
5-02-03-220-01 | Furnitures & Fixtures Exp | 10IMB | Neg 53.9 | [17 empty] | 10IMB |  | MOOE | [8 empty] | 2023-04-11 | 2023-04-12 | 2023-04-25 | 2023-05-04 | 2023-05-04 | MOOE | 45000 | 45000 |  | 44290 | 44290
5-02-03-210-01 | Semi-EX Mil, Pol & Sec Equipt | 10IMB | Neg 53.9 | [17 empty] | 10IMB |  | MOOE | [8 empty] | 2023-04-11 | 2023-04-12 | 2023-04-25 | 2023-05-04 | 2023-05-04 | MOOE | 30000 | 30000 |  | 21350 | 21350
5-02-13-040-01 | R&M Building | 1003BDE | Neg 53.9 | [17 empty] | 1003BDE |  | SPP | [8 empty] | 2023-04-11 | 2023-04-12 | 2023-04-28 | 2023-05-08 | 2023-05-08 | MOOE | 83000 | 83000 |  | 81310 | 81310
5-02-13-050-03 | R&M ICT | 1003BDE | Neg 53.9 | [17 empty] | 1003BDE |  | MOOE | [8 empty] | 2023-04-11 | 2023-04-12 | 2023-04-28 | 2023-05-08 | 2023-05-08 | MOOE | 25690 | 25690 |  | 25550 | 25550
5-02-13-040-99 | R&M Other Structure | 1001BDE | Neg 53.9 | [17 empty] | 1001BDE |  | MOOE | [8 empty] | 2023-04-14 | 2023-04-17 | 2023-04-25 | 2023-05-17 | 2023-05-17 | MOOE | 30000 | 30000 |  | 27975 | 27975
5-02-03-210-99 | Semi-EX Other Machinery | 1001BDE | Neg 53.9 | [17 empty] | 1001BDE | [10 empty] | 2023-04-14 | 2023-04-17 | 2023-04-25 | 2023-06-07 |  | MOOE | 15000 | 15000 |  | 14990 | 14990
5-02-03-210-03 | Semi-Ex ICT | 1001BDE | Neg 53.9 | [17 empty] | 1001BDE | [10 empty] | 2023-04-17 | 2023-04-18 | 2023-04-25 | 2023-05-18 |  | MOOE | 60000 | 60000 |  | 58999 | 58999
5-02-03-010-00 | Office Supplies Expenses | 1001BDE | Neg 53.9 | [17 empty] | 1001BDE | [10 empty] | 2023-04-17 | 2023-04-18 | 2023-04-25 | 2023-05-02 |  | MOOE | 62000 | 62000 |  | 54958 | 54958
5-02-03-210-03 | Semi-EX ICT | 1001BDE | Neg 53.9 | [17 empty] | 1001BDE | [10 empty] | 2023-04-16 | 2023-04-17 | 2023-04-25 | 2023-05-03 |  | MOOE | 30000 | 30000 |  | 29700 | 29700
5-+02-03-210-03 | Semi-EX ICT | 39IB | Neg 53.9 | [17 empty] | 39IB | [10 empty] | 2023-04-18 | 2023-04-19 | 2023-04-25 | 2023-05-18 |  | MOOE | 60000 | 60000 |  | 59889 | 59889
5-02-03-210-02 | Semi-EX Office Equipt | 10MIB | Neg 53.9 | [17 empty] | 10MIB | [10 empty] | 2023-04-17 | 2023-04-18 | 2023-04-25 | 2023-05-08 |  | MOOE | 30000 | 30000 |  | 29940 | 29940
5-02-03-070-00 | Drugs & Medicines | 1003BDE | Neg 53.9 | [17 empty] | 1003BDE | [10 empty] | 2023-04-17 | 2023-04-18 | 2023-04-28 | 2023-05-05 |  | MOOE | 10000 | 10000 |  | 9475 | 9475
5-02-03-210-03 | Semi-EX ICT | 10CMOBN | Neg 53.9 | [17 empty] | 10CMOBN | [10 empty] | 2023-04-24 | 2023-04-25 | 2023-05-08 | 2023-05-12 |  | MOOE | 100000 | 100000 |  | 98349 | 98349
5-02-03-210-03 | Semi-EX ICT | 10CMOBN | Neg 53.9 | [17 empty] | 10CMOBN | [10 empty] | 2023-04-24 | 2023-04-25 | 2023-05-08 | 2023-05-12 |  | MOOE | 100000 | 100000 |  | 99999 | 99999
5-02-13-060-01 | R&M Motor Vehicle | 1003BDE | Neg 53.9 | [17 empty] | 1003BDE | [10 empty] | 2023-04-24 | 2023-04-25 | 2023-05-08 | 2023-05-12 |  | MOOE | 92000 | 92000 |  | 91930 | 91930
5-02-03-010-02 | Office Supplies Expenses | 1003BDE | Neg 53.9 | [17 empty] | 1003BDE | [10 empty] | 2023-04-24 | 2023-04-25 | 2023-05-08 | 2023-05-11 |  | MOOE | 61312 | 61312 |  | 56607.5 | 56607.5
5-02-03-990-00 | Other Supplies Expenses | 1003BDE | Neg 53.9 | [17 empty] | 1003BDE | [10 empty] | 2023-04-24 | 2023-04-25 | 2023-05-08 | 2023-05-23 |  | MOOE | 104000 | 104000 |  | 102802.7 | 102802.7
5-02-03-210-99 | Semi-Ex Other Machinery | 67IB | Neg 53.9 | [17 empty] | 67IB | [10 empty] | 2023-04-27 | 2023-04-28 | 2023-05-16 | 2023-05-22 |  | MOOE | 12500 | 12500 |  | 11500 | 11500
5-02-13-040-99 | R&M Other Structure | 67IB | Neg 53.9 | [17 empty] | 67IB | [10 empty] | 2023-04-27 | 2023-04-28 | 2023-05-15 | 2023-05-26 |  | MOOE | 37000 | 37000 |  | 36765 | 36765
5-02-13-040-99 | R&M Building | 67IB | Neg 53.9 | [17 empty] | 67IB | [10 empty] | 2023-04-27 | 2023-04-28 | 2023-05-15 | 2023-05-26 |  | MOOE | 25000 | 25000 |  | 24900 | 24900
5-02-03-210-03 | Semi-EX ICT | 28IB | Neg 53.9 | [17 empty] | 28IB | [10 empty] | 2023-05-02 | 2023-05-03 | 2023-05-11 | 2023-06-07 |  | MOOE | 60000 | 60000 |  | 58999 | 58999
5-02-13-040-01 | R&M Building | TFD | Neg 53.9 | [17 empty] | TFD | [10 empty] | 2023-04-27 | 2023-04-28 | 2023-05-08 | 2023-05-26 |  | MOOE | 29000 | 29000 |  | 28950 | 28950
5-02-13-060-04 | R&M Watercrafts | TFD | Neg 53.9 | [17 empty] | TFD | [10 empty] | 2023-04-27 | 2023-04-28 | 2023-05-08 | 2023-05-24 |  | MOOE | 45000 | 45000 |  | 44968.1 | 44968.1
5-02-03-060-01 | R&M Motor Vehicle | TFD | Neg 53.9 | [17 empty] | TFD | [10 empty] | 2023-04-27 | 2023-04-28 | 2023-05-08 | 2023-05-12 |  | MOOE | 35000 | 35000 |  | 34800 | 34800
5-02-03-210-03 | Semi-EX ICT | 1003BDE | Neg 53.9 | [17 empty] | 1003BDE | [10 empty] | 2023-04-27 | 2023-04-28 | 2023-05-11 | 2023-05-18 |  | MOOE | 34000 | 34000 |  | 25990 | 25990
5-02-13-010-02 | Office Supplies Expenses | 66IB | Neg 53.9 | [17 empty] | 66IB | [10 empty] | 2023-04-28 | 2023-05-02 | 2023-05-16 | 2023-05-24 |  | MOOE | 30000 | 30000 |  | 29930 | 29930
5-02-03-080-00 | Med, Dent & Lab Sup Exp | 66IB | Neg 53.9 | [17 empty] | 66IB | [10 empty] | 2023-04-28 | 2023-05-02 | 2023-05-15 | 2023-05-25 |  | MOOE | 15000 | 15000 |  | 14890 | 14890
5-02-03-210-03 | Semi-EX ICT | 66IB | Neg 53.9 | [17 empty] | 66IB | [10 empty] | 2023-05-02 | 2023-05-03 | 2023-05-11 | 2023-05-18 |  | MOOE | 91000 | 91000 |  | 89294 | 89294
5-02-03-210-08 | Semi-EX DRRO Equipt | 66IB | Neg 53.9 | [17 empty] | 66IB | [10 empty] | 2023-05-02 | 2023-05-03 | 2023-05-16 | 2023-05-22 |  | MOOE | 60000 | 60000 |  | 57700 | 57700
5-02-13-040-01 | R&M Building | 66IB | Neg 53.9 | [17 empty] | 66IB | [10 empty] | 2023-05-02 | 2023-05-03 | 2023-05-15 | 2023-05-26 |  | MOOE | 80000 | 80000 |  | 79990 | 79990
5-20-03-990-00 | Other Supplies Expenses | 10MIB | Neg 53.9 | [17 empty] | 10MIB | [10 empty] | 2023-05-12 | 2023-05-15 | 2023-05-25 | 2023-06-02 |  | MOOE | 81010 | 81010 |  | 80882 | 80882
5-02-03-010-00 | Office Supply Expenses | SSBN | Neg 53.9 | [17 empty] | SSBN | [10 empty] | 2023-05-10 | 2023-05-11 | 2023-05-24 | 2023-05-31 |  | MOOE | 35000 | 35000 |  | 34937.5 | 34937.5
5-02-13-050-03 | R&M ICT | 67IB | Neg 53.9 | [17 empty] | 67IB | [10 empty] | 2023-05-11 | 2023-05-12 | 2023-05-25 | 2023-06-02 |  | MOOE | 18750 | 18750 |  | 18679 | 18679
5-02-03-210-03 | Semi-EX ICT | 67IB | Neg 53.9 | [17 empty] | 67IB | [10 empty] | 2023-05-15 | 2023-05-16 | 2023-05-25 | 2023-06-07 |  | MOOE | 60000 | 60000 |  | 58999 | 58999
5-02-03-990-00 | Other Supplies Expenses | SSBN | Neg 53.9 | [17 empty] | SSBN | [10 empty] | 2023-05-15 | 2023-05-16 | 2023-05-24 | 2023-05-31 |  | MOOE | 31000 | 31000 |  | 30977 | 30977
5-02-03-210-07 | Semi-Ex Commo Equipt | 1003BDE | Neg 53.9 | [17 empty] | 1003BDE | [10 empty] | 2023-05-15 | 2023-05-16 | 2023-05-24 | 2023-06-06 |  | MOOE | 200000 | 200000 |  | 198075 | 198075
5-02-03-990-00 | Other Supplies Expenses | 1001BDE | Neg 53.9 | [17 empty] | 1001BDE | [10 empty] | 2023-05-15 | 2023-05-16 | 2023-05-25 | 2023-06-02 |  | MOOE | 34500 | 34500 |  | 33356 | 33356
5-02-03-080-00 | Med, Dent & Lab Sup Exp | 1001BDE | Neg 53.9 | [17 empty] | 1001BDE | [10 empty] | 2023-05-15 | 2023-05-16 | 2023-05-25 | 2023-06-06 |  | MOOE | 49410 | 49410 |  | 46810 | 46810
5-02-03-010-00 | Office Supplies Expenses | 10MIB | Neg 53.9 | [17 empty] | 10MIB | [10 empty] | 2023-05-15 | 2023-05-16 | 2023-05-24 | 2023-05-31 |  | MOOE | 45700 | 45700 |  | 45623.5 | 45623.5
5-02-03-210-03 | Semi-EX ICT | 60IB | Neg 53.9 | [17 empty] | 60IB | [10 empty] | 2023-05-22 | 2023-05-23 | 2023-05-27 | 2023-06-07 |  | MOOE | 60000 | 60000 |  | 58999 | 58999
5-02-13-040-01 | R&M Building | 25IB | Neg 53.9 | [17 empty] | 25IB | [10 empty] | 2023-05-22 | 2023-05-23 | 2023-05-27 | 2023-06-07 |  | MOOE | 18200 | 18200 |  | 18170 | 18170
5-02-13-060-01 | R&M Motor Vehicle | 1001BDE | Neg 53.9 | [17 empty] | 1001BDE | [10 empty] | 2023-05-22 | 2023-05-23 | 2023-06-01 | 2023-06-15 |  | MOOE | 110500 | 110500 |  | 100400 | 100400
5-02-13-060-01 | R&M Motor Vehicle | SSBN | Neg 53.9 | [17 empty] | SSBN | [10 empty] | 2023-05-22 | 2023-05-23 | 2023-06-01 | 2023-06-07 |  | MOOE | 115000 | 115000 |  | 114960 | 114960
5-02-13-060-01 | R&M Motor Vehicle | 10MIB | Neg 53.9 | [17 empty] | 10MIB | [10 empty] | 2023-05-22 | 2023-05-23 | 2023-06-01 | 2023-06-07 |  | MOOE | 86000 | 86000 |  | 85400 | 85400
5-02-03-990-00 | Other Supplies Expenses | 66IB | Neg 53.9 | [17 empty] | 66IB | [10 empty] | 2023-05-22 | 2023-05-23 | 2023-05-29 | 2023-06-07 |  | MOOE | 35500 | 35500 |  | 35275 | 35275
5-02-03-210-99 | Semi-Ex Other Machinery | 25IB | Neg 53.9 | [17 empty] | 25IB | [10 empty] | 2023-05-22 | 2023-05-23 | 2023-05-29 | 2023-06-07 |  | MOOE | 31250 | 31250 |  | 29980 | 29980
5-02-13-210-03 | R&M ICT | 25IB | Neg 53.9 | [17 empty] | 25IB | [10 empty] | 2023-05-22 | 2023-05-23 | 2023-05-27 | 2023-06-02 |  | MOOE | 36000 | 36000 |  | 35770 | 35770
5-02-03-210-03 | Semi-EX ICT | 25IB | Neg 53.9 | [17 empty] | 25IB | [10 empty] | 2023-05-22 | 2023-05-23 | 2023-06-01 | 2023-06-07 |  | MOOE | 65500 | 65500 |  | 60800 | 60800
5-02-03-210-07 | Semi-Ex Commo Equipt | 10DTS | Neg 53.9 | [17 empty] | 10DTS | [10 empty] | 2023-05-24 | 2023-05-25 | 2023-05-27 | 2023-06-06 |  | MOOE | 17498.25 | 17498.25 |  | 17465 | 17465
5-02-13-060-01 | R&M Motor Vehicle | 10DTS | Neg 53.9 | [17 empty] | 10DTS | [10 empty] | 2023-05-24 | 2023-05-25 | 2023-06-01 | 2023-06-07 |  | MOOE | 8800 | 8800 |  | 8780 | 8780
5-02-13-210-03 | R&M ICT | 10DTS | Neg 53.9 | [17 empty] | 10DTS | [10 empty] | 2023-05-24 | 2023-05-25 | 2023-05-27 | 2023-06-02 |  | MOOE | 44991 | 44991 |  | 44970 | 44970
5-02-03-010-02 | Office Supplies Expenses | 10DTS | Neg 53.9 | [17 empty] | 10DTS | [10 empty] | 2023-05-24 | 2023-05-25 | 2023-06-01 | 2023-06-07 |  | MOOE | 29399.75 | 29399.75 |  | 29309.75 | 29309.75
5-02-13-040-99 | R&M Other Structure | 10DTS | Neg 53.9 | [17 empty] | 10DTS | [10 empty] | 2023-05-24 | 2023-05-25 | 2023-05-27 | 2023-06-07 |  | MOOE | 24000 | 24000 |  | 23908 | 23908
5-02-13-040-01 | R&M Building | 10DTS | Neg 53.9 | [17 empty] | 10DTS | [10 empty] | 2023-05-24 | 2023-05-25 | 2023-05-27 | 2023-06-07 |  | MOOE | 44900 | 44900 |  | 44864 | 44864
5-0203-080-00 | Med, Dent & Lab Sup Exp | 10DTS | Neg 53.9 | [17 empty] | 10DTS | [10 empty] | 2023-05-25 | 2023-05-26 | 27 maa 2 | 2023-06-02 |  | MOOE | 7000 | 7000 |  | 6992 | 6992
5-02-03-210-03 | Semi-EX ICT | 27IB | Neg 53.9 | [17 empty] | 27IB | [10 empty] | 2023-05-29 | 2023-05-30 | 2023-06-01 | 2023-06-07 |  | MOOE | 49999 | 49999 |  | 40995 | 40995
5-02-03-210-03 | Semi-EX ICT | 27IB | Neg 53.9 | [17 empty] | 27IB | [10 empty] | 2023-05-29 | 2023-05-30 | 2023-06-01 | 2023-06-07 |  | MOOE | 17820 | 17820 |  | 14479 | 14479
5-02-03-990-00 | Other Supplies Expenses | 27IB | Neg 53.9 | [17 empty] | 27IB | [10 empty] | 2023-05-29 | 2023-05-30 | 2023-06-01 | 2023-06-07 |  | MOOE | 31060 | 31060 |  | 30883 | 30883
5-02-03-010-02 | Office Supplies Expenses | 27IB | Neg 53.9 | [17 empty] | 27IB | [10 empty] | 2023-05-29 | 2023-05-30 | 2023-06-01 | 2023-06-07 |  | MOOE | 10940 | 10940 |  | 10776 | 10776
5-02-05-040-00 | Cable Expenses | OG6 | Dir Cont | [17 empty] | OG6 | [15 empty] | MOOE | 690 | 690 |  | 690 | 690
5-02-05-030-00 | Internet Subcription | OG6 | Dir Cont | [17 empty] | OG6 | [15 empty] | MOOE | 33600 | 33600 |  | 33600 | 33600
5-02-05-040-00 | Cable Expenses | OG6 | Dir Cont | [17 empty] | OG6 | [15 empty] | MOOE | 1810 | 1810 |  | 1810 | 1810
5-02-05-040-00 | Cable Expenses | OG6 | Dir Cont | [17 empty] | OG6 | [15 empty] | MOOE | 1580 | 1580 |  | 1580 | 1580
5-02-05-040-00 | Cable Expenses | OG6 | Dir Cont | [17 empty] | OG6 | [15 empty] | MOOE | 1580 | 1580 |  | 1580 | 1580
5-02-05-040-00 | Cable Expenses | OG6 | Dir Cont | [17 empty] | OG6 | [15 empty] | MOOE | 690 | 690 |  | 690 | 690
5-02-05-020-01 | Mobile Expenses | OG6 | Dir Cont | [17 empty] | OG6 | [15 empty] | MOOE | 3000 | 3000 |  | 3000 | 3000
5-02-05-040-00 | Cable Expenses | OG6 | Dir Cont | [17 empty] | OG6 | [15 empty] | MOOE | 2580 | 2580 |  | 2580 | 2580
5-02-05-030-00 | Internet Subcription | OG6 | Dir Cont | [17 empty] | OG6 | [15 empty] | MOOE | 6000 | 6000 |  | 6000 | 6000
5-02-05-030-00 | Internet Subcription | OG6 | Dir Cont | [17 empty] | OG6 | [15 empty] | MOOE | 3133.71 | 3133.71 |  | 3133.71 | 3133.71
5-02-05-020-01 | Mobile Expenses | OG6 | Dir Cont | [17 empty] | OG6 | [15 empty] | MOOE | 999 | 999 |  | 999 | 999
5-02-05-040-00 | Cable Expenses | OG6 | Dir Cont | [17 empty] | OG6 | [15 empty] | MOOE | 1100 | 1100 |  | 1100 | 1100
5-02-05-020-01 | Cable Expenses | OG6 | Dir Cont | [17 empty] | OG6 | [15 empty] | MOOE | 1580 | 1580 |  | 1580 | 1580
5-02-05-030-00 | Cable Expenses | OG6 | Dir Cont | [17 empty] | OG6 | [15 empty] | MOOE | 1580 | 1580 |  | 1580 | 1580
5-02-05-040-00 | Internet Subcription | OG6 | Dir Cont | [17 empty] | OG6 | [15 empty] | MOOE | 6000 | 6000 |  | 6000 | 6000
5-02-05-040-00 | Cable Expenses | OG6 | Dir Cont | [17 empty] | OG6 | [15 empty] | MOOE | 690 | 690 |  | 690 | 690
5-02-05-030-00 | Cable Expenses | OG6 | Dir Cont | [17 empty] | OG6 | [15 empty] | MOOE | 690 | 690 |  | 690 | 690
5-02-05-040-00 | Cable Expenses | OG6 | Dir Cont | [17 empty] | OG6 | [15 empty] | MOOE | 1810 | 1810 |  | 1810 | 1810
5-02-05-040-00 | Cable Expenses | OG6 | Dir Cont | [17 empty] | OG6 | [15 empty] | MOOE | 690 | 690 |  | 690 | 690
5-02-05-040-00 | Cable Expenses | OG6 | Dir Cont | [17 empty] | OG6 | [15 empty] | MOOE | 2580 | 2580 |  | 2580 | 2580
5-02-05-040-00 | Internet Subcription | 67IB | Dir Cont | [17 empty] | 67IB | [15 empty] | MOOE | 5137.34 | 5137.34 |  | 5137.34 | 5137.34
5-02-05-040-00 | Internet Subcription | 67IB | Dir Cont | [17 empty] | 67IB | [15 empty] | MOOE | 5137.34 | 5137.34 |  | 5137.34 | 5137.34
5-02-05-030-00 | Cable Expenses | OG6 | Dir Cont | [17 empty] | OG6 | [15 empty] | MOOE | 1810 | 1810 |  | 1810 | 1810
5-02-05-030-00 | Cable Expenses | OG6 | Dir Cont | [17 empty] | OG6 | [15 empty] | MOOE | 1580 | 1580 |  | 1580 | 1580
5-02-00-040-00 | Cable Expenses | OG6 | Dir Cont | [17 empty] | OG6 | [15 empty] | MOOE | 1580 | 1580 |  | 1580 | 1580
5-02-05-040-00 | Internet Subcription | OG6 | Dir Cont | [17 empty] | OG6 | [15 empty] | MOOE | 6000 | 6000 |  | 6000 | 6000
5-02-05-040-00 | Cable Expenses | OG6 | Dir Cont | [17 empty] | OG6 | [15 empty] | MOOE | 2580 | 2580 |  | 2580 | 2580
5-02-05-030-00 | Cable Expenses | OG6 | Dir Cont | [17 empty] | OG6 | [15 empty] | MOOE | 690 | 690 |  | 690 | 690
5-02-05-040-00 | Cable Expenses | OG6 | Dir Cont | [17 empty] | OG6 | [15 empty] | MOOE | 690 | 690 |  | 690 | 690
5-02-05-040-00 | Internet Subcription | 10MIB | Dir Cont | [17 empty] | 10MIB | [15 empty] | MOOE | 7840 | 7840 |  | 7840 | 7840
5-02-05-040-00 | Cable Expenses | 66IB | Dir Cont | [17 empty] | 66IB | [15 empty] | MOOE | 2200 | 2200 |  | 2200 | 2200
5-02-03-030-00 | Mobile Expenses | 66IB | Dir Cont | [17 empty] | 66IB | [15 empty] | MOOE | 996 | 996 |  | 996 | 996
5-02-05-040-00 | Internet Subcription | 10MIB | Dir Cont | [17 empty] | 10MIB | [15 empty] | MOOE | 1299 | 1299 |  | 1299 | 1299
5-02-05-020-01 | Internet Subcription | 67IB | Dir Cont | [17 empty] | 67IB | [15 empty] | MOOE | 9181.34 | 9181.34 |  | 9181.34 | 9181.34
5-02-05-020-01 | Internet Subcription | 10CMOBN | Dir Cont | [17 empty] | 10CMOBN | [15 empty] | MOOE | 8372.36 | 8372.36 |  | 8372.36 | 8372.36
5-02-05-030-00 | Internet Subcription | 10CMOBN | Dir Cont | [17 empty] | 10CMOBN | [15 empty] | MOOE | 1898 | 1898 |  | 1898 | 1898
5-02-05-040-00 | Internet Subcription | OG6 | Dir Cont | [17 empty] | OG6 | [15 empty] | MOOE | 6000 | 6000 |  | 6000 | 6000
5-02-05-030-00 | Cable Expenses | OG6 | Dir Cont | [17 empty] | OG6 | [15 empty] | MOOE | 2580 | 2580 |  | 2580 | 2580
5-02-05-030-00 | Cable Expenses | OG6 | Dir Cont | [17 empty] | OG6 | [15 empty] | MOOE | 1580 | 1580 |  | 1580 | 1580
5-02-03-030-00 | Cable Expenses | OG6 | Dir Cont | [17 empty] | OG6 | [15 empty] | MOOE | 690 | 690 |  | 690 | 690
5-02-03-030-00 | Cable Expenses | OG6 | Dir Cont | [17 empty] | OG6 | [15 empty] | MOOE | 690 | 690 |  | 690 | 690
5-02-03-030-00 | Cable Expenses | OG6 | Dir Cont | [17 empty] | OG6 | [15 empty] | MOOE | 690 | 690 |  | 690 | 690
5-02-05-040-00 | Mobile Expenses | OG6 | Dir Cont | [17 empty] | OG6 | [15 empty] | MOOE | 3900 | 3900 |  | 3900 | 3900
5-02-05-040-00 | Internet Subcription | 1003Bde | Dir Cont | [17 empty] | 1003Bde | [15 empty] | MOOE | 4999 | 4999 |  | 4999 | 4999
5-02-05-040-00 | Internet Subcription | 10MIB | Dir Cont | [17 empty] | 10MIB | [15 empty] | MOOE | 1299 | 1299 |  | 1299 | 1299
5-02-05-040-00 | Internet Subcription | 1003BDE | Dir Cont | [17 empty] | 1003BDE | [15 empty] | MOOE | 4889.1 | 4889.1 |  | 4889.1 | 4889.1
5-02-05-040-00 | Internet Subcription | 10MIB | Dir Cont | [17 empty] | 10MIB | [15 empty] | MOOE | 1217.82 | 1217.82 |  | 1217.82 | 1217.82
5-02-05-020-01 | Internet Subcription | 10MIB | Dir Cont | [17 empty] | 10MIB | [15 empty] | MOOE | 7350 | 7350 |  | 7350 | 7350
Total Alloted Budget of Procurement Activities | [37 empty] | 6263933.86
Total Contract Price of Procurement Actitvites Conducted | [40 empty] | 6129503.31 | [10 empty] | 6128503.31
Total Savings (Total Alloted Budget - Total Contract Price) | [37 empty] | 134430.55
0N-GOING PROCUREMENT ACTIVITIES
5-02-03-010-02 | Office Supplies Expenses | 60IB | Neg 53.9 | [17 empty] | 60IB | [10 empty] | 2023-04-28 | 2023-05-02 | 2023-05-15 |  |  | MOOE | 15000 | 15000 |  | 13932.6 | 13932.6
5-02-03-210-07 | Semi-Ex Commo Equipt | 67IB | Neg 53.9 | [17 empty] | 67IB | [10 empty] | 2023-05-15 | 2023-05-16 | 2023-05-26 |  |  | MOOE | 60000 | 60000 |  | 54300 | 54300
5-02-03-210-00 | Semi-EX Office Equipt | 28IB | Neg 53.9 | [17 empty] | 28IB | [10 empty] | 2023-06-05 | 2023-06-06 |  |  |  | MOOE | 166500 | 166500 |  | 162200 | 162200
5-02-13-040-01 | R&M Building | 39IB | Neg 53.9 | [17 empty] | 39IB | [10 empty] | 2023-06-05 | 2023-06-06 |  |  |  | MOOE | 93800 | 93800 |  | 92980 | 92980
5-02-03-080-00 | Med, Dent & Lab Sup Exp | 28IB | Neg 53.9 | [17 empty] | 28IB | [10 empty] | 2023-06-05 | 2023-06-06 |  |  |  | MOOE | 34000 | 34000 |  | 33830 | 33830
5-02-03-010-00 | Office Supplies Expenses | 1003BDE | Neg 53.9 | [17 empty] | 1003BDE | [10 empty] | 2023-06-09 | 2023-06-13 |  |  |  | MOOE | 58949 | 58949 |  | 51982 | 51982
5-02-13-060-01 | R&M Motor Vehicle | 1003BDE | Neg 53.9 | [17 empty] | 1003BDE | [10 empty] | 2023-06-09 | 2023-06-13 |  |  |  | MOOE | 112000 | 112000 |  | 111270 | 111270
5-02-13-210-99 | R&M Other Machinery | 1003BDE | Neg 53.9 | [17 empty] | 1003BDE | [10 empty] | 2023-06-09 | 2023-06-13 |  |  |  | MOOE | 90000 | 90000 |  | 83690 | 83690
5-02-03-210-03 | Semi-EX ICT | OG4 | Neg 53.9 | [17 empty] | OG4 | [10 empty] | 2023-06-09 | 2023-06-13 |  |  |  | MOOE | 25890 | 25890 |  | 25850 | 25850
5-02-03-010-01 | Office Supplies Expenses | OG4 | Neg 53.9 | [17 empty] | OG4 | [10 empty] | 2023-06-09 | 2023-06-13 |  |  |  | MOOE | 28150 | 28150 |  | 27760 | 27760
5-02-13-040-01 | R&M Building | 1003BDE | Neg 53.9 | [17 empty] | 1003BDE | [10 empty] | 2023-06-13 | 2023-06-14 |  |  |  | MOOE | 90000 | 90000 |  | 80971 | 80971
Total Alloted Budget of On-going Procurement Activities | [37 empty] | 774289
|  | VALIDATED BY: | [33 empty] | NOTED BY:
Formulas:
Inspection & Acceptance = [Delivery/ Completion]
Prepared by:
Edwin P Pagunsan
Ssg (MI) PA
Operations NCO
H E A D Q U A R T E R S
10TH INFANTRY (AGILA) DIVISION, PA
Camp General Manuel T Yan Sr, Brgy Tuboran, Mawab, Davao de Oro
PROJECT MONITORING REPORT
01 Jan to 30 June 2023