## PMR 01 JAN-30 JUN 2023
|  |  | ANNEX A | [14 empty] | ANNEX B
|  |  | Department of Budget and Management Annual Procurement Plan for FY 2006 | [14 empty] | 115th Contracting Office, AFPPS |  |  |  | Procurement Monitoring Report from 01 January - 30 June 2023
| Code (PAP) | Procurement Project | PMO/ End-User | Mode of Procurement | Schedule for Each Procurement Activity | [11 empty] | Source of Funds | PMO/ End-User | Is this an Early Procurement Activity? | Mode of Procurement | Actual Procurement Activity | [12 empty] | Source of Funds | ABC (PhP) |  |  | Contract Cost (PhP) |  |  | List of Invited Observers | Date of Receipt of Invitation | [5 empty] | Remarks (Explaining changes from the APP)
[5 empty] | Pre-Proc Conference | Ads/Post of IAEB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Contract Award | Contract Signing | Notice to Proceed | Delivery/ Accept | Payment Process |  |  |  |  | Pre-Proc Conference | Ads/Post of IB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Date of BAC Resolution Recommending Award | Notice of Award | Contract Signing | Notice to Proceed | Delivery/ Completion | Inspection & Acceptance |  | Total | MOOE | CO | Total | MOOE | CO |  | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Delivery/ Completion/ Acceptance (If applicable)
PROCUREMENT ACTIVITIES
1 | 5-02-02-010-00 | Training Supplies | [15 empty] | 41IB | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-02-02 | 2023-02-02 | 2023-02-02 | N/A | N/A | 2023-02-02 | 2023-02-02 | 2023-02-20 | 2023-02-27 | 2023-02-27 | MOOE | 10000 | 10000 |  | 9865 | 9865 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
2 | 5-02-99-030-00 | Grocery Items | [15 empty] | 104IB | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-02-02 | 2023-02-02 | 2023-02-02 | N/A | N/A | 2023-02-02 | 2023-02-02 | 2023-03-07 | 2023-03-14 | 2023-03-14 | MOOE | 52000 | 52000 |  | 51650 | 51650 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
3 | 5-02-02-010-00 | Training Supplies | [15 empty] | 104IB | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-02-02 | 2023-02-02 | 2023-02-02 | N/A | N/A | 2023-02-02 | 2023-02-02 | 2023-03-06 | 2023-03-14 | 2023-03-14 | MOOE | 92500 | 92500 |  | 92100 | 92100 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
4 | 5-02-99-030-00 | Grocery Items | [15 empty] | 41IB | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-02-02 | 2023-02-02 | 2023-02-02 | N/A | N/A | 2023-02-02 | 2023-02-02 | 2023-02-20 | 2023-03-06 | 2023-03-06 | MOOE | 184000 | 184000 |  | 183350 | 183350 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5 | 5-02-99-030-00 | Grocery Items | [15 empty] | 100IB | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-02-07 | 2023-02-07 | 2023-02-07 | N/A | N/A | 2023-02-07 | 2023-02-07 | 2023-02-20 | 2023-03-06 | 2023-03-06 | MOOE | 13750 | 13750 |  | 13605 | 13605 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
6 | 5-02-05-020-01 | Telephone Expense-Mobile | [15 empty] | 35IB | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-02-07 | 2023-02-07 | 2023-02-07 | N/A | N/A | 2023-02-07 | 2023-02-07 | 2023-02-20 | 2023-03-06 | 2023-03-06 | MOOE | 15000 | 15000 |  | 14940 | 14940 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
7 | 5-02-03-210-08 | DRRE-SE | [15 empty] | 11DTS | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-02-07 | 2023-02-07 | 2023-02-07 | N/A | N/A | 2023-02-07 | 2023-02-07 | 2023-02-20 | 2023-02-28 | 2023-02-28 | MOOE | 50000 | 50000 |  | 49850 | 49850 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
8 | 5-02-03-210-07 | Commo Equipment-SE | [15 empty] | 32IB | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-02-07 | 2023-02-07 | 2023-02-07 | N/A | N/A | 2023-02-07 | 2023-02-07 | 2023-02-28 | 2023-03-07 | 2023-03-07 | MOOE | 45000 | 45000 |  | 44750 | 44750 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
9 | 5-02-03-080-00 | Med Dent Lab Supplies | [15 empty] | 1102Bde | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-02-07 | 2023-02-07 | 2023-02-07 | N/A | N/A | 2023-02-07 | 2023-02-07 | 2023-03-07 | 2023-03-14 | 2023-03-14 | MOOE | 35000 | 35000 |  | 34800 | 34800 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
10 | 5-02-99-030-00 | Grocery Items | [15 empty] | 35IB | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-02-07 | 2023-02-07 | 2023-02-07 | N/A | N/A | 2023-02-07 | 2023-02-07 | 2023-02-28 | 2023-03-07 | 2023-03-07 | MOOE | 8000 | 8000 |  | 7880 | 7880 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
11 | 5-02-02-010-00 | Training Supplies | [15 empty] | 15CMOBN | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-02-08 | 2023-02-08 | 2023-02-08 | N/A | N/A | 2023-02-08 | 2023-02-08 | 2023-02-17 | 2023-02-21 | 2023-02-21 | MOOE | 28000 | 28000 |  | 27745 | 27745 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
12 | 5-02-05-020-01 | Telephone Expense-Mobile | [15 empty] | 1102Bde | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-02-08 | 2023-02-08 | 2023-02-08 | N/A | N/A | 2023-02-08 | 2023-02-08 | 2023-02-17 | 2023-02-21 | 2023-02-21 | MOOE | 10000 | 10000 |  | 9960 | 9960 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
13 | 5-02-99-030-00 | Grocery Items | [15 empty] | 21IB | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-02-08 | 2023-02-08 | 2023-02-08 | N/A | N/A | 2023-02-08 | 2023-02-08 | 2023-02-21 | 2023-03-03 | 2023-03-03 | MOOE | 15000 | 15000 |  | 14810 | 14810 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
14 | 5-02-02-010-00 | Training Supplies | [15 empty] | 21IB | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-02-08 | 2023-02-08 | 2023-02-08 | N/A | N/A | 2023-02-08 | 2023-02-08 | 2023-03-02 | 2023-03-08 | 2023-03-08 | MOOE | 20000 | 20000 |  | 19750 | 19750 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
15 | 5-02-03-070-00 | Drugs & Meds | [15 empty] | 32IB | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-02-07 | 2023-02-07 | 2023-02-07 | N/A | N/A | 2023-02-07 | 2023-02-07 | 2023-03-02 | 2023-03-07 | 2023-03-07 | MOOE | 25000 | 25000 |  | 24720 | 24720 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
16 | 5-02-02-010-00 | Training Supplies | [15 empty] | 32IB | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-02-08 | 2023-02-08 | 2023-02-08 | N/A | N/A | 2023-02-08 | 2023-02-08 | 2023-03-02 | 2023-03-07 | 2023-03-07 | MOOE | 40000 | 40000 |  | 39681 | 39681 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
17 | 5-02-03-210-07 | Commo Equipment-SE | [15 empty] | 1102Bde | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-02-08 | 2023-02-08 | 2023-02-08 | N/A | N/A | 2023-02-08 | 2023-02-08 | 2023-03-02 | 2023-03-07 | 2023-03-07 | MOOE | 30000 | 30000 |  | 29700 | 29700 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
18 | 5-02-13-060-01 | Vehicle Parts & Acc | [15 empty] | 1103Bde | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-02-09 | 2023-02-09 | 2023-02-09 | N/A | N/A | 2023-02-09 | 2023-02-09 | 2023-03-07 | 2023-03-14 | 2023-03-14 | MOOE | 69985 | 69985 |  | 69385 | 69385 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
19 | 5-02-02-010-00 | Training Supplies | [15 empty] | 1103Bde | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-02-09 | 2023-02-09 | 2023-02-09 | N/A | N/A | 2023-02-09 | 2023-02-09 | 2023-03-07 | 2023-03-14 | 2023-03-14 | MOOE | 181000 | 181000 |  | 180520 | 180520 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
20 | 5-02-03-010-00 | Office Supplies | [15 empty] | 1103Bde | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-02-09 | 2023-02-09 | 2023-02-09 | N/A | N/A | 2023-02-09 | 2023-02-09 | 2023-03-06 | 2023-03-06 | 2023-03-06 | MOOE | 150000 | 150000 |  | 149450 | 149450 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
21 | 5-02-99-030-00 | Grocery Items | [15 empty] | 1103Bde | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-02-09 | 2023-02-09 | 2023-02-09 | N/A | N/A | 2023-02-09 | 2023-02-09 | 2023-03-07 | 2023-03-14 | 2023-03-14 | MOOE | 292875 | 292875 |  | 292015 | 292015 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
22 | 5-02-02-010-00 | Training Supplies | [15 empty] | 100IB | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-02-09 | 2023-02-09 | 2023-02-09 | N/A | N/A | 2023-02-09 | 2023-02-09 | 2023-03-07 | 2023-03-14 | 2023-03-14 | MOOE | 57450 | 57450 |  | 57045 | 57045 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
23 | 5-02-99-030-00 | Grocery Items | [15 empty] | 100IB | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-02-09 | 2023-02-09 | 2023-02-09 | N/A | N/A | 2023-02-09 | 2023-02-09 | 2023-03-07 | 2023-03-14 | 2023-03-14 | MOOE | 80000 | 80000 |  | 79680 | 79680 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
24 | 5-02-03-990-00 | Other Supplies | [15 empty] | 21IB | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-02-09 | 2023-02-09 | 2023-02-09 | N/A | N/A | 2023-02-09 | 2023-02-09 | 2023-03-07 | 2023-03-14 | 2023-03-14 | MOOE | 100000 | 100000 |  | 99680 | 99680 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
25 | 5-02-99-030-00 | Grocery Items | [15 empty] | 1102Bde | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-02-09 | 2023-02-09 | 2023-02-09 | N/A | N/A | 2023-02-09 | 2023-02-09 | 2023-03-07 | 2023-03-14 | 2023-03-14 | MOOE | 488700 | 488700 |  | 487720 | 487720 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
26 | 5-02-13-040-01 | Contruction Material & Supplies | [15 empty] | 11DTS | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-02-09 | 2023-02-09 | 2023-02-09 | N/A | N/A | 2023-02-09 | 2023-02-09 | 2023-03-07 | 2023-03-14 | 2023-03-14 | MOOE | 125000 | 125000 |  | 124570 | 124570 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
27 | 5-02-99-030-00 | Grocery Items | [15 empty] | 11DTS | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-02-09 | 2023-02-09 | 2023-02-09 | N/A | N/A | 2023-02-09 | 2023-02-09 | 2023-03-07 | 2023-03-14 | 2023-03-14 | MOOE | 115000 | 115000 |  | 114450 | 114450 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
28 | 5-02-03-210-03 | ICT Equipment-SE | [15 empty] | 11DTS | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-02-09 | 2023-02-09 | 2023-02-09 | N/A | N/A | 2023-02-09 | 2023-02-09 | 2023-03-07 | 2023-03-14 | 2023-03-14 | MOOE | 84000 | 84000 |  | 83550 | 83550 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
29 | 5-02-99-030-00 | Grocery Items | [15 empty] | 32IB | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-02-09 | 2023-02-09 | 2023-02-09 | N/A | N/A | 2023-02-09 | 2023-02-09 | 2023-02-20 | 2023-02-20 | 2023-02-20 | MOOE | 73500 | 73500 |  | 73050 | 73050 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
30 | 5-02-99-030-00 | Grocery Items | [15 empty] | 35IB | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-02-09 | 2023-02-09 | 2023-02-09 | N/A | N/A | 2023-02-09 | 2023-02-09 | 2023-03-07 | 2023-03-14 | 2023-03-14 | MOOE | 59000 | 59000 |  | 58530 | 58530 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
31 | 5-02-02-010-00 | Training Supplies | [15 empty] | 35IB | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-02-09 | 2023-02-09 | 2023-02-09 | N/A | N/A | 2023-02-09 | 2023-02-09 | 2023-03-06 | 2023-03-14 | 2023-03-14 | MOOE | 110000 | 110000 |  | 109365 | 109365 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
32 | 5-02-02-010-00 | Training Supplies | [15 empty] | 1102Bde | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-02-09 | 2023-02-09 | 2023-02-09 | N/A | N/A | 2023-02-09 | 2023-02-09 | 2023-02-20 | 2023-03-06 | 2023-03-06 | MOOE | 100548.25 | 100548.25 |  | 100125.25 | 100125.25 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
33 | 5-02-03-080-00 | Med Dent Lab Supplies | [15 empty] | 11SSBN | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-02-13 | 2023-02-13 | 2023-02-13 | N/A | N/A | 2023-02-13 | 2023-02-13 | 2023-02-20 | 2023-03-06 | 2023-03-06 | MOOE | 40000 | 40000 |  | 39640 | 39640 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
34 | 5-02-03-210-08 | DRRE-SE | [15 empty] | 11ID | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-02-13 | 2023-02-13 | 2023-02-13 | N/A | N/A | 2023-02-13 | 2023-02-13 | 2023-02-20 | 2023-03-06 | 2023-03-06 | MOOE | 10000 | 10000 |  | 9800 | 9800 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
35 | 5-02-05-020-01 | Telephone Expense-Mobile | [15 empty] | 11SSBN | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-02-13 | 2023-02-13 | 2023-02-13 | N/A | N/A | 2023-02-13 | 2023-02-13 | 2023-02-20 | 2023-02-28 | 2023-02-28 | MOOE | 5000 | 5000 |  | 4978 | 4978 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
36 | 5-02-05-040-00 | Cable Expense | [15 empty] | 11SSBN | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-02-13 | 2023-02-13 | 2023-02-13 | N/A | N/A | 2023-02-13 | 2023-02-13 | 2023-02-28 | 2023-03-07 | 2023-03-07 | MOOE | 10000 | 10000 |  | 9960 | 9960 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
37 | 5-02-99-030-00 | Grocery Items | [15 empty] | 1102Bde | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-02-13 | 2023-02-13 | 2023-02-13 | N/A | N/A | 2023-02-13 | 2023-02-13 | 2023-03-07 | 2023-03-14 | 2023-03-14 | MOOE | 32000 | 32000 |  | 31775 | 31775 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
38 | 5-02-03-210-07 | Commo Equipment-SE | [15 empty] | 1103Bde | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-02-13 | 2023-02-13 | 2023-02-13 | N/A | N/A | 2023-02-13 | 2023-02-13 | 2023-03-07 | 2023-03-14 | 2023-03-14 | MOOE | 20000 | 20000 |  | 19700 | 19700 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
39 | 5-02-03-210-03 | ICT Equipment-SE | [15 empty] | 1103Bde | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-02-13 | 2023-02-13 | 2023-02-13 | N/A | N/A | 2023-02-13 | 2023-02-13 | 2023-03-06 | 2023-03-14 | 2023-03-14 | MOOE | 50000 | 50000 |  | 49680 | 49680 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
40 | 5-02-05-040-00 | Cable Expense | [15 empty] | 1103Bde | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-02-13 | 2023-02-13 | 2023-02-13 | N/A | N/A | 2023-02-13 | 2023-02-13 | 2023-02-20 | 2023-03-06 | 2023-03-06 | MOOE | 7500 | 7500 |  | 7480 | 7480 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
41 | 5-02-02-010-00 | Training Supplies | [15 empty] | 11DCAU | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-02-13 | 2023-02-13 | 2023-02-13 | N/A | N/A | 2023-02-13 | 2023-02-13 | 2023-02-20 | 2023-03-06 | 2023-03-06 | MOOE | 50000 | 50000 |  | 49650 | 49650 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
42 | 5-02-02-010-00 | Training Supplies | [15 empty] | 11SSBN | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-02-13 | 2023-02-13 | 2023-02-13 | N/A | N/A | 2023-02-13 | 2023-02-13 | 2023-02-20 | 2023-03-06 | 2023-03-06 | MOOE | 33000 | 33000 |  | 32740 | 32740 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
43 | 5-02-03-080-00 | Med Dent Lab Supplies | [15 empty] | 11DCAU | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-02-13 | 2023-02-13 | 2023-02-13 | N/A | N/A | 2023-02-13 | 2023-02-13 | 2023-02-20 | 2023-02-28 | 2023-02-28 | MOOE | 25000 | 25000 |  | 24800 | 24800 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
44 | 5-02-05-040-00 | Cable Expense | [15 empty] | 11DCAU | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-02-13 | 2023-02-13 | 2023-02-13 | N/A | N/A | 2023-02-13 | 2023-02-13 | 2023-02-28 | 2023-03-07 | 2023-03-07 | MOOE | 6000 | 6000 |  | 5976 | 5976 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
45 | 5-02-02-010-00 | Training Supplies | [15 empty] | 45IB | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-02-13 | 2023-02-13 | 2023-02-13 | N/A | N/A | 2023-02-13 | 2023-02-13 | 2023-03-07 | 2023-03-14 | 2023-03-14 | MOOE | 30000 | 30000 |  | 29760 | 29760 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
46 | 5-02-03-010-01 | Office Supplies-ICT | [15 empty] | 21IB | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-02-13 | 2023-02-13 | 2023-02-13 | N/A | N/A | 2023-02-13 | 2023-02-13 | 2023-03-07 | 2023-03-14 | 2023-03-14 | MOOE | 25000 | 25000 |  | 24690 | 24690 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
47 | 5-02-03-210-08 | DRRE-SE | [15 empty] | 11SSBN | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-02-14 | 2023-02-14 | 2023-02-14 | N/A | N/A | 2023-02-14 | 2023-02-14 | 2023-02-22 | 2023-03-04 | 2023-03-04 | MOOE | 31000 | 31000 |  | 30800 | 30800 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
48 | 5-02-13-040-01 | Construction Material & Supplies | [15 empty] | 11SSBN | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-02-14 | 2023-02-14 | 2023-02-14 | N/A | N/A | 2023-02-14 | 2023-02-14 | 2023-02-22 | 2023-03-04 | 2023-03-04 | MOOE | 35000 | 35000 |  | 34760 | 34760 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
49 | 5-02-03-210-07 | Commo Equipment-SE | [15 empty] | 11SSBN | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-02-14 | 2023-02-14 | 2023-02-14 | N/A | N/A | 2023-02-14 | 2023-02-14 | 2023-02-22 | 2023-03-04 | 2023-03-04 | MOOE | 5000 | 5000 |  | 4900 | 4900 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
50 | 5-02-13-040-01 | Construction Material & Supplies | [15 empty] | 11HHSBN | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-02-14 | 2023-02-14 | 2023-02-14 | N/A | N/A | 2023-02-14 | 2023-02-14 | 2023-02-22 | 2023-03-04 | 2023-03-04 | MOOE | 32700 | 32700 |  | 32400 | 32400 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
51 | 5-02-03-210-99 | Other Machinery-SE | [15 empty] | 11HHSBN | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-02-14 | 2023-02-14 | 2023-02-14 | N/A | N/A | 2023-02-14 | 2023-02-14 | 2023-02-22 | 2023-03-04 | 2023-03-04 | MOOE | 11500 | 11500 |  | 11350 | 11350 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
52 | 5-02-13-060-01 | Vehicle Parts & Acc | [15 empty] | 11HHSBN | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-02-14 | 2023-02-14 | 2023-02-14 | N/A | N/A | 2023-02-14 | 2023-02-14 | 2023-02-22 | 2023-03-04 | 2023-03-04 | MOOE | 34000 | 34000 |  | 33700 | 33700 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
53 | 5-02-02-010-00 | Training Supplies | [15 empty] | 11DTS | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-02-14 | 2023-02-14 | 2023-02-14 | N/A | N/A | 2023-02-14 | 2023-02-14 | 2023-02-22 | 2023-03-04 | 2023-03-04 | MOOE | 50000 | 50000 |  | 49670 | 49670 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
54 | 5-02-13-060-01 | Vehicle Parts & Acc | [15 empty] | 21IB | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-02-14 | 2023-02-14 | 2023-02-14 | N/A | N/A | 2023-02-14 | 2023-02-14 | 2023-02-22 | 2023-03-04 | 2023-03-04 | MOOE | 35000 | 35000 |  | 34780 | 34780 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
55 | 5-02-13-040-01 | Construction Material & Supplies | [15 empty] | 11ID | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-02-14 | 2023-02-14 | 2023-02-14 | N/A | N/A | 2023-02-14 | 2023-02-14 | 2023-02-22 | 2023-03-04 | 2023-03-04 | MOOE | 10000 | 10000 |  | 9850 | 9850 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
56 | 5-02-99-030-00 | Grocery Items | [15 empty] | 11SSBN | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-02-14 | 2023-02-14 | 2023-02-14 | N/A | N/A | 2023-02-14 | 2023-02-14 | 2023-02-22 | 2023-03-04 | 2023-03-04 | MOOE | 231000 | 231000 |  | 230400 | 230400 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
57 | 5-02-99-030-00 | Grocery Items | [15 empty] | 45IB | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-02-14 | 2023-02-14 | 2023-02-14 | N/A | N/A | 2023-02-14 | 2023-02-14 | 2023-02-22 | 2023-03-04 | 2023-03-04 | MOOE | 122000 | 122000 |  | 121595 | 121595 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
58 | 5-02-13-060-01 | Vehicle Parts & Acc | [15 empty] | 1102Bde | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-02-14 | 2023-02-14 | 2023-02-14 | N/A | N/A | 2023-02-14 | 2023-02-14 | 2023-02-22 | 2023-03-04 | 2023-03-04 | MOOE | 245100 | 245100 |  | 244375 | 244375 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
59 | 5-02-99-030-00 | Grocery Items | [15 empty] | 11DCAU | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-02-14 | 2023-02-14 | 2023-02-14 | N/A | N/A | 2023-02-14 | 2023-02-14 | 2023-02-22 | 2023-03-04 | 2023-03-04 | MOOE | 161300 | 161300 |  | 160740 | 160740 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
60 | 5-02-99-030-00 | Grocery Items | [15 empty] | 15CMOBN | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-02-14 | 2023-02-14 | 2023-02-14 | N/A | N/A | 2023-02-14 | 2023-02-14 | 2023-02-22 | 2023-03-04 | 2023-03-04 | MOOE | 309700 | 309700 |  | 309060 | 309060 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
61 | 5-02-13-040-01 | Construction Material & Supplies | [15 empty] | 41IB | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-02-14 | 2023-02-14 | 2023-02-14 | N/A | N/A | 2023-02-14 | 2023-02-14 | 2023-02-22 | 2023-03-04 | 2023-03-04 | MOOE | 61000 | 61000 |  | 60700 | 60700 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
62 | 5-02-13-060-01 | Vehicle Parts & Acc | [15 empty] | 15CMOBN | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-02-14 | 2023-02-14 | 2023-02-14 | N/A | N/A | 2023-02-14 | 2023-02-14 | 2023-02-22 | 2023-03-04 | 2023-03-04 | MOOE | 90000 | 90000 |  | 89640 | 89640 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
63 | 5-02-05-020-01 | Telephone Expense-Mobile | [15 empty] | 15CMOBN | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-02-14 | 2023-02-14 | 2023-02-14 | N/A | N/A | 2023-02-14 | 2023-02-14 | 2023-02-22 | 2023-03-04 | 2023-03-04 | MOOE | 95000 | 95000 |  | 94600 | 94600 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
64 | 5-02-02-010-00 | Training Supplies | [15 empty] | 45IB | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-02-17 | 2023-02-17 | 2023-02-17 | N/A | N/A | 2023-02-17 | 2023-02-17 | 2023-02-27 | 2023-03-08 | 2023-03-08 | MOOE | 52440 | 52440 |  | 52050 | 52050 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
65 | 5-02-02-010-00 | Training Supplies | [15 empty] | 1101Bde | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-02-17 | 2023-02-17 | 2023-02-17 | N/A | N/A | 2023-02-17 | 2023-02-17 | 2023-02-27 | 2023-03-08 | 2023-03-08 | MOOE | 60000 | 60000 |  | 59600 | 59600 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
66 | 5-02-03-210-03 | ICT Equipment-SE | [15 empty] | 1101Bde | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-02-17 | 2023-02-17 | 2023-02-17 | N/A | N/A | 2023-02-17 | 2023-02-17 | 2023-02-27 | 2023-03-08 | 2023-03-08 | MOOE | 67500 | 67500 |  | 67050 | 67050 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
67 | 5-02-03-080-00 | Med Dent Lab Supplies | [15 empty] | 1101Bde | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-02-17 | 2023-02-17 | 2023-02-17 | N/A | N/A | 2023-02-17 | 2023-02-17 | 2023-02-27 | 2023-03-08 | 2023-03-08 | MOOE | 77500 | 77500 |  | 76940 | 76940 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
68 | 5-02-03-210-03 | ICT Equipment-SE | [15 empty] | 1101Bde | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-02-17 | 2023-02-17 | 2023-02-17 | N/A | N/A | 2023-02-17 | 2023-02-17 | 2023-02-27 | 2023-03-08 | 2023-03-08 | MOOE | 130000 | 130000 |  | 129380 | 129380 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
69 | 5-02-13-060-01 | Vehicle Parts & Acc | [15 empty] | 1101Bde | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-02-17 | 2023-02-17 | 2023-02-17 | N/A | N/A | 2023-02-17 | 2023-02-17 | 2023-02-27 | 2023-03-08 | 2023-03-08 | MOOE | 130000 | 130000 |  | 129500 | 129500 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
70 | 5-02-99-030-00 | Grocery Items | [15 empty] | 1101Bde | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-02-17 | 2023-02-17 | 2023-02-17 | N/A | N/A | 2023-02-17 | 2023-02-17 | 2023-02-27 | 2023-03-08 | 2023-03-08 | MOOE | 325490 | 325490 |  | 324950 | 324950 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
71 | 5-02-03-210-02 | Office Equipment-SE | [15 empty] | 11ID | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-02-17 | 2023-02-17 | 2023-02-17 | N/A | N/A | 2023-02-17 | 2023-02-17 | 2023-02-27 | 2023-03-08 | 2023-03-08 | MOOE | 73000 | 73000 |  | 72520 | 72520 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
72 | 5-02-99-030-00 | Grocery Items | [15 empty] | 101IB | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-02-17 | 2023-02-17 | 2023-02-17 | N/A | N/A | 2023-02-17 | 2023-02-17 | 2023-02-27 | 2023-03-08 | 2023-03-08 | MOOE | 122650 | 122650 |  | 121990 | 121990 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
73 | 5-02-03-210-03 | ICT Equipment-SE | [15 empty] | 11ID | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-02-17 | 2023-02-17 | 2023-02-17 | N/A | N/A | 2023-02-17 | 2023-02-17 | 2023-02-27 | 2023-03-08 | 2023-03-08 | MOOE | 52500 | 52500 |  | 52000 | 52000 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
74 | 5-02-13-060-01 | Vehicle Parts & Acc | [15 empty] | 11ID | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-02-17 | 2023-02-17 | 2023-02-17 | N/A | N/A | 2023-02-17 | 2023-02-17 | 2023-02-27 | 2023-03-08 | 2023-03-08 | MOOE | 350000 | 350000 |  | 349080 | 349080 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
75 | 5-02-03-080-00 | Med Dent Lab Supplies | [15 empty] | 101IB | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-02-17 | 2023-02-17 | 2023-02-17 | N/A | N/A | 2023-02-17 | 2023-02-17 | 2023-02-27 | 2023-03-08 | 2023-03-08 | MOOE | 125000 | 125000 |  | 124400 | 124400 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
76 | 5-02-02-010-00 | Training Supplies | [15 empty] | 101IB | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-02-21 | 2023-02-21 | 2023-02-21 | N/A | N/A | 2023-02-21 | 2023-02-21 | 2023-03-03 | 2023-03-14 | 2023-03-14 | MOOE | 10000 | 10000 |  | 9880 | 9880 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
77 | 5-02-03-210-09 | Mil Pol Sec Eqmt-SE | [15 empty] | 111DRC | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-02-21 | 2023-02-21 | 2023-02-21 | N/A | N/A | 2023-02-21 | 2023-02-21 | 2023-03-03 | 2023-03-14 | 2023-03-14 | MOOE | 10000 | 10000 |  | 9900 | 9900 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
78 | 5-02-03-210-03 | ICT Equipment-SE | [15 empty] | 101IB | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-02-21 | 2023-02-21 | 2023-02-21 | N/A | N/A | 2023-02-21 | 2023-02-21 | 2023-03-03 | 2023-03-14 | 2023-03-14 | MOOE | 40000 | 40000 |  | 39650 | 39650 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
79 | 5-02-03-010-00 | Office Supplies | [15 empty] | 101IB | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-02-21 | 2023-02-21 | 2023-02-21 | N/A | N/A | 2023-02-21 | 2023-02-21 | 2023-03-03 | 2023-03-14 | 2023-03-14 | MOOE | 50000 | 50000 |  | 49600 | 49600 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
80 | 5-02-05-040-00 | Cable Expense | [15 empty] | 1101Bde | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-02-21 | 2023-02-21 | 2023-02-21 | N/A | N/A | 2023-02-21 | 2023-02-21 | 2023-03-03 | 2023-03-14 | 2023-03-14 | MOOE | 12500 | 12500 |  | 12350 | 12350 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
81 | 5-02-13-060-01 | Vehicle Parts & Acc | [15 empty] | 11DCAU | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-02-28 | 2023-02-28 | 2023-02-28 | N/A | N/A | 2023-02-28 | 2023-02-28 | 2023-03-03 | 2023-03-14 | 2023-03-14 | MOOE | 45000 | 45000 |  | 44730 | 44730 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
82 | 5-02-02-010-00 | Training Supplies | [15 empty] | 21IB | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-02-28 | 2023-02-28 | 2023-02-28 | N/A | N/A | 2023-02-28 | 2023-02-28 | 2023-03-03 | 2023-03-14 | 2023-03-14 | MOOE | 10000 | 10000 |  | 9825 | 9825 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
83 | 5-02-99-030-00 | Grocery Items | [15 empty] | 41IB | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-02-28 | 2023-02-28 | 2023-02-28 | N/A | N/A | 2023-02-28 | 2023-02-28 | 2023-03-03 | 2023-03-14 | 2023-03-14 | MOOE | 25000 | 25000 |  | 24800 | 24800 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
84 | 5-02-02-010-00 | Training Supplies | [15 empty] | 101IB | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-02-28 | 2023-02-28 | 2023-02-28 | N/A | N/A | 2023-02-28 | 2023-02-28 | 2023-03-03 | 2023-03-14 | 2023-03-14 | MOOE | 10000 | 10000 |  | 9840 | 9840 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
85 | 5-02-02-010-00 | Training Supplies | [15 empty] | 101IB | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-02-28 | 2023-02-28 | 2023-02-28 | N/A | N/A | 2023-02-28 | 2023-02-28 | 2023-03-03 | 2023-03-14 | 2023-03-14 | MOOE | 22650 | 22650 |  | 22270 | 22270 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
86 | 5-02-03-010-00 | Office Supplies | [15 empty] | 101IB | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-02-28 | 2023-02-28 | 2023-02-28 | N/A | N/A | 2023-02-28 | 2023-02-28 | 2023-03-03 | 2023-03-14 | 2023-03-14 | MOOE | 50000 | 50000 |  | 49625 | 49625 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
87 | 5-02-13-040-01 | Construction Material & Supplies | [15 empty] | 1103Bde | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-02-28 | 2023-02-28 | 2023-02-28 | N/A | N/A | 2023-02-28 | 2023-02-28 | 2023-03-03 | 2023-03-14 | 2023-03-14 | MOOE | 50000 | 50000 |  | 49610 | 49610 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
88 | 5-02-03-210-03 | ICT Equipment-SE | [15 empty] | 111DRC | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-02-28 | 2023-02-28 | 2023-02-28 | N/A | N/A | 2023-02-28 | 2023-02-28 | 2023-03-03 | 2023-03-14 | 2023-03-14 | MOOE | 20000 | 20000 |  | 19700 | 19700 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
89 | 5-02-03-210-03 | ICT Equipment-SE | [15 empty] | 41IB | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-02-28 | 2023-02-28 | 2023-02-28 | N/A | N/A | 2023-02-28 | 2023-02-28 | 2023-03-03 | 2023-03-14 | 2023-03-14 | MOOE | 37375 | 37375 |  | 37000 | 37000 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
90 | 5-02-03-080-00 | Med Dent Lab Supplies | [15 empty] | 11ID | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-02-28 | 2023-02-28 | 2023-02-28 | N/A | N/A | 2023-02-28 | 2023-02-28 | 2023-03-03 | 2023-03-14 | 2023-03-14 | MOOE | 25000 | 25000 |  | 24750 | 24750 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
91 | 5-02-05-040-00 | Cable Expense | [15 empty] | 35IB | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-02-28 | 2023-02-28 | 2023-02-28 | N/A | N/A | 2023-02-28 | 2023-02-28 | 2023-03-03 | 2023-03-14 | 2023-03-14 | MOOE | 16400 | 16400 |  | 16330 | 16330 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
92 | 5-02-99-030-00 | Grocery Items | [15 empty] | 11DTS | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-03-02 | 2023-03-02 | 2023-03-02 | N/A | N/A | 2023-03-02 | 2023-03-02 | 2023-03-14 | 2023-03-18 | 2023-03-18 | MOOE | 145000 | 145000 |  | 144525 | 144525 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
93 | 5-02-03-080-00 | Med Dent Lab Supplies | [15 empty] | 11DTS | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-03-07 | 2023-03-07 | 2023-03-07 | N/A | N/A | 2023-03-07 | 2023-03-07 | 2023-03-17 | 2023-03-24 | 2023-03-24 | MOOE | 20000 | 20000 |  | 19840 | 19840 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
94 | 5-02-02-010-00 | Training Supplies | [15 empty] | 101IB | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-03-07 | 2023-03-07 | 2023-03-07 | N/A | N/A | 2023-03-07 | 2023-03-07 | 2023-03-17 | 2023-03-24 | 2023-03-24 | MOOE | 10000 | 10000 |  | 9880 | 9880 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
95 | 5-02-03-990-00 | Other Supplies | [15 empty] | 32IB | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-03-07 | 2023-03-07 | 2023-03-07 | N/A | N/A | 2023-03-07 | 2023-03-07 | 2023-03-17 | 2023-03-24 | 2023-03-24 | MOOE | 2000 | 2000 |  | 1970 | 1970 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
96 | 5-02-02-010-00 | Training Supplies | [15 empty] | 101IB | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-03-07 | 2023-03-07 | 2023-03-07 | N/A | N/A | 2023-03-07 | 2023-03-07 | 2023-03-17 | 2023-03-24 | 2023-03-24 | MOOE | 10000 | 10000 |  | 9900 | 9900 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
97 | 5-02-13-050-03 | RM ICT | [15 empty] | 11HHSBN | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-03-07 | 2023-03-07 | 2023-03-07 | N/A | N/A | 2023-03-07 | 2023-03-07 | 2023-03-17 | 2023-03-24 | 2023-03-24 | MOOE | 52500 | 52500 |  | 52180 | 52180 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
98 | 5-02-02-010-00 | Training Supplies | [15 empty] | 1101Bde | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-03-07 | 2023-03-07 | 2023-03-07 | N/A | N/A | 2023-03-07 | 2023-03-07 | 2023-03-17 | 2023-03-24 | 2023-03-24 | MOOE | 60000 | 60000 |  | 59700 | 59700 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
99 | 5-02-03-990-00 | Other Supplies | [15 empty] | 1101Bde | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-03-07 | 2023-03-07 | 2023-03-07 | N/A | N/A | 2023-03-07 | 2023-03-07 | 2023-03-17 | 2023-03-24 | 2023-03-24 | MOOE | 251760 | 251760 |  | 251150 | 251150 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
100 | 5-02-05-020-01 | Telephone Expense-Mobile | [15 empty] | 1101Bde | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-03-07 | 2023-03-07 | 2023-03-07 | N/A | N/A | 2023-03-07 | 2023-03-07 | 2023-03-17 | 2023-03-24 | 2023-03-24 | MOOE | 71000 | 71000 |  | 70590 | 70590 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
101 | 5-02-99-030-00 | Grocery Items | [15 empty] | 1101Bde | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-03-07 | 2023-03-07 | 2023-03-07 | N/A | N/A | 2023-03-07 | 2023-03-07 | 2023-03-17 | 2023-03-24 | 2023-03-24 | MOOE | 436990 | 436990 |  | 436390 | 436390 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
102 | 5-02-13-040-99 | (OS) Construction Supplies | [15 empty] | 101IB | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-03-07 | 2023-03-07 | 2023-03-07 | N/A | N/A | 2023-03-07 | 2023-03-07 | 2023-03-17 | 2023-03-24 | 2023-03-24 | MOOE | 50800 | 50800 |  | 50400 | 50400 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
103 | 5-02-03-210-03 | ICT Equipment-SE | [15 empty] | 11DTS | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-03-07 | 2023-03-07 | 2023-03-07 | N/A | N/A | 2023-03-07 | 2023-03-07 | 2023-03-17 | 2023-03-24 | 2023-03-24 | MOOE | 92000 | 92000 |  | 91510 | 91510 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
104 | 5-02-99-030-00 | Grocery Items | [15 empty] | 101IB | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-03-07 | 2023-03-07 | 2023-03-07 | N/A | N/A | 2023-03-07 | 2023-03-07 | 2023-03-17 | 2023-03-24 | 2023-03-24 | MOOE | 127050 | 127050 |  | 126690 | 126690 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
105 | 5-02-13-060-01 | Vehicle Parts & Acc | [15 empty] | 11DTS | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-03-07 | 2023-03-07 | 2023-03-07 | N/A | N/A | 2023-03-07 | 2023-03-07 | 2023-03-17 | 2023-03-24 | 2023-03-24 | MOOE | 92000 | 92000 |  | 91660 | 91660 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
106 | 5-02-13-060-01 | Vehicle Parts & Acc | [15 empty] | 1101Bde | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-03-07 | 2023-03-07 | 2023-03-07 | N/A | N/A | 2023-03-07 | 2023-03-07 | 2023-03-17 | 2023-03-24 | 2023-03-24 | MOOE | 100000 | 100000 |  | 99650 | 99650 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
107 | 5-02-05-020-01 | Telephone Expense-Mobile | [15 empty] | 15CMOBN | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-03-07 | 2023-03-07 | 2023-03-07 | N/A | N/A | 2023-03-07 | 2023-03-07 | 2023-03-17 | 2023-03-24 | 2023-03-24 | MOOE | 95000 | 95000 |  | 94400 | 94400 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
108 | 5-02-99-030-00 | Grocery Items | [15 empty] | 41IB | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-03-07 | 2023-03-07 | 2023-03-07 | N/A | N/A | 2023-03-07 | 2023-03-07 | 2023-03-17 | 2023-03-24 | 2023-03-24 | MOOE | 113000 | 113000 |  | 112550 | 112550 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
109 | 5-02-13-040-01 | (RMB) Construction Supplies | [15 empty] | 41IB | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-03-07 | 2023-03-07 | 2023-03-07 | N/A | N/A | 2023-03-07 | 2023-03-07 | 2023-03-17 | 2023-03-24 | 2023-03-24 | MOOE | 70000 | 70000 |  | 69700 | 69700 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
110 | 5-02-05-040-00 | Cable Expense | [15 empty] | 11SSBN | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-03-14 | 2023-03-14 | 2023-03-14 | N/A | N/A | 2023-03-14 | 2023-03-14 | 2023-03-29 | 2023-04-07 | 2023-04-07 | MOOE | 10000 | 10000 |  | 9960 | 9960 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
111 | 5-02-05-020-01 | Telephone Expense-Mobile | [15 empty] | 11SSBN | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-03-14 | 2023-03-14 | 2023-03-14 | N/A | N/A | 2023-03-14 | 2023-03-14 | 2023-03-29 | 2023-04-07 | 2023-04-07 | MOOE | 5000 | 5000 |  | 4978 | 4978 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
112 | 5-02-03-070-00 | Drugs & Meds | [15 empty] | 11SSBN | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-03-14 | 2023-03-14 | 2023-03-14 | N/A | N/A | 2023-03-14 | 2023-03-14 | 2023-03-29 | 2023-04-07 | 2023-04-07 | MOOE | 40000 | 40000 |  | 39500 | 39500 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
113 | 5-02-03-210-03 | ICT Equipment-SE | [15 empty] | 11SSBN | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-03-14 | 2023-03-14 | 2023-03-14 | N/A | N/A | 2023-03-14 | 2023-03-14 | 2023-03-29 | 2023-04-07 | 2023-04-07 | MOOE | 5000 | 5000 |  | 4900 | 4900 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
114 | 5-02-03-210-03 | ICT Equipment-SE | [15 empty] | 11SSBN | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-03-14 | 2023-03-14 | 2023-03-14 | N/A | N/A | 2023-03-14 | 2023-03-14 | 2023-03-29 | 2023-04-07 | 2023-04-07 | MOOE | 20000 | 20000 |  | 19660 | 19660 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
115 | 5-02-05-020-01 | Telephone Expense-Mobile | [15 empty] | 1102Bde | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-03-14 | 2023-03-14 | 2023-03-14 | N/A | N/A | 2023-03-14 | 2023-03-14 | 2023-03-29 | 2023-04-07 | 2023-04-07 | MOOE | 10000 | 10000 |  | 9960 | 9960 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
116 | 5-02-03-210-03 | ICT Equipment-SE | [15 empty] | 11MIB | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-03-14 | 2023-03-14 | 2023-03-14 | N/A | N/A | 2023-03-14 | 2023-03-14 | 2023-03-29 | 2023-04-07 | 2023-04-07 | MOOE | 35000 | 35000 |  | 34550 | 34550 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
117 | 5-02-03-210-03 | ICT Equipment-SE | [15 empty] | 11MIB | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-03-14 | 2023-03-14 | 2023-03-14 | N/A | N/A | 2023-03-14 | 2023-03-14 | 2023-03-29 | 2023-04-07 | 2023-04-07 | MOOE | 35000 | 35000 |  | 34550 | 34550 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
118 | 5-02-13-040-99 | (OS) Construction Supplies | [15 empty] | 21IB | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-03-14 | 2023-03-14 | 2023-03-14 | N/A | N/A | 2023-03-14 | 2023-03-14 | 2023-03-29 | 2023-04-07 | 2023-04-07 | MOOE | 20000 | 20000 |  | 19660 | 19660 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
119 | 5-02-02-010-00 | Training Supplies | [15 empty] | 41IB | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-03-14 | 2023-03-14 | 2023-03-14 | N/A | N/A | 2023-03-14 | 2023-03-14 | 2023-03-29 | 2023-04-07 | 2023-04-07 | MOOE | 35000 | 35000 |  | 34575 | 34575 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
120 | 5-02-99-030-00 | Grocery Items | [15 empty] | 41IB | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-03-14 | 2023-03-14 | 2023-03-14 | N/A | N/A | 2023-03-14 | 2023-03-14 | 2023-03-29 | 2023-04-07 | 2023-04-07 | MOOE | 25000 | 25000 |  | 24750 | 24750 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
121 | 5-02-03-210-03 | ICT Equipment-SE | [15 empty] | 41IB | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-03-14 | 2023-03-14 | 2023-03-14 | N/A | N/A | 2023-03-14 | 2023-03-14 | 2023-03-29 | 2023-04-07 | 2023-04-07 | MOOE | 37375 | 37375 |  | 37000 | 37000 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
122 | 5-02-13-050-07 | (RM) Commo Equipment | [15 empty] | 1101Bde | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-03-14 | 2023-03-14 | 2023-03-14 | N/A | N/A | 2023-03-14 | 2023-03-14 | 2023-03-29 | 2023-04-07 | 2023-04-07 | MOOE | 35000 | 35000 |  | 34720 | 34720 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
123 | 5-02-03-990-00 | Other Supplies | [15 empty] | 15CMOBN | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-03-14 | 2023-03-14 | 2023-03-14 | N/A | N/A | 2023-03-14 | 2023-03-14 | 2023-03-29 | 2023-04-07 | 2023-04-07 | MOOE | 40000 | 40000 |  | 39670 | 39670 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
124 | 5-02-05-020-01 | Telephone Expense-Mobile | [15 empty] | 35IB | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-03-15 | 2023-03-15 | 2023-03-15 | N/A | N/A | 2023-03-15 | 2023-03-15 | 2023-03-29 | 2023-04-07 | 2023-04-07 | MOOE | 15500 | 15500 |  | 15440 | 15440 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
125 | 5-02-99-030-00 | Grocery Items | [15 empty] | 35IB | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-03-15 | 2023-03-15 | 2023-03-15 | N/A | N/A | 2023-03-15 | 2023-03-15 | 2023-03-29 | 2023-04-07 | 2023-04-07 | MOOE | 8000 | 8000 |  | 7880 | 7880 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
126 | 5-02-03-080-00 | Med Dent Lab Supplies | [15 empty] | 15CMOBN | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-03-14 | 2023-03-14 | 2023-03-14 | N/A | N/A | 2023-03-14 | 2023-03-14 | 2023-03-29 | 2023-04-07 | 2023-04-07 | MOOE | 22272 | 22272 |  | 21920 | 21920 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
127 | 5-02-03-210-03 | ICT Equipment-SE | [15 empty] | 15CMOBN | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-03-14 | 2023-03-14 | 2023-03-14 | N/A | N/A | 2023-03-14 | 2023-03-14 | 2023-03-29 | 2023-04-07 | 2023-04-07 | MOOE | 45000 | 45000 |  | 44600 | 44600 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
128 | 5-02-03-080-00 | Med Dent Lab Supplies | [15 empty] | 1102Bde | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-03-15 | 2023-03-15 | 2023-03-15 | N/A | N/A | 2023-03-15 | 2023-03-15 | 2023-03-29 | 2023-04-07 | 2023-04-07 | MOOE | 18000 | 18000 |  | 17820 | 17820 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
129 | 5-02-03-990-00 | Other Supplies | [15 empty] | 21IB | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-03-15 | 2023-03-15 | 2023-03-15 | N/A | N/A | 2023-03-15 | 2023-03-15 | 2023-03-29 | 2023-04-07 | 2023-04-07 | MOOE | 44000 | 44000 |  | 43500 | 43500 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
130 | 5-02-13-060-01 | Vehicle Parts & Acc | [15 empty] | 21IB | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-03-15 | 2023-03-15 | 2023-03-15 | N/A | N/A | 2023-03-15 | 2023-03-15 | 2023-03-29 | 2023-04-07 | 2023-04-07 | MOOE | 50000 | 50000 |  | 49680 | 49680 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
131 | 5-02-03-210-03 | ICT Equipment-SE | [15 empty] | 11MIB | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-03-15 | 2023-03-15 | 2023-03-15 | N/A | N/A | 2023-03-15 | 2023-03-15 | 2023-03-29 | 2023-04-07 | 2023-04-07 | MOOE | 28750 | 28750 |  | 28390 | 28390 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
132 | 5-02-03-210-03 | ICT Equipment-SE | [15 empty] | 11MIB | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-03-15 | 2023-03-15 | 2023-03-15 | N/A | N/A | 2023-03-15 | 2023-03-15 | 2023-03-29 | 2023-04-07 | 2023-04-07 | MOOE | 28750 | 28750 |  | 28390 | 28390 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
133 | 5-02-05-020-01 | Telephone Expense-Mobile | [15 empty] | 11ID | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-03-15 | 2023-03-15 | 2023-03-15 | N/A | N/A | 2023-03-15 | 2023-03-15 | 2023-03-29 | 2023-04-07 | 2023-04-07 | MOOE | 15000 | 15000 |  | 14940 | 14940 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
134 | 5-02-03-080-00 | Med Dent Lab Supplies | [15 empty] | 11ID | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-03-15 | 2023-03-15 | 2023-03-15 | N/A | N/A | 2023-03-15 | 2023-03-15 | 2023-03-29 | 2023-04-07 | 2023-04-07 | MOOE | 47500 | 47500 |  | 47160 | 47160 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
135 | 5-02-02-010-00 | Training Supplies | [15 empty] | 21IB | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-03-15 | 2023-03-15 | 2023-03-15 | N/A | N/A | 2023-03-15 | 2023-03-15 | 2023-03-29 | 2023-04-07 | 2023-04-07 | MOOE | 30000 | 30000 |  | 29880 | 29880 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
136 | 5-02-02-010-00 | Training Supplies | [15 empty] | 35IB | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-03-17 | 2023-03-17 | 2023-03-17 | N/A | N/A | 2023-03-17 | 2023-03-17 | 2023-03-29 | 2023-04-07 | 2023-04-07 | MOOE | 186000 | 186000 |  | 185417 | 185417 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
137 | 5-02-99-030-00 | Grocery Items | [15 empty] | 1102Bde | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-03-17 | 2023-03-17 | 2023-03-17 | N/A | N/A | 2023-03-17 | 2023-03-17 | 2023-04-14 | 2023-04-21 | 2023-04-21 | MOOE | 453700 | 453700 |  | 452800 | 452800 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
138 | 5-02-13-040-99 | (OS) Construction Supplies | [15 empty] | 1102Bde | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-03-20 | 2023-03-20 | 2023-03-20 | N/A | N/A | 2023-03-20 | 2023-03-20 | 2023-04-12 | 2023-04-21 | 2023-04-21 | MOOE | 55000 | 55000 |  | 54640 | 54640 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
139 | 5-02-02-010-00 | Training Supplies | [15 empty] | 11DCAU | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-03-20 | 2023-03-20 | 2023-03-20 | N/A | N/A | 2023-03-20 | 2023-03-20 | 2023-04-12 | 2023-04-21 | 2023-04-21 | MOOE | 64800 | 64800 |  | 64440 | 64440 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
140 | 5-02-13-060-01 | Vehicle Parts & Acc | [15 empty] | 1102Bde | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-03-20 | 2023-03-20 | 2023-03-20 | N/A | N/A | 2023-03-20 | 2023-03-20 | 2023-04-18 | 2023-04-21 | 2023-04-21 | MOOE | 152000 | 152000 |  | 151400 | 151400 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
141 | 5-02-99-030-00 | Grocery Items | [15 empty] | 11DCAU | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-03-20 | 2023-03-20 | 2023-03-20 | N/A | N/A | 2023-03-20 | 2023-03-20 | 2023-04-12 | 2023-04-21 | 2023-04-21 | MOOE | 205300 | 205300 |  | 204580 | 204580 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
142 | 5-02-05-020-01 | Telephone Expense-Mobile | [15 empty] | 11ID | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-03-20 | 2023-03-20 | 2023-03-20 | N/A | N/A | 2023-03-20 | 2023-03-20 | 2023-04-27 | 2023-05-05 | 2023-05-05 | MOOE | 79000 | 79000 |  | 78660 | 78660 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
143 | 5-02-13-040-99 | (OS) Construction Supplies | [15 empty] | 21IB | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-03-20 | 2023-03-20 | 2023-03-20 | N/A | N/A | 2023-03-20 | 2023-03-20 | 2023-04-27 | 2023-05-05 | 2023-05-05 | MOOE | 90000 | 90000 |  | 89500 | 89500 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
144 | 5-02-02-010-00 | Training Supplies | [15 empty] | 1102Bde | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-03-21 | 2023-03-21 | 2023-03-21 | N/A | N/A | 2023-03-21 | 2023-03-21 | 2023-04-20 | 2023-05-03 | 2023-05-03 | MOOE | 220855.25 | 220855.25 |  | 220227 | 220227 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
145 | 5-02-99-030-00 | Grocery Items | [15 empty] | 15CMOBN | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-03-21 | 2023-03-21 | 2023-03-21 | N/A | N/A | 2023-03-21 | 2023-03-21 | 2023-04-20 | 2023-05-03 | 2023-05-03 | MOOE | 299700 | 299700 |  | 299110 | 299110 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
146 | 5-02-13-060-01 | Vehicle Parts & Acc | [15 empty] | 15CMOBN | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-03-21 | 2023-03-21 | 2023-03-21 | N/A | N/A | 2023-03-21 | 2023-03-21 | 2023-04-20 | 2023-05-03 | 2023-05-03 | MOOE | 57500 | 57500 |  | 57200 | 57200 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
147 | 5-02-03-210-07 | Commo Equipment-SE | [15 empty] | 11ID | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-03-21 | 2023-03-21 | 2023-03-21 | N/A | N/A | 2023-03-21 | 2023-03-21 | 2023-04-14 | 2023-04-21 | 2023-04-21 | MOOE | 40000 | 40000 |  | 39600 | 39600 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
148 | 5-02-05-040-00 | Cable Expense | [15 empty] | 11DCAU | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-03-21 | 2023-03-21 | 2023-03-21 | N/A | N/A | 2023-03-21 | 2023-03-21 | 2023-02-28 | 2023-03-10 | 2023-03-10 | MOOE | 6000 | 6000 |  | 5976 | 5976 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
149 | 5-02-13-210-07 | (RM) Commo Equipment | [15 empty] | 1102Bde | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-03-21 | 2023-03-21 | 2023-03-21 | N/A | N/A | 2023-03-21 | 2023-03-21 | 2023-02-17 | 2023-02-21 | 2023-02-21 | MOOE | 30000 | 30000 |  | 29700 | 29700 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
150 | 5-02-13-210-03 | (RM) ICT | [15 empty] | 1103Bde | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-03-21 | 2023-03-21 | 2023-03-21 | N/A | N/A | 2023-03-21 | 2023-03-21 | 2023-03-28 | 2023-04-07 | 2023-04-07 | MOOE | 20000 | 20000 |  | 19750 | 19750 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
151 | 5-02-02-010-00 | Training Supplies | [15 empty] | 21IB | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-03-21 | 2023-03-21 | 2023-03-21 | N/A | N/A | 2023-03-21 | 2023-03-21 | 2023-03-28 | 2023-04-07 | 2023-04-07 | MOOE | 16680 | 16680 |  | 16470 | 16470 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
152 | 5-02-02-010-00 | Training Supplies | [15 empty] | 21IB | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-03-21 | 2023-03-21 | 2023-03-21 | N/A | N/A | 2023-03-21 | 2023-03-21 | 2023-03-28 | 2023-04-07 | 2023-04-07 | MOOE | 10000 | 10000 |  | 9905 | 9905 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
153 | 5-02-02-010-00 | Training Supplies | [15 empty] | 15CMOBN | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-03-21 | 2023-03-21 | 2023-03-21 | N/A | N/A | 2023-03-21 | 2023-03-21 | 2023-03-28 | 2023-04-07 | 2023-04-07 | MOOE | 38000 | 38000 |  | 37725 | 37725 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
154 | 5-02-02-010-00 | Training Supplies | [15 empty] | 45IB | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-03-21 | 2023-03-21 | 2023-03-21 | N/A | N/A | 2023-03-21 | 2023-03-21 | 2023-03-28 | 2023-04-07 | 2023-04-07 | MOOE | 30000 | 30000 |  | 29700 | 29700 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
155 | 5-02-13-060-01 | Vehicle Parts & Acc | [15 empty] | 11DCAU | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-03-28 | 2023-03-28 | 2023-03-28 | N/A | N/A | 2023-03-28 | 2023-03-28 | 2023-04-15 | 2023-04-21 | 2023-04-21 | MOOE | 45000 | 45000 |  | 44634 | 44634 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
156 | 5-02-05-020-01 | Telephone Expense-Mobile | [15 empty] | 35IB | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-03-28 | 2023-03-28 | 2023-03-28 | N/A | N/A | 2023-03-28 | 2023-03-28 | 2023-04-15 | 2023-04-21 | 2023-04-21 | MOOE | 16400 | 16400 |  | 16336 | 16336 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
157 | 5-02-13-060-01 | Vehicle Parts & Acc | [15 empty] | 11SSBN | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-03-28 | 2023-03-28 | 2023-03-28 | N/A | N/A | 2023-03-28 | 2023-03-28 | 2023-04-15 | 2023-04-21 | 2023-04-21 | MOOE | 125000 | 125000 |  | 124470 | 124470 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
158 | 5-02-03-210-03 | ICT Equipment-SE | [15 empty] | 11ID | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-03-28 | 2023-03-28 | 2023-03-28 | N/A | N/A | 2023-03-28 | 2023-03-28 | 2023-04-15 | 2023-04-21 | 2023-04-21 | MOOE | 57500 | 57500 |  | 57000 | 57000 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
159 | 5-02-03-010-01 | ICT Office Supplies | [15 empty] | 35IB | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-03-28 | 2023-03-28 | 2023-03-28 | N/A | N/A | 2023-03-28 | 2023-03-28 | 2023-04-15 | 2023-04-21 | 2023-04-21 | MOOE | 86000 | 86000 |  | 85615 | 85615 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
160 | 5-02-13-040-01 | (RM) Building | [15 empty] | 11ID | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-03-28 | 2023-03-28 | 2023-03-28 | N/A | N/A | 2023-03-28 | 2023-03-28 | 2023-04-15 | 2023-04-21 | 2023-04-21 | MOOE | 389500 | 389500 |  | 388750 | 388750 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
161 | 5-02-99-030-00 | Grocery Items | [15 empty] | 104IB | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-03-28 | 2023-03-28 | 2023-03-28 | N/A | N/A | 2023-03-28 | 2023-03-28 | 2023-04-15 | 2023-04-21 | 2023-04-21 | MOOE | 60000 | 60000 |  | 59600 | 59600 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
162 | 5-02-99-030-00 | Grocery Items | [15 empty] | 104IB | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-03-28 | 2023-03-28 | 2023-03-28 | N/A | N/A | 2023-03-28 | 2023-03-28 | 2023-04-15 | 2023-04-21 | 2023-04-21 | MOOE | 73000 | 73000 |  | 72560 | 72560 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
163 | 5-02-03-010-01 | ICT Office Supplies | [15 empty] | 11ID | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-03-30 | 2023-03-30 | 2023-03-30 | N/A | N/A | 2023-03-30 | 2023-03-30 | 2023-04-15 | 2023-04-21 | 2023-04-21 | MOOE | 26000 | 26000 |  | 25740 | 25740 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
164 | 5-02-05-040-00 | Cable Expense | [15 empty] | 1101Bde | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-03-30 | 2023-03-30 | 2023-03-30 | N/A | N/A | 2023-03-30 | 2023-03-30 | 2023-04-15 | 2023-04-21 | 2023-04-21 | MOOE | 12500 | 12500 |  | 12350 | 12350 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
165 | 5-02-99-030-00 | Grocery Items | [15 empty] | 32IB | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-03-30 | 2023-03-30 | 2023-03-30 | N/A | N/A | 2023-03-30 | 2023-03-30 | 2023-04-15 | 2023-04-21 | 2023-04-21 | MOOE | 82500 | 82500 |  | 82080 | 82080 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
166 | 5-02-99-030-00 | Grocery Items | [15 empty] | 104IB | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-03-30 | 2023-03-30 | 2023-03-30 | N/A | N/A | 2023-03-30 | 2023-03-30 | 2023-04-15 | 2023-04-21 | 2023-04-21 | MOOE | 114500 | 114500 |  | 114052 | 114052 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
167 | 5-02-03-990-00 | Other Supplies | [15 empty] | 32IB | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-04-18 | 2023-04-18 | 2023-04-18 | N/A | N/A | 2023-04-18 | 2023-04-18 | 2023-04-27 | 2023-05-05 | 2023-05-05 | MOOE | 50000 | 50000 |  | 49620 | 49620 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
168 | 5-02-03-080-00 | Med Dent Lab Supplies | [15 empty] | 32IB | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-04-18 | 2023-04-18 | 2023-04-18 | N/A | N/A | 2023-04-18 | 2023-04-18 | 2023-04-27 | 2023-05-05 | 2023-05-05 | MOOE | 25000 | 25000 |  | 24682 | 24682 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
169 | 5-02-99-030-00 | Grocery Items | [15 empty] | 104IB | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-04-18 | 2023-04-18 | 2023-04-18 | N/A | N/A | 2023-04-18 | 2023-04-18 | 2023-04-27 | 2023-05-05 | 2023-05-05 | MOOE | 15000 | 15000 |  | 14760 | 14760 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
170 | 5-02-99-030-00 | Grocery Items | [15 empty] | 104IB | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-04-18 | 2023-04-18 | 2023-04-18 | N/A | N/A | 2023-04-18 | 2023-04-18 | 2023-04-27 | 2023-05-05 | 2023-05-05 | MOOE | 18000 | 18000 |  | 17700 | 17700 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
171 | 5-02-03-210-08 | DRRE-SE | [15 empty] | 11ID | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-04-18 | 2023-04-18 | 2023-04-18 | N/A | N/A | 2023-04-18 | 2023-04-18 | 2023-04-27 | 2023-05-05 | 2023-05-05 | MOOE | 10000 | 10000 |  | 9750 | 9750 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
172 | 5-02-03-210-03 | ICT Equipment-SE | [15 empty] | 1103Bde | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-04-18 | 2023-04-18 | 2023-04-18 | N/A | N/A | 2023-04-18 | 2023-04-18 | 2023-04-27 | 2023-05-05 | 2023-05-05 | MOOE | 36500 | 36500 |  | 36100 | 36100 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
173 | 5-02-05-040-00 | Cable Expense | [15 empty] | 1103Bde | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-04-18 | 2023-04-18 | 2023-04-18 | N/A | N/A | 2023-04-18 | 2023-04-18 | 2023-04-27 | 2023-05-05 | 2023-05-05 | MOOE | 7500 | 7500 |  | 7460 | 7460 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
174 | 5-02-13-210-03 | (RM) ICT | [15 empty] | 15CMOBN | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-04-18 | 2023-04-18 | 2023-04-18 | N/A | N/A | 2023-04-18 | 2023-04-18 | 2023-04-27 | 2023-05-05 | 2023-05-05 | MOOE | 50000 | 50000 |  | 49700 | 49700 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
175 | 5-02-13-210-03 | (RM) ICT | [15 empty] | 101IB | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-04-18 | 2023-04-18 | 2023-04-18 | N/A | N/A | 2023-04-18 | 2023-04-18 | 2023-04-27 | 2023-05-05 | 2023-05-05 | MOOE | 5000 | 5000 |  | 4880 | 4880 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
176 | 5-02-03-210-03 | ICT Equipment-SE | [15 empty] | HHSBN | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-04-18 | 2023-04-18 | 2023-04-18 | N/A | N/A | 2023-04-18 | 2023-04-18 | 2023-04-27 | 2023-05-05 | 2023-05-05 | MOOE | 9200 | 9200 |  | 9000 | 9000 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
177 | 5-02-03-010-01 | ICT Office Supplies | [15 empty] | 11ID | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-04-18 | 2023-04-18 | 2023-04-18 | N/A | N/A | 2023-04-18 | 2023-04-18 | 2023-04-27 | 2023-05-05 | 2023-05-05 | MOOE | 15000 | 15000 |  | 14760 | 14760 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
178 | 5-02-03-010-01 | ICT Office Supplies | [15 empty] | 11ID | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-04-18 | 2023-04-18 | 2023-04-18 | N/A | N/A | 2023-04-18 | 2023-04-18 | 2023-04-27 | 2023-05-05 | 2023-05-05 | MOOE | 46000 | 46000 |  | 45575 | 45575 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
179 | 5-02-13-060-01 | Vehicle Parts & Acc | [15 empty] | 1101Bde | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-04-18 | 2023-04-18 | 2023-04-18 | N/A | N/A | 2023-04-18 | 2023-04-18 | 2023-04-27 | 2023-05-05 | 2023-05-05 | MOOE | 50000 | 50000 |  | 49500 | 49500 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
180 | 5-02-13-040-01 | (RM) Building | [15 empty] | 100IB | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-04-20 | 2023-04-20 | 2023-04-20 | N/A | N/A | 2023-04-20 | 2023-04-20 | 2023-04-28 | 2023-05-05 | 2023-05-05 | MOOE | 64000 | 64000 |  | 63520 | 63520 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
181 | 5-02-13-060-01 | Vehicle Parts & Acc | [15 empty] | HHSBN | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-04-20 | 2023-04-20 | 2023-04-20 | N/A | N/A | 2023-04-20 | 2023-04-20 | 2023-04-28 | 2023-05-05 | 2023-05-05 | MOOE | 71050 | 71050 |  | 70650 | 70650 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
182 | 5-02-03-990-00 | Other Supplies | [15 empty] | 35IB | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-04-20 | 2023-04-20 | 2023-04-20 | N/A | N/A | 2023-04-20 | 2023-04-20 | 2023-04-28 | 2023-05-05 | 2023-05-05 | MOOE | 53000 | 53000 |  | 52646 | 52646 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
183 | 5-02-03-010-00 | office supplies | [15 empty] | 11ID | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-04-20 | 2023-04-20 | 2023-04-20 | N/A | N/A | 2023-04-20 | 2023-04-20 | 2023-04-28 | 2023-05-05 | 2023-05-05 | MOOE | 258000 | 258000 |  | 257000 | 257000 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
184 | 5-02-05-020-01 | Telephone Expense-Mobile | [15 empty] | 11ID | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-04-20 | 2023-04-20 | 2023-04-20 | N/A | N/A | 2023-04-20 | 2023-04-20 | 2023-04-28 | 2023-05-05 | 2023-05-05 | MOOE | 229000 | 229000 |  | 228084 | 228084 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
185 | 5-02-03-010-00 | office supplies | [15 empty] | 11ID | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-04-20 | 2023-04-20 | 2023-04-20 | N/A | N/A | 2023-04-20 | 2023-04-20 | 2023-04-28 | 2023-05-05 | 2023-05-05 | MOOE | 363900 | 363900 |  | 362600 | 362600 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
186 | 5-02-99-030-00 | Grocery Items | [15 empty] | 1103Bde | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-04-20 | 2023-04-20 | 2023-04-20 | N/A | N/A | 2023-04-20 | 2023-04-20 | 2023-04-28 | 2023-05-05 | 2023-05-05 | MOOE | 301140 | 301140 |  | 300090 | 300090 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
187 | 5-02-02-010-00 | Training Supplies | [15 empty] | 1103Bde | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-04-20 | 2023-04-20 | 2023-04-20 | N/A | N/A | 2023-04-20 | 2023-04-20 | 2023-04-28 | 2023-05-05 | 2023-05-05 | MOOE | 156000 | 156000 |  | 155400 | 155400 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
188 | 5-02-03-210-99 | Other Machinery-SE | [15 empty] | 11ID | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-04-20 | 2023-04-20 | 2023-04-20 | N/A | N/A | 2023-04-20 | 2023-04-20 | 2023-04-28 | 2023-05-05 | 2023-05-05 | MOOE | 139000 | 139000 |  | 138400 | 138400 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
189 | 5-02-03-210-02 | Office Equipment-SE | [15 empty] | 11ID | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-04-20 | 2023-04-20 | 2023-04-20 | N/A | N/A | 2023-04-20 | 2023-04-20 | 2023-04-28 | 2023-05-05 | 2023-05-05 | MOOE | 53000 | 53000 |  | 52700 | 52700 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
190 | 5-02-03-010-00 | office supplies | [15 empty] | 11ID | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-04-20 | 2023-04-20 | 2023-04-20 | N/A | N/A | 2023-04-20 | 2023-04-20 | 2023-04-28 | 2023-05-05 | 2023-05-05 | MOOE | 190000 | 190000 |  | 189330 | 189330 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
191 | 5-02-03-080-00 | Med Dent Lab Supplies | [15 empty] | 11DCAU | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-04-24 | 2023-04-24 | 2023-04-24 | N/A | N/A | 2023-04-24 | 2023-04-24 | 2023-05-04 | 2023-05-12 | 2023-05-12 | MOOE | 25000 | 25000 |  | 24800 | 24800 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
192 | 5-02-13-210-14 | (RM) Other Machinery | [15 empty] | 11ID | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-04-24 | 2023-04-24 | 2023-04-24 | N/A | N/A | 2023-04-24 | 2023-04-24 | 2023-05-04 | 2023-05-12 | 2023-05-12 | MOOE | 45000 | 45000 |  | 44450 | 44450 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
193 | 5-02-03-210-03 | ICT Equipment-SE | [15 empty] | 11ID | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-04-24 | 2023-04-24 | 2023-04-24 | N/A | N/A | 2023-04-24 | 2023-04-24 | 2023-05-04 | 2023-05-12 | 2023-05-12 | MOOE | 50000 | 50000 |  | 49500 | 49500 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
194 | 5-02-13-210-03 | (RM) ICT | [15 empty] | 11ID | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-04-24 | 2023-04-24 | 2023-04-24 | N/A | N/A | 2023-04-24 | 2023-04-24 | 2023-05-04 | 2023-05-12 | 2023-05-12 | MOOE | 15000 | 15000 |  | 14800 | 14800 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
195 | 5-02-03-210-99 | Other Machinery-SE | [15 empty] | HHSBN | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-04-24 | 2023-04-24 | 2023-04-24 | N/A | N/A | 2023-04-24 | 2023-04-24 | 2023-05-04 | 2023-05-12 | 2023-05-12 | MOOE | 11500 | 11500 |  | 11350 | 11350 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
196 | 5-02-13-040-01 | (RM) Building | [15 empty] | 100IB | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-04-24 | 2023-04-24 | 2023-04-24 | N/A | N/A | 2023-04-24 | 2023-04-24 | 2023-05-04 | 2023-05-12 | 2023-05-12 | MOOE | 16000 | 16000 |  | 15820 | 15820 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
197 | 5-02-05-020-01 | Telephone Expense-Mobile | [15 empty] | 11ID | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-04-24 | 2023-04-24 | 2023-04-24 | N/A | N/A | 2023-04-24 | 2023-04-24 | 2023-05-04 | 2023-05-12 | 2023-05-12 | MOOE | 15000 | 15000 |  | 14940 | 14940 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
198 | 5-02-13-040-01 | (RM) Building | [15 empty] | 11ID | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-04-24 | 2023-04-24 | 2023-04-24 | N/A | N/A | 2023-04-24 | 2023-04-24 | 2023-05-04 | 2023-05-12 | 2023-05-12 | MOOE | 10000 | 10000 |  | 9900 | 9900 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
199 | 5-02-03-210-02 | Office Equipment-SE | [15 empty] | 11ID | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-04-24 | 2023-04-24 | 2023-04-24 | N/A | N/A | 2023-04-24 | 2023-04-24 | 2023-05-04 | 2023-05-12 | 2023-05-12 | MOOE | 20000 | 20000 |  | 19800 | 19800 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
200 | 5-02-13-210-01 | (RM) Office Equipment | [15 empty] | 11ID | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-04-24 | 2023-04-24 | 2023-04-24 | N/A | N/A | 2023-04-24 | 2023-04-24 | 2023-05-04 | 2023-05-12 | 2023-05-12 | MOOE | 20000 | 20000 |  | 19760 | 19760 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
201 | 5-02-03-070-00 | Drugs & Meds | [15 empty] | HHSBN | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-04-24 | 2023-04-24 | 2023-04-24 | N/A | N/A | 2023-04-24 | 2023-04-24 | 2023-05-04 | 2023-05-12 | 2023-05-12 | MOOE | 35000 | 35000 |  | 34700 | 34700 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
202 | 5-02-03-990-00 | Other Supplies | [15 empty] | 100IB | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-04-24 | 2023-04-24 | 2023-04-24 | N/A | N/A | 2023-04-24 | 2023-04-24 | 2023-05-04 | 2023-05-12 | 2023-05-12 | MOOE | 54500 | 54500 |  | 53880 | 53880 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
203 | 5-02-02-010-00 | Training Supplies | [15 empty] | 100IB | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-04-24 | 2023-04-24 | 2023-04-24 | N/A | N/A | 2023-04-24 | 2023-04-24 | 2023-05-04 | 2023-05-12 | 2023-05-12 | MOOE | 57450 | 57450 |  | 56981 | 56981 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
204 | 5-02-99-030-00 | Grocery Items | [15 empty] | 100IB | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-04-24 | 2023-04-24 | 2023-04-24 | N/A | N/A | 2023-04-24 | 2023-04-24 | 2023-05-04 | 2023-05-12 | 2023-05-12 | MOOE | 60000 | 60000 |  | 59535 | 59535 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
205 | 5-02-03-210-03 | ICT Equipment-SE | [15 empty] | 104IB | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-04-24 | 2023-04-24 | 2023-04-24 | N/A | N/A | 2023-04-24 | 2023-04-24 | 2023-05-04 | 2023-05-12 | 2023-05-12 | MOOE | 55000 | 55000 |  | 54660 | 54660 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
206 | 5-02-13-060-01 | Vehicle Parts & Acc | [15 empty] | 11ID | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-04-24 | 2023-04-24 | 2023-04-24 | N/A | N/A | 2023-04-24 | 2023-04-24 | 2023-05-04 | 2023-05-12 | 2023-05-12 | MOOE | 457000 | 457000 |  | 456242 | 456242 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
207 | 5-02-13-060-01 | Vehicle Parts & Acc | [15 empty] | 11ID | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-04-24 | 2023-04-24 | 2023-04-24 | N/A | N/A | 2023-04-24 | 2023-04-24 | 2023-05-05 | 2023-05-12 | 2023-05-12 | MOOE | 60000 | 60000 |  | 59650 | 59650 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
208 | 5-02-13-040-01 | (RM) Building | [15 empty] | HHSBN | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-04-24 | 2023-04-24 | 2023-04-24 | N/A | N/A | 2023-04-24 | 2023-04-24 | 2023-05-05 | 2023-05-12 | 2023-05-12 | MOOE | 64900 | 64900 |  | 64510 | 64510 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
209 | 5-02-13-040-01 | (RM) Building | [15 empty] | 11DTS | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-04-24 | 2023-04-24 | 2023-04-24 | N/A | N/A | 2023-04-24 | 2023-04-24 | 2023-05-05 | 2023-05-12 | 2023-05-12 | MOOE | 140600 | 140600 |  | 140000 | 140000 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
210 | 5-02-03-210-03 | ICT Equipment-SE | [15 empty] | 11ID | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-04-24 | 2023-04-24 | 2023-04-24 | N/A | N/A | 2023-04-24 | 2023-04-24 | 2023-05-05 | 2023-05-12 | 2023-05-12 | MOOE | 55000 | 55000 |  | 54650 | 54650 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
211 | 5-02-02-010-00 | Training Supplies | [15 empty] | 32IB | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-04-25 | 2023-04-25 | 2023-04-25 | N/A | N/A | 2023-04-25 | 2023-04-25 | 2023-05-05 | 2023-05-12 | 2023-05-12 | MOOE | 65000 | 65000 |  | 64460 | 64460 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
212 | 5-02-03-210-03 | ICT Equipment-SE | [15 empty] | 11ID | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-04-27 | 2023-04-27 | 2023-04-27 | N/A | N/A | 2023-04-27 | 2023-04-27 | 2023-05-17 | 2023-06-01 | 2023-06-01 | MOOE | 30000 | 30000 |  | 29775 | 29775 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
213 | 5-02-03-080-00 | Med Dent Lab Supplies | [15 empty] | 11ID | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-04-27 | 2023-04-27 | 2023-04-27 | N/A | N/A | 2023-04-27 | 2023-04-27 | 2023-05-17 | 2023-06-01 | 2023-06-01 | MOOE | 39000 | 39000 |  | 38700 | 38700 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
214 | 5-02-03-210-03 | ICT Equipment-SE | [15 empty] | 11ID | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-04-27 | 2023-04-27 | 2023-04-27 | N/A | N/A | 2023-04-27 | 2023-04-27 | 2023-05-17 | 2023-06-01 | 2023-06-01 | MOOE | 30000 | 30000 |  | 29790 | 29790 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
215 | 5-02-03-010-00 | Office Supplies | [15 empty] | 11ID | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-04-27 | 2023-04-27 | 2023-04-27 | N/A | N/A | 2023-04-27 | 2023-04-27 | 2023-05-17 | 2023-06-01 | 2023-06-01 | MOOE | 5000 | 5000 |  | 4900 | 4900 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
216 | 5-02-03-210-99 | Other Machinery-SE | [15 empty] | 11ID | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-04-28 | 2023-04-28 | 2023-04-28 | N/A | N/A | 2023-04-28 | 2023-04-28 | 2023-05-17 | 2023-06-01 | 2023-06-01 | MOOE | 139000 | 139000 |  | 138260 | 138260 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
217 | 5-02-13-040-01 | (RM) Building | [15 empty] | 11ID | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-04-28 | 2023-04-28 | 2023-04-28 | N/A | N/A | 2023-04-28 | 2023-04-28 | 2023-05-17 | 2023-06-01 | 2023-06-01 | MOOE | 219500 | 219500 |  | 218850 | 218850 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
218 | 5-02-03-080-00 | Med Dent Lab Supplies | [15 empty] | 15CMOBN | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-04-28 | 2023-04-28 | 2023-04-28 | N/A | N/A | 2023-04-28 | 2023-04-28 | 2023-05-17 | 2023-06-01 | 2023-06-01 | MOOE | 51000 | 51000 |  | 50640 | 50640 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
219 | 5-02-13-040-01 | (RM) Other Machinery | [15 empty] | 1103Bde | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-04-28 | 2023-04-28 | 2023-04-28 | N/A | N/A | 2023-04-28 | 2023-04-28 | 2023-05-17 | 2023-06-01 | 2023-06-01 | MOOE | 80000 | 80000 |  | 79665 | 79665 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
220 | 5-02-13-040-01 | (RM) Building | [15 empty] | 21IB | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-05-05 | 2023-05-05 | 2023-05-05 | N/A | N/A | 2023-05-05 | 2023-05-05 | 2023-05-24 | 2023-06-06 | 2023-06-06 | MOOE | 110000 | 110000 |  | 109650 | 109650 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
221 | 5-02-13-060-01 | Vehicle Parts & Acc | [15 empty] | 1103Bde | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-05-08 | 2023-05-08 | 2023-05-08 | N/A | N/A | 2023-05-08 | 2023-05-08 | 2023-05-24 | 2023-06-06 | 2023-06-06 | MOOE | 35000 | 35000 |  | 34820 | 34820 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
222 | 5-02-03-010-00 | Office Supplies | [15 empty] | 11SSBN | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-06-06 | 2023-06-06 | 2023-06-06 | N/A | N/A | 2023-06-06 | 2023-06-06 | 2023-06-09 | 2023-06-15 | 2023-06-15 | MOOE | 2000 | 2000 |  | 1960 | 1960 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
223 | 5-02-03-080-00 | Med Dent Lab Supplies | [15 empty] | 11ID | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-06-06 | 2023-06-06 | 2023-06-06 | N/A | N/A | 2023-06-06 | 2023-06-06 | 2023-06-09 | 2023-06-15 | 2023-06-15 | MOOE | 47500 | 47500 |  | 47132 | 47132 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
224 | 5-2-13-210-14 | (RM) Other Machinery-SE | [15 empty] | HHSBN | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-06-06 | 2023-06-06 | 2023-06-06 | N/A | N/A | 2023-06-06 | 2023-06-06 | 2023-06-09 | 2023-06-15 | 2023-06-15 | MOOE | 13750 | 13750 |  | 13630 | 13630 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
225 | 5-02-13-040-01 | (RM) Building | [15 empty] | 1103Bde | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-06-08 | 2023-06-08 | 2023-06-08 | N/A | N/A | 2023-06-08 | 2023-06-08 | 2023-06-15 | 2023-06-22 | 2023-06-22 | MOOE | 100000 | 100000 |  | 99550 | 99550 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
226 | 5-02-13-210-10 | (RM) Med Equipment | [15 empty] | 11ID | NO | Negotiated 53.9 | N/A | N/A | N/A | 2023-06-13 | 2023-06-13 | 2023-06-13 | N/A | N/A | 2023-06-13 | 2023-06-13 | 2023-06-16 | 2023-06-22 | 2023-06-22 | MOOE | 39000 | 39000 |  | 38700 | 38700 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
[35 empty] | 16797785.5 | 16797785.5 |  | 16716582.25 | 16716582.25
| Total Alloted Budget of Procurement Activities | [33 empty] | 16797785.5
| Total Contract Price of Procurement Actitvites Conducted | [36 empty] | 16716582.25
| Total Savings (Total Alloted Budget - Total Contract Price) | [33 empty] | 81203.25
0N-GOING PROCUREMENT ACTIVITIES
Total Alloted Budget of On-going Procurement Activities
|  | Prepared By: | [18 empty] | Certified Correct By: | [6 empty] | Noted By: | [11 empty] | APPROVED:
[18 empty] | Christian Junn G Mauro |  |  |  | MSg Antonieto J Igmen PA | [6 empty] | MAJ MICHAEL B DE GUIA (CE) PA | [10 empty] | MGEN IGNATIUS N PATRIMONIO PA
[18 empty] | Sgt (OS) PA |  |  |  | First Seargent | [6 empty] | Commanding Officer | [10 empty] | COMMANDER, 11ID,PA
Operations NCO
Formulas:
Inspection & Acceptance = [Delivery/ Completion]

## Sheet1 (hidden)
Competitive Bidding | GoP | YES
Limited Source Bidding | Foreign | NO
Direct Contracting | Special Purpose Fund
Repeat Order | Corporate Budget
Shopping | Income
NP-53.1 Two Failed Biddings | Others
NP-53.2 Emergency Cases
NP-53.3 Take-Over of Contracts
NP-53.4 Adjacent or Contiguous
NP-53.5 Agency-to-Agency
NP-53.6 Scientific, Scholarly, Artistic Work, Exclusive Technology and Media Services
NP-53.7 Highly Technical Consultants
NP-53.8 Defense Cooperation Agreement
NP-53.9 - Small Value Procurement
NP-53.10 Lease of Real Property and Venue
NP-53.11 NGO Participation
NP-53.12 Community Participation
NP-53.13 UN Agencies, Int'l Organizations or International Financing Institutions
Others - Foreign-funded procurement