## PMR
ANNEX B
Procurement Monitoring Report CY 2023
Code (PAP) | Procurement Project | PMO/ End-User | Is this an Early Procurement Activity? | Mode of Procurement | Actual Procurement Activity | [12 empty] | Source of Funds | ABC (PhP) |  |  | Contract Cost (PhP) |  |  | List of Invited Observers | Date of Receipt of Invitation | [5 empty] | Remarks (Explaining changes from the APP)
[5 empty] | Pre-Proc Conference | Ads/Post of IB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Date of BAC Resolution Recommending Award | Notice of Award | Contract Signing | Notice to Proceed | Delivery/ Completion | Inspection & Acceptance |  | Total | MOOE | CO | Total | MOOE | CO |  | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Delivery/ Completion/ Acceptance (If applicable)
COMPLETED PROCUREMENT ACTIVITIES
5-02-99-030-00 | Representation Expenses | ESC | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-14 | 2023-02-15 | 2023-03-01 | 2023-03-07 | 2023-03-07 | GoP | 103400 | 103400 | N/A | 103300 | 103300 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-02-010-00 | Training Expenses | ESC | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-14 | 2023-02-15 | 2023-03-06 | 2023-03-07 | 2023-03-07 | GoP | 55018 | 55018 | N/A | 54601 | 54601 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-05-020-01 | Mobile Expenses | ESC | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-14 | 2023-02-15 | 2023-03-01 | 2023-03-07 | 2023-03-07 | GoP | 11500 | 11500 | N/A | 11329 | 11329 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-210-02 | Semi-Expendable Office Equipment | ESC | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-14 | 2023-02-15 | 2023-03-02 | 2023-03-07 | 2023-03-07 | GoP | 73300 | 73300 | N/A | 71358 | 71358 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-02-010-00 | Training Expenses | ESC | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-14 | 2023-02-15 | 2023-03-07 | 2023-03-07 | 2023-03-07 | GoP | 30000 | 30000 | N/A | 29700 | 29700 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-010-00 | Office Supplies Expenses | ESC | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-14 | 2023-02-15 | 2023-03-07 | 2023-03-07 | 2023-03-07 | GoP | 10000 | 10000 | N/A | 9930 | 9930 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-99-030-00 | Representation Expenses | 51EBde, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-14 | 2023-02-15 | 2023-03-06 | 2023-03-09 | 2023-03-09 | GoP | 175573 | 175573 | N/A | 175564 | 175564 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-13-050-02 | Repair and Maintenance of Office Equipment | 51EBde, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-14 | 2023-02-15 | 2023-03-06 | 2023-03-09 | 2023-03-09 | GoP | 14775 | 14775 | N/A | 14685 | 14685 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-13-060-01 | Repair and Maintenance of Motor Vehicle | 51EBde, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-14 | 2023-02-15 | 2023-03-06 | 2023-03-09 | 2023-03-09 | GoP | 185750 | 185750 | N/A | 185600 | 185600 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-010-00 | Office Supplies Expenses | 51EBde, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-14 | 2023-02-15 | 2023-03-13 | 2023-03-15 | 2023-03-15 | GoP | 62899 | 62899 | N/A | 62617 | 62617 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-99-030-00 | Representation Expenses | 51EBde, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-14 | 2023-02-15 | 2023-03-07 | 2023-03-10 | 2023-03-10 | GoP | 302635 | 302635 | N/A | 302215 | 302215 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-99-020-00 | Printing and Pubrication Expenses | 51EBde, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-14 | 2023-02-15 | 2023-03-13 | 2023-03-15 | 2023-03-15 | GoP | 9500 | 9500 | N/A | 9425 | 9425 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-02-010-00 | Training Expenses | 51EBde, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-14 | 2023-02-15 | 2023-03-06 | 2023-03-09 | 2023-03-09 | GoP | 54660 | 54660 | N/A | 54651 | 54651 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-080-00 | Medical and Dental Laboratory Supplies Expenses | 51EBde, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-14 | 2023-02-15 | 2023-03-07 | 2023-03-10 | 2023-03-10 | GoP | 75000 | 75000 | N/A | 74694 | 74694 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-99-030-00 | Representation Expenses | 514ECB | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-14 | 2023-02-15 | 2023-03-06 | 2023-03-07 | 2023-03-07 | GoP | 108450 | 108450 | N/A | 108441 | 108441 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-13-060-01 | Repair and Maintenance of Motor Vehicle | 514ECB | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-14 | 2023-02-15 | 2023-03-02 | 2023-03-07 | 2023-03-07 | GoP | 40000 | 40000 | N/A | 39870 | 39870 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-210-08 | Semi-Expendable Disaster Response and Rescue Equipment | 514ECB | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-14 | 2023-02-15 | 2023-03-02 | 2023-03-07 | 2023-03-07 | GoP | 108000 | 108000 | N/A | 106580 | 106580 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-99-030-00 | Representation Expenses | 525ECB | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-14 | 2023-02-15 | 2023-03-02 | 2023-03-07 | 2023-03-07 | GoP | 6300 | 6300 | N/A | 6201 | 6201 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-010-00 | Office Supplies Expenses | 525ECB | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-14 | 2023-02-15 | 2023-03-02 | 2023-03-07 | 2023-03-07 | GoP | 51370 | 51370 | N/A | 51150 | 51150 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-990-00 | Other Supplies and Materials Expenses | 525ECB | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-14 | 2023-02-15 | 2023-03-02 | 2023-03-07 | 2023-03-07 | GoP | 23390 | 23390 | N/A | 23245 | 23245 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-210-09 | Semi-Expendable Military, Police and Security Equipment | 525ECB | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-14 | 2023-02-15 | 2023-03-02 | 2023-03-07 | 2023-03-07 | GoP | 10000 | 10000 | N/A | 9990 | 9990 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-02-010-00 | Training Expenses | 525ECB | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-14 | 2023-02-15 | 2023-03-13 | 2023-03-07 | 2023-03-07 | GoP | 10500 | 10500 | N/A | 10290 | 10290 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-080-00 | Medical and Dental Laboratory Supplies Expenses | 548ECB | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-14 | 2023-02-15 | 2023-03-07 | 2023-03-14 | 2023-03-14 | GoP | 10000 | 10000 | N/A | 9925 | 9925 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-070-00 | Drugs and Medicines Expenses | 548ECB | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-14 | 2023-02-15 | 2023-03-14 | 2023-03-15 | 2023-03-15 | GoP | 5000 | 5000 | N/A | 4910 | 4910 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-99-030-00 | Representation Expenses | 548ECB | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-14 | 2023-02-15 | 2023-03-07 | 2023-03-09 | 2023-03-09 | GoP | 89092 | 89092 | N/A | 88742 | 88742 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-010-00 | Office Supplies Expenses | 548ECB | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-14 | 2023-02-15 | 2023-03-06 | 2023-03-07 | 2023-03-07 | GoP | 30000 | 30000 | N/A | 29910 | 29910 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-010-00 | Office Supplies Expenses | 564ECB | NO | Shopping 52.1(b) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-14 | 2023-02-15 | 2023-03-01 | 2023-03-07 | 2023-03-07 | GoP | 27000 | 27000 | N/A | 26920 | 26920 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-210-08 | Semi-Expendable Disaster Response and Rescue Equipment | 564ECB | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-14 | 2023-02-15 | 2023-03-02 | 2023-03-07 | 2023-03-07 | GoP | 12500 | 12500 | N/A | 12250 | 12250 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-990-00 | Other Supplies and Materials Expenses | 564ECB | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-14 | 2023-02-15 | 2023-03-07 | 2023-03-10 | 2023-03-10 | GoP | 6500 | 6500 | N/A | 6400 | 6400 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-99-030-00 | Representation Expenses | 564ECB | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-14 | 2023-02-15 | 2023-03-07 | 2023-03-10 | 2023-03-10 | GoP | 61250 | 61250 | N/A | 60940 | 60940 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-02-010-00 | Training Expenses | 564ECB | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-14 | 2023-02-15 | 2023-03-07 | 2023-03-10 | 2023-03-10 | GoP | 62000 | 62000 | N/A | 61725 | 61725 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-13-040-01 | Repair and Maintenance of Building | 525ECB | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-14 | 2023-02-15 | 2023-03-13 | 2023-03-15 | 2023-03-15 | GoP | 11290 | 11290 | N/A | 11243 | 11243 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-99-030-00 | Representation Expenses | 525ECB | NO | Shopping 52.1(b) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-14 | 2023-02-15 | 2023-03-13 | 2023-03-15 | 2023-03-15 | GoP | 20000 | 20000 | N/A | 19500 | 19500 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-13-060-01 | Repair and Maintenance of Motor Vehicle | 525ECB | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-14 | 2023-02-15 | 2023-03-02 | 2023-03-07 | 2023-03-07 | GoP | 90000 | 90000 | N/A | 89988 | 89988 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-13-050-99 | Repair and Maintenance of Other Machinery and Equipment | 525ECB | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-14 | 2023-02-15 | 2023-03-02 | 2023-03-07 | 2023-03-07 | GoP | 15000 | 15000 | N/A | 14999 | 14999 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-02-010-00 | Training Expenses | 525ECB | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-14 | 2023-02-15 | 2023-03-02 | 2023-03-07 | 2023-03-07 | GoP | 54500 | 54500 | N/A | 54490 | 54490 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-05-020-01 | Mobile Expenses | 51EBde, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-14 | 2023-02-15 | 2023-03-13 | 2023-03-15 | 2023-03-15 | GoP | 67000 | 67000 | N/A | 66230 | 66230 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-05-020-01 | Mobile Expenses | 514ECB | NO | Shopping 52.1(b) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-14 | 2023-02-15 | 2023-03-02 | 2023-03-07 | 2023-03-07 | GoP | 12600 | 12600 | N/A | 12438 | 12438 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-02-010-00 | Training Expenses | 514ECB | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-14 | 2023-02-15 | 2023-03-06 | 2023-03-09 | 2023-03-09 | GoP | 40000 | 40000 | N/A | 39784 | 39784 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-210-03 | Sem-Expendable ICT Equipment Expenses | 564ECB | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-14 | 2023-02-15 | 2023-03-01 | 2023-03-07 | 2023-03-07 | GoP | 45100 | 45100 | N/A | 45000 | 45000 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-080-00 | Medical and Dental Laboratory Supplies Expenses | ESC | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-21 | 2023-02-22 | 2023-03-13 | 2023-03-14 | 2023-03-14 | GoP | 33451.5 | 33451.5 | N/A | 33334 | 33334 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-05-020-01 | Mobile Expenses | ESC | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-21 | 2023-02-22 | 2023-03-13 | 2023-03-14 | 2023-03-14 | GoP | 9000 | 9000 | N/A | 8775 | 8775 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-05-020-01 | Mobile Expenses | 525ECB | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-21 | 2023-02-22 | 2023-03-14 | 2023-03-15 | 2023-03-15 | GoP | 9600 | 9600 | N/A | 9576 | 9576 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-010-00 | Office Supplies Expenses | RDC, ASCOM, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-14 | 2023-02-15 | 2023-03-14 | 2023-03-15 | 2023-03-15 | GoP | 128383 | 128383 | N/A | 128203 | 128203 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-010-00 | Office Supplies Expenses | 112CO | NO | Shopping 52.1(b) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-21 | 2023-02-22 | 2023-03-14 | 2023-03-15 | 2023-03-15 | GoP | 16250 | 16250 | N/A | 15930 | 15930 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-05-020-01 | Mobile Expenses | 51EBde, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-28 | 2023-03-01 | 2023-03-13 | 2023-03-14 | 2023-03-14 | GoP | 8400 | 8400 | N/A | 8391 | 8391 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-010-00 | Office Supplies Expenses | 51EBde, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-28 | 2023-03-01 | 2023-03-13 | 2023-03-14 | 2023-03-14 | GoP | 6900 | 6900 | N/A | 6888 | 6888 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-99-030-00 | Representation Expenses | 51EBde, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-28 | 2023-03-01 | 2023-03-14 | 2023-03-15 | 2023-03-15 | GoP | 3200 | 3200 | N/A | 3191 | 3191 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-99-030-00 | Representation Expenses | 51EBde, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-28 | 2023-03-01 | 2023-03-14 | 2023-03-15 | 2023-03-15 | GoP | 50000 | 50000 | N/A | 49970 | 49970 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-99-030-00 | Representation Expenses | 514ECB | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-28 | 2023-03-01 | 2023-03-14 | 2023-03-15 | 2023-03-15 | GoP | 24900 | 24900 | N/A | 24720 | 24720 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-05-020-01 | Mobile Expenses | 514ECB | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-28 | 2023-03-01 | 2023-03-14 | 2023-03-15 | 2023-03-15 | GoP | 39000 | 39000 | N/A | 38610 | 38610 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-05-020-01 | Mobile Expenses | 548ECB | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-28 | 2023-02-28 | 2023-03-20 | 2023-03-23 | 2023-03-23 | GoP | 13900 | 13900 | N/A | 13850 | 13850 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-99-030-00 | Representation Expenses | 548ECB | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-28 | 2023-03-01 | 2023-03-20 | 2023-03-23 | 2023-03-23 | GoP | 50000 | 50000 | N/A | 49950 | 49950 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-02-010-00 | Training Expenses | 51EBde, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-28 | 2023-03-01 | 2023-03-13 | 2023-03-14 | 2023-03-14 | GoP | 150000 | 150000 | N/A | 149850 | 149850 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-99-030-00 | Representation Expenses | 51EBde, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-28 | 2023-03-01 | 2023-03-13 | 2023-03-14 | 2023-03-14 | GoP | 30000 | 30000 | N/A | 29991 | 29991 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-990-00 | Other Supplies and Materials Expenses | 564ECB | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-28 | 2023-03-01 | 2023-03-14 | 2023-03-16 | 2023-03-16 | GoP | 18240 | 18240 | N/A | 18140 | 18140 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-99-030-00 | Representation Expenses | 564ECB | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-28 | 2023-03-01 | 2023-03-14 | 2023-03-16 | 2023-03-16 | GoP | 27950 | 27950 | N/A | 27774 | 27774 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-010-00 | Office Supplies Expenses | 564ECB | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-28 | 2023-02-28 | 2023-03-14 | 2023-03-16 | 2023-03-16 | GoP | 6910 | 6910 | N/A | 6860 | 6860 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-05-020-01 | Mobile Expenses | 564ECB | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-28 | 2023-03-01 | 2023-03-14 | 2023-03-16 | 2023-03-16 | GoP | 10800 | 10800 | N/A | 10796 | 10796 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-13-040-01 | Repair and Maintenance of Building | ESC | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-28 | 2023-03-01 | 2023-03-17 | 2023-03-20 | 2023-03-20 | GoP | 125000 | 125000 | N/A | 124655 | 124655 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-990-00 | Other Supplies and Materials Expenses | 525ECB | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-28 | 2023-03-01 | 2023-03-15 | 2023-03-16 | 2023-03-16 | GoP | 150000 | 150000 | N/A | 149986 | 149986 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-13-040-01 | Repair and Maintenance of Building | 514ECB | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-03 | 2023-03-01 | 2023-04-13 | 2023-04-14 | 2023-04-14 | GoP | 995206.4 | 995206.4 | N/A | 994406 | 994406 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-02-010-00 | Training Expenses | 51EBde, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-03 | 2023-03-04 | 2023-03-28 | 2023-03-29 | 2023-03-29 | GoP | 41000 | 41000 | N/A | 40928 | 40928 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-010-00 | Office Supplies Expenses | 51EBde, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-03 | 2023-03-08 | 2023-03-28 | 2023-03-29 | 2023-03-29 | GoP | 30000 | 30000 | N/A | 29956 | 29956 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-05-020-01 | Mobile Expenses | 51EBde, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-03 | 2023-03-03 | 2023-03-28 | 2023-03-29 | 2023-03-29 | GoP | 11000 | 11000 | N/A | 10955 | 10955 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-99-030-00 | Representation Expenses | 51EBde, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-03 | 2023-03-03 | 2023-04-24 | 2023-04-26 | 2023-04-26 | GoP | 43000 | 43000 | N/A | 42970 | 42970 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-990-00 | Other Supplies and Materials Expenses | 51EBde, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-03 | 2023-03-08 | 2023-04-11 | 2023-04-12 | 2023-04-12 | GoP | 100000 | 100000 | N/A | 99650 | 99650 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-990-00 | Other Supplies and Materials Expenses | 51EBde, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-03 | 2023-03-08 | 2023-04-11 | 2023-04-12 | 2023-04-12 | GoP | 100000 | 100000 | N/A | 99650 | 99650 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-990-00 | Other Supplies and Materials Expenses | 51EBde, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-03 | 2023-03-08 | 2023-04-11 | 2023-04-12 | 2023-04-12 | GoP | 50000 | 50000 | N/A | 49800 | 49800 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-13-040-99 | Repair and Maintenance of Other Structure | 548ECB | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-14 | 2023-03-15 | 2023-04-13 | 2023-04-14 | 2023-04-14 | GoP | 150000 | 150000 | N/A | 148600 | 148600 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-13-040-99 | Repair and Maintenance of Other Structure | 548ECB | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-14 | 2023-03-15 | 2023-03-28 | 2023-03-29 | 2023-03-29 | GoP | 49200 | 49200 | N/A | 48872 | 48872 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-13-040-99 | Repair and Maintenance of Other Structure | 548ECB | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-14 | 2023-03-15 | 2023-03-28 | 2023-03-29 | 2023-03-29 | GoP | 49415.13 | 49415.13 | N/A | 49089 | 49089 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-13-040-99 | Repair and Maintenance of Other Structure | 548ECB | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-14 | 2023-03-15 | 2023-03-28 | 2023-03-29 | 2023-03-29 | GoP | 7958 | 7958 | N/A | 7916 | 7916 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-990-00 | Other Supplies and Materials Expenses | RDC, ASCOM, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-14 | 2023-03-15 | 2023-04-13 | 2023-04-14 | 2023-04-14 | GoP | 389938 | 389938 | N/A | 389038 | 389038 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-080-00 | Medical and Dental Laboratory Supplies Expenses | 51EBde, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-14 | 2023-03-15 | 2023-04-11 | 2023-04-12 | 2023-04-12 | GoP | 36000 | 36000 | N/A | 35985 | 35985 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-13-040-01 | Repair and Maintenance of Building | 51EBde, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-14 | 2023-03-15 | 2023-04-13 | 2023-04-14 | 2023-04-14 | GoP | 350000 | 350000 | N/A | 349268 | 349268 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-990-00 | Other Supplies and Materials Expenses | 514ECB | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-14 | 2023-03-15 | 2023-04-13 | 2023-04-14 | 2023-04-14 | GoP | 150000 | 150000 | N/A | 149540 | 149540 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-210-03 | Sem-Expendable ICT Equipment Expenses | 51EBde, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-14 | 2023-03-15 | 2023-04-11 | 2023-04-12 | 2023-04-12 | GoP | 60000 | 60000 | N/A | 58300 | 58300 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-080-00 | Medical and Dental Laboratory Supplies Expenses | 51EBde, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-14 | 2023-03-15 | 2023-05-08 | 2023-05-08 | 2023-05-08 | GoP | 86000 | 86000 | N/A | 85994 | 85994 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-13-040-01 | Repair and Maintenance of Building | 548ECB | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-14 | 2023-03-15 | 2023-04-25 | 2023-05-02 | 2023-05-02 | GoP | 250000 | 250000 | N/A | 249470 | 249470 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-13-040-99 | Repair and Maintenance of Other Structure | 548ECB | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-14 | 2023-03-15 | 2023-04-14 | 2023-04-14 | 2023-04-14 | GoP | 7042 | 7042 | N/A | 6919 | 6919 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-99-030-00 | Representation Expenses | 51EBde, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-14 | 2023-03-15 | 2023-04-24 | 2023-04-26 | 2023-04-26 | GoP | 10000 | 10000 | N/A | 9994 | 9994 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-99-030-00 | Representation Expenses | 51EBde, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-14 | 2023-03-15 | 2023-04-24 | 2023-04-25 | 2023-04-25 | GoP | 20000 | 20000 | N/A | 19937 | 19937 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-99-030-00 | Representation Expenses | 51EBde, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-14 | 2023-03-15 | 2023-05-23 | 2023-05-24 | 2023-05-24 | GoP | 100000 | 100000 | N/A | 99900 | 99900 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-99-030-00 | Representation Expenses | 51EBde, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-14 | 2023-03-15 | 2023-04-24 | 2023-04-25 | 2023-04-25 | GoP | 2000 | 2000 | N/A | 1970 | 1970 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-99-030-00 | Representation Expenses | 51EBde, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-21 | 2023-03-15 | 2023-04-24 | 2023-04-26 | 2023-04-26 | GoP | 30000 | 30000 | N/A | 29988 | 29988 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-02-010-00 | Training Expenses | 51EBde, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-21 | 2023-03-22 | 2023-04-24 | 2023-04-26 | 2023-04-26 | GoP | 120000 | 120000 | N/A | 119650 | 119650 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-990-00 | Other Supplies and Materials Expenses | 14FPAO | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-28 | 2023-03-22 | 2023-05-15 | 2023-05-17 | 2023-05-17 | GoP | 93750 | 93750 | N/A | 93720 | 93720 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-13-040-01 | Repair and Maintenance of Building | 564ECB | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-28 | 2023-03-29 | 2023-05-22 | 2023-05-24 | 2023-05-24 | GoP | 150000 | 150000 | N/A | 149670 | 149670 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-99-030-00 | Representation Expenses | ESC, 51EBde, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-28 | 2023-03-29 | 2023-05-15 | 2023-05-16 | 2023-05-16 | GoP | 17548.5 | 17548.5 | N/A | 17485 | 17485 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-080-00 | Medical and Dental Laboratory Supplies Expenses | 51EBde, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-28 | 2023-03-29 | 2023-05-23 | 2023-05-24 | 2023-05-24 | GoP | 70100 | 70100 | N/A | 70029 | 70029 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-990-00 | Other Supplies and Materials Expenses | 514ECB | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-28 | 2023-03-29 | 2023-05-23 | 2023-05-24 | 2023-05-24 | GoP | 150000 | 150000 | N/A | 149890 | 149890 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-13-040-01 | Repair and Maintenance of Building | 513ECB | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-28 | 2023-03-29 | 2023-05-23 | 2023-05-24 | 2023-05-24 | GoP | 854060 | 854060 | N/A | 853435 | 853435 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-13-040-01 | Repair and Maintenance of Building | 513ECB | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-28 | 2023-03-29 | 2023-05-23 | 2023-05-24 | 2023-05-24 | GoP | 854060 | 854060 | N/A | 853185 | 853185 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-990-00 | Other Supplies and Materials Expenses | 548ECB | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-28 | 2023-03-29 | 2023-05-23 | 2023-05-24 | 2023-05-24 | GoP | 150000 | 150000 | N/A | 149722.5 | 149722.5 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-99-030-00 | Representation Expenses | RDC, ASCOM, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-28 | 2023-03-29 | 2023-03-14 | 2023-03-20 | 2023-03-20 | GoP | 100000 | 100000 | N/A | 99000 | 99000 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-080-00 | Medical and Dental Laboratory Supplies Expenses | RDC, ASCOM, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-28 | 2023-03-29 | 2023-03-14 | 2023-03-15 | 2023-03-15 | GoP | 15000 | 15000 | N/A | 14900 | 14900 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-13-040-01 | Repair and Maintenance of Building | RDC, ASCOM, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-28 | 2023-03-29 | 2023-03-14 | 2023-03-15 | 2023-03-15 | GoP | 36500 | 36500 | N/A | 36375 | 36375 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-02-010-00 | Training Expenses | RDC, ASCOM, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-28 | 2023-03-29 | 2023-03-14 | 2023-03-15 | 2023-03-15 | GoP | 10000 | 10000 | N/A | 9960 | 9960 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-990-00 | Other Supplies and Materials Expenses | 51EBde, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-28 | 2023-03-29 | 2023-03-10 | 2023-03-17 | 2023-03-17 | GoP | 75985 | 75985 | N/A | 75765 | 75765 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-070-00 | Drugs and Medicines Expenses | 51EBde, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-28 | 2023-03-29 | 2023-03-13 | 2023-03-17 | 2023-03-17 | GoP | 37285 | 37285 | N/A | 37245 | 37245 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-080-00 | Medical and Dental Laboratory Supplies Expenses | 514ECB | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-28 | 2023-03-29 | 2023-03-14 | 2023-03-16 | 2023-03-16 | GoP | 17500 | 17500 | N/A | 17400 | 17400 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-13-040-01 | Repair and Maintenance of Building | 14FPAO | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-28 | 2023-03-29 | 2023-03-10 | 2023-03-17 | 2023-03-17 | GoP | 119128 | 119128 | N/A | 118678 | 118678 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-210-03 | Sem-Expendable ICT Equipment Expenses | 14FPAO | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-28 | 2023-03-29 | 2023-03-13 | 2023-03-17 | 2023-03-17 | GoP | 61000 | 61000 | N/A | 60990 | 60990 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-210-03 | Sem-Expendable ICT Equipment Expenses | 14FPAO | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-28 | 2023-03-29 | 2023-03-13 | 2023-03-17 | 2023-03-17 | GoP | 60500 | 60500 | N/A | 60490 | 60490 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-080-00 | Medical and Dental Laboratory Supplies Expenses | 525ECB | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-28 | 2023-03-29 | 2023-03-13 | 2023-03-16 | 2023-03-16 | GoP | 3500 | 3500 | N/A | 3400 | 3400 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-070-00 | Drugs and Medicines Expenses | 564ECB | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-28 | 2023-03-29 | 2023-03-10 | 2023-03-16 | 2023-03-16 | GoP | 3000 | 3000 | N/A | 2950 | 2950 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-080-00 | Medical and Dental Laboratory Supplies Expenses | 564ECB | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-28 | 2023-03-29 | 2023-03-10 | 2023-03-15 | 2023-03-15 | GoP | 8000 | 8000 | N/A | 7920 | 7920 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-070-00 | Drugs and Medicines Expenses | RDC, ASCOM, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-28 | 2023-03-29 | 2023-03-14 | 2023-03-15 | 2023-03-15 | GoP | 5000 | 5000 | N/A | 4900 | 4900 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-99-030-00 | Representation Expenses | ESC | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-28 | 2023-03-29 | 2023-03-14 | 2023-03-21 | 2023-03-21 | GoP | 17548.5 | 17548.5 | N/A | 17489 | 17489 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-13-060-01 | Repair and Maintenance of Motor Vehicle | ESC | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-28 | 2023-03-29 | 2023-03-13 | 2023-03-21 | 2023-03-21 | GoP | 40721 | 40721 | N/A | 40641 | 40641 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-010-00 | Office Supplies Expenses | 14FPAO | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-28 | 2023-03-29 | 2023-03-10 | 2023-03-17 | 2023-03-17 | GoP | 73020 | 73020 | N/A | 72720 | 72720 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-13-050-03 | ICT Office Supplies Expenses | 14FPAO | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-28 | 2023-03-29 | 2023-03-10 | 2023-03-17 | 2023-03-17 | GoP | 84525 | 84525 | N/A | 84075 | 84075 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-990-00 | Other Supplies and Materials Expenses | 14FPAO | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-28 | 2023-03-29 | 2023-03-10 | 2023-03-17 | 2023-03-17 | GoP | 27500 | 27500 | N/A | 27347 | 27347 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-02-010-00 | Training Expenses | 14FPAO | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-28 | 2023-03-29 | 2023-03-10 | 2023-03-17 | 2023-03-17 | GoP | 32000 | 32000 | N/A | 31920 | 31920 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-05-020-01 | Mobile Expenses | 14FPAO | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-28 | 2023-03-29 | 2023-03-10 | 2023-03-17 | 2023-03-17 | GoP | 5900 | 5900 | N/A | 5876 | 5876 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-99-030-00 | Representation Expenses | 14FPAO | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-28 | 2023-03-29 | 2023-03-10 | 2023-03-17 | 2023-03-17 | GoP | 19000 | 19000 | N/A | 18940 | 18940 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-13-050-03 | ICT Office Supplies Expenses | 514ECB | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-28 | 2023-03-29 | 2023-03-14 | 2023-03-16 | 2023-03-16 | GoP | 3000 | 3000 | N/A | 2980 | 2980 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-010-00 | Office Supplies Expenses | 514ECB | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-28 | 2023-03-29 | 2023-03-14 | 2023-03-16 | 2023-03-16 | GoP | 55600 | 55600 | N/A | 55352 | 55352 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-13-050-08 | Repair and Maintenance of Construction of Heavy Equipment | 525ECB | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-28 | 2023-03-29 | 2023-03-14 | 2023-03-21 | 2023-03-21 | GoP | 25000 | 25000 | N/A | 24940 | 24940 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-99-030-00 | Representation Expenses | 525ECB | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-28 | 2023-03-29 | 2023-03-14 | 2023-03-16 | 2023-03-16 | GoP | 122790 | 122790 | N/A | 122430 | 122430 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-210-03 | Sem-Expendable ICT Equipment Expenses | 525ECB | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-28 | 2023-03-29 | 2023-03-13 | 2023-03-16 | 2023-03-16 | GoP | 50500 | 50500 | N/A | 48200 | 48200 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-080-00 | Medical and Dental Laboratory Supplies Expenses | 525ECB | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-28 | 2023-03-29 | 2023-03-14 | 2023-03-16 | 2023-03-16 | GoP | 50700 | 50700 | N/A | 50540 | 50540 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-99-030-00 | Representation Expenses | 525ECB | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-28 | 2023-03-29 | 2023-03-14 | 2023-03-16 | 2023-03-16 | GoP | 66450 | 66450 | N/A | 66250 | 66250 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-05-020-01 | Mobile Expenses | 112CO | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-04 | 2023-03-29 | 2023-03-14 | 2023-03-17 | 2023-03-17 | GoP | 5000 | 5000 | N/A | 4990 | 4990 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-990-00 | Other Supplies and Materials Expenses | 112CO | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-04 | 2023-04-05 | 2023-03-14 | 2023-03-17 | 2023-03-17 | GoP | 18750 | 18750 | N/A | 18630 | 18630 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-02-010-00 | Training Expenses | RDC, ASCOM, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-04 | 2023-04-05 | 2023-03-03 | 2023-03-13 | 2023-03-13 | GoP | 35000 | 35000 | N/A | 34940 | 34940 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-130-00 | Chemical and Filtering Supplies Expenses | RDC, ASCOM, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-04 | 2023-04-05 | 2023-03-14 | 2023-03-15 | 2023-03-15 | GoP | 69300 | 69300 | N/A | 69045 | 69045 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-990-00 | Other Supplies and Materials Expenses | RDC, ASCOM, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-04 | 2023-04-05 | 2023-03-14 | 2023-03-16 | 2023-03-16 | GoP | 50000 | 50000 | N/A | 49900 | 49900 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-13-040-01 | Repair and Maintenance of Building | 548ECB | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-04 | 2023-04-05 | 2023-03-20 | 2023-03-27 | 2023-03-27 | GoP | 102100 | 102100 | N/A | 102000 | 102000 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-13-060-01 | Repair and Maintenance of Motor Vehicle | 564ECB | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-04 | 2023-04-05 | 2023-03-17 | 2023-03-22 | 2023-03-22 | GoP | 51800 | 51800 | N/A | 51700 | 51700 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-13-040-01 | Repair and Maintenance of Building | 564ECB | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-04 | 2023-04-05 | 2023-03-14 | 2023-03-21 | 2023-03-21 | GoP | 85200 | 85200 | N/A | 84800 | 84800 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-010-00 | Office Supplies Expenses | 14FSFO | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-04 | 2023-04-05 | 2023-03-15 | 2023-03-22 | 2023-03-22 | GoP | 50988.08 | 50988.08 | N/A | 50913 | 50913 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-13-060-01 | Repair and Maintenance of Motor Vehicle | 548ECB | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-04 | 2023-04-05 | 2023-03-20 | 2023-03-27 | 2023-03-27 | GoP | 70455 | 70455 | N/A | 70405 | 70405 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-080-00 | Medical and Dental Laboratory Supplies Expenses | 514ECB | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-04 | 2023-04-05 | 2023-03-15 | 2023-03-17 | 2023-03-17 | GoP | 42600 | 42600 | N/A | 42449 | 42449 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-080-00 | Medical and Dental Laboratory Supplies Expenses | 548ECB | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-04 | 2023-04-05 | 2023-03-15 | 2023-03-17 | 2023-03-17 | GoP | 42600 | 42600 | N/A | 42379 | 42379 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-080-00 | Medical and Dental Laboratory Supplies Expenses | 564ECB | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-04 | 2023-04-05 | 2023-03-24 | 2023-04-03 | 2023-04-03 | GoP | 42600 | 42600 | N/A | 42220 | 42220 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-99-030-00 | Representation Expenses | RDC, ASCOM, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-04 | 2023-04-05 | 2023-04-25 | 2023-03-28 | 2023-03-28 | GoP | 105117 | 105117 | N/A | 105009 | 105009 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-13-040-01 | Repair and Maintenance of Building | 14FSFO | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-04 | 2023-04-05 | 2023-04-11 | 2023-03-17 | 2023-03-17 | GoP | 212810 | 212810 | N/A | 211960 | 211960 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-210-02 | Semi-Expendable Office Equipment | 14FAU | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-04 | 2023-04-05 | 2023-04-11 | 2023-04-13 | 2023-04-13 | GoP | 64980 | 64980 | N/A | 63000 | 63000 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-210-03 | Sem-Expendable ICT Equipment Expenses | 14FAU | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-04 | 2023-04-05 | 2023-04-11 | 2023-04-13 | 2023-04-13 | GoP | 104993 | 104993 | N/A | 101000 | 101000 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-210-08 | Semi-Expendable Disaster Response and Rescue Equipment | 14FAU | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-04 | 2023-04-05 | 2023-04-11 | 2023-04-13 | 2023-04-13 | GoP | 15000 | 15000 | N/A | 13700 | 13700 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-210-10 | Semi-Expendable Medical Equipment | 14FAU | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-04 | 2023-04-05 | 2023-04-11 | 2023-04-13 | 2023-04-13 | GoP | 9500 | 9500 | N/A | 9000 | 9000 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-13-060-01 | Repair and Maintenance of Motor Vehicle | 14FAU | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-04 | 2023-04-05 | 2023-04-18 | 2023-04-19 | 2023-04-19 | GoP | 25600 | 25600 | N/A | 25440 | 25440 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-210-03 | Sem-Expendable ICT Equipment Expenses | 14FAU | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-04 | 2023-04-05 | 2023-04-18 | 2023-04-19 | 2023-04-19 | GoP | 312000 | 312000 | N/A | 311640 | 311640 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-02-010-00 | Training Expenses | 51EBde, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-18 | 2023-04-19 | 2023-04-24 | 2023-04-28 | 2023-04-28 | GoP | 35340 | 35340 | N/A | 35280 | 35280 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-13-050-03 | Repair and Maintenance ICT Equipment | 14FAU | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-18 | 2023-04-19 | 2023-04-18 | 2023-04-19 | 2023-04-19 | GoP | 10000 | 10000 | N/A | 9985 | 9985 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-13-050-02 | Repair and Maintenance of Office Equipment | 14FAU | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-18 | 2023-04-19 | 2023-04-18 | 2023-04-19 | 2023-04-19 | GoP | 7000 | 7000 | N/A | 6940 | 6940 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-990-00 | Other Supplies and Materials Expenses | 14FAU | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-18 | 2023-04-19 | 2023-04-18 | 2023-04-19 | 2023-04-19 | GoP | 27500 | 27500 | N/A | 27284 | 27284 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-99-030-00 | Representation Expenses | 14FAU | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-18 | 2023-04-19 | 2023-04-18 | 2023-04-19 | 2023-04-19 | GoP | 20851.8 | 20851.8 | N/A | 20724 | 20724 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-070-00 | Drugs and Medicines Expenses | 525ECB | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-18 | 2023-04-19 | 2023-04-24 | 2023-05-01 | 2023-05-01 | GoP | 5000 | 5000 | N/A | 4950 | 4950 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-080-00 | Medical and Dental Laboratory Supplies Expenses | 525ECB | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-18 | 2023-04-19 | 2023-04-26 | 2023-05-02 | 2023-05-02 | GoP | 8500 | 8500 | N/A | 8460 | 8460 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-13-040-01 | Repair and Maintenance of Building | 525ECB | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-18 | 2023-04-19 | 2023-04-24 | 2023-05-02 | 2023-05-02 | GoP | 249988 | 249988 | N/A | 249638 | 249638 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-080-00 | Medical and Dental Laboratory Supplies Expenses | 525ECB | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-18 | 2023-04-19 | 2023-04-24 | 2023-05-01 | 2023-05-01 | GoP | 50700 | 50700 | N/A | 50640 | 50640 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-05-020-01 | Mobile Expenses | 525ECB | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-18 | 2023-04-19 | 2023-05-02 | 2023-05-08 | 2023-05-08 | GoP | 7200 | 7200 | N/A | 7150 | 7150 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-02-010-00 | Training Expenses | 525ECB | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-18 | 2023-04-19 | 2023-04-24 | 2023-05-02 | 2023-05-02 | GoP | 42000 | 42000 | N/A | 41860 | 41860 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-05-020-01 | Mobile Expenses | 525ECB | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-18 | 2023-04-19 | 2023-04-26 | 2023-05-02 | 2023-05-02 | GoP | 9600 | 9600 | N/A | 9500 | 9500 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-99-030-00 | Representation Expenses | 525ECB | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-18 | 2023-04-19 | 2023-04-24 | 2023-05-01 | 2023-05-01 | GoP | 66450 | 66450 | N/A | 66378 | 66378 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-13-060-01 | Repair and Maintenance of Motor Vehicle | 525ECB | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-18 | 2023-04-19 | 2023-04-24 | 2023-05-02 | 2023-05-02 | GoP | 42000 | 42000 | N/A | 41994 | 41994 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-13-050-08 | Repair and Maintenance of Construction of Heavy Equipment | 525ECB | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-18 | 2023-04-19 | 2023-04-24 | 2023-05-02 | 2023-05-02 | GoP | 40000 | 40000 | N/A | 39994 | 39994 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-13-040-01 | Repair and Maintenance of Building | 525ECB | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-18 | 2023-04-19 | 2023-04-26 | 2023-05-02 | 2023-05-02 | GoP | 6000 | 6000 | N/A | 5975 | 5975 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-13-070-00 | Semi-Expendable Furniture and Fixture | 14FAU | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-18 | 2023-04-19 | 2023-04-24 | 2023-04-27 | 2023-04-27 | GoP | 25027 | 25027 | N/A | 25000 | 25000 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-210-07 | Semi-Expendable Communication Equipment | 525ECB | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-18 | 2023-04-19 | 2023-05-02 | 2023-05-05 | 2023-05-05 | GoP | 32500 | 32500 | N/A | 32000 | 32000 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-210-09 | Semi-Expendable Military, Police and Security Equipment | 525ECB | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-18 | 2023-04-19 | 2023-05-08 | 2023-05-14 | 2023-05-14 | GoP | 10000 | 10000 | N/A | 9995 | 9995 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-02-010-00 | Training Expenses | 548ECB | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-18 | 2023-04-19 | 2023-04-26 | 2023-05-02 | 2023-05-02 | GoP | 139542 | 139542 | N/A | 139492 | 139492 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-010-00 | Office Supplies Expenses | 548ECB | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-18 | 2023-04-19 | 2023-04-24 | 2023-04-27 | 2023-04-27 | GoP | 36000 | 36000 | N/A | 35940 | 35940 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-070-00 | Drugs and Medicines Expenses | 548ECB | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-18 | 2023-04-19 | 2023-04-24 | 2023-04-27 | 2023-04-27 | GoP | 5000 | 5000 | N/A | 4910 | 4910 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-990-00 | Other Supplies and Materials Expenses | 548ECB | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-18 | 2023-04-19 | 2023-04-25 | 2023-04-27 | 2023-04-27 | GoP | 22200 | 22200 | N/A | 22020 | 22020 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-05-020-01 | Mobile Expenses | 548ECB | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-18 | 2023-04-19 | 2023-04-24 | 2023-04-27 | 2023-04-27 | GoP | 9700 | 9700 | N/A | 9559 | 9559 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-080-00 | Medical and Dental Laboratory Supplies Expenses | 548ECB | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-18 | 2023-04-19 | 2023-04-25 | 2023-04-27 | 2023-04-27 | GoP | 42600 | 42600 | N/A | 42550 | 42550 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-05-020-01 | Mobile Expenses | 548ECB | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-18 | 2023-04-19 | 2023-04-25 | 2023-04-27 | 2023-04-27 | GoP | 13900 | 13900 | N/A | 13795 | 13795 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-99-030-00 | Representation Expenses | 548ECB | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-18 | 2023-04-19 | 2023-04-24 | 2023-04-27 | 2023-04-27 | GoP | 50000 | 50000 | N/A | 49936 | 49936 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-13-050-99 | Other Machineries | 525ECB | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-18 | 2023-04-19 | 2023-05-08 | 2023-05-12 | 2023-05-12 | GoP | 10000 | 10000 | N/A | 9950 | 9950 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-13-050-07 | Repair and Maintenance of Communication Equipment | 525ECB | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-18 | 2023-04-19 | 2023-05-08 | 2023-05-12 | 2023-05-12 | GoP | 10000 | 10000 | N/A | 9950 | 9950 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-13-060-04 | Repair and Maintenance of Water Craft | 525ECB | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-18 | 2023-04-19 | 2023-05-08 | 2023-05-12 | 2023-05-12 | GoP | 30000 | 30000 | N/A | 29849 | 29849 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-010-00 | Office Supplies Expenses | 525ECB | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-18 | 2023-04-19 | 2023-05-02 | 2023-05-08 | 2023-05-08 | GoP | 60970 | 60970 | N/A | 60666 | 60666 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-99-030-00 | Representation Expenses | 51EBde, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-25 | 2023-04-19 | 2023-04-24 | 2023-05-02 | 2023-05-02 | GoP | 383210 | 383210 | N/A | 383070 | 383070 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-990-00 | Other Supplies and Materials Expenses | 51EBde, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-18 | 2023-04-26 | 2023-04-24 | 2023-04-28 | 2023-04-28 | GoP | 77795 | 77795 | N/A | 77726 | 77726 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-070-00 | Drugs and Medicines Expenses | 51EBde, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-18 | 2023-04-19 | 2023-04-24 | 2023-04-28 | 2023-04-28 | GoP | 37285 | 37285 | N/A | 37225 | 37225 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-05-020-01 | Mobile Expenses | 51EBde, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-18 | 2023-04-19 | 2023-05-02 | 2023-05-08 | 2023-05-08 | GoP | 76500 | 76500 | N/A | 76358.5 | 76358.5 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-13-040-01 | Repair and Maintenance of Building | 514ECB | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-18 | 2023-04-19 | 2023-04-24 | 2023-04-28 | 2023-04-28 | GoP | 940125 | 940125 | N/A | 938625 | 938625 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-13-040-01 | Repair and Maintenance of Building | 514ECB | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-18 | 2023-04-19 | 2023-05-08 | 2023-05-10 | 2023-05-10 | GoP | 150000 | 150000 | N/A | 149575 | 149575 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-13-040-01 | Repair and Maintenance of Building | 514ECB | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-18 | 2023-04-19 | 2023-04-24 | 2023-04-28 | 2023-04-28 | GoP | 907938 | 907938 | N/A | 906438 | 906438 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-13-050-07 | Repair and Maintenance of Communication Equipment | 51EBde, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-18 | 2023-04-19 | 2023-04-24 | 2023-04-28 | 2023-04-28 | GoP | 100000 | 100000 | N/A | 99665 | 99665 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-13-040-01 | Repair and Maintenance of Building | 51EBde, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-18 | 2023-04-19 | 2023-05-02 | 2023-05-08 | 2023-05-08 | GoP | 162281 | 162281 | N/A | 161837.5 | 161837.5 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-080-00 | Medical and Dental Laboratory Supplies Expenses | 51EBde, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-18 | 2023-04-19 | 2023-04-24 | 2023-04-28 | 2023-04-28 | GoP | 75000 | 75000 | N/A | 74910 | 74910 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-13-060-01 | Repair and Maintenance of Motor Vehicle | 51EBde, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-18 | 2023-04-19 | 2023-04-24 | 2023-04-28 | 2023-04-28 | GoP | 209300 | 209300 | N/A | 209180 | 209180 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-010-00 | Office Supplies Expenses | 14FAU | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-18 | 2023-04-19 | 2023-05-15 | 2023-04-18 | 2023-04-18 | GoP | 42841 | 42841 | N/A | 42733 | 42733 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-05-020-01 | Mobile Expenses | RDC, ASCOM, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-18 | 2023-04-19 | 2023-05-08 | 2023-05-12 | 2023-05-12 | GoP | 12500 | 12500 | N/A | 12470 | 12470 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-02-010-00 | Training Expenses | RDC, ASCOM, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-25 | 2023-04-19 | 2023-05-08 | 2023-05-12 | 2023-05-12 | GoP | 45000 | 45000 | N/A | 44940 | 44940 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-010-00 | Office Supplies Expenses | 112CO | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-25 | 2023-04-26 | 2023-05-08 | 2023-05-15 | 2023-05-15 | GoP | 16250 | 16250 | N/A | 16200 | 16200 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-05-020-01 | Mobile Expenses | 112CO | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-25 | 2023-04-26 | 2023-05-08 | 2023-05-15 | 2023-05-15 | GoP | 5000 | 5000 | N/A | 4995 | 4995 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-990-00 | Other Supplies and Materials Expenses | 112CO | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-25 | 2023-04-26 | 2023-05-08 | 2023-05-15 | 2023-05-15 | GoP | 18750 | 18750 | N/A | 18570 | 18570 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-02-010-00 | Training Expenses | 51EBde, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-25 | 2023-04-26 | 2023-05-15 | 2023-05-22 | 2023-05-22 | GoP | 118970 | 118970 | N/A | 118570 | 118570 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-13-050-03 | ICT Office Supplies Expenses | 51EBde, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-25 | 2023-04-26 | 2023-05-15 | 2023-05-22 | 2023-05-22 | GoP | 53840 | 53840 | N/A | 53819 | 53819 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-990-00 | Other Supplies and Materials Expenses | 51EBde, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-25 | 2023-04-26 | 2023-05-15 | 2023-05-22 | 2023-05-22 | GoP | 100000 | 100000 | N/A | 99985 | 99985 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-010-00 | Office Supplies Expenses | 51EBde, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-25 | 2023-04-26 | 2023-05-15 | 2023-05-19 | 2023-05-19 | GoP | 14775 | 14775 | N/A | 14735 | 14735 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-010-00 | Office Supplies Expenses | 51EBde, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-25 | 2023-04-26 | 2023-05-15 | 2023-05-19 | 2023-05-19 | GoP | 75044 | 75044 | N/A | 74876 | 74876 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-210-01 | Semi Expendable Machinery | 14FSFO | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-25 | 2023-04-26 | 2023-05-08 | 2023-05-08 | 2023-05-08 | GoP | 48214 | 48214 | N/A | 46800 | 46800 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-210-02 | Semi Expendable Office Equipment | 14FSFO | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-25 | 2023-04-26 | 2023-05-15 | 2023-05-18 | 2023-05-18 | GoP | 12721.79 | 12721.79 | N/A | 10550 | 10550 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-13-040-01 | Repair and Maintenance of Building | RDC, ASCOM, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-25 | 2023-04-26 | 2023-05-08 | 2023-05-12 | 2023-05-12 | GoP | 146500 | 146500 | N/A | 146491 | 146491 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-13-040-99 | Repair and Maintenance of Other Structure | RDC, ASCOM, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-25 | 2023-04-26 | 2023-05-08 | 2023-05-12 | 2023-05-12 | GoP | 98812 | 98812 | N/A | 98803 | 98803 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-13-050-03 | ICT Office Supplies Expenses | 14FPAO | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-25 | 2023-04-26 | 2023-05-08 | 2023-05-11 | 2023-05-11 | GoP | 12000 | 12000 | N/A | 11930 | 11930 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-02-010-00 | Training Expenses | 14FPAO | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-25 | 2023-04-26 | 2023-05-15 | 2023-05-19 | 2023-05-19 | GoP | 22000 | 22000 | N/A | 21925 | 21925 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-010-00 | Office Supplies Expenses | 14FPAO | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-25 | 2023-04-26 | 2023-05-08 | 2023-05-11 | 2023-05-11 | GoP | 73020 | 73020 | N/A | 72930 | 72930 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-02-010-00 | Training Expenses | 14FPAO | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-25 | 2023-04-26 | 2023-05-15 | 2023-05-19 | 2023-05-19 | GoP | 40590 | 40590 | N/A | 40520 | 40520 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-210-08 | Semi-Expendable Disaster Response and Rescue Equipment | 14FPAO | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-25 | 2023-04-26 | 2023-05-08 | 2023-05-11 | 2023-05-11 | GoP | 39000 | 39000 | N/A | 38500 | 38500 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-05-020-01 | Mobile Expenses | 14FPAO | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-25 | 2023-04-26 | 2023-05-08 | 2023-05-11 | 2023-05-11 | GoP | 5900 | 5900 | N/A | 5850 | 5850 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-010-00 | Office Supplies Expenses | 14FPAO | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-25 | 2023-04-26 | 2023-05-08 | 2023-05-11 | 2023-05-11 | GoP | 84525 | 84525 | N/A | 84441 | 84441 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-990-00 | Other Supplies and Materials Expenses | 14FPAO | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-25 | 2023-04-26 | 2023-05-08 | 2023-05-11 | 2023-05-11 | GoP | 27500 | 27500 | N/A | 27200 | 27200 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-080-00 | Medical and Dental Laboratory Supplies Expenses | ESC | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-25 | 2023-04-26 | 2023-05-15 | 2023-05-18 | 2023-05-18 | GoP | 33451.5 | 33451.5 | N/A | 33391.5 | 33391.5 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-05-020-01 | Mobile Expenses | ESC | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-25 | 2023-04-26 | 2023-05-15 | 2023-05-18 | 2023-05-18 | GoP | 9000 | 9000 | N/A | 8955 | 8955 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-070-00 | Drugs and Medicines Expenses | 564ECB | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-25 | 2023-04-26 | 2023-05-15 | 2023-05-22 | 2023-05-22 | GoP | 3000 | 3000 | N/A | 2960 | 2960 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-210-07 | Semi Expendable Communication Equipment | 564ECB | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-25 | 2023-04-26 | 2023-05-15 | 2023-05-23 | 2023-05-23 | GoP | 15000 | 15000 | N/A | 14975 | 14975 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-13-060-01 | Repair and Maintenance of Motor Vehicle | 564ECB | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-25 | 2023-04-26 | 2023-05-15 | 2023-05-22 | 2023-05-22 | GoP | 48500 | 48500 | N/A | 48300 | 48300 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-99-030-00 | Representation Expenses | 564ECB | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-25 | 2023-04-26 | 2023-05-15 | 2023-05-23 | 2023-05-23 | GoP | 58750 | 58750 | N/A | 58575 | 58575 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-02-010-00 | Training Expenses | 564ECB | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-25 | 2023-04-26 | 2023-05-15 | 2023-05-23 | 2023-05-23 | GoP | 56000 | 56000 | N/A | 55846 | 55846 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-080-00 | Medical and Dental Laboratory Supplies Expenses | 564ECB | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-25 | 2023-04-26 | 2023-05-15 | 2023-05-22 | 2023-05-22 | GoP | 8000 | 8000 | N/A | 7960 | 7960 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-010-00 | Office Supplies Expenses | 564ECB | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-25 | 2023-04-26 | 2023-05-15 | 2023-05-19 | 2023-05-19 | GoP | 41500 | 41500 | N/A | 41226 | 41226 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-210-08 | Semi-Expendable Disaster Response and Rescue Equipment | 564ECB | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-25 | 2023-04-26 | 2023-05-17 | 2023-05-22 | 2023-05-22 | GoP | 31000 | 31000 | N/A | 29500 | 29500 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-13-040-99 | Repair and Maintenance of Other Structure | 564ECB | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-25 | 2023-04-26 | 2023-05-15 | 2023-05-23 | 2023-05-23 | GoP | 69740 | 69740 | N/A | 69440 | 69440 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-990-00 | Other Supplies and Materials Expenses | 564ECB | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-25 | 2023-04-26 | 2023-05-15 | 2023-05-19 | 2023-05-19 | GoP | 18240 | 18240 | N/A | 18163 | 18163 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-99-030-00 | Representation Expenses | 564ECB | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-25 | 2023-04-26 | 2023-05-15 | 2023-05-19 | 2023-05-19 | GoP | 27950 | 27950 | N/A | 27845 | 27845 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-080-00 | Medical and Dental Laboratory Supplies Expenses | 564ECB | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-25 | 2023-04-26 | 2023-05-15 | 2023-05-22 | 2023-05-22 | GoP | 42600 | 42600 | N/A | 42530 | 42530 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-010-00 | Office Supplies Expenses | 564ECB | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-25 | 2023-04-26 | 2023-05-15 | 2023-05-22 | 2023-05-22 | GoP | 6910 | 6910 | N/A | 6859 | 6859 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-05-020-01 | Mobile Expenses | 564ECB | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-25 | 2023-04-26 | 2023-05-15 | 2023-05-22 | 2023-05-22 | GoP | 10800 | 10800 | N/A | 10731 | 10731 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-02-010-00 | Training Expenses | 14FPAO | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-25 | 2023-04-26 | 2023-05-15 | 2023-05-22 | 2023-05-22 | GoP | 18000 | 18000 | N/A | 17880 | 17880 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-13-060-01 | Repair and Maintenance of Motor Vehicle | 14FPAO | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-25 | 2023-04-26 | 2023-05-15 | 2023-05-22 | 2023-05-22 | GoP | 101268 | 101268 | N/A | 100618 | 100618 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-13-050-02 | Repair and Maintenance of Office Equipment | 14FPAO | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-25 | 2023-04-26 | 2023-05-15 | 2023-05-22 | 2023-05-22 | GoP | 13505 | 13505 | N/A | 13472 | 13472 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-990-00 | Other Supplies and Materials Expenses | RDC, ASCOM, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-25 | 2023-04-26 | 2023-05-15 | 2023-05-16 | 2023-05-16 | GoP | 50000 | 50000 | N/A | 49925 | 49925 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-99-030-00 | Representation Expenses | 564ECB | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-25 | 2023-04-26 | 2023-05-22 | 2023-05-29 | 2023-05-29 | GoP | 39000 | 39000 | N/A | 38837.5 | 38837.5 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-05-020-01 | Mobile Expenses | ESC, 51Ebde, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-25 | 2023-04-26 | 2023-05-15 | 2023-05-18 | 2023-05-18 | GoP | 11500 | 11500 | N/A | 11155 | 11155 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-02-010-00 | Training Expenses | ESC, 51Ebde, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-25 | 2023-04-26 | 2023-05-15 | 2023-05-18 | 2023-05-18 | GoP | 64204.8 | 64204.8 | N/A | 63853 | 63853 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-010-00 | Office Supplies Expenses | ESC, 51Ebde, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-25 | 2023-04-26 | 2023-05-15 | 2023-05-18 | 2023-05-18 | GoP | 10000 | 10000 | N/A | 9960 | 9960 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-210-99 | Semi-Expendable Other Machinery and Equipment | RDC, ASCOM, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-02 | 2023-04-26 | 2023-05-15 |  | 2023-05-18 | GoP | 168650 | 168650 | N/A | 165475 | 165475 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-080-00 | Medical and Dental Laboratory Supplies Expenses | RDC, ASCOM, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-02 | 2023-05-03 | 2023-05-15 | 2023-05-16 | 2023-05-16 | GoP | 30000 | 30000 | N/A | 29700 | 29700 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-05-020-01 | Mobile Expenses | 514ECB | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-02 | 2023-05-03 | 2023-05-15 | 2023-05-18 | 2023-05-18 | GoP | 39000 | 39000 | N/A | 38550 | 38550 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-99-030-00 | Representation Expenses | 514ECB | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-02 | 2023-05-03 | 2023-05-15 | 2023-05-18 | 2023-05-18 | GoP | 24900 | 24900 | N/A | 24661 | 24661 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-080-00 | Medical and Dental Laboratory Supplies Expenses | 514ECB | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-02 | 2023-05-03 | 2023-05-15 | 2023-05-22 | 2023-05-22 | GoP | 42600 | 42600 | N/A | 42300 | 42300 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-13-060-01 | Repair and Maintenance of Motor Vehicle | 514ECB | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-02 | 2023-05-03 | 2023-05-15 | 2023-05-18 | 2023-05-18 | GoP | 47400 | 47400 | N/A | 47253 | 47253 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-13-050-03 | Repair and Maintenance ICT Equipment | 514ECB | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-02 | 2023-05-03 | 2023-05-15 | 2023-05-18 | 2023-05-18 | GoP | 19500 | 19500 | N/A | 19460 | 19460 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-99-030-00 | Representation Expenses | 514ECB | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-02 | 2023-05-03 | 2023-05-15 | 2023-05-23 | 2023-05-23 | GoP | 168145 | 168145 | N/A | 167505 | 167505 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-010-00 | Office Supplies Expenses | 514ECB | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-02 | 2023-05-03 | 2023-05-15 | 2023-05-18 | 2023-05-18 | GoP | 44805 | 44805 | N/A | 44754 | 44754 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-05-020-01 | Mobile Expenses | 514ECB | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-02 | 2023-05-03 | 2023-05-15 | 2023-05-18 | 2023-05-18 | GoP | 12600 | 12600 | N/A | 12546 | 12546 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-080-00 | Medical and Dental Laboratory Supplies Expenses | 514ECB | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-02 | 2023-05-03 | 2023-05-15 | 2023-05-18 | 2023-05-18 | GoP | 2500 | 2500 | N/A | 2475 | 2475 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-13-040-01 | Repair and Maintenance of Building | 514ECB | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-02 | 2023-05-03 | 2023-05-15 | 2023-05-23 | 2023-05-23 | GoP | 282430 | 282430 | N/A | 281977 | 281977 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-13-040-01 | Repair and Maintenance of Building | 548ECB | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-02 | 2023-05-03 | 2023-05-08 | 2023-05-23 | 2023-05-23 | GoP | 100000 | 100000 | N/A | 99606 | 99606 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-13-060-01 | Repair and Maintenance of Motor Vehicle | 548ECB | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-02 | 2023-05-03 | 2023-05-08 | 2023-05-10 | 2023-05-10 | GoP | 45700 | 45700 | N/A | 45500 | 45500 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-99-030-00 | Representation Expenses | ESC, 51Ebde, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-02 | 2023-05-03 | 2023-05-15 | 2023-05-08 | 2023-05-08 | GoP | 175400 | 175400 | N/A | 175320.1 | 175320.1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-13-050-03 | ICT Office Supplies Expenses | 514ECB | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-02 | 2023-05-03 | 2023-05-15 | 2023-05-18 | 2023-05-18 | GoP | 8000 | 8000 | N/A | 7960 | 7960 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-990-00 | Other Supplies and Materials Expenses | 514ECB | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-02 | 2023-05-03 | 2023-05-15 | 2023-05-23 | 2023-05-23 | GoP | 50000 | 50000 | N/A | 49410 | 49410 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-02-010-00 | Training Expenses | 514ECB | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-02 | 2023-05-03 | 2023-05-15 | 2023-05-23 | 2023-05-23 | GoP | 72500 | 72500 | N/A | 72150 | 72150 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-13-060-01 | Repair and Maintenance of Motor Vehicle | 14FSFO | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-02 | 2023-05-03 | 2023-05-16 | 2023-05-23 | 2023-05-23 | GoP | 61000 | 61000 | N/A | 60800 | 60800 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-99-030-00 | Representation Expenses | 14FSFO | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-02 | 2023-05-03 | 2023-05-18 | 2023-05-25 | 2023-05-25 | GoP | 27998.9 | 27998.9 | N/A | 27748 | 27748 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-010-00 | Office Supplies Expenses | 14FSFO | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-02 | 2023-05-03 | 2023-05-16 | 2023-05-22 | 2023-05-22 | GoP | 57014.48 | 57014.48 | N/A | 56866 | 56866 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-02-010-00 | Training Expenses | 14FSFO | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-02 | 2023-05-03 | 2023-05-16 | 2023-05-22 | 2023-05-22 | GoP | 42000 | 42000 | N/A | 41871.5 | 41871.5 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-990-00 | Other Supplies and Materials Expenses | 14FSFO | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-02 | 2023-05-03 | 2023-05-18 | 2023-05-25 | 2023-05-25 | GoP | 40000 | 40000 | N/A | 39800 | 39800 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-13-040-99 | Repair and Maintenance of Other Structure | 564ECB | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-02 | 2023-05-03 | 2023-05-23 | 2023-05-25 | 2023-05-25 | GoP | 7135 | 7135 | N/A | 7104 | 7104 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-05-020-01 | Mobile Expenses | 14FSFO | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-02 | 2023-05-03 | 2023-05-18 | 2023-05-25 | 2023-05-25 | GoP | 21000 | 21000 | N/A | 20974 | 20974 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-010-00 | Office Supplies Expenses | 14FSFO | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-02 | 2023-05-03 | 2023-05-16 | 2023-05-23 | 2023-05-23 | GoP | 7000 | 7000 | N/A | 6960 | 6960 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-99-030-00 | Representation Expenses | 14FSFO | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-02 | 2023-05-03 | 2023-05-16 | 2023-05-23 | 2023-05-23 | GoP | 16200 | 16200 | N/A | 16130 | 16130 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-99-030-00 | Representation Expenses | 14FSFO | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-02 | 2023-05-03 | 2023-05-16 | 2023-05-23 | 2023-05-23 | GoP | 19000 | 19000 | N/A | 18949 | 18949 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-13-040-01 | Repair and Maintenance of Building | 564ECB | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-09 | 2023-05-03 | 2023-05-22 | 2023-05-25 | 2023-05-25 | GoP | 229190 | 229190 | N/A | 228790 | 228790 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-02-010-00 | Training Expenses | 14FAU | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-09 | 2023-05-10 | 2023-05-22 | 2023-05-26 | 2023-05-26 | GoP | 62120 | 62120 | N/A | 61823 | 61823 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-13-070-00 | Semi-Expendable Furniture and Fixture | 14FSFO | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-09 | 2023-05-10 | 2023-05-16 | 2023-05-22 | 2023-05-22 | GoP | 10000 | 10000 | N/A | 9999 | 9999 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-13-040-01 | Repair and Maintenance of Building | 14FAU | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-09 | 2023-05-10 | 2023-05-16 | 2023-05-18 | 2023-05-18 | GoP | 111800 | 111800 | N/A | 111700 | 111700 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-210-03 | Sem-Expendable ICT Equipment Expenses | RDC, ASCOM, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-09 | 2023-05-10 | 2023-05-23 | 2023-05-26 | 2023-05-26 | GoP | 20000 | 20000 | N/A | 19950 | 19950 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-13-050-03 | Repair and Maintenance ICT Equipment | 525ECB | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-09 | 2023-05-10 | 2023-05-23 | 2023-05-29 | 2023-05-29 | GoP | 6900 | 6900 | N/A | 6860 | 6860 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-210-03 | Sem-Expendable ICT Equipment Expenses | 525ECB | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-09 | 2023-05-10 | 2023-05-18 | 2023-05-24 | 2023-05-24 | GoP | 10530 | 10530 | N/A | 10480 | 10480 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-990-00 | Other Supplies and Materials Expenses | 525ECB | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-09 | 2023-05-10 | 2023-05-23 | 2023-05-29 | 2023-05-29 | GoP | 57560 | 57560 | N/A | 57240 | 57240 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-13-050-03 | Repair and Maintenance ICT Equipment | 525ECB | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-09 | 2023-05-10 | 2023-05-18 | 2023-05-24 | 2023-05-24 | GoP | 24850 | 24850 | N/A | 24730 | 24730 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
NEGOTIATED (OTHER SOURCE OF FUND CY 2023)
5-02-03-010-00 | Office Supplies Expenses | RDC, ASCOM, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-09 | 2023-05-10 | 2023-05-30 | 2023-06-05 | 2023-06-05 | GoP | 126983 | 126983 | N/A | 126856 | 126856 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing
5-02-03-990-00 | Other Supplies and Materials Expenses | 51EBde, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-09 | 2023-05-10 | 2023-05-24 | 2023-05-30 | 2023-05-30 | GoP | 300000 | 300000 | N/A | 299685 | 299685 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing
5-02-03-990-00 | Other Supplies and Materials Expenses | 51EBde, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-09 | 2023-05-10 | 2023-05-30 | 2023-06-05 | 2023-06-05 | GoP | 250900 | 250900 | N/A | 250124 | 250124 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing
5-02-13-040-01 | Repair and Maintenance of Building | 564ECB | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-09 | 2023-05-10 | 2023-05-29 | 2023-06-04 | 2023-06-04 | GoP | 132909 | 132909 | N/A | 132889 | 132889 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing
5-02-03-990-00 | Other Supplies and Materials Expenses | 525ECB | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-09 | 2023-05-10 | 2023-05-26 | 2023-06-01 | 2023-06-01 | GoP | 150000 | 150000 | N/A | 149990 | 149990 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing
5-02-13-040-01 | Repair and Maintenance of Building | 514ECB | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-09 | 2023-05-10 | 2023-05-31 | 2023-06-06 | 2023-06-06 | GoP | 317250 | 317250 | N/A | 316612 | 316612 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing
5-02-03-990-00 | Other Supplies and Materials Expenses | 514ECB | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-16 | 2023-05-10 | 2023-05-31 | 2023-06-06 | 2023-06-06 | GoP | 10000 | 10000 | N/A | 9832 | 9832 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing
5-02-03-210-03 | Sem-Expendable ICT Equipment Expenses | 51EBde, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-16 | 2023-05-17 | 2023-05-29 | 2023-06-04 | 2023-06-04 | GoP | 149371 | 149371 | N/A | 149364 | 149364 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing
5-02-13-040-01 | Repair and Maintenance of Building | 564ECB | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-16 | 2023-05-17 | 2023-05-30 | 2023-06-05 | 2023-06-05 | GoP | 150000 | 150000 | N/A | 149440 | 149440 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing
5-02-13-040-01 | Repair and Maintenance of Building | 548ECB | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-16 | 2023-05-17 | 2023-05-31 | 2023-06-06 | 2023-06-06 | GoP | 753152.35 | 753152.35 | N/A | 752552 | 752552 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing
5-02-13-040-01 | Repair and Maintenance of Building | 548ECB | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-16 | 2023-05-17 | 2023-05-28 | 2023-06-03 | 2023-06-03 | GoP | 22594.57 | 22594.57 | N/A | 22391 | 22391 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing
5-02-13-040-01 | Repair and Maintenance of Building | 565ECB | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-16 | 2023-05-17 | 2023-06-01 | 2023-06-07 | 2023-06-07 | GoP | 854060 | 854060 | N/A | 853390 | 853390 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing
5-02-13-040-01 | Repair and Maintenance of Building | 565ECB | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-16 | 2023-05-17 | 2023-06-01 | 2023-06-07 | 2023-06-07 | GoP | 753945 | 753945 | N/A | 753230 | 753230 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing
5-02-03-990-00 | Other Supplies and Materials Expenses | 14FPAO | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-16 | 2023-05-17 | 2023-06-06 | 2023-06-12 | 2023-06-12 | GoP | 100000 | 100000 | N/A | 99550 | 99550 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing
5-02-13-040-01 | Repair and Maintenance of Building | 514ECB | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-16 | 2023-05-17 |  |  |  | GoP | 854060 | 854060 | N/A | 852860 | 852860 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing
5-02-03-210-03 | Sem-Expendable ICT Equipment Expenses | 51EBde, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-23 | 2023-05-24 |  |  |  | GoP | 99185 | 99185 | N/A | 96658.5 | 96658.5 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing
5-02-03-990-00 | Other Supplies and Materials Expenses | 51EBde, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-23 | 2023-05-24 |  |  |  | GoP | 26375 | 26375 | N/A | 26250 | 26250 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing
5-02-05-020-01 | Mobile Expenses | 51EBde, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-23 | 2023-05-24 |  |  |  | GoP | 11000 | 11000 | N/A | 10825 | 10825 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing
5-02-99-030-00 | Representation Expenses | 51EBde, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-23 | 2023-05-24 |  |  |  | GoP | 43000 | 43000 | N/A | 42640 | 42640 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing
5-02-03-080-00 | Medical and Dental Laboratory Supplies Expenses | 51EBde, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-23 | 2023-05-24 |  |  |  | GoP | 36000 | 36000 | N/A | 35853 | 35853 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing
5-02-13-040-01 | Repair and Maintenance of Building | ESC, 51EBde, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-23 | 2023-05-24 |  |  |  | GoP | 125000 | 125000 | N/A | 124792 | 124792 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing
5-02-13-040-01 | Repair and Maintenance of Building | 522ECB | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-23 | 2023-05-24 | 2023-06-13 | 2023-06-19 | 2023-06-19 | GoP | 854060 | 854060 | N/A | 853160 | 853160 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing
5-02-13-040-01 | Repair and Maintenance of Building | 513ECB | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-23 | 2023-05-24 |  |  |  | GoP | 49074.9 | 49074.9 | N/A | 48766 | 48766 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing
5-02-13-040-01 | Repair and Maintenance of Building | 513ECB | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-23 | 2023-05-24 |  |  |  | GoP | 429840.76 | 429840.76 | N/A | 429415 | 429415 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing
5-02-13-050-02 | Repair and Maintenance of Office Equipment | 14FSFO | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-23 | 2023-05-24 |  |  |  | GoP | 8800 | 8800 | N/A | 8740 | 8740 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing
5-02-02-010-00 | Training Expenses | 51EBde, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-23 | 2023-05-24 | 2023-06-20 |  |  | GoP | 170550 | 170550 | N/A | 170207 | 170207 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing
5-02-13-050-08 | Repair and Maintenance of Construction of Heavy Equipment | 51EBde, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-23 | 2023-05-24 | 2023-06-20 |  |  | GoP | 24150 | 24150 | N/A | 24077 | 24077 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing
5-02-13-050-08 | Repair and Maintenance of Construction of Heavy Equipment | 51EBde, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-23 | 2023-05-24 | 2023-06-20 |  |  | GoP | 9280 | 9280 | N/A | 9252 | 9252 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing
5-02-13-050-08 | Repair and Maintenance of Construction of Heavy Equipment | 51EBde, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-23 | 2023-05-24 | 2023-06-20 |  |  | GoP | 10170 | 10170 | N/A | 10138 | 10138 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing
5-02-99-030-00 | Representation Expenses | 51EBde, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-30 | 2023-05-24 | 2023-06-20 |  |  | GoP | 25000 | 25000 | N/A | 24686 | 24686 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing
5-02-13-040-01 | Repair and Maintenance of Building | ESC, 51EBde, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-30 | 2023-05-31 |  |  |  | GoP | 54185 | 54185 | N/A |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing
5-02-03-990-00 | Other Supplies and Materials Expenses | RDC, ASCOM, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-30 | 2023-05-31 |  |  |  | GoP | 40000 | 40000 | N/A |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing
5-02-03-990-00 | Other Supplies and Materials Expenses | 525ECB-02-2023-044 | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [5 empty] | GoP | 10000 | 10000 | N/A |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing
NEGOTIATED (MOOE CY 2023)
5-02-05-020-01 | Mobile Expenses | RDC, ASCOM, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-06 | 2023-06-07 | 2023-03-01 | 2023-03-07 | 2023-03-07 | GoP | 12500 | 12500 | N/A | 12430 | 12430 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing
5-02-03-210-03 | Sem-Expendable ICT Equipment Expenses | RDC, ASCOM, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-06 | 2023-06-07 | 2023-03-02 | 2023-03-09 | 2023-03-09 | GoP | 12200 | 12200 | N/A | 11955 | 11955 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing
5-02-03-210-03 | Sem-Expendable ICT Equipment Expenses | RDC, ASCOM, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-06 | 2023-06-07 | 2023-03-01 | 2023-03-07 | 2023-03-07 | GoP | 8000 | 8000 | N/A | 7950 | 7950 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing
5-02-03-210-02 | Semi-Expendable Office Equipment | RDC, ASCOM, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-06 | 2023-06-07 | 2023-03-02 | 2023-03-08 | 2023-03-08 | GoP | 20000 | 20000 | N/A | 19600 | 19600 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing
5-02-03-210-99 | Semi-Expendable Other Machinery and Equipment | RDC, ASCOM, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-06 | 2023-06-07 | 2023-03-02 | 2023-03-08 | 2023-03-08 | GoP | 8700 | 8700 | N/A | 8200 | 8200 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing
5-02-03-220-01 | Semi-Expendable Furniture and Fixture | RDC, ASCOM, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-06 | 2023-06-07 | 2023-02-27 | 2023-03-05 | 2023-03-05 | GoP | 10000 | 10000 | N/A | 9950 | 9950 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing
5-02-99-030-00 | Representation Expenses | 525ECB | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-06 | 2023-06-07 | 2023-03-14 | 2023-03-20 | 2023-03-20 | GoP | 50000 | 50000 | N/A | 49765 | 49765 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing
5-02-02-010-00 | Training Expenses | RDC, ASCOM, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-06 | 2023-06-07 | 2023-05-15 | 2023-05-21 | 2023-05-21 | GoP | 50000 | 50000 | N/A | 49960 | 49960 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing
5-02-99-030-00 | Representation Expenses | 14FPAO | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-06 | 2023-06-07 | 2023-05-15 | 2023-05-21 | 2023-05-21 | GoP | 19000 | 19000 | N/A | 18940 | 18940 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing
5-02-99-020-00 | Printing and Pubrication Expenses | 51EBde, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-06 | 2023-06-07 | 2023-05-29 | 2023-06-04 | 2023-06-04 | GoP | 144500 | 144500 | N/A | 144425.75 | 144425.75 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing
5-02-99-030-00 | Representation Expenses | 14FSFO | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-06 | 2023-06-07 | 2023-05-17 | 2023-05-23 | 2023-05-23 | GoP | 30000 | 30000 | N/A | 29920 | 29920 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing
5-02-99-030-00 | Representation Expenses | RDC, ASCOM, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-13 | 2023-06-07 | 2023-05-30 | 2023-06-05 | 2023-06-05 | GoP | 115462 | 115462 | N/A | 115356 | 115356 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing
5-02-13-050-03 | ICT Office Supplies Expenses | RDC, ASCOM, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-13 | 2023-06-14 | 2023-05-30 | 2023-06-05 | 2023-06-05 | GoP | 7000 | 7000 | N/A | 6990 | 6990 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing
5-02-99-030-00 | Representation Expenses | RDC, ASCOM, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-13 | 2023-06-14 | 2023-06-13 | 2023-06-19 | 2023-06-19 | GoP | 88050 | 88050 | N/A | 87698 | 87698 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing
5-02-03-210-09 | Semi-Expendable Military, Police and Security Equipment | 564ECB | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-13 | 2023-06-14 | 2023-05-24 | 2023-05-30 | 2023-05-30 | GoP | 20000 | 20000 | N/A | 19950 | 19950 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing
5-02-03-210-01 | Semi Expendable Machinery | 548ECB | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-13 | 2023-06-14 | 2023-05-24 | 2023-05-30 | 2023-05-30 | GoP | 14400 | 14400 | N/A | 14350 | 14350 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing
5-02-03-210-08 | Semi-Expendable Disaster Response and Rescue Equipment | 548ECB | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-13 | 2023-06-14 | 2023-05-26 | 2023-06-01 | 2023-06-01 | GoP | 100000 | 100000 | N/A | 90000 | 90000 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing
5-02-99-030-00 | Representation Expenses | 14FSFO | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-13 | 2023-06-14 | 2023-05-17 | 2023-05-23 | 2023-05-23 | GoP | 15000 | 15000 | N/A | 14960 | 14960 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing
5-02-03-130-00 | Chemical and Filtering Supplies Expenses | RDC, ASCOM, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-13 | 2023-06-14 | 2023-05-30 | 2023-06-05 | 2023-06-05 | GoP | 20000 | 20000 | N/A | 19800 | 19800 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing
5-02-03-210-02 | Semi-Expendable Office Equipment | RDC, ASCOM, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-13 | 2023-06-14 | 2023-05-30 | 2023-06-05 | 2023-06-05 | GoP | 29800 | 29800 | N/A | 28000 | 28000 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing
5-02-13-050-03 | ICT Office Supplies Expenses | 14FPAO | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-13 | 2023-06-14 | 2023-05-24 | 2023-05-30 | 2023-05-30 | GoP | 16641.66 | 16641.66 | N/A | 16579 | 16579 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing
5-02-99-030-00 | Representation Expenses | 14FPAO | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-13 | 2023-06-14 | 2023-05-24 | 2023-05-30 | 2023-05-30 | GoP | 36814.67 | 36814.67 | N/A | 36742 | 36742 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing
5-02-13-050-03 | ICT Office Supplies Expenses | 14FPAO | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-13 | 2023-06-14 | 2023-05-24 | 2023-05-30 | 2023-05-30 | GoP | 39677 | 39677 | N/A | 39617 | 39617 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing
5-02-03-210-08 | Semi-Expendable Disaster Response and Rescue Equipment | 525ECB | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-13 | 2023-06-14 | 2023-05-26 | 2023-06-01 | 2023-06-01 | GoP | 40000 | 40000 | N/A | 39980 | 39980 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing
5-02-99-030-00 | Representation Expenses | 525ECB | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-13 | 2023-06-14 |  |  |  | GoP | 36000 | 36000 | N/A | 35500 | 35500 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing
5-02-99-030-00 | Representation Expenses | 525ECB | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-13 | 2023-06-14 |  |  |  | GoP | 20000 | 20000 | N/A | 19500 | 19500 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing
5-02-02-010-00 | Training Expenses | 525ECB | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-13 | 2023-06-14 | 2023-05-26 | 2023-06-01 | 2023-06-01 | GoP | 98600 | 98600 | N/A | 98580 | 98580 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing
5-02-02-010-00 | Training Expenses | 525ECB | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-13 | 2023-06-14 |  |  |  | GoP | 10400 | 10400 | N/A | 10200 | 10200 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing
5-02-99-030-00 | Representation Expenses | 51EBde, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-13 | 2023-06-14 | 2023-05-30 | 2023-06-05 | 2023-06-05 | GoP | 40190 | 40190 | N/A | 40120 | 40120 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing
5-02-03-210-03 | Sem-Expendable ICT Equipment Expenses | RDC, ASCOM, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-13 | 2023-06-14 | 2023-05-26 | 2023-06-01 | 2023-06-01 | GoP | 42000 | 42000 | N/A | 41997 | 41997 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing
5-02-13-060-01 | Repair and Maintenance of Motor Vehicle | RDC, ASCOM, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-13 | 2023-06-14 | 2023-05-30 | 2023-06-05 | 2023-06-05 | GoP | 112000 | 112000 | N/A | 111972 | 111972 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing
5-02-03-210-03 | Sem-Expendable ICT Equipment Expenses | 564ECB | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-13 | 2023-06-14 | 2023-05-26 | 2023-06-01 | 2023-06-01 | GoP | 10000 | 10000 | N/A | 9999 | 9999 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing
5-02-13-040-01 | Repair and Maintenance of Building | 564ECB | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-13 | 2023-06-14 | 2023-05-20 | 2023-05-26 | 2023-05-26 | GoP | 250000 | 250000 | N/A | 249586 | 249586 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing
5-02-03-990-00 | Other Supplies and Materials Expenses | 548ECB | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-13 | 2023-06-14 | 2023-05-29 | 2023-06-04 | 2023-06-04 | GoP | 10000 | 10000 | N/A | 9980 | 9980 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing
5-02-13-050-03 | Repair and Maintenance of ICT Equipment | 548ECB | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-13 | 2023-06-14 | 2023-05-29 | 2023-06-04 | 2023-06-04 | GoP | 78935 | 78935 | N/A | 78915 | 78915 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing
5-02-13-050-03 | Repair and Maintenance of ICT Equipment | RDC, ASCOM, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-13 | 2023-06-14 |  |  |  | GoP | 20000 | 20000 | N/A | 19970 | 19970 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing
5-02-13-050-03 | Repair and Maintenance of ICT Equipment | ESC, 51Ebde, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-13 | 2023-06-14 | 2023-06-03 | 2023-06-09 | 2023-06-09 | GoP | 5200 | 5200 | N/A | 5184 | 5184 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing
5-02-13-050-03 | ICT Software Subscription | ESC, 51Ebde, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-13 | 2023-06-14 | 2023-05-29 | 2023-06-04 | 2023-06-04 | GoP | 2500 | 2500 | N/A | 2492 | 2492 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing
5-02-13-050-03 | Repair and Maintenance of ICT Equipment | 548ECB | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-15 | 2023-06-16 | 2023-05-31 | 2023-06-06 | 2023-06-06 | GoP | 40500 | 40500 | N/A | 40372 | 40372 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing
5-02-02-010-00 | ICT Training Expenses | 51EBde, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-15 | 2023-06-16 | 2023-05-31 | 2023-06-06 | 2023-06-06 | GoP | 52630 | 52630 | N/A | 52483 | 52483 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing
5-02-13-050-03 | Repair and Maintenance of ICT Equipment | 51EBde, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-15 | 2023-06-16 |  |  |  | GoP | 21000 | 21000 | N/A | 20937 | 20937 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing
5-02-02-010-00 | Training Expenses | RDC, ASCOM, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-15 | 2023-06-16 | 2023-06-13 | 2023-06-19 | 2023-06-19 | GoP | 2760 | 2760 | N/A | 2706 | 2706 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing
5-02-03-210-03 | Sem-Expendable ICT Equipment Expenses | ESC, 51Ebde, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-15 | 2023-06-16 |  |  |  | GoP | 2500 | 2500 | N/A | 2492 | 2492 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing
5-02-13-050-08 | Repair and Maintenance of Construction of Heavy Equipment | 525ECB | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-15 | 2023-06-16 |  |  |  | GoP | 210256 | 210256 | N/A | 210244 | 210244 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing
5-02-99-030-00 | Representation Expenses | 525ECB | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-15 | 2023-06-16 |  |  |  | GoP | 112080 | 112080 | N/A | 111816 | 111816 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing
5-02-13-040-01 | Repair and Maintenance of Building | ESC, 51EBde, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-15 | 2023-06-16 |  |  |  | GoP | 54185 | 54185 | N/A | 53926.5 | 53926.5 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing
5-02-03-990-00 | Other Supplies and Materials Expenses | RDC, ASCOM, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-15 | 2023-06-16 |  |  |  | GoP | 40000 | 40000 | N/A | 39934 | 39934 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing
Total Alloted Budget of On-going Procurement Activities | [18 empty] | 24201747.85 |  |  |  | 24201747.85
| Prepared by: | [11 empty] | Checked by: | [9 empty] | Submitted by:
| DARREN R RINGKA | [11 empty] | ABDULHAN O SABDANI JR | [9 empty] | ANTONIO C ROTA JR
| LTC GSC (CE) PA | [11 empty] | MAJ (CE) PA | [9 empty] | Brigadier General PA
| AC of S for Logistics, G4 | [11 empty] | AAC of S for Financial Mngt, G10 | [9 empty] | Commander

## Sheet1 (hidden)
Competitive Bidding | GoP | YES
Limited Source Bidding | Foreign | NO
Direct Contracting | Special Purpose Fund
Repeat Order | Corporate Budget
Shopping | Income
NP-53.1 Two Failed Biddings | Others
NP-53.2 Emergency Cases
NP-53.3 Take-Over of Contracts
NP-53.4 Adjacent or Contiguous
NP-53.5 Agency-to-Agency
NP-53.6 Scientific, Scholarly, Artistic Work, Exclusive Technology and Media Services
NP-53.7 Highly Technical Consultants
NP-53.8 Defense Cooperation Agreement
NP-53.9 - Small Value Procurement
NP-53.10 Lease of Real Property and Venue
NP-53.11 NGO Participation
NP-53.12 Community Participation
NP-53.13 UN Agencies, Int'l Organizations or International Financing Institutions
Others - Foreign-funded procurement