## AAR
H E A D Q U A R T E R S
ARMY ARTILLERY REGIMENT, PHILIPPINE ARMY
Fort Magsaysay, 3130 Nueva Ecija
PROJECT MONITORING REPORT
01 January to 30 June 2023
Code (PAP) | Procurement Project | PMO/ End-User | Mode of Procurement | Schedule for Each Procurement Activity | [11 empty] | Source of Funds | ABC (PhP) |  |  | Remarks (brief description of Program/Project) | PMO/ End-User | Is this an Early Procurement Activity? | Mode of Procurement | Actual Procurement Activity | [12 empty] | Source of Funds | ABC (PhP) |  |  | Contract Cost (PhP) |  |  | List of Invited Observers | Date of Receipt of Invitation | [5 empty] | Remarks (Explaining changes from the APP)
|  |  |  | Pre-Proc Conference | Ads/Post of IAEB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Contract Award | Contract Signing | Notice to Proceed | Delivery/ Accept | Payment Process |  | Total | MOOE | CO |  |  |  |  | Pre-Proc Conference | Ads/Post of IB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Date of BAC Resolution Recommending Award | Notice of Award | Contract Signing | Notice to Proceed | Delivery/ Completion | Inspection & Acceptance |  | Total | MOOE | CO | Total | MOOE | CO |  | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Delivery/ Completion/ Acceptance (If applicable)
COMPLETED PROCUREMENT ACTIVITIES
5-02-03-210-99 | Semi-Exp Other Machinery Equipment | HAAR | Neg 53.9 | [17 empty] | HAAR |  | MOOE | [8 empty] | 2023-02-06 | N/A | 2023-02-17 | 2023-02-22 | 2023-02-22 | MOOE | 110000 | 110000 |  | 109650 | 109650
5-02-03-210-12 | Semi-Exp Sport Equipment | HAAR | Neg 53.9 | [17 empty] | HAAR |  | MOOE | [8 empty] | 2023-02-06 | N/A | 2023-02-17 | 2023-02-22 | 2023-02-22 | MOOE | 10000 | 10000 |  | 9920 | 9920
5-02-13-060-01 | R&M of Motor Veh | HAAR | Neg 53.9 | [17 empty] | HAAR |  | MOOE | [8 empty] | 2023-02-06 | N/A | 2023-02-17 | 2023-02-22 | 2023-02-22 | MOOE | 365000 | 365000 |  | 364590 | 364590
5-02-13-210-99 | R&M of Other Machinery and Equipment | HAAR | Neg 53.9 | [17 empty] | HAAR |  | MOOE | [8 empty] | 2023-02-06 | N/A | 2023-02-17 | 2023-02-22 | 2023-02-22 | MOOE | 152500 | 152500 |  | 152100 | 152100
5-02-13-050-10 | R&M of MP and SE | HAAR | Neg 53.9 | [17 empty] | HAAR |  | MOOE | [8 empty] | 2023-02-06 | N/A | 2023-02-17 | 2023-02-22 | 2023-02-22 | MOOE | 80000 | 80000 |  | 79700 | 79700
5-02-03-210-00 | Semi Exp Office Equipment (2MLRS) | HAAR | Neg 53.9 | [17 empty] | HAAR |  | MOOE | [8 empty] | 2023-02-06 | N/A | 2023-02-17 | 2023-02-22 | 2023-02-22 | MOOE | 37500 | 37500 |  | 37320 | 37320
5-02-13-040-01 | R&M of Building | HAAR | Neg 53.9 | [17 empty] | HAAR |  | MOOE | [8 empty] | 2023-03-10 | N/A | 2023-03-23 | 2023-03-29 | 2023-03-29 | MOOE | 490000 | 490000 |  | 489550 | 489550
5-02-13-050-10 | R&M of MP and SE | HAAR | Neg 53.9 | [17 empty] | HAAR |  | MOOE | [8 empty] | 2023-03-10 | N/A | 2023-03-23 | 2023-03-29 | 2023-03-29 | MOOE | 80000 | 80000 |  | 79550 | 79550
5-02-03-220-01 | Semi-Exp F&F | HAAR | Neg 53.9 | [17 empty] | HAAR |  | MOOE | [8 empty] | 2023-03-10 | N/A | 2023-03-23 | 2023-03-29 | 2023-03-29 | MOOE | 40000 | 40000 |  | 39680 | 39680
5-02-13-060-01 | R&M of Vehicle | HAAR | Neg 53.9 | [17 empty] | HAAR |  | MOOE | [8 empty] | 2023-03-10 | N/A | 2023-03-23 | 2023-03-29 | 2023-03-29 | MOOE | 351000 | 351000 |  | 350480 | 350480
5-02-03-990-00 | Other Supplies and Materials Exps | HAAR | Neg 53.9 | [17 empty] | HAAR |  | MOOE | [8 empty] | 2023-03-10 | N/A | 2023-03-23 | 2023-03-29 | 2023-03-29 | MOOE | 373213 | 373213 |  | 373000 | 373000
5-02-13-050-99 | R&M of Other Machinery and Equipment | HAAR | Neg 53.9 | [17 empty] | HAAR |  | MOOE | [8 empty] | 2023-03-10 | N/A | 2023-03-23 | 2023-03-29 | 2023-03-29 | MOOE | 152500 | 152500 |  | 152000 | 152000
5-02-03-080-00 | Medical Dental and Lab Exps | HAAR | Neg 53.9 | [17 empty] | HAAR |  | MOOE | [8 empty] | 2023-03-10 | N/A | 2023-03-23 | 2023-03-29 | 2023-03-29 | MOOE | 97000 | 97000 |  | 96650 | 96650
5-02-03-210-99 | Semi-Exp Other machinery | HAAR | Neg 53.9 | [17 empty] | HAAR |  | MOOE | [8 empty] | 2023-03-10 | N/A | 2023-03-23 | 2023-03-29 | 2023-03-29 | MOOE | 85000 | 85000 |  | 84400 | 84400
5-02-03-210-03 | Semi-Exp ICT Equipment | HAAR | Neg 53.9 | [17 empty] | HAAR |  | MOOE | [8 empty] | 2023-03-10 | N/A | 2023-03-23 | 2023-03-29 | 2023-03-29 | MOOE | 31490 | 31490 |  | 31000 | 31000
5-02-03-210-12 | Semi-Exp Sport Equipt | HAAR | Neg 53.9 | [17 empty] | HAAR |  | MOOE | [8 empty] | 2023-03-10 | N/A | 2023-03-23 | 2023-03-29 | 2023-03-29 | MOOE | 10000 | 10000 |  | 9680 | 9680
5-02-99-030-00 | Representation Exps | HAAR | Neg 53.9 | [17 empty] | HAAR |  | MOOE | [8 empty] | 2023-03-10 | N/A | 2023-03-23 | 2023-03-29 | 2023-03-29 | MOOE | 282150 | 282150 |  | 281550 | 281550
5-02-99-030-00 | Representation Exps | HAAR | Neg 53.9 | [17 empty] | HAAR |  | MOOE | [8 empty] | 2023-03-10 | N/A | 2023-03-23 | 2023-03-29 | 2023-03-29 | MOOE | 743500 | 743500 |  | 743000 | 743000
5-02-13-040-99 | R&M of Other Structure | HAAR | Neg 53.9 | [17 empty] | HAAR |  | MOOE | [8 empty] | 2023-03-10 | N/A | 2023-03-23 | 2023-03-29 | 2023-03-29 | MOOE | 20000 | 20000 |  | 19720 | 19720
5-02-03-990-00 | Other Supplies and Mat Exps (2ADA ) | ADA Battery | Neg 53.9 | [17 empty] | ADA Battery | [10 empty] | 2023-03-22 | N/A | 2023-04-14 | 2023-04-20 | 2023-04-20 | MOOE | 22500 | 22500 |  | 22180 | 22180
5-02-13-040-01 | R&M of Building(1ADA&2ADA) | ADA Battery | Neg 53.9 | [17 empty] | ADA Battery | [10 empty] | 2023-03-22 | N/A | 2023-04-14 | 2023-04-20 | 2023-04-20 | MOOE | 187700 | 187700 |  | 186000 | 186000
5-02-03-070-00 | Drugs and Med 1&2 MLRS | MLRS Battery | Neg 53.9 | [17 empty] | MLRS Battery | [10 empty] | 2023-03-22 | N/A | 2023-04-14 | 2023-04-20 | 2023-04-20 | MOOE | 30000 | 30000 |  | 29680 | 29680
5-02-03-990-00 | Other Supplies and Materials Exps 1&2 MLRS | MLRS Battery | Neg 53.9 | [17 empty] | MLRS Battery | [10 empty] | 2023-03-22 | N/A | 2023-04-14 | 2023-04-20 | 2023-04-20 | MOOE | 45000 | 45000 |  | 44420 | 44420
5-02-99-030-00 | Representation Exps (LBMS) | LBMS Battery | Neg 53.9 | [17 empty] | LBMS Battery | [10 empty] | 2023-03-22 | N/A | 2023-04-14 | 2023-04-20 | 2023-04-20 | MOOE | 22840 | 22840 |  | 22640 | 22640
5-02-03-070-00 | Drugs and Medicine(1&2MLRS,LBMS) | MLRS Battery | Neg 53.9 | [17 empty] | MLRS Battery | [10 empty] | 2023-03-22 | N/A | 2023-04-14 | 2023-04-20 | 2023-04-20 | MOOE | 45000 | 45000 |  | 44820 | 44820
5-02-03-080-00 | Medical,Dental & Lab Exps(1ADA,SALBAT&HAAR) | Line Batteries | Neg 53.9 | [17 empty] | Line Batteries | [10 empty] | 2023-03-22 | N/A | 2023-04-14 | 2023-04-20 | 2023-04-20 | MOOE | 112000 | 112000 |  | 111660 | 111660
5-02-03-990-00 | Other Supplies and Materials Exps (1&2ADA,1&2MLRS,LBMS and SALBAT)) | Line Batteries | Neg 53.9 | [17 empty] | Line Batteries | [10 empty] | 2023-03-22 | N/A | 2023-04-14 | 2023-04-20 | 2023-04-20 | MOOE | 112500 | 112500 |  | 112150 | 112150
5-02-03-990-00 | Other Supplies and Materials Exps (1MLRS) | MLRS Battery | Neg 53.9 | [17 empty] | MLRS Battery | [10 empty] | 2023-03-22 | N/A | 2023-04-14 | 2023-04-20 | 2023-04-20 | MOOE | 75000 | 75000 |  | 74680 | 74680
5-02-02-010-02 | Training Expense (1MLRS) | MLRS Battery | Neg 53.9 | [17 empty] | MLRS Battery | [10 empty] | 2023-03-22 | N/A | 2023-04-14 | 2023-04-20 | 2023-04-20 | MOOE | 22000 | 22000 |  | 21717 | 21717
5-02-99-030-00 | Representation Exps (LBMS) | LBMS Battery | Neg 53.9 | [17 empty] | LBMS Battery | [10 empty] | 2023-03-22 | N/A | 2023-04-14 | 2023-04-20 | 2023-04-20 | MOOE | 24840 | 24840 |  | 24766 | 24766
5-02-13-040-99 | R&M of Other Structure (2MLRS) | MLRS Battery | Neg 53.9 | [17 empty] | MLRS Battery | [10 empty] | 2023-03-22 | N/A | 2023-04-14 | 2023-04-20 | 2023-04-20 | MOOE | 11000 | 11000 |  | 10805 | 10805
5-02-03-210-00 | Semi-Expendable Office Equipment (2MLRS) | MLRS Battery | Neg 53.9 | [17 empty] | MLRS Battery | [10 empty] | 2023-03-22 | N/A | 2023-04-14 | 2023-04-20 | 2023-04-20 | MOOE | 37500 | 37500 |  | 37250 | 37250
5-02-03-080-00 | Medical, Dental & Lab Exps- MOOE | HAAR | Neg 53.9 | [17 empty] | HAAR | [10 empty] | 2023-04-13 | N/A | 2023-05-13 | 2023-06-05 | 2023-06-05 | MOOE | 15000 | 15000 |  | 14745 | 14745
5-02-03-080-00 | Medical, Dental & Lab Exps- OSS | HAAR | Neg 53.9 | [17 empty] | HAAR | [10 empty] | 2023-04-13 | N/A | 2023-05-13 | 2023-06-05 | 2023-06-05 | MOOE | 82000 | 82000 |  | 81590 | 81590
Total Alloted Budget of Procurement Activities | [37 empty] | 4355733
Total Contract Price of Procurement Actitvites Conducted | [40 empty] | 4342643 | [10 empty] | 6128503.31
Total Savings (Total Alloted Budget - Total Contract Price) | [37 empty] | 13090
0N-GOING PROCUREMENT ACTIVITIES
5-02-03-080-00 | Medical Dental and Lab Exps | [37 empty] | 12000
5-02-02-010-02 | Training Expense | [36 empty] | 36000 | 36000
5-02-03-210-03 | Semi EX ICT Equipment | [36 empty] | 74920 | 74920
5-02-03-210-12 | Semi-EX Sport Equipment | [36 empty] | 10000 | 10000
5-02-03-210-99 | Semi-EX Other Machinery Equipment | [36 empty] | 110000 | 110000
5-02-03-990-00 | Other Supplies and Materials Exps | [36 empty] | 274763 | 274763
5-02-13-040-01 | R&M of Building | [36 empty] | 570000 | 570000
5-02-13-050-10 | R&M of Military police and Security Equipment | [36 empty] | 100000 | 100000
5-02-13-050-99 | R&M of Other Machinery and Equipment | [36 empty] | 152500 | 152500
5-02-13-060-01 | R&M of Motor Vehicle | [36 empty] | 361000 | 361000
5-02-13-220-01 | R&M of Semi-EX F&F | [36 empty] | 40000 | 40000
5-02-99-030-00 | Representation Exps | [36 empty] | 534580 | 534580
5-02-03-210-00 | Semi-EX Office Equipment | [36 empty] | 15000 | 15000
5-02-03-080-00 | Medical, Dental Lab Supplies | [36 empty] | 82000 | 82000
5-02-03-990-00 | Other Supplies and Materials Exps | [36 empty] | 400000 | 400000
5-02-03-010-02 | Office Supplies Exps | [36 empty] | 200000 | 200000
5-02-03-210-03 | Semi-EX ICT Equipment | [36 empty] | 145525 | 145525
5-02-03-010-01 | ICT-Office Supplies | [36 empty] | 53934 | 53934
5-02-03-010-02 | Office Supplies Exps | [36 empty] | 371620 | 371620
Total Alloted Budget of On-going Procurement Activities | [37 empty] | 3543842
| Prepared By: | [37 empty] | NOTED BY:
| AVELINO H CADALIG JR | [37 empty] | FRANCIS ANTHONY M CORONEL
| Major (ART) PA | [37 empty] | Brigadier General PA
| OIC, OG4 | [37 empty] | Commander
Prepared by:
Edwin P Pagunsan
Ssg (MI) PA
Operations NCO