## OG1, PA
|  | ANNEX A | [18 empty] | ANNEX B
|  | Department of Budget and Management Annual Procurement Plan for FY 2006 | [18 empty] | OG1, PA -PROJECT MONITORING REPORT 01 JAN-30 JUNE 2023 - Big Tickets
Code (PAP) | Procurement Project | PMO/ End-User | Mode of Procurement | Schedule for Each Procurement Activity | [11 empty] | Source of Funds | ABC (PhP) |  |  | Remarks (brief description of Program/Project) | PMO/ End-User | Is this an Early Procurement Activity? | Mode of Procurement | Actual Procurement Activity | [12 empty] | Source of Funds | ABC (PhP) |  |  | Contract Cost (PhP) |  |  | List of Invited Observers | Date of Receipt of Invitation | [5 empty] | Remarks (Explaining changes from the APP)
|  |  |  | Pre-Proc Conference | Ads/Post of IAEB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Contract Award | Contract Signing | Notice to Proceed | Delivery/ Accept | Payment Process |  | Total | MOOE | CO |  |  |  |  | Pre-Proc Conference | Ads/Post of IB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Date of BAC Resolution Recommending Award | Notice of Award | Contract Signing | Notice to Proceed | Delivery/ Completion | Inspection & Acceptance |  | Total | PS | CO | Total | PS | CO |  | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Delivery/ Completion/ Acceptance (If applicable)
COMPLETED PROCUREMENT ACTIVITIES
5-01-02-040-05 | Pershing Cap for O4/O5/O6 | [17 empty] | 4400000 |  | PA-WIDE | YES | PUBLIC BIDDING | [8 empty] | 2023-01-19 |  | 2023-02-15 | 2023-05-05 | 2023-05-29 | PS |  | 4400000 |  |  | 3816000
5-01-02-040-05 | Belt Waist, Garterized, OD | [17 empty] | 2138400 |  | PA-WIDE | YES | PUBLIC BIDDING | [8 empty] | 2023-02-15 |  | 2023-03-13 | 2023-05-05 | 2023-05-29 | PS |  | 2138400 |  |  | 2122480
Total Alloted Budget of Procurement Activities | [37 empty] | 6538400
Total Contract Price of Procurement Actitvites Conducted | [40 empty] | 5938480
Total Savings (Total Alloted Budget - Total Contract Price) | [37 empty] | 599920
0N-GOING PROCUREMENT ACTIVITIES
5-01-02-040-05 | Bar Mosquito Polyester Warp Knit | [17 empty] | 2277000 |  | PA-WIDE | YES | PUBLIC BIDDING | [8 empty] | 2023-01-19 |  | 2023-02-24 | 2023-04-14 |  | PS |  | 2277000 |  |  | 2277000
5-01-02-040-05 | Cloth for GOU | [17 empty] | 2772000 |  | PA-WIDE | YES | PUBLIC BIDDING | [8 empty] | 2023-01-19 |  | 2023-03-28 | 2023-05-25 |  | PS |  | 2772000 |  |  | 2752200
5-01-02-040-05 | Blanket, OD | [17 empty] | 3322000 |  | PA-WIDE | YES | PUBLIC BIDDING | [8 empty] | 2023-01-19 |  | 2023-02-16 | 2023-04-14 |  | PS |  | 3322000 |  |  | 3322000
5-01-02-040-05 | Hydration Pack, #L Capacity, PHILARPAT | [17 empty] | 20310400 |  | PA-WIDE | YES | PUBLIC BIDDING | [8 empty] | 2023-01-19 |  | 2023-03-09 | 2023-06-05 |  | PS |  | 20310400 |  |  | 20285012
5-01-02-040-05 | Mat, Canvass, Polyester, OD | [17 empty] | 3289000 |  | PA-WIDE | YES | PUBLIC BIDDING | [8 empty] | 2023-01-19 |  | 2023-02-15 | 2023-06-29 |  | PS |  | 3289000 |  |  | 1740640
5-01-02-040-05 | Mattress Cover, Fitted,OD | [17 empty] | 2037000 |  | PA-WIDE | YES | PUBLIC BIDDING | [8 empty] | 2023-01-19 |  | 2023-02-16 | 2023-05-25 |  | PS |  | 2037000 |  |  | 2031180
5-01-02-040-05 | Plastic Mess, Gear | [17 empty] | 3989480 |  | PA-WIDE | YES | PUBLIC BIDDING | [8 empty] | 2023-01-19 |  | 2023-03-13 | 2023-06-05 |  | PS |  | 3989480 |  |  | 2992110
5-01-02-040-05 | Socks for Boots Black | [17 empty] | 3016000 |  | PA-WIDE | YES | PUBLIC BIDDING | [8 empty] | 2023-01-19 |  | 2023-03-13 | 2023-04-20 |  | PS |  | 3016000 |  |  | 2895360
5-01-02-040-05 | Shoes Dress, Low Cut, Rubber Sole | [17 empty] | 12384500 |  | PA-WIDE | YES | PUBLIC BIDDING | [8 empty] | 2023-01-19 |  | 2023-03-09 | 2023-06-09 |  | PS |  | 12384500 |  |  | 12384500
5-01-02-040-05 | Short, Cycling (Compression) Black | [17 empty] | 6820000 |  | PA-WIDE | YES | PUBLIC BIDDING | [8 empty] | 2023-01-19 |  | 2023-04-04 | 2023-05-23 |  | PS |  | 6820000 |  |  | 6792720
5-01-02-040-05 | Towel Bath and Face (Microfiber), OD | [17 empty] | 3168000 |  | PA-WIDE | YES | PUBLIC BIDDING | [8 empty] | 2023-01-19 |  | 2023-02-16 | 2023-05-15 |  | PS |  | 3168000 |  |  | 3157440
5-01-02-040-05 | Undershirt Raglan, Polyester, Spandex Round Neck | [17 empty] | 18700000 |  | PA-WIDE | YES | PUBLIC BIDDING | [8 empty] | 2023-01-19 |  | 2023-03-18 | 2023-06-01 |  | PS |  | 18700000 |  |  | 18606500
5-01-02-040-05 | PHILARPAT, BDU with Ball Cap | [17 empty] | 56977050 |  | PA-WIDE | YES | PUBLIC BIDDING | [8 empty] | 2023-01-19 |  | 2023-03-29 |  |  | PS |  | 56977050 |  |  | 41510916
5-01-02-040-05 | Poncho Tent PHILARPAT | [17 empty] | 12789700 |  | PA-WIDE | YES | PUBLIC BIDDING | [8 empty] | 2023-01-19 |  | 2023-03-13 |  |  | PS |  | 12789700 |  |  | 12789700
5-01-02-040-05 | Socks, Athletic, Gray | [17 empty] | 3015700 |  | PA-WIDE | YES | PUBLIC BIDDING | [8 empty] | 2023-01-19 |  | 2023-03-13 |  |  | PS |  | 3015700 |  |  | 2322089
5-01-02-040-05 | Army Combat Boots Suede, Field Use | [17 empty] | 61079200 |  | PA-WIDE | YES | PUBLIC BIDDING | [8 empty] | 2023-01-19 |  | 2023-03-09 |  |  | PS |  | 61079200 |  |  | 60904688
5-01-02-040-05 | Backpack Tactical MOLLE PHILARPAT | [17 empty] | 36185000 |  | PA-WIDE | YES | PUBLIC BIDDING | [8 empty] | 2023-01-23 |  | 2023-05-25 |  |  | PS |  | 36185000 |  |  | 36170526
5-01-02-040-05 | Buckle, Alluminum, Belt, Waist | [17 empty] | 2030000 |  | PA-WIDE | YES | PUBLIC BIDDING | [8 empty] | 2023-02-16 |  | 2023-03-20 |  |  | PS |  | 2030000 |  |  | 2021880
5-01-02-040-05 | Belt, Waist for BDU with Buckle | [17 empty] | 6040000 |  | PA-WIDE | YES | PUBLIC BIDDING | [8 empty] | 2023-01-19 |  | 2023-02-28 |  |  | PS |  | 6040000 |  |  | 6015840
5-01-02-040-05 | Combat Chest Rig. PHILARPAT for M16/M14 | [17 empty] | 21622400 |  | PA-WIDE | YES | PUBLIC BIDDING | [8 empty] | 2023-01-19 |  | 2023-03-09 |  |  | PS |  | 21622400 |  |  | 21554830
5-01-02-040-05 | Philippine Army Athletic Shoes, Black | [17 empty] | 60463500 |  | PA-WIDE | YES | PUBLIC BIDDING | [8 empty] | 2023-06-19 |  |  |  |  | PS |  | 60463500 |  |  | 60088000
5-01-02-040-05 | PA Ballistic Helmet | [17 empty] | 20000000 |  | PA-WIDE | YES | PUBLIC BIDDING | [8 empty] | 2023-01-19 |  | 2023-04-18 |  |  | PS |  | 20000000 |  |  | 19642400
Total Alloted Budget of On-going Procurement Activities | [37 empty] | 362287930
12384500
|  | 6792720 | [18 empty] | Prepared by: | [10 empty] | Recommended for Approval by: | [10 empty] | APPROVED:
3157440
18606500
[21 empty] | Ronnalyn L Razon | [10 empty] | ROGELIO S VELANO | [10 empty] | Head of the Procuring Entity
[21 empty] | SSg (MS) PA | [10 empty] | MAJ (FS) PA
[21 empty] | ICIE NCO, PBB, OG1, PA | [10 empty] | Chief, PBB, OG1, PA