## PMR-4th QTR
|  | ANNEX A | [18 empty] | ANNEX B
|  | Department of Budget and Management Annual Procurement Plan for FY 2006 | [18 empty] | 6ID, PA-PROJECT MONITORING REPORT from 01 October 2022 to 31 December 2022
Code (PAP) | Procurement Project | PMO/ End-User | Mode of Procurement | Schedule for Each Procurement Activity | [11 empty] | Source of Funds | ABC (PhP) |  |  | Remarks (brief description of Program/Project) | PMO/ End-User | Is this an Early Procurement Activity? | Mode of Procurement | Actual Procurement Activity | [12 empty] | Source of Funds | ABC (PhP) |  |  | Contract Cost (PhP) |  |  | List of Invited Observers | Date of Receipt of Invitation | [5 empty] | Remarks (Explaining changes from the APP)
|  |  |  | Pre-Proc Conference | Ads/Post of IAEB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Contract Award | Contract Signing | Notice to Proceed | Delivery/ Accept | Payment Process |  | Total | MOOE | CO |  |  |  |  | Pre-Proc Conference | Ads/Post of IB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Date of BAC Resolution Recommending Award | Notice of Award | Contract Signing | Notice to Proceed | Delivery/ Completion | Inspection & Acceptance |  | Total | MOOE | CO | Total | MOOE | CO |  | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Delivery/ Completion/ Acceptance (If applicable)
COMPLETED PROCUREMENT ACTIVITIES
1 | 3 ea Microsoft Office & 1 L/I | [17 empty] | 10000 |  | SSBN, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2002-07-13 | 2002-07-13 | 2022-09-29 | 2022-09-30 | 2022-09-30 | GAA | 10000 | MOOE |  | 9950 | MOOE
2 | 6 Can Fruit Cocktail & 12 L/I | [17 empty] | 10000 |  | 6DENTAL, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-08-01 | 2022-08-01 | 2022-09-29 | 2022-09-30 | 2022-09-30 | GAA | 10000 | MOOE |  | 9880 | MOOE
3 | 1 Pc Halogen Bulb & 8 L/I | [17 empty] | 10000 |  | 6DENTAL, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-08-01 | 2022-08-01 | 2022-09-29 | 2022-09-30 | 2022-09-30 | GAA | 10000 | MOOE |  | 9892 | MOOE
4 | 3 pcs keyboard & 1 L/I | [17 empty] | 5000 |  | 6DENTAL, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-08-01 | 2022-08-01 | 2022-09-29 | 2022-09-30 | 2022-09-30 | GAA | 5000 | MOOE |  | 4910 | MOOE
5 | 8 Gal Flat Latex White & 15 L/I | [17 empty] | 33901.25 |  | 6DENTAL, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-08-02 | 2022-08-02 | 2022-09-29 | 2022-09-30 | 2022-09-30 | GAA | 33901.25 | MOOE |  | 33821.25 | MOOE
6 | 9 Gal Latex Paint White & 10 L/I | [17 empty] | 25000 |  | 6DENTAL, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-08-01 | 2022-08-01 | 2022-09-29 | 2022-09-30 | 2022-09-30 | GAA | 25000 | MOOE |  | 24910 | MOOE
7 | 2 pcs Motherboard ATX, MSI H510m Pro- E Socket & 9 L/I | [17 empty] | 100000 |  | 5SFBN, SFRAA, SOCOM, PA |  | Negotiated 53.9 | [8 empty] | 2022-08-05 | 2022-08-05 | 2022-09-29 | 2022-09-30 | 2022-09-30 | GAA | 100000 | SPCL REL |  | 99000 | SPCL REL
8 | 1 Pc Brake Master w/ Hyrovac Assy & 48 L/I | [17 empty] | 105290 |  | SSBN, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-08-15 | 2022-08-15 | 2022-09-29 | 2022-09-30 | 2022-09-30 | GAA | 105290 | SPCL REL |  | 104390 | SPCL REL
9 | 10 pcs Globe Prepaid Card 500 & 4 L/I | [17 empty] | 25000 |  | 6IMB,IMCOM, PA |  | Negotiated 53.9 | [8 empty] | 2022-08-22 | 2022-08-22 | 2022-09-29 | 2022-09-30 | 2022-09-30 | GAA | 25000 | MOOE |  | 24592 | MOOE
10 | 85 pcs White Board Marker & 22 L/I | [17 empty] | 100000 |  | 6IMB,IMCOM, PA |  | Negotiated 53.9 | [8 empty] | 2022-08-26 | 2022-08-26 | 2022-09-29 | 2022-09-30 | 2022-09-30 | GAA | 100000 | SPCL REL |  | 99000 | SPCL REL
11 | 4 gal. Paint Olive Green & 12 L/I | [17 empty] | 55000 |  | 6IMB,IMCOM, PA |  | Negotiated 53.9 | [8 empty] | 2022-08-26 | 2022-08-26 | 2022-09-29 | 2022-09-30 | 2022-09-30 | GAA | 55000 | SPCL REL |  | 54820 | SPCL REL
12 | 120 can Juice in Can & 11 L/I | [17 empty] | 30000 |  | 6IMB,IMCOM, PA |  | Negotiated 53.9 | [8 empty] | 2022-08-23 | 2022-08-23 | 2022-09-29 | 2022-09-30 | 2022-09-30 | GAA | 30000 | MOOE |  | 29860 | MOOE
13 | 50 mtrs TW Gree Wire 30m & 7 L/I | [17 empty] | 200000 |  | 1MECH BDE, ARMOR DIV, PA |  | Negotiated 53.9 | [8 empty] | 2022-08-25 | 2022-08-25 | 2022-09-29 | 2022-09-30 | 2022-09-30 | GAA | 200000 | SPCL REL |  | 198000 | SPCL REL
14 | 10 pcs Polytupf & 10 L/I | [17 empty] | 50000 |  | 12ISU, AIR, PA |  | Negotiated 53.9 | [8 empty] | 2022-08-05 | 2022-08-05 | 2022-09-22 | 2022-09-23 | 2022-09-23 | GAA | 50000 | MOOE |  | 49500 | MOOE
15 | 1 Unit Software System | [17 empty] | 5000 |  | 12ISU, AIR, PA |  | Negotiated 53.9 | [8 empty] | 2022-08-30 | 2022-08-30 | 2022-08-22 | 2022-09-23 | 2022-09-23 | GAA | 5000 | MOOE |  | 4900 | MOOE
16 | 2 Pcs Satellite Phone | [17 empty] | 25000 |  | 12ISU, AIR, PA |  | Negotiated 53.9 | [8 empty] | 2022-08-30 | 2022-08-30 | 2022-09-30 | 2022-09-30 | 2022-09-30 | GAA | 25000 | MOOE |  | 24800 | MOOE
17 | 3 box Rapid Antigen kits Nasal & 1 L/I | [17 empty] | 51300 |  | 6MIB ,6ID ,PA |  | Negotiated 53.9 | [8 empty] | 2022-08-05 | 2022-08-05 | 2022-09-29 | 2022-09-30 | 2022-09-30 | GAA | 51300 | MOOE |  | 51000 | MOOE
18 | 30 bags Cement & 18 L/I | [17 empty] | 61950 |  | 6MIB ,6ID ,PA |  | Negotiated 53.9 | [8 empty] | 2022-08-05 | 2022-08-05 | 2022-09-30 | 2022-09-30 | 2022-09-30 | GAA | 61950 | MOOE |  | 61050 | MOOE
19 | 16 rms Bond Paper A4 & 17 L/I | [17 empty] | 60000 |  | 6MIB ,6ID ,PA |  | Negotiated 53.9 | [8 empty] | 2022-08-05 | 2022-08-05 | 2022-09-30 | 2022-09-30 | 2022-09-30 | GAA | 60000 | MOOE |  | 59700 | MOOE
20 | 21 pack Great Taste Coffee (Twen pack ) & 6 L/I | [17 empty] | 23400 |  | 34IB, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-08-05 | 2022-08-05 | 2022-09-30 | 2022-09-30 | 2022-09-30 | GAA | 23400 | MOOE |  | 23345 | MOOE
21 | 1 pc Hard Disk Drive & 3 L/I | [17 empty] | 10000 |  | 34IB, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-01 | 2022-09-01 | 2022-11-15 | 2022-11-16 | 2022-11-16 | GAA | 10000 | MOOE |  | 9900 | MOOE
22 | 1 pc Flight Controller 4 in 1 ESC & 5 L/I | [17 empty] | 15000 |  | 34IB, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-01 | 2022-09-01 | 2022-11-15 | 2022-11-16 | 2022-11-16 | GAA | 15000 | MOOE |  | 14880 | MOOE
23 | 100 pcs Folder Brown (Long) & 3 L/I | [17 empty] | 5000 |  | 34IB, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-01 | 2022-09-01 | 2022-10-27 | 2022-10-28 | 2022-10-28 | GAA | 5000 | MOOE |  | 4940 | MOOE
24 | 65 reams Bond Paper A4 & 9 L/I | [17 empty] | 45000 |  | 34IB, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-01 | 2022-09-01 | 2022-09-30 | 2022-10-03 | 2022-10-03 | GAA | 45000 | MOOE |  | 45340 | MOOE
25 | 25 Bags Cement & 6 L/I | [17 empty] | 39000 |  | 34IB, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-01 | 2022-09-01 | 2022-09-29 | 2022-09-30 | 2022-09-30 | GAA | 39000 | MOOE |  | 38850 | MOOE
26 | 1 pc Washing Machine Timer & 3 L/I | [17 empty] | 8500 |  | 34IB, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-01 | 2022-09-01 | 2022-09-29 | 2022-09-30 | 2022-09-30 | GAA | 8500 | MOOE |  | 8400 | MOOE
27 | 150 pcs Brown Envelop Short & 17 L/I | [17 empty] | 103387.5 |  | 38IB, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-01 | 2022-09-01 | 2022-09-29 | 2022-09-30 | 2022-09-30 | GAA | 103387.5 | MOOE |  | 102597 | MOOE
28 | 30 pcs G.I Sheet & 8 L/I | [17 empty] | 50000 |  | 38IB, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-01 | 2022-09-01 | 2022-10-10 | 2022-10-11 | 2022-10-11 | GAA | 50000 | MOOE |  | 49700 | MOOE
29 | 20 Pack Sliced Bread & 8 L/I | [17 empty] | 7500 |  | 38IB, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-01 | 2022-09-01 | 2022-09-29 | 2022-09-30 | 2022-09-30 | GAA | 7500 | MOOE |  | 7440 | MOOE
30 | 2 set USB Speakers & 6 L/I | [17 empty] | 20000 |  | 6IB, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-01 | 2022-09-01 | 2022-09-29 | 2022-09-30 | 2022-09-30 | GAA | 20000 | MOOE |  | 19880 | MOOE
31 | 5 Pcs Cignal Prepaid Card Load 1000 & 1 L/I | [17 empty] | 5400 |  | 6IB, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-01 | 2022-09-01 | 2022-09-29 | 2022-09-30 | 2022-09-30 | GAA | 5400 | MOOE |  | 5350 | MOOE
32 | 250 pcs Fig 14 Target Paper & 10 L/I | [17 empty] | 60000 |  | 6IB, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-05 | 2022-09-05 | 2022-09-29 | 2022-09-30 | 2022-09-30 | GAA | 60000 | MOOE |  | 59535 | MOOE
33 | 30 reams Bond Paper A4 and 12 L/I | [17 empty] | 27500 |  | SSBN, 6ID, PA |  | Shopping | [8 empty] | 2022-09-01 | 2022-09-01 | 2022-10-10 | 2022-10-11 | 2022-10-11 | GAA | 27500 | MOOE |  | 27350 | MOOE
34 | 50 Bottle Water 500ml & 10 L/I | [17 empty] | 20000 |  | SSBN, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-01 | 2022-09-01 | 2022-11-15 | 2022-10-11 | 2022-10-11 | GAA | 20000 | MOOE |  | 19700 | MOOE
35 | 1 Pc Brake Master w/ Hyrovac Assy & 48 L/I | [17 empty] | 89274 |  | SSBN, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-06 | 2022-09-06 | 2022-09-29 | 2022-09-30 | 2022-09-30 | GAA | 89274 | SPCL REL |  | 88474 | SPCL REL
36 | 625 bottle Water & 15 L/I | [17 empty] | 179900 |  | SSBN, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-06 | 2022-09-06 | 2022-09-30 | 2022-10-03 | 2022-10-03 | GAA | 179900 | MOOE |  | 177890 | MOOE
37 | 10 rms Bond Paper A4 & 7 L/I | [17 empty] | 15000 |  | 90IB, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-06 | 2022-09-06 | 2022-11-22 | 2022-11-23 | 2022-11-23 | GAA | 15000 | MOOE |  | 14935 | MOOE
38 | 20 Pcs Smart Prepaid Card & 3 L/I | [17 empty] | 45000 |  | 90IB, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-06 | 2022-09-06 | 2022-09-30 | 2022-10-03 | 2022-10-03 | GAA | 45000 | MOOE |  | 44580 | MOOE
39 | 3 pcs Hard Disk 1TB & 8 L/I | [17 empty] | 25000 |  | 90IB, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-06 | 2022-09-06 | 2022-09-30 | 2022-10-03 | 2022-10-03 | GAA | 25000 | MOOE |  | 24700 | MOOE
40 | 50 pcs Lumber (2x2x10) & 11 L/I | [17 empty] | 25400 |  | 90IB, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-06 | 2022-09-06 | 2022-09-29 | 2022-09-30 | 2022-09-30 | GAA | 25400 | MOOE |  | 24875 | MOOE
41 | 12 kls Nail, Common #2 & 6 L/I | [17 empty] | 20000 |  | 5SFBN, SFRAA, SOCOM, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-07 | 2022-09-07 | 2022-10-07 | 2022-10-08 | 2022-10-08 | GAA | 20000 | MOOE |  | 19760 | MOOE
42 | 6 pcs Cable TV Prepaid Card (Cignal ) & 2 L/I | [17 empty] | 16800 |  | 5SFBN, SFRAA, SOCOM, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-07 | 2022-09-07 | 2022-09-29 | 2022-09-30 | 2022-09-30 | GAA | 16800 | MOOE |  | 16530 | MOOE
43 | 4 Pcs Bosh Iridium Spark plug TMX & 52 L/I | [17 empty] | 111380 |  | 5SFBN, SFRAA, SOCOM, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-07 | 2022-09-07 | 2022-09-29 | 2022-09-30 | 2022-09-30 | GAA | 111380 | MOOE |  | 110625 | MOOE
44 | 1200 bottle Energy Drink & 12 L/I | [17 empty] | 232700 |  | 5SFBN, SFRAA, SOCOM, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-07 | 2022-09-07 | 2022-09-29 | 2022-09-30 | 2022-09-30 | GAA | 232700 | MOOE |  | 231856 | MOOE
45 | 24 pcs Internet Card, Prepaid (Globe) 500 & 1 L/I | [17 empty] | 45000 |  | 5SFBN, SFRAA, SOCOM, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-07 | 2022-09-07 | 2022-09-30 | 2022-10-03 | 2022-10-03 | GAA | 45000 | MOOE |  | 44550 | MOOE
46 | 50 Bags Cement & 11 L/I | [17 empty] | 182046 |  | 603RD BDE, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-07 | 2022-09-07 | 2022-09-30 | 2022-10-03 | 2022-10-03 | GAA | 182046 | MOOE |  | 181296 | MOOE
47 | 2 Pcs Video Card & 4 L/I | [17 empty] | 22800 |  | 603RD BDE, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-08 | 2022-09-08 | 2022-09-30 | 2022-10-03 | 2022-10-03 | GAA | 22800 | MOOE |  | 22700 | MOOE
48 | 4 Pcs Cignal Card & 1 L/I | [17 empty] | 5400 |  | 603RD BDE, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-07 | 2022-09-07 | 2022-10-10 | 2022-10-11 | 2022-10-11 | GAA | 5400 | MOOE |  | 5300 | MOOE
49 | 5 pcs Clutch Lining Disc (M35) & 37 L/I | [17 empty] | 141988.5 |  | 603RD BDE, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-07 | 2022-09-07 | 2022-10-10 | 2022-10-11 | 2022-10-11 | GAA | 141988.5 | MOOE |  | 140988.5 | MOOE
50 | 1 pc Cooper Tube & 4 L/I | [17 empty] | 11511.5 |  | 603RD BDE, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-08 | 2022-09-08 | 2022-10-13 | 2022-10-14 | 2022-10-14 | GAA | 11511.5 | MOOE |  | 11411 | MOOE
51 | 35 Rms Paper ,Multi-purpose 70 GSM,& 130 L/I | [17 empty] | 62510 |  | 603RD BDE, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-07 | 2022-09-07 | 2022-10-27 | 2022-10-28 | 2022-10-28 | GAA | 62510 | MOOE |  | 62445 | MOOE
52 | 4 pcs Forcep Mosquito Stright & 15 L/I | [17 empty] | 30000 |  | SSBN, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-08 | 2022-09-08 | 2022-11-15 | 2022-11-16 | 2022-11-16 | GAA | 30000 | MOOE |  | 29750 | MOOE
53 | 15 pcs Grease Gun & 6 L/I | [17 empty] | 100000 |  | 6FAB, AAR, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-08 | 2022-09-08 | 2022-10-17 | 2022-10-18 | 2022-10-18 | GAA | 100000 | MOOE |  | 99300 | MOOE
54 | 4 pcs Fuel Filter & 17 L/I | [17 empty] | 90000 |  | 6FAB, AAR, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-08 | 2022-09-08 | 2022-10-17 | 2022-10-18 | 2022-10-18 | GAA | 90000 | MOOE |  | 89300 | MOOE
55 | 1 Pc Memory Card RAM 8GB & 6 L/I | [17 empty] | 30000 |  | 6FAB, AAR, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-08 | 2022-09-08 | 2022-10-10 | 2022-10-11 | 2022-10-11 | GAA | 30000 | MOOE |  | 29850 | MOOE
56 | 54 Bags Cement & 16 L/I | [17 empty] | 93850 |  | 40IB, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-08 | 2022-09-08 | 2022-10-10 | 2022-10-11 | 2022-10-11 | GAA | 93850 | MOOE |  | 93150 | MOOE
57 | 18 Rms Bond Paper A4 & 4 L/I | [17 empty] | 5000 |  | 40IB, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-09 | 2022-09-09 | 2022-10-27 | 2022-10-28 | 2022-10-28 | GAA | 5000 | MOOE |  | 4950 | MOOE
58 | 4 Ctns Lucky Me Noodles & 4 L/I | [17 empty] | 21000 |  | 40IB, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-09 | 2022-09-09 | 2022-10-13 | 2022-10-14 | 2022-10-14 | GAA | 21000 | MOOE |  | 20895 | MOOE
59 | 4 set Overhauling Gasket Assy & 47 L/I | [17 empty] | 500000 |  | 12FSSU, ASCOM, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-09 | 2022-09-09 | 2022-10-25 | 2022-10-26 | 2022-10-26 | GAA | 500000 | SPCL REL |  | 495500 | SPCL REL
60 | 12 Set W80 Dual Band Water Resistant Two Way Radio & 1 L/I | [17 empty] | 60000 |  | 33IB, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-09 | 2022-09-09 | 2022-10-25 | 2022-10-27 | 2022-10-27 | GAA | 60000 | MOOE |  | 59460 | MOOE
61 | 1 Unit Alternator 15KVA | [17 empty] | 30000 |  | 33IB, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-09 | 2022-09-09 | 2022-09-29 | 2022-09-30 | 2022-09-30 | GAA | 30000 | MOOE |  | 29800 | MOOE
62 | 18 ctns Calamansi Juice & 5 L/I | [17 empty] | 56000 |  | 33IB, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-09 | 2022-09-09 | 2022-09-29 | 2022-09-30 | 2022-09-30 | GAA | 56000 | MOOE |  | 55400 | MOOE
63 | 25 Bags Cement & 9 L/I | [17 empty] | 50000 |  | 33IB, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-09 | 2022-09-09 | 2022-09-29 | 2022-09-30 | 2022-09-30 | GAA | 50000 | MOOE |  | 49550 | MOOE
64 | 13 Set Lithium-Ion Battery Pack & 6 L/I | [17 empty] | 52500 |  | 33IB, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-09 | 2022-09-09 | 2022-09-29 | 2022-09-30 | 2022-09-30 | GAA | 52500 | MOOE |  | 51850 | MOOE
65 | 12 Pcs Prepaid Cards 450's (Cignal SD and HD) | [17 empty] | 5250 |  | 33IB, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-09 | 2022-09-09 | 2022-09-29 | 2022-09-30 | 2022-09-30 | GAA | 5250 | MOOE |  | 5160 | MOOE
66 | 10 pcs Bulb, LED, 15w & 17 L/I | [17 empty] | 65520 |  | 5SFBN, SFRAA, SOCOM, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-07 | 2022-09-07 | 2022-09-29 | 2022-09-30 | 2022-09-30 | GAA | 65520 | MOOE |  | 64770 | MOOE
67 | 10 Bot Alcohol & 4 L/I | [17 empty] | 5000 |  | 12FPAO, APAO, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-12 | 2022-09-12 | 2022-11-23 | 2022-11-25 | 2022-11-25 | GAA | 5000 | MOOE |  | 4920 | MOOE
68 | 2 Pack Biscuit & 15 L/I | [17 empty] | 92869 |  | 12FPAO, APAO, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-13 | 2022-09-13 | 2022-10-20 | 2022-10-21 | 2022-10-21 | GAA | 92869 | MOOE |  | 92419 | MOOE
69 | 2 Set Cup & Saucer & 7 L/I | [17 empty] | 16935 |  | 12FPAO, APAO, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-12 | 2022-09-12 | 2022-10-20 | 2022-10-21 | 2022-10-21 | GAA | 16935 | MOOE |  | 16681 | MOOE
70 | 2 ea Mouse & 3 L/I | [17 empty] | 7313 |  | 12FPAO, APAO, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-12 | 2022-09-12 | 2022-10-20 | 2022-10-21 | 2022-10-21 | GAA | 7313 | MOOE |  | 7250 | MOOE
71 | 31 pcs Ball pen & 6 L/I | [17 empty] | 6000 |  | 12FPAO, APAO, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-12 | 2022-09-12 | 2022-10-20 | 2022-10-21 | 2022-10-21 | GAA | 6000 | MOOE |  | 5924 | MOOE
72 | 80 Rolls Barb Wire & 40 L/I | [17 empty] | 753060 |  | 6DCAU, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-12 | 2022-09-12 | 2022-10-20 | 2022-10-21 | 2022-10-21 | GAA | 753060 | SPCL REL |  | 750755 | SPCL REL
73 | 100 kls Spaghitti Pasta & 21 L/I | [17 empty] | 392000 |  | 601ST BDE, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-12 | 2022-09-12 | 2022-10-20 | 2022-10-21 | 2022-10-21 | GAA | 392000 | MOOE |  | 389674 | MOOE
74 | 20 reams Bond paper (A4) & 10 L/I | [17 empty] | 11000 |  | 601ST BDE, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-12 | 2022-09-12 | 2022-10-27 | 2022-10-28 | 2022-10-28 | GAA | 11000 | MOOE |  | 10385 | MOOE
75 | 100 pc Hollow Bolcks 4x4x6 & 6 L/I | [17 empty] | 58000 |  | 1MECH BDE, ARMOR DIV, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-12 | 2022-09-12 | 2022-10-10 | 2022-10-11 | 2022-10-11 | GAA | 58000 | MOOE |  | 57312 | MOOE
76 | 18 pcs Mouse Wireless & 3 L/I | [17 empty] | 100000 |  | 1MECH BDE, ARMOR DIV, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-12 | 2022-09-12 | 2022-10-25 | 2022-10-11 | 2022-10-11 | GAA | 100000 | MOOE |  | 98710 | MOOE
77 | 2 pcs Break Pad & 4 L/I | [17 empty] | 20000 |  | 1MECH BDE, ARMOR DIV, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-12 | 2022-09-12 | 2022-11-15 | 2022-11-16 | 2022-11-16 | GAA | 20000 | MOOE |  | 19450 | MOOE
78 | 10 Box Bond Paper (Long) & 5 L/I | [17 empty] | 52000 |  | 1MECH BDE, ARMOR DIV, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-12 | 2022-09-12 | 2022-10-27 | 2022-10-28 | 2022-10-28 | GAA | 52000 | MOOE |  | 51950 | MOOE
79 | 40 pcs Lumber 2x2x12 & 6 L/I | [17 empty] | 78000 |  | 34IB, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-12 | 2022-09-12 | 2022-09-30 | 2022-10-03 | 2022-10-03 | GAA | 78000 | SPCL REL |  | 77700 | SPCL REL
80 | 2 Box Diluent & 14 L/I | [17 empty] | 159000 |  | CSSH, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-12 | 2022-09-12 | 2022-10-17 | 2022-10-18 | 2022-10-18 | GAA | 159000 | MOOE |  | 158500 | MOOE
81 | 1 ea license Operating System (OS) Windows 10 | [17 empty] | 8000 |  | TF-GENSAN, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-12 | 2022-09-12 | 2022-10-17 | 2022-10-18 | 2022-10-18 | GAA | 8000 | MOOE |  | 7900 | MOOE
82 | 1 pc LCD Monitor Full HD (236"59.9cm diag) & 1 L/I | [17 empty] | 10000 |  | TF-GENSAN, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-12 | 2022-09-12 | 2022-10-17 | 2022-10-18 | 2022-10-18 | GAA | 10000 | MOOE |  | 9650 | MOOE
83 | 10 case Mineral Water 350ml & 2 L/I | [17 empty] | 12000 |  | TF-GENSAN, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-13 | 2022-09-13 | 2022-10-10 | 2022-10-11 | 2022-10-11 | GAA | 12000 | MOOE |  | 11950 | MOOE
84 | 10 case Mineral Water 350ml & 2 L/I | [17 empty] | 21350 |  | TF-GENSAN, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-14 | 2022-09-14 | 2022-10-10 | 2022-10-11 | 2022-10-11 | GAA | 21350 | MOOE |  | 21200 | MOOE
85 | 22 case Bottled Water 500ml & 11 L/I | [17 empty] | 60000 |  | TF-GENSAN, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-14 | 2022-09-14 | 2022-10-10 | 2022-10-11 | 2022-10-11 | GAA | 60000 | MOOE |  | 59820 | MOOE
86 | 28 pcs 2x2x3 & 5 L/I | [17 empty] | 30240 |  | 1MECH BN, ARMOR DIV, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-14 | 2022-09-14 | 2022-09-30 | 2022-10-03 | 2022-10-03 | GAA | 30240 | MOOE |  | 29931 | MOOE
87 | 60 pack Coffee 3 in 1 & 11 L/I | [17 empty] | 91080 |  | 1MECH BN, ARMOR DIV, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-14 | 2022-09-14 | 2022-09-30 | 2022-10-03 | 2022-10-03 | GAA | 91080 | MOOE |  | 90233 | MOOE
88 | 40 pack CupCake & 11 L/I | [17 empty] | 40000 |  | 1MECH BN, ARMOR DIV, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-14 | 2022-09-14 | 2022-10-17 | 2022-10-18 | 2022-10-18 | GAA | 40000 | MOOE |  | 39300 | MOOE
89 | 1 pc Oil Filter & 9 L/I | [17 empty] | 40000 |  | 1MECH BN, ARMOR DIV, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-14 | 2022-09-14 | 2022-10-17 | 2022-10-18 | 2022-10-18 | GAA | 40000 | MOOE |  | 39400 | MOOE
90 | 1 pc Compressor & 2 L/I | [17 empty] | 15000 |  | 1MECH BN, ARMOR DIV, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-14 | 2022-09-14 | 2022-10-17 | 2022-10-18 | 2022-10-18 | GAA | 15000 | MOOE |  | 14850 | MOOE
91 | 1 pc Anti-Virus net, sec 1 user | [17 empty] | 6000 |  | 1MECH BN, ARMOR DIV, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-14 | 2022-09-14 | 2022-10-17 | 2022-10-18 | 2022-10-18 | GAA | 6000 | MOOE |  | 5900 | MOOE
92 | 4 pcs Prepaid Cell Card (Globe) | [17 empty] | 26000 |  | 1MECH BN, ARMOR DIV, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-14 | 2022-09-14 | 2022-10-17 | 2022-10-18 | 2022-10-18 | GAA | 26000 | MOOE |  | 25600 | MOOE
93 | 1 pc 460RAM 64GB ROM & 6 L/I | [17 empty] | 30000 |  | 1MECH BN, ARMOR DIV, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-15 | 2022-09-15 | 2022-11-15 | 2022-11-16 | 2022-11-16 | GAA | 30000 | MOOE |  | 29685 | MOOE
94 | 4 box Macroset & 6 L/I | [17 empty] | 10500 |  | 1MECH BN, ARMOR DIV, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-15 | 2022-09-15 | 2022-11-15 | 2022-11-16 | 2022-11-16 | GAA | 10500 | MOOE |  | 10300 | MOOE
95 | 18 pcs Hammer & 9 L/I | [17 empty] | 124500 |  | 2MECH BN, ARMOR, DIV, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-15 | 2022-09-15 | 2022-09-30 | 2022-10-03 | 2022-10-03 | GAA | 124500 | MOOE |  | 123695 | MOOE
96 | 12 ea Pressure Switch & 13 L/I | [17 empty] | 49350 |  | 2MECH BN, ARMOR, DIV, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-15 | 2022-09-15 | 2022-09-30 | 2022-10-03 | 2022-10-03 | GAA | 49350 | MOOE |  | 49080 | MOOE
97 | 6 pcs Keyboard & 4 L/I | [17 empty] | 67500 |  | 2MECH BN, ARMOR, DIV, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-15 | 2022-09-15 | 2022-09-30 | 2022-10-03 | 2022-10-03 | GAA | 67500 | MOOE |  | 66900 | MOOE
98 | 45 pcs Coco Lumber 4x4x10 & 11 L/I | [17 empty] | 180000 |  | 2MECH BN, ARMOR, DIV, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-15 | 2022-09-15 | 2022-09-30 | 2022-09-30 | 2022-09-30 | GAA | 180000 | MOOE |  | 178875 | MOOE
99 | 15 Pack 3 in 1 Coffee 28gx10's & 5 L/I | [17 empty] | 19000 |  | 2MECH BN, ARMOR, DIV, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-15 | 2022-09-15 | 2022-10-27 | 2022-10-28 | 2022-10-28 | GAA | 19000 | MOOE |  | 18888 | MOOE
100 | 34 Reams Bond Paper (A4 (Sized) & 8 L/I | [17 empty] | 45000 |  | 2MECH BN, ARMOR, DIV, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-15 | 2022-09-15 | 2022-09-30 | 2022-09-30 | 2022-09-30 | GAA | 45000 | MOOE |  | 44865 | MOOE
101 | 18 box Mineral Water, 300ml x24's | [17 empty] | 103000 |  | 2MECH BN, ARMOR, DIV, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-15 | 2022-09-15 | 2022-10-24 | 2022-10-25 | 2022-10-25 | GAA | 103000 | MOOE |  | 102290 | MOOE
102 | 2 Reams Bond Paper A4 & 13 L/I | [17 empty] | 13000 |  | 3RD CAV COY, ARMOR, DIV PA |  | Negotiated 53.9 | [8 empty] | 2022-09-15 | 2022-09-15 | 2022-09-29 | 2022-09-30 | 2022-09-30 | GAA | 13000 | MOOE |  | 12986 | MOOE
103 | 283 Bottls Mineral Water 350ml | [17 empty] | 13000 |  | 3RD CAV COY, ARMOR, DIV PA |  | Negotiated 53.9 | [8 empty] | 2022-09-15 | 2022-09-15 | 2022-09-29 | 2022-09-30 | 2022-09-30 | GAA | 13000 | MOOE |  | 12895 | MOOE
104 | 22 Mango Juice Drink & 4 L/I | [17 empty] | 5000 |  | 3RD CAV COY, ARMOR, DIV PA |  | Negotiated 53.9 | [8 empty] | 2022-09-15 | 2022-09-15 | 2022-10-27 | 2022-10-28 | 2022-10-28 | GAA | 5000 | MOOE |  | 4920 | MOOE
105 | 13 Bags Cement & 6 L/I | [17 empty] | 15000 |  | 3RD CAV COY, ARMOR, DIV PA |  | Negotiated 53.9 | [8 empty] | 2022-09-16 | 2022-09-16 | 2022-09-29 | 2022-09-30 | 2022-09-30 | GAA | 15000 | MOOE |  | 14940 | MOOE
106 | 10 pcs Sign Pen 0.7 Blue, Green & 10 L/I | [17 empty] | 15000 |  | 1MECH BN, ARMOR DIV, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-16 | 2022-09-16 | 2022-10-27 | 2022-10-28 | 2022-10-28 | GAA | 15000 | MOOE |  | 14845 | MOOE
107 | 1 Set Cable Accelarator Pedal & 10 L/I | [17 empty] | 19000 |  | 12RCDG, HARESCOM, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-16 | 2022-09-16 | 2022-10-20 | 2022-10-22 | 2022-10-22 | GAA | 19000 | MOOE |  | 18850 | MOOE
108 | 1 ea power Suply & 1 L/I | [17 empty] | 14018 |  | 12RCDG, HARESCOM, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-16 | 2022-09-16 | 2022-10-20 | 2022-10-21 | 2022-10-21 | GAA | 14018 | MOOE |  | 13818 | MOOE
109 | 12 ea globe Prepaid Card P-700 | [17 empty] | 61491 |  | 12RCDG, HARESCOM, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-16 | 2022-09-16 | 2022-10-20 | 2022-10-21 | 2022-10-21 | GAA | 61491 | MOOE |  | 60355 | MOOE
110 | 60 Pcs Angle Bar 1 1/2x1 1/2x 1/4 & 9 L/I | [17 empty] | 90000 |  | 12RCDG, HARESCOM, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-16 | 2022-09-16 | 2022-10-20 | 2022-10-21 | 2022-10-21 | GAA | 90000 | MOOE |  | 89620 | MOOE
111 | 6 ea Gasket Sealant & 5 L/I | [17 empty] | 10000 |  | 12RCDG, HARESCOM, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-16 | 2022-09-16 | 2022-10-20 | 2022-10-21 | 2022-10-21 | GAA | 10000 | MOOE |  | 9895 | MOOE
112 | 35 rms A4 Bond Paper & 3 L/I | [17 empty] | 63500 |  | 12RCDG, HARESCOM, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-16 | 2022-09-16 | 2022-11-22 | 2022-10-24 | 2022-10-24 | GAA | 63500 | MOOE |  | 63385 | MOOE
113 | 801 pcs Tiles & 3 L/I | [17 empty] | 214000 |  | 6DTS, 6ID ,PA |  | Negotiated 53.9 | [8 empty] | 2022-09-19 | 2022-09-19 | 2022-10-27 | 2022-10-28 | 2022-10-28 | GAA | 214000 | MOOE |  | 212800 | MOOE
114 | 3 Pcs Cignal Cable Prepaid Card 1,000's & 1 L/I | [17 empty] | 5250 |  | 6DTS, 6ID ,PA |  | Negotiated 53.9 | [8 empty] | 2022-09-16 | 2022-09-16 | 2022-10-27 | 2022-10-28 | 2022-10-28 | GAA | 5250 | MOOE |  | 5190 | MOOE
115 | 2 pcs HDMI Cable & 2 L/I | [17 empty] | 8500 |  | 6DTS, 6ID ,PA |  | Negotiated 53.9 | [8 empty] | 2022-09-16 | 2022-09-16 | 2022-10-27 | 2022-10-28 | 2022-10-28 | GAA | 8500 | MOOE |  | 8400 | MOOE
116 | 20 rms Bond Paper A4 & 4 L/I | [17 empty] | 6100 |  | 37IB, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-19 | 2022-09-19 | 2022-11-22 | 2022-10-24 | 2022-10-24 | GAA | 6100 | MOOE |  | 5828 | MOOE
117 | 3 Pcs YC Portable Antenna KL470-510-UHF & 4 L/I | [17 empty] | 13117.5 |  | 37IB, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-19 | 2022-09-19 | 2022-10-27 | 2022-10-28 | 2022-10-28 | GAA | 13117.5 | MOOE |  | 13011 | MOOE
118 | 3 set Eset Internet Security Anti-Virus & 1 L/I | [17 empty] | 10000 |  | 37IB, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-19 | 2022-09-19 | 2022-10-27 | 2022-10-28 | 2022-10-28 | GAA | 10000 | MOOE |  | 9480 | MOOE
119 | 6 pcs Cignal Card & 1 L/I | [17 empty] | 6000 |  | 37IB, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-19 | 2022-09-19 | 2022-10-27 | 2022-10-28 | 2022-10-28 | GAA | 6000 | MOOE |  | 5940 | MOOE
120 | 12 Pcs Globe Pre-Paid Card & 3 L/I | [17 empty] | 18000 |  | 37IB, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-19 | 2022-09-19 | 2022-10-27 | 2022-10-28 | 2022-10-28 | GAA | 18000 | MOOE |  | 17655 | MOOE
121 | 3 pc Freon 22 | [17 empty] | 15000 |  | 37IB, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-19 | 2022-09-19 | 2022-10-27 | 2022-10-28 | 2022-10-28 | GAA | 15000 | MOOE |  | 14850 | MOOE
122 | 3 pcs 12v Electric AC Compressor | [17 empty] | 15000 |  | 37IB, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-19 | 2022-09-19 | 2022-10-27 | 2022-10-28 | 2022-10-28 | GAA | 15000 | MOOE |  | 14850 | MOOE
123 | 4 ea Monoblock Foldable Table &14 L/I | [17 empty] | 52350 |  | 37IB, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-19 | 2022-09-19 | 2022-10-21 | 2022-10-24 | 2022-10-24 | GAA | 52350 | MOOE |  | 51750 | MOOE
124 | 50pcs Def Bar 9mm & 14 L/I | [17 empty] | 100000 |  | 37IB, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-16 | 2022-09-16 | 2022-10-20 | 2022-09-19 | 2022-09-19 | GAA | 100000 | MOOE |  | 99300 | MOOE
125 | 34 pack Biscuits & 2 L/I | [17 empty] | 17000 |  | 40IB, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-19 | 2022-09-19 | 2022-10-17 | 2022-09-20 | 2022-09-20 | GAA | 17000 | MOOE |  | 16820 | MOOE
126 | 1 pc Drone Gimbal Camera & 3 L/I | [17 empty] | 38887.5 |  | 40IB, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-09 | 2022-09-09 | 2022-10-17 | 2022-09-12 | 2022-09-12 | GAA | 38887.5 | MOOE |  | 38785 | MOOE
127 | 70 packs Biscuits & 13 L/I | [17 empty] | 75590 |  | 40IB, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-19 | 2022-09-19 | 2022-10-17 | 2022-10-28 | 2022-10-28 | GAA | 75590 | MOOE |  | 74890 | MOOE
128 | 7 Ctns 3 in 1 Coffee & 4 L/I | [17 empty] | 28985 |  | 38IB, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-20 | 2022-09-20 | 2022-10-25 | 2022-09-26 | 2022-09-26 | GAA | 28985 | MOOE |  | 28475 | MOOE
129 | 1 set Brake Master & 15 L/I | [17 empty] | 20000 |  | 38IB, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-20 | 2022-09-20 | 2022-10-27 | 2022-10-28 | 2022-10-28 | GAA | 20000 | MOOE |  | 19810 | MOOE
130 | 46 Packs Sliced Bread & 8 L/I | [17 empty] | 14500 |  | 38IB, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-20 | 2022-09-20 | 2022-10-27 | 2022-10-28 | 2022-10-28 | GAA | 14500 | MOOE |  | 14353 | MOOE
131 | 100 Pcs Folder Long & 10 L/I | [17 empty] | 30000 |  | 38IB, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-20 | 2022-09-20 | 2022-10-25 | 2022-10-26 | 2022-10-26 | GAA | 30000 | MOOE |  | 29517 | MOOE
132 | 1 pc Stainless Steel Stering & 4 L/I | [17 empty] | 10000 |  | 90IB, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-21 | 2022-09-21 | 2022-10-27 | 2022-10-28 | 2022-10-28 | GAA | 10000 | MOOE |  | 9850 | MOOE
133 | 20 pcs Lumber & 21 L/I | [17 empty] | 200000 |  | 90IB, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-23 | 2022-09-23 | 2022-10-20 | 2022-10-21 | 2022-10-21 | GAA | 200000 | MOOE |  | 198500 | MOOE
134 | 10 Sacks Rice & 8 L/I | [17 empty] | 68400 |  | 90IB, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-23 | 2022-09-23 | 2022-10-20 | 2022-10-21 | 2022-10-21 | GAA | 68400 | MOOE |  | 67950 | MOOE
135 | 25 Reams Bond Paper (A4) & 12 L/I | [17 empty] | 30000 |  | 64TH DRC, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-21 | 2022-09-21 | 2022-10-26 | 2022-10-27 | 2022-10-27 | GAA | 30000 | MOOE |  | 29900 | MOOE
136 | 35 Pack 3 in 1 Coffee 20gx36 & 24 L/I | [17 empty] | 40000 |  | 12FAU,PA |  | Negotiated 53.9 | [8 empty] | 2022-09-21 | 2022-09-21 | 2022-10-19 | 2022-10-20 | 2022-10-20 | GAA | 40000 | MOOE |  | 39825 | MOOE
137 | 10 Bot Elmer's Glue & 19 L/I | [17 empty] | 34000 |  | 12FAU,PA |  | Negotiated 53.9 | [8 empty] | 2022-09-21 | 2022-09-21 | 2022-10-19 | 2022-10-20 | 2022-10-20 | GAA | 34000 | MOOE |  | 33900 | MOOE
138 | 2 Unit Shredder Machine & 1 L/I | [17 empty] | 50000 |  | 12FAU,PA |  | Negotiated 53.9 | [8 empty] | 2022-09-23 | 2022-09-23 | 2022-10-19 | 2022-10-20 | 2022-10-20 | GAA | 50000 | MOOE |  | 49600 | MOOE
139 | 1 Quart Vulcaseal & 12 L/I | [17 empty] | 70000 |  | H6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-23 | 2022-09-23 | 2022-10-19 | 2022-10-20 | 2022-10-20 | GAA | 70000 | MOOE |  | 69600 | MOOE
140 | 8 Pcs Battery (11) Plates & 10 L/I | [17 empty] | 370375 |  | H6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-23 | 2022-09-23 | 2022-10-19 | 2022-10-20 | 2022-10-20 | GAA | 370375 | MOOE |  | 367790 | MOOE
141 | 30 Pcs Mouse & 9 L/I | [17 empty] | 140265 |  | H6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-23 | 2022-09-23 | 2022-10-19 | 2022-10-20 | 2022-10-20 | GAA | 140265 | MOOE |  | 139050 | MOOE
142 | 90 pcs marine Plywood 5mm x4's x8' & 287 L/I | [17 empty] | 796537 |  | H6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-23 | 2022-09-23 | 2022-10-20 | 2022-10-21 | 2022-10-21 | GAA | 796537 | MOOE |  | 792187 | MOOE
143 | 12 Rems Bond Paper (A4) & 5 L/I | [17 empty] | 4500 |  | 62ND DRC, 6ID,PA |  | Negotiated 53.9 | [8 empty] | 2022-09-21 | 2022-09-21 | 2022-10-27 | 2022-10-28 | 2022-10-28 | GAA | 4500 | MOOE |  | 4475 | MOOE
144 | 150 pcs Alcohol 70% Solution 500ml & 2 L/I | [17 empty] | 20000 |  | 62ND DRC, 6ID,PA |  | Negotiated 53.9 | [8 empty] | 2022-09-21 | 2022-09-21 | 2022-10-27 | 2022-10-28 | 2022-10-28 | GAA | 20000 | MOOE |  | 19800 | MOOE
145 | 3 Pcs Power Supply & 4 L/I | [17 empty] | 23000 |  | 63RD DRC, 6ID ,PA |  | Negotiated 53.9 | [8 empty] | 2022-09-21 | 2022-09-21 | 2022-10-20 | 2022-10-21 | 2022-10-21 | GAA | 23000 | MOOE |  | 22895 | MOOE
146 | 150 pcs Alcohol 70% Solution 500ml & 2 L/I | [17 empty] | 20000 |  | 63RD DRC, 6ID ,PA |  | Negotiated 53.9 | [8 empty] | 2022-09-21 | 2022-09-21 | 2022-10-27 | 2022-10-28 | 2022-10-28 | GAA | 20000 | MOOE |  | 19800 | MOOE
147 | 1 Ea Monitor & 2 L/I | [17 empty] | 10000 |  | 61ST DRC, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-21 | 2022-09-21 | 2022-10-27 | 2022-10-28 | 2022-10-28 | GAA | 10000 | MOOE |  | 9895 | MOOE
148 | 13 Pcs Ball Pen & 13 L/I | [17 empty] | 15000 |  | 61ST DRC, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-21 | 2022-09-21 | 2022-10-27 | 2022-10-28 | 2022-10-28 | GAA | 15000 | MOOE |  | 14950 | MOOE
149 | 2 Box Choco Drinks 280g & 5 L/I | [17 empty] | 5000 |  | 61ST DRC, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-21 | 2022-09-21 | 21 No 22 | 2022-11-22 | 2022-11-22 | GAA | 5000 | MOOE |  | 4950 | MOOE
150 | 4 Box Examination Gloves & 2 L/I | [17 empty] | 20000 |  | 61ST DRC, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-21 | 2022-09-21 | 2022-10-27 | 2022-10-28 | 2022-10-28 | GAA | 20000 | MOOE |  | 19800 | MOOE
151 | 50 Bags Cement & 18 L/I | [17 empty] | 105000 |  | 602ND BDE, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-26 | 2022-09-26 | 2022-10-26 | 2022-10-28 | 2022-10-28 | GAA | 105000 | MOOE |  | 104100 | MOOE
152 | 50 Bags Cement & 7 L/I | [17 empty] | 40000 |  | 602ND BDE, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-22 | 2022-09-22 | 2022-11-15 | 2022-10-17 | 2022-10-17 | GAA | 40000 | MOOE |  | 39700 | MOOE
153 | 30 Bags Cement & 17 L/I | [17 empty] | 72000 |  | 602ND BDE, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-26 | 2022-09-26 | 2022-10-25 | 2022-10-26 | 2022-10-26 | GAA | 72000 | MOOE |  | 71400 | MOOE
154 | 40 Pack Coffee 3 in 1` & 4 L/I | [17 empty] | 45100 |  | 602ND BDE, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-22 | 2022-09-22 | 2022-10-25 | 2022-10-26 | 2022-10-26 | GAA | 45100 | MOOE |  | 44700 | MOOE
155 | 20 Box Corned Beef & 7 L/I | [17 empty] | 250000 |  | 602ND BDE, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-26 | 2022-09-26 | 2022-10-20 | 2022-10-21 | 2022-10-21 | GAA | 250000 | MOOE |  | 248000 | MOOE
156 | 100 pcs prepaid Card | [17 empty] | 50000 |  | 602ND BDE, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-26 | 2022-09-26 | 2022-10-20 | 2022-10-21 | 2022-10-21 | GAA | 50000 | MOOE |  | 49500 | MOOE
157 | 140 Reams Bond Paper A4 & 6 L/I | [17 empty] | 50000 |  | 602ND BDE, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-26 | 2022-09-26 | 2022-10-27 | 2022-10-28 | 2022-10-28 | GAA | 50000 | MOOE |  | 49808 | MOOE
158 | 15 pcs Shovel & 5 L/I | [17 empty] | 188235.29 |  | 602ND BDE, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-26 | 2022-09-26 | 2022-10-20 | 2022-10-21 | 2022-10-21 | GAA | 188235.29 | MOOE |  | 186700 | MOOE
159 | 5 load Cignal prepaid load | [17 empty] | 5000 |  | 602ND BDE, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-22 | 2022-09-22 | 2022-11-22 | 2022-10-23 | 2022-10-23 | GAA | 5000 | MOOE |  | 4750 | MOOE
160 | 5 load Cignal prepaid load | [17 empty] | 4500 |  | 602ND BDE, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-22 | 2022-09-22 | 2022-10-27 | 2022-10-28 | 2022-10-28 | GAA | 4500 | MOOE |  | 4250 | MOOE
161 | 2 pcs Battery & 43 L/I | [17 empty] | 232000 |  | 602ND BDE, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-26 | 2022-09-26 | 2022-10-26 | 2022-10-27 | 2022-10-27 | GAA | 232000 | MOOE |  | 230000 | MOOE
162 | 2 pcs Battery & 43 L/I | [17 empty] | 232000 |  | 602ND BDE, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-26 | 2022-09-26 | 2022-10-26 | 2022-10-27 | 2022-10-27 | GAA | 232000 | MOOE |  | 230000 | MOOE
163 | 50 boxis Amoxicilin 500mg Cup & 7 L/I | [17 empty] | 50000 |  | 602ND BDE, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-26 | 2022-09-26 | 2022-10-20 | 2022-10-21 | 2022-10-21 | GAA | 50000 | MOOE |  | 49500 | MOOE
164 | 1 Pc Relay Unit, 24v & 6 L/I | [17 empty] | 20000 |  | TF-GENSAN, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-22 | 2022-09-22 | 2022-10-27 | 2022-10-28 | 2022-10-28 | GAA | 20000 | MOOE |  | 19740 | MOOE
165 | 6 pcs Marine Plywood 1/4 Thick & Coco lumber | [17 empty] | 45000 |  | TF-GENSAN, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-22 | 2022-09-22 | 2022-10-27 | 2022-10-28 | 2022-10-28 | GAA | 45000 | MOOE |  | 44490 | MOOE
166 | 11 Case Mineral Water 350ml & 10 L/I | [17 empty] | 30000 |  | TF-GENSAN, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-22 | 2022-09-22 | 2022-10-27 | 2022-10-28 | 2022-10-28 | GAA | 30000 | MOOE |  | 29415 | MOOE
167 | 6 Reams A4 Bond Paper & 8 L/I | [17 empty] | 10000 |  | 601ST BDE, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-22 | 2022-09-22 | 2022-10-20 | 2022-10-21 | 2022-10-21 | GAA | 10000 | MOOE |  | 9884 | MOOE
168 | 40 Bot Gatorade (350ml) & 4 L/I | [17 empty] | 25000 |  | 601ST BDE, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-22 | 2022-09-22 | 2022-10-20 | 2022-10-21 | 2022-10-21 | GAA | 25000 | MOOE |  | 24875 | MOOE
169 | 25 mtrs Shridders Hose & 5 L/I | [17 empty] | 15000 |  | 57IB, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-22 | 2022-09-22 | 2022-10-27 | 2022-10-28 | 2022-10-28 | GAA | 15000 | MOOE |  | 14825 | MOOE
170 | 10 Each paper, Multi purpose (Copy) A4 & 16 L/I | [17 empty] | 35000 |  | 57IB, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-22 | 2022-09-22 | 2022-10-25 | 2022-10-26 | 2022-10-26 | GAA | 35000 | MOOE |  | 34710 | MOOE
171 | 2 Each Shovel & 3 L/I | [17 empty] | 5000 |  | 57IB, 6ID, PA |  | Negotiated 53.9 | [10 empty] | 2022-10-27 | 2022-10-28 | 2022-10-28 | GAA | 5000 | MOOE |  | 4620 | MOOE
172 | 1 Each Multi Tester & 1 L/I | [17 empty] | 4500 |  | 57IB, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-22 | 2022-09-22 | 2022-10-27 | 2022-10-28 | 2022-10-28 | GAA | 4500 | MOOE |  | 4700 | MOOE
173 | 20 Pad Sand Paper & 12 L/I | [17 empty] | 72200 |  | 57IB, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-26 | 2022-09-26 | 2022-10-20 | 2022-10-21 | 2022-10-21 | GAA | 72200 | MOOE |  | 71500 | MOOE
174 | 6 Sacks Rice & 7 L/I | [17 empty] | 30000 |  | 601ST BDE, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-26 | 2022-09-26 | 2022-11-11 | 2022-11-14 | 2022-11-14 | GAA | 30000 | MOOE |  | 29800 | MOOE
175 | 11 Set PPE Suit & 1 L/I | [17 empty] | 50000 |  | 601ST BDE, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-27 | 2022-09-27 | 2022-11-11 | 2022-11-14 | 2022-11-14 | GAA | 50000 | MOOE |  | 49500 | MOOE
176 | 1 pcs Monitor | [17 empty] | 5000 |  | 6DENTAL, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-27 | 2022-09-27 | 2022-11-11 | 2022-11-14 | 2022-11-14 | GAA | 5000 | MOOE |  | 4950 | MOOE
177 | 11 Pcs Plywood 5mm & 11 L/I | [17 empty] | 33901.25 |  | 6DENTAL, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-27 | 2022-09-27 | 2022-11-11 | 2022-11-14 | 2022-11-14 | GAA | 33901.25 | MOOE |  | 33669 | MOOE
178 | 2 Pcs Hand Pieace Bearing & 1 L/I | [17 empty] | 10000 |  | 6DENTAL, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-27 | 2022-09-27 | 2022-11-11 | 2022-11-14 | 2022-11-14 | GAA | 10000 | MOOE |  | 9800 | MOOE
179 | 2 Rolls Cotton 400gms & 13 L/I | [17 empty] | 89213.5 |  | CSSH, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-27 | 2022-09-27 | 2022-11-11 | 2022-11-14 | 2022-11-14 | GAA | 89213.5 | MOOE |  | 89000 | MOOE
180 | 100 Pcs Acetylcysteine 600mg Tab & 27 L/I | [17 empty] | 107414 |  | CSSH, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-27 | 2022-09-27 | 2022-11-11 | 2022-11-14 | 2022-11-14 | GAA | 107414 | MOOE |  | 107199.18 | MOOE
181 | 2 Each hard Disk (320 GB) | [17 empty] | 13640 |  | 6IB, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-27 | 2022-09-27 | 2022-10-25 | 2022-10-26 | 2022-10-26 | GAA | 13640 | MOOE |  | 13540 | MOOE
182 | 7 ea Bulb & 9 Line items | [17 empty] | 35560 |  | 6IB, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-27 | 2022-09-27 | 2022-10-26 | 2022-10-28 | 2022-10-28 | GAA | 35560 | MOOE |  | 35480 | MOOE
183 | 36 pcs Globe prepaid Card 500's and4 Line Items | [17 empty] | 63180 |  | 6IB, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-27 | 2022-09-27 | 2022-10-25 | 2022-10-26 | 2022-10-26 | GAA | 63180 | MOOE |  | 62105 | MOOE
184 | 24 pcs Plastic Sealed & 9 L/I | [17 empty] | 12000 |  | 5SFBN, SFRAA, SOCOM, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-26 | 2022-09-26 | 2022-10-20 | 2022-10-21 | 2022-10-21 | GAA | 12000 | MOOE |  | 11880 | MOOE
185 | 36 Pack Special Mamon 10's and 9 Line Items | [17 empty] | 30000 |  | 5SFBN, SFRAA, SOCOM, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-27 | 2022-09-27 | 2022-10-10 | 2022-10-11 | 2022-10-11 | GAA | 30000 | MOOE |  | 29880 | MOOE
186 | 25 pcs White Board Marker & 8 L/I | [17 empty] | 50320 |  | 7IB, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-28 | 2022-09-28 | 2022-10-20 | 2022-10-21 | 2022-10-21 | GAA | 50320 | MOOE |  | 49377 | MOOE
187 | 3 kls Elbow Macaroni & 9 L/I | [17 empty] | 5950 |  | 7IB, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-28 | 2022-09-28 | 2022-10-20 | 2022-10-21 | 2022-10-21 | GAA | 5950 | MOOE |  | 5850 | MOOE
188 | 26 Pcs Sign Pen (Blue) & 3 L/I | [17 empty] | 36010 |  | 7IB, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-28 | 2022-09-28 | 2022-10-20 | 2022-10-21 | 2022-10-21 | GAA | 36010 | MOOE |  | 35656 | MOOE
189 | 2 sets Brake Pads & 8 L/I | [17 empty] | 46294 |  | CSSH, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-28 | 2022-09-28 | 2022-10-20 | 2022-10-21 | 2022-10-21 | GAA | 46294 | MOOE |  | 45819 | MOOE
190 | 5 cum. Find Sand & 19 L/I | [17 empty] | 60000 |  | 57IB, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-28 | 2022-09-28 | 2022-10-25 | 2022-10-26 | 2022-10-26 | GAA | 60000 | MOOE |  | 59465 | MOOE
191 | 46 Cup Cake & 14 L/I | [17 empty] | 95500 |  | 57IB, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-28 | 2022-09-28 | 2022-10-25 | 2022-10-26 | 2022-10-26 | GAA | 95500 | MOOE |  | 94505 | MOOE
192 | 1ea Multi Tester & 5 L/I | [17 empty] | 25500 |  | 57IB, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-28 | 2022-09-28 | 2022-10-25 | 2022-10-26 | 2022-10-26 | GAA | 25500 | MOOE |  | 25100 | MOOE
193 | 25 ea Genuine Operating System (OS) | [17 empty] | 25000 |  | 57IB, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-28 | 2022-09-28 | 2022-10-27 | 2022-10-28 | 2022-10-28 | GAA | 25000 | MOOE |  | 24250 | MOOE
194 | 2 ea Hard Disk drive(HDD) | [17 empty] | 5000 |  | 57IB, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-28 | 2022-09-28 | 2022-10-27 | 2022-10-28 | 2022-10-28 | GAA | 5000 | MOOE |  | 4800 | MOOE
195 | 4 pairs AA Battery black (Energizer) & 10 L/I | [17 empty] | 32050 |  | 57IB, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-28 | 2022-09-28 | 2022-10-25 | 2022-10-26 | 2022-10-26 | GAA | 32050 | MOOE |  | 31486 | MOOE
196 | 5 Roll Barbed Wire & 11 L/I | [17 empty] | 45000 |  | 57IB, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-28 | 2022-09-28 | 2022-10-25 | 2022-10-26 | 2022-10-26 | GAA | 45000 | MOOE |  | 44320 | MOOE
197 | 5 bot SC Liquid & 7 L/I | [17 empty] | 5000 |  | 6TH SIGNAL BN, ASR, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-29 | 2022-09-29 | 2022-11-15 | 2022-11-16 | 2022-11-16 | GAA | 5000 | MOOE |  | 4795 | MOOE
198 | 5 Ctn Mineral Water & 8 L/I | [17 empty] | 11525 |  | 6TH SIGNAL BN, ASR, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-29 | 2022-09-29 | 2022-11-15 | 2022-11-16 | 2022-11-16 | GAA | 11525 | MOOE |  | 11235 | MOOE
199 | 50 pcs Notebook 80 Leaves & 8L/I | [17 empty] | 6000 |  | 6TH SIGNAL BN, ASR, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-29 | 2022-09-29 | 2022-11-15 | 2022-11-16 | 2022-11-16 | GAA | 6000 | MOOE |  | 5860 | MOOE
200 | 8 pcs Soldering Led & 6 L/I | [17 empty] | 20500 |  | 6TH SIGNAL BN, ASR, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-29 | 2022-09-29 | 2022-11-15 | 2022-11-16 | 2022-11-16 | GAA | 20500 | MOOE |  | 19990 | MOOE
201 | 15 pcs Angle Bar (2)' & 7 L/I | [17 empty] | 40000 |  | 6TH SIGNAL BN, ASR, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-29 | 2022-09-29 | 2022-11-15 | 2022-11-16 | 2022-11-16 | GAA | 40000 | MOOE |  | 39425 | MOOE
202 | 2 pcs Hard dish 1TB | [17 empty] | 33350 |  | 6TH SIGNAL BN, ASR, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-28 | 2022-09-28 | 2022-11-15 | 2022-11-16 | 2022-11-16 | GAA | 33350 | MOOE |  | 32953 | MOOE
203 | 12 pcs Prepaid Card (Smart) & 1 L/I | [17 empty] | 12000 |  | 6TH SIGNAL BN, ASR, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-28 | 2022-09-28 | 2022-11-15 | 2022-11-16 | 2022-11-16 | GAA | 12000 | MOOE |  | 11520 | MOOE
204 | 2 Pcs Aircon Compressor | [17 empty] | 10500 |  | 12ISU, AIR, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-29 | 2022-09-29 | 2022-11-15 | 2022-11-16 | 2022-11-16 | GAA | 10500 | MOOE |  | 10300 | MOOE
205 | 2 Pcs Tire (Toyota Innova) 205/R65 R15 & 1 L/I | [17 empty] | 26000 |  | 12ISU, AIR, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-29 | 2022-09-29 | 2022-11-15 | 2022-11-16 | 2022-11-16 | GAA | 26000 | MOOE |  | 25700 | MOOE
206 | 20 pcs Coffee 3 in 1 Orig 28gx30 & 11 L/I | [17 empty] | 19500 |  | 106CO,AFPPS |  | Negotiated 53.9 | [8 empty] | 2022-09-29 | 2022-09-29 | 2022-11-15 | 2022-11-16 | 2022-11-16 | GAA | 19500 | MOOE |  | 19380 | MOOE
207 | 10 pcs Cell Card (500) | [17 empty] | 5000 |  | 106CO,AFPPS |  | Negotiated 53.9 | [8 empty] | 2022-09-29 | 2022-09-29 | 2022-11-15 | 2022-11-16 | 2022-11-16 | GAA | 5000 | MOOE |  | 4900 | MOOE
208 | 35 Reams Bond Paper, Multi-purpose 70GSM, A4 & 11 L/I | [17 empty] | 17500 |  | 106CO,AFPPS |  | Negotiated 53.9 | [8 empty] | 2022-09-29 | 2022-09-29 | 2022-11-15 | 2022-11-16 | 2022-11-16 | GAA | 17500 | MOOE |  | 17486 | MOOE
209 | 6 Pcs Cell Card (500) | [17 empty] | 3000 |  | 106CO,AFPPS |  | Negotiated 53.9 | [8 empty] | 2022-09-29 | 2022-09-29 | 2022-11-15 | 2022-11-16 | 2022-11-16 | GAA | 3000 | MOOE |  | 2940 | MOOE
210 | 2 Pack Spaghetti Pasta 1kl & 14 L/I | [17 empty] | 5000 |  | 106CO,AFPPS |  | Negotiated 53.9 | [8 empty] | 2022-09-29 | 2022-09-29 | 2022-11-15 | 2022-11-16 | 2022-11-16 | GAA | 5000 | MOOE |  | 4975 | MOOE
211 | 6 doz Spoon & 7 L/I | [17 empty] | 40000 |  | 603RD BDE, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-30 | 2022-09-30 | 2022-11-15 | 2022-11-16 | 2022-11-16 | GAA | 40000 | SPCL REL |  | 39550 | SPCL REL
212 | 35 Gal. Flat Latex & 63 L/I | [17 empty] | 572226 |  | 603RD BDE, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-10-03 | 2022-10-03 | 2022-10-25 | 2022-10-26 | 2022-10-26 | GAA | 572226 | SPCL REL |  | 570446 | SPCL REL
213 | 30 meters Expanded Wire/Galvanized Welded Wire mesh 4ft & 12 L/I | [17 empty] | 39435 |  | CSSH, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-30 | 2022-09-30 | 2022-10-25 | 2022-10-26 | 2022-10-26 | GAA | 39435 | MOOE |  | 39240 | MOOE
214 | 2 Letters Body Filler & 11 L/I | [17 empty] | 24232.5 |  | CSSH, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-30 | 2022-09-30 | 2022-10-25 | 2022-10-26 | 2022-10-26 | GAA | 24232.5 | MOOE |  | 23965 | MOOE
215 | 2 unit Double Push Door Full in Post Swing with Overhead Closer D/Gray Glass | [17 empty] | 43122 |  | CSSH, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-30 | 2022-09-30 | 2022-10-25 | 2022-10-26 | 2022-10-26 | GAA | 43122 | MOOE |  | 42000 | MOOE
216 | 5 pcs Tubing Adapter 3x2mm | [17 empty] | 10000 |  | 6DENTAL, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-30 | 2022-09-30 | 2022-10-25 | 2022-10-26 | 2022-10-26 | GAA | 10000 | MOOE |  | 9870 | MOOE
217 | 7 ream Book Paper long & 19 L/I | [17 empty] | 37500 |  | 6DENTAL, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-30 | 2022-09-30 | 2022-10-25 | 2022-10-26 | 2022-10-26 | GAA | 37500 | MOOE |  | 37270 | MOOE
218 | 10 Rms Bond Paper A4 & 16 L/I | [17 empty] | 27000 |  | 57IB, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-09-30 | 2022-09-30 | 2022-10-25 | 2022-10-26 | 2022-10-26 | GAA | 27000 | MOOE |  | 26425 | MOOE
219 | 70 pcs Biometric Device & 1 L/I | [17 empty] | 916400 |  | 6DCAU, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-10-10 | 2022-10-10 | 2022-10-25 | 2022-10-26 | 2022-10-26 | GAA | 916400 | SPCL REL |  | 909000 | SPCL REL
220 | 6 pcs External Drive 1TB & 15 L/I | [17 empty] | 200000 |  | 6DCAU, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-10-10 | 2022-10-10 | 2022-10-25 | 2022-10-26 | 2022-10-26 | GAA | 200000 | SPCL REL |  | 199000 | SPCL REL
221 | 1 set Overhouling Gasket & 51 L/I | [17 empty] | 244965 |  | 12FSSU, ASCOM, PA |  | Negotiated 53.9 | [8 empty] | 2022-10-03 | 2022-10-03 | 2022-12-05 | 2022-12-06 | 2022-12-06 | GAA | 244965 | SPCL REL |  | 243255 | SPCL REL
222 | 1 set Clutch Disc & 49 L/I | [17 empty] | 162929 |  | 12FSSU, ASCOM, PA |  | Negotiated 53.9 | [8 empty] | 2022-10-03 | 2022-10-03 | 2022-12-05 | 2022-12-06 | 2022-12-06 | GAA | 162929 | SPCL REL |  | 161285 | SPCL REL
223 | 14 set Desktop Computer & 2 L/I | [17 empty] | 221040 |  | 12RCDG, HARESCOM, PA |  | Negotiated 53.9 | [8 empty] | 2022-10-07 | 2022-10-07 | 2022-12-05 | 2022-12-06 | 2022-12-06 | GAA | 221040 | SPCL REL |  | 220100 | SPCL REL
224 | 1pc Coffee Boiler & 18 L/I | [17 empty] | 75000 |  | 6MIB ,6ID ,PA |  | Negotiated 53.9 | [8 empty] | 2022-10-10 | 2022-10-10 | 2022-12-05 | 2022-12-06 | 2022-12-06 | GAA | 75000 | SPCL REL |  | 74520 | SPCL REL
225 | 3 pcs Mouse & 5 L/I | [17 empty] | 20000 |  | 6DCAU, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-10-07 | 2022-10-07 | 2022-12-05 | 2022-12-06 | 2022-12-06 | GAA | 20000 | MOOE |  | 19800 | MOOE
226 | 35 pcs Round Post | [17 empty] | 72500 |  | 6DCAU, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-10-10 | 2022-10-10 | 2022-12-05 | 2022-12-06 | 2022-12-06 | GAA | 72500 | MOOE |  | 71975 | MOOE
227 | 3 pcs Battery Pack & 1 L/I | [17 empty] | 15000 |  | 6DCAU, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-10-07 | 2022-10-07 | 2022-12-05 | 2022-12-06 | 2022-12-06 | GAA | 15000 | MOOE |  | 14850 | MOOE
228 | 1 set Brake Pad (Front) & 9 L/I | [17 empty] | 30000 |  | 6DCAU, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-10-07 | 2022-10-07 | 2022-12-05 | 2022-12-06 | 2022-12-06 | GAA | 30000 | MOOE |  | 29850 | MOOE
229 | 149 rms Bond Paper A4 & 19 L/I | [17 empty] | 150000 |  | 6DCAU, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-10-10 | 2022-10-10 | 2022-12-05 | 2022-12-06 | 2022-12-06 | GAA | 150000 | SPCL REL |  | 148950 | SPCL REL
230 | 135 Board Feet Good Lumber & 13 L/I | [17 empty] | 60000 |  | 5SFBN, SFRAA, SOCOM, PA |  | Negotiated 53.9 | [8 empty] | 2022-10-10 | 2022-10-10 | 2022-10-17 | 2022-10-18 | 2022-10-18 | GAA | 60000 | SPCL REL |  | 59550 | SPCL REL
231 | 5 kls Comon nails Nr 4 & 15 L/I | [17 empty] | 100000 |  | 603RD BDE, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-10-10 | 2022-10-10 | 2022-10-25 | 2022-10-18 | 2022-10-18 | GAA | 100000 | SPCL REL |  | 99380 | SPCL REL
232 | 30 PCS Video Card & 4 L/I | [17 empty] | 30000 |  | 6CMO BN, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-10-13 | 2022-10-13 | 2022-11-15 | 2022-11-16 | 2022-11-16 | GAA | 30000 | MOOE |  | 29790 | MOOE
233 | 1 Pcs Christmas Tree (7ft) & 5 L/I | [17 empty] | 30000 |  | 6CMO BN, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-10-13 | 2022-10-13 | 2022-11-15 | 2022-11-16 | 2022-11-16 | GAA | 30000 | MOOE |  | 29850 | MOOE
234 | 2 Unit Shredder Machine & 1 L/I | [17 empty] | 50000 |  | 12FAU,PA |  | Negotiated 53.9 | [8 empty] | 2022-10-13 | 2022-10-13 | 2022-11-15 | 2022-11-16 | 2022-11-16 | GAA | 50000 | MOOE |  | 49500 | MOOE
235 | 10 bot Elmer's Glue & 19 L/I | [17 empty] | 30000 |  | 12FAU,PA |  | Negotiated 53.9 | [8 empty] | 2022-10-13 | 2022-10-13 | 2022-11-15 | 2022-11-16 | 2022-11-16 | GAA | 30000 | MOOE |  | 29850 | MOOE
236 | 238 Bags Cement & 135 Line Items | [17 empty] | 997321 |  | 603RD BDE, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-10-17 | 2022-10-17 | 2022-11-15 | 2022-11-16 | 2022-11-16 | GAA | 997321 | SPCL REL |  | 990021 | SPCL REL
237 | 50 reams Bond Paper A3 & 8 L/I | [17 empty] | 96650 |  | 6CMO BN, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-10-17 | 2022-10-17 | 2022-11-15 | 2022-11-16 | 2022-11-16 | GAA | 96650 | SPCL REL |  | 95900 | SPCL REL
238 | 2 Units DigitalCopier Ecosys M2540dn/L | [17 empty] | 95998 |  | 6CMO BN, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-10-17 | 2022-10-17 | 2022-11-15 | 2022-11-16 | 2022-11-16 | GAA | 95998 | SPCL REL |  | 95000 | SPCL REL
239 | 36 Pack Nestle cream & 11 L/I | [17 empty] | 50000 |  | 37IB, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-10-17 | 2022-10-17 | 2022-11-15 | 2022-11-16 | 2022-11-16 | GAA | 50000 | MOOE |  | 49600 | MOOE
240 | 12 Pcs Pineapple Juice Powder 40g & 5 L/I | [17 empty] | 30000 |  | 1MECH BDE, ARMOR DIV, PA |  | Negotiated 53.9 | [8 empty] | 2022-10-17 | 2022-10-17 | 2022-11-15 | 2022-11-16 | 2022-11-16 | GAA | 30000 | MOOE |  | 29900 | MOOE
241 | 3 Boxis Rapid Antigen Kits Nasal & 1 L/I | [17 empty] | 51300 |  | 6MIB ,6ID ,PA |  | Negotiated 53.9 | [8 empty] | 2022-10-25 | 2022-10-25 | 2022-11-15 | 2022-11-16 | 2022-11-16 | GAA | 51300 | MOOE |  | 49740 | MOOE
242 | 23 Reams Bond Paper A4 & 21 L/I | [17 empty] | 121950 |  | 6MIB ,6ID ,PA |  | Negotiated 53.9 | [8 empty] | 2022-10-25 | 2022-10-25 | 2022-11-15 | 2022-11-16 | 2022-11-16 | GAA | 121950 | MOOE |  | 121372 | MOOE
243 | 3 Ream Bond Paper A4 & 10 L/I | [17 empty] | 6000 |  | 7FAB, AAR, PA |  | Negotiated 53.9 | [8 empty] | 2022-10-20 | 2022-10-20 | 2022-11-15 | 2022-11-16 | 2022-11-16 | GAA | 6000 | MOOE |  | 5940 | MOOE
244 | 4 pack Coffee 3 in 1 & 5 L/I | [17 empty] | 12500 |  | 7FAB, AAR, PA |  | Negotiated 53.9 | [8 empty] | 2022-10-20 | 2022-10-20 | 2022-11-15 | 2022-11-16 | 2022-11-16 | GAA | 12500 | MOOE |  | 12300 | MOOE
245 | 10 bags Cement & 7 L/I | [17 empty] | 10000 |  | 7FAB, AAR, PA |  | Negotiated 53.9 | [8 empty] | 2022-10-20 | 2022-10-20 | 2022-12-05 | 2022-12-06 | 2022-12-06 | GAA | 10000 | MOOE |  | 9800 | MOOE
246 | 14 Packs Bihon & 19 L/I | [17 empty] | 50000 |  | 7FAB, AAR, PA |  | Negotiated 53.9 | [8 empty] | 2022-10-25 | 2022-10-25 | 21 No 22 | 2022-11-22 | 2022-11-22 | GAA | 50000 | MOOE |  | 49720 | MOOE
247 | 215 Pcs THk Marine Plywood & 17 L/I | [17 empty] | 309170 |  | 6DTS, 6ID ,PA |  | Negotiated 53.9 | [8 empty] | 2022-10-25 | 2022-10-25 | 21 No 22 | 2022-11-22 | 2022-11-22 | GAA | 309170 | SPCL REL |  | 306770 | SPCL REL
248 | 45 Reams Bond Paper A 4 & 18 L/I | [17 empty] | 30300 |  | 602ND BDE, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-10-20 | 2022-10-20 | 2022-12-05 | 2022-12-06 | 2022-12-06 | GAA | 30300 | MOOE |  | 30180 | MOOE
249 | 10 Load Cignal Prepaid load | [17 empty] | 10000 |  | 602ND BDE, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-10-20 | 2022-10-20 | 2022-11-15 | 2022-11-16 | 2022-11-16 | GAA | 10000 | MOOE |  | 9900 | MOOE
250 | 500 Bags Cement & 14 L/I | [17 empty] | 500000 |  | 603RD BDE, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-11-02 | 2022-11-02 | 2022-11-15 | 2022-11-16 | 2022-11-16 | GAA | 500000 | SPCL REL |  | 499250 | SPCL REL
251 | 1 Unit Intel Core i5, 12500H Processor, 8GB RAM DDR4 & 5 L/I | [17 empty] | 98340 |  | 6CMO BN, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-11-08 | 2022-11-08 | 2022-11-15 | 2022-11-16 | 2022-11-16 | GAA | 98340 | SPCL REL |  | 97440 | SPCL REL
252 | 5 pcs Hard Disk SSD & 18 L/I | [17 empty] | 182783.18 |  | 6TH SIGNAL BN, ASR, PA |  | Negotiated 53.9 | [8 empty] | 2022-11-14 | 2022-11-14 | 2022-11-15 | 2022-11-16 | 2022-11-16 | GAA | 182783.18 | SPCL REL |  | 182000 | SPCL REL
253 | 85 pcs White Board Marker & 22 L/I | [17 empty] | 100000 |  | 6IMB,IMCOM, PA |  | Negotiated 53.9 | [8 empty] | 2022-11-14 | 2022-11-14 | 2022-12-05 | 2022-12-06 | 2022-12-06 | GAA | 100000 | SPCL REL |  | 99500 | SPCL REL
254 | 5 Sack Rice & 15 L/I | [17 empty] | 117000 |  | 6IMB,IMCOM, PA |  | Negotiated 53.9 | [8 empty] | 2022-11-14 | 2022-11-14 | 2022-12-05 | 2022-12-06 | 2022-12-06 | GAA | 117000 | SPCL REL |  | 116250 | SPCL REL
255 | 10 pcs Globe Prepaid Card 500 & 4 L/I | [17 empty] | 25000 |  | 6IMB,IMCOM, PA |  | Negotiated 53.9 | [8 empty] | 2022-11-10 | 2022-11-10 | 2022-12-05 | 2022-12-06 | 2022-12-06 | GAA | 25000 | MOOE |  | 24592 | MOOE
256 | 10 Sacks Rice & 7 L/I | [17 empty] | 68400 |  | 90IB, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-11-14 | 2022-11-14 | 2022-12-05 | 2022-12-06 | 2022-12-06 | GAA | 68400 | MOOE |  | 68000 | MOOE
257 | 1 Ltrs Oil & 6 L/I | [17 empty] | 10000 |  | 33IB, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-11-10 | 2022-11-10 | 21 No 22 | 2022-11-22 | 2022-11-22 | GAA | 10000 | MOOE |  | 9900 | MOOE
258 | 30 pcs Corrugated Sheet & 10 L/I | [17 empty] | 50800 |  | 33IB, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-11-14 | 2022-11-14 | 21 No 22 | 2022-11-22 | 2022-11-22 | GAA | 50800 | MOOE |  | 50300 | MOOE
259 | 40 Rms Bond paper A4 & 6 L/I | [17 empty] | 15000 |  | 33IB, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-11-10 | 2022-11-10 | 21 No 22 | 2022-11-22 | 2022-11-22 | GAA | 15000 | MOOE |  | 14650 | MOOE
260 | 1 ea Grass Cutter & 2 L/I | [17 empty] | 20200 |  | 33IB, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-11-10 | 2022-11-10 | 21 No 22 | 2022-11-22 | 2022-11-22 | GAA | 20200 | MOOE |  | 20000 | MOOE
261 | 7 pcs WD40 Multipurpose lubricant & 14 L/I | [17 empty] | 62660 |  | 40IB, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-11-14 | 2022-11-14 | 21 No 22 | 2022-11-22 | 2022-11-22 | GAA | 62660 | MOOE |  | 62360 | MOOE
262 | 22 length 31x16x2'x6mm Angular Bar & 79 L/I | [17 empty] | 499822 |  | 3EODC, ASCOM, PA |  | Negotiated 53.9 | [8 empty] | 2022-11-22 | 2022-11-22 | 2022-12-05 | 2022-12-06 | 2022-12-06 | GAA | 499822 | SPCL REL |  | 496222 | SPCL REL
263 | 50 Bags Cement & 13 ZL/I | [17 empty] | 134920 |  | 7IB, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-11-14 | 2022-11-14 | 2022-11-15 | 2022-11-16 | 2022-11-16 | GAA | 134920 | MOOE |  | 133870 | MOOE
264 | 1 Pc Stainless Steel Steering & 4 L/I | [17 empty] | 10000 |  | 90IB, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-11-11 | 2022-11-11 | 2022-12-05 | 2022-12-06 | 2022-12-06 | GAA | 10000 | MOOE |  | 9850 | MOOE
265 | 150 Pcs Folfer Brown (Long) and 8 L/I | [17 empty] | 20000 |  | 34IB, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-11-11 | 2022-11-11 | 21 No 22 | 2022-11-22 | 2022-11-22 | GAA | 20000 | MOOE |  | 19775 | MOOE
266 | 55 Mtrs Soldering Led and 7 Line Items | [17 empty] | 35000 |  | 34IB, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-11-11 | 2022-11-11 | 21 No 22 | 2022-11-22 | 2022-11-22 | GAA | 35000 | MOOE |  | 34890 | MOOE
267 | 4 Ctn Mineral Water 350ml & 6 L/I | [17 empty] | 28000 |  | 34IB, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-11-11 | 2022-11-11 | 21 No 22 | 2022-11-22 | 2022-11-22 | GAA | 28000 | MOOE |  | 27800 | MOOE
268 | 2 pcs Hard Dish Drive | [17 empty] | 30000 |  | 34IB, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-11-11 | 2022-11-11 | 21 No 22 | 2022-11-22 | 2022-11-22 | GAA | 30000 | MOOE |  | 29700 | MOOE
269 | 36 Pack Special Mamon 10's and 9 Line Items | [17 empty] | 30000 |  | 5SFBN, SFRAA, SOCOM, PA |  | Negotiated 53.9 | [8 empty] | 2022-11-15 | 2022-11-15 | 2022-12-05 | 2022-12-06 | 2022-12-06 | GAA | 30000 | MOOE |  | 29880 | MOOE
270 | 10 pack Pancit Bihon, 545g & 14 L/I | [17 empty] | 16000 |  | 5SFBN, SFRAA, SOCOM, PA |  | Negotiated 53.9 | [8 empty] | 2022-11-15 | 2022-11-15 | 2022-12-05 | 2022-12-06 | 2022-12-06 | GAA | 16000 | MOOE |  | 15800 | MOOE
271 | 84 Pack Sliced Bread & 6 L/I | [17 empty] | 26150 |  | 38IB, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-11-16 | 2022-11-16 | 21 No 22 | 2022-12-06 | 2022-12-06 | GAA | 26150 | MOOE |  | 25975 | MOOE
272 | 2 Set Brake Master & 15 L/I | [17 empty] | 40550 |  | 38IB, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-11-16 | 2022-11-16 | 2022-12-05 | 2022-12-06 | 2022-12-06 | GAA | 40550 | MOOE |  | 40250 | MOOE
273 | 30 pcs Brown Envelop Short * 9 L/I | [17 empty] | 10000 |  | 38IB, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-11-16 | 2022-11-16 | 2022-12-05 | 2022-12-06 | 2022-12-06 | GAA | 10000 | MOOE |  | 9860 | MOOE
274 | 5 Ctn 3 in 1 Coffee & 8 L/I | [17 empty] | 38145 |  | 38IB, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-11-16 | 2022-11-16 | 2022-12-05 | 2022-12-06 | 2022-12-06 | GAA | 38145 | MOOE |  | 36945 | MOOE
275 | 1 Set Oil Seal & 7 L/I | [17 empty] | 10000 |  | 5SFBN, SFRAA, SOCOM, PA |  | Negotiated 53.9 | [8 empty] | 2022-11-16 | 2022-11-16 | 2022-12-05 | 2022-12-06 | 2022-12-06 | GAA | 10000 | MOOE |  | 9900 | MOOE
276 | 69 Case Bottled Water 350ml x24 bottles & 8 L/I | [17 empty] | 250000 |  | 1MECH BDE, ARMOR DIV, PA |  | Negotiated 53.9 | [8 empty] | 2022-11-18 | 2022-11-18 | 2022-12-05 | 2022-12-06 | 2022-12-06 | GAA | 250000 | SPCL REL |  | 248879 | SPCL REL
277 | 24 pcs Plastic Sealed & 9 L/I | [17 empty] | 12000 |  | 5SFBN, SFRAA, SOCOM, PA |  | Negotiated 53.9 | [8 empty] | 2022-11-16 | 2022-11-16 | 2022-12-05 | 2022-12-06 | 2022-12-06 | GAA | 12000 | MOOE |  | 11880 | MOOE
278 | 40 Bags Cement & 11 L/I | [17 empty] | 150000 |  | 603RD BDE, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-11-18 | 2022-11-18 | 2022-12-05 | 2022-12-06 | 2022-12-06 | GAA | 150000 | MOOE |  | 149200 | MOOE
279 | 1 pc DSLR Camera w/ 18-55mm Lens & 1 L/I | [17 empty] | 50000 |  | TF-GENSAN, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-11-21 | 2022-11-21 | 2022-12-01 | 2022-12-06 | 2022-12-06 | GAA | 50000 | SPCL REL |  | 49500 | SPCL REL
280 | 310 Bags Cement & 97 L/I | [17 empty] | 498988 |  | 6IMB,IMCOM, PA |  | Negotiated 53.9 | [8 empty] | 2022-11-21 | 2022-11-21 | 2022-12-05 | 2022-12-06 | 2022-12-06 | GAA | 498988 | SPCL REL |  | 498872 | SPCL REL
281 | 2 Pcs Aircon Compressor | [17 empty] | 10500 |  | 12ISU, AIR, PA |  | Negotiated 53.9 | [8 empty] | 2022-11-21 | 2022-11-21 | 2022-12-05 | 2022-12-06 | 2022-12-06 | GAA | 10500 | MOOE |  | 10400 | MOOE
282 | 3 set Horn & 12 L/I | [17 empty] | 30000 |  | 12ISU, AIR, PA |  | Negotiated 53.9 | [8 empty] | 2022-11-21 | 2022-11-21 | 2022-12-05 | 2022-12-06 | 2022-12-06 | GAA | 30000 | MOOE |  | 29850 | MOOE
283 | 20 Pad Sand Paper & 12 L/I | [17 empty] | 72200 |  | 57IB, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-11-25 | 2022-11-25 | 2022-12-05 | 2022-12-06 | 2022-12-06 | GAA | 72200 | MOOE |  | 71700 | MOOE
284 | 25 Pack Cup Cakje & 14 L/I | [17 empty] | 60000 |  | 57IB, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-11-25 | 2022-11-25 | 2022-12-05 | 2022-12-06 | 2022-12-06 | GAA | 60000 | MOOE |  | 59500 | MOOE
285 | 20 Each Paper, Multi-Purpose (Copy) A4 | [17 empty] | 50000 |  | 57IB, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-11-25 | 2022-11-25 | 2022-12-05 | 2022-12-06 | 2022-12-06 | GAA | 50000 | MOOE |  | 49500 | MOOE
286 | 1 Ea Multi Tester & 1 L/I | [17 empty] | 4500 |  | 57IB, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-11-21 | 2022-11-21 | 2022-12-05 | 2022-12-06 | 2022-12-06 | GAA | 4500 | MOOE |  | 4400 | MOOE
287 | 25 mtrs Shridders Hose & 5 L/I | [17 empty] | 15000 |  | 57IB, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-11-21 | 2022-11-21 | 2022-12-05 | 2022-12-06 | 2022-12-06 | GAA | 15000 | MOOE |  | 14875 | MOOE
288 | 12 Each Biotin & 6 L/I | [17 empty] | 20000 |  | 57IB, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-11-21 | 2022-11-21 | 2022-12-05 | 2022-12-06 | 2022-12-06 | GAA | 20000 | MOOE |  | 19880 | MOOE
289 | 2 Each Shovel & 3 L/I | [17 empty] | 5000 |  | 57IB, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-11-21 | 2022-11-21 | 2022-12-05 | 2022-12-06 | 2022-12-06 | GAA | 5000 | MOOE |  | 4900 | MOOE
290 | 7 rms Bond Paper A4 Size & 8 L/I | [17 empty] | 8500 |  | 37IB, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-11-21 | 2022-11-21 | 2022-12-05 | 2022-12-06 | 2022-12-06 | GAA | 8500 | MOOE |  | 8320 | MOOE
291 | 1 Can Ampalaya Seeds & 8 L/I | [17 empty] | 43750 |  | 37IB, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-11-21 | 2022-11-21 | 2022-12-05 | 2022-12-06 | 2022-12-06 | GAA | 43750 | MOOE |  | 43650 | MOOE
292 | 5 pcs Globe Prepaid Card & 3 L/I | [17 empty] | 11750 |  | 37IB, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-11-21 | 2022-11-21 | 2022-12-05 | 2022-12-06 | 2022-12-06 | GAA | 11750 | MOOE |  | 11525 | MOOE
293 | 36 pcs Globe prepaid Card 500's and4 Line Items | [17 empty] | 63180 |  | 6IB, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-11-25 | 2022-11-25 | 2022-12-05 | 2022-12-06 | 2022-12-06 | GAA | 63180 | MOOE |  | 62105 | MOOE
294 | 5 Case Mineral Water 350ml & 7 L/I | [17 empty] | 50000 |  | TF-GENSAN, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-11-25 | 2022-11-25 | 2022-12-01 | 2022-12-02 | 2022-12-02 | GAA | 50000 | SPCL REL |  | 49500 | SPCL REL
295 | 55 Rms Bond Paper A4 & 19 L/I | [17 empty] | 30000 |  | 33IB, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-11-23 | 2022-11-23 | 2022-12-01 | 2022-12-02 | 2022-12-02 | GAA | 30000 | MOOE |  | 29865 | MOOE
296 | 12 Pcs Prepaid Card Globe 500 50's & 3 L/I | [17 empty] | 30000 |  | 33IB, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-11-23 | 2022-11-23 | 2022-12-01 | 2022-12-02 | 2022-12-02 | GAA | 30000 | MOOE |  | 29460 | MOOE
297 | 8 set portable Butani Stove & 9 L/I | [17 empty] | 40000 |  | 33IB, 6ID, PA |  | Negotiated 53.9 | [8 empty] | 2022-11-23 | 2022-11-23 | 2022-12-01 | 2022-12-02 | 2022-12-02 | GAA | 40000 | MOOE |  | 39800 | MOOE
298 | 4 Pcs Cooking Pot & 12 L/I | [17 empty] | 217387.5 |  | 3EODC, ASCOM, PA |  | Negotiated 53.9 | [8 empty] | 2022-11-28 | 2022-11-28 | 2022-12-05 | 2022-12-06 | 2022-12-06 | GAA | 217387.5 | MOOE |  | 215387.5 | MOOE
299 | 4 Pcs Air Tank | [17 empty] | 251480 |  | 2MECH BN, ARMOR, DIV, PA |  | Negotiated 53.9 | [8 empty] | 2022-12-05 | 2022-12-05 | 2022-12-05 | 2022-12-06 | 2022-12-06 | GAA | 251480 | SPCL REL |  | 249480 | SPCL REL
300 | 2 pcs Compressor Motor SD510 & 20 L/I | [17 empty] | 232840 |  | 2MECH BN, ARMOR, DIV, PA |  | Negotiated 53.9 | [8 empty] | 2022-12-05 | 2022-12-05 | 2022-12-05 | 2022-12-06 | 2022-12-06 | GAA | 232840 | SPCL REL |  | 230840 | SPCL REL
[38 empty] | 21662348.97 |  |  | 7190987.75
Total Alloted of Budget Procurement Activities | [36 empty] | 0
Total Contrct PriceOf Procurement Activites Conducted | [39 empty] | 7190987.75
Total Savings (Total Alloted Budget - Total Contract Price | [36 empty] | 14471361.22
ONGOING PROCUREMENT ACTIVITIES
| None | [17 empty] | 0 |  | None |  | Negotiated 53.9 | [8 empty] | None | None | None | None | None | GAA | 0 | MOOE |  | 0 | MOOE
Total Alloted of Budget Ongoing Procurement Activities | [40 empty] | 0
[21 empty] | Prepared by: | [21 empty] | NOTED BY:
FARCON G CANAUGAN
MAJ (OS) PA
[21 empty] | Armando A Diada | [17 empty] | Commanding Officer
TSg (INF) PA
Operation NCO