## Sheet1
ANNEX B
8ID, PA-PROJECT MONITORING REPORT 01 July 2022 to 30 September 2022
Code (PAP) | Procurement Project | PMO/ End-User | Mode of Procurement | Schedule for Each Procurement Activity | [11 empty] | Source of Funds | ABC (PhP) |  |  | Remarks (brief description of Program/Project) | PMO/ End-User | Is this an Early Procurement Activity? | Mode of Procurement | Actual Procurement Activity | [12 empty] | Source of Funds | ABC (PhP) |  |  | Contract Cost (PhP) |  |  | List of Invited Observers | Date of Receipt of Invitation | [5 empty] | Remarks (Explaining changes from the APP)
|  |  |  | Pre-Proc Conference | Ads/Post of IAEB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Contract Award | Contract Signing | Notice to Proceed | Delivery/ Accept | Payment Process |  | Total | MOOE | CO |  |  |  |  | Pre-Proc Conference | Ads/Post of IB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Date of BAC Resolution Recommending Award | Notice of Award | Contract Signing | Notice to Proceed | Delivery/ Completion | Inspection & Acceptance |  | Total | MOOE | CO | Total | MOOE | CO |  | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Delivery/ Completion/ Acceptance (If applicable)
COMPLETED PROCUREMENT ACTIVITIES
| Office Supplies Expense | [19 empty] | OG4 |  | Shopping | [13 empty] | MOOE | 80000 | 79904 | 96 | 80000 | 79904 | 96
| Office Supplies Expense | [19 empty] | OG2 |  | Shopping | [13 empty] | MOOE | 80205 | 80204 | 1 | 80205 | 80204 | 1
| Office Supplies Expense | [19 empty] | 801BDE |  | Shopping | [13 empty] | MOOE | 60000 | 59792 | 208 | 60000 | 59792 | 208
| Office Supplies Expense | [19 empty] | 19IB |  | Shopping | [13 empty] | MOOE | 2750 | 2748 | 2 | 2750 | 2748 | 2
| Office Supplies Expense | [19 empty] | DRO |  | Shopping | [13 empty] | MOOE | 10000 | 9998 | 2 | 10000 | 9998 | 2
| Office Supplies Expense | [19 empty] | TAP |  | Shopping | [13 empty] | MOOE | 21100 | 21100 | 0 | 21100 | 21100 | 0
| Office Supplies Expense | [19 empty] | 63IB |  | Shopping | [13 empty] | MOOE | 3000 | 2860 | 140 | 3000 | 2860 | 140
| Office Supplies Expense | [19 empty] | Dental |  | Shopping | [13 empty] | MOOE | 7512 | 7479 | 33 | 7512 | 7479 | 33
| Office Supplies Expense | [19 empty] | ODPM |  | Shopping | [13 empty] | MOOE | 6000 | 5992 | 8 | 6000 | 5992 | 8
| Office Supplies Expense | [19 empty] | ODIG |  | Shopping | [13 empty] | MOOE | 14660 | 14648 | 12 | 14660 | 14648 | 12
| Office Supplies Expense | [19 empty] | PDS |  | Shopping | [13 empty] | MOOE | 5000 | 5000 | 0 | 5000 | 5000 | 0
| Office Supplies Expense | [19 empty] | GADO |  | Shopping | [13 empty] | MOOE | 10400 | 10399 | 1 | 10400 | 10399 | 1
| Office Supplies Expense | [19 empty] | 8DTS |  | Shopping | [13 empty] | MOOE | 25000 | 24926 | 74 | 25000 | 24926 | 74
| Office Supplies Expense | [19 empty] | OG7 |  | Shopping | [13 empty] | MOOE | 40800 | 40800 | 0 | 40800 | 40800 | 0
| Office Supplies Expense | [19 empty] | ODSJA |  | Shopping | [13 empty] | MOOE | 4900 | 4870 | 20 | 4900 | 4870 | 20
| Office Supplies Expense | [19 empty] | 802BDE |  | Shopping | [13 empty] | MOOE | 30647 | 30480 | 167 | 30647 | 30480 | 167
| Office Supplies Expense | [19 empty] | OESPA |  | Shopping | [13 empty] | MOOE | 9200 | 9137 | 63 | 9200 | 9137 | 63
| Office Supplies Expense | [19 empty] | SSBN |  | Shopping | [13 empty] | MOOE | 22500 | 22455 | 50 | 22500 | 22455 | 50
| Office Supplies Expense | [19 empty] | 20IB |  | Shopping | [13 empty] | MOOE | 3130 | 3124 | 6 | 3130 | 3124 | 6
| Office Supplies Expense | [19 empty] | 803BDE |  | Shopping | [13 empty] | MOOE | 30000 | 29999 | 1 | 30000 | 29999 | 1
| Office Supplies Expense | [19 empty] | ODCS |  | Shopping | [13 empty] | MOOE | 5000 | 4948 | 52 | 5000 | 4948 | 52
| Office Supplies Expense | [19 empty] | OG2 |  | Shopping | [13 empty] | MOOE | 20000 | 19975 | 25 | 20000 | 19975 | 25
| Office Supplies Expense | [19 empty] | 78IB |  | Shopping | [13 empty] | MOOE | 7560 | 7530 | 30 | 7560 | 7530 | 30
| Office Supplies Expense | [19 empty] | OG8 |  | Shopping | [13 empty] | MOOE | 8500 | 8460 | 40 | 8500 | 8460 | 40
| Office Supplies Expense | [19 empty] | Chaplain |  | Shopping | [13 empty] | MOOE | 12000 | 11985 | 15 | 12000 | 11985 | 15
| Office Supplies Expense | [19 empty] | 14IB |  | Shopping | [13 empty] | MOOE | 12000 | 11970 | 30 | 12000 | 11970 | 30
| Office Supplies Expense | [19 empty] | 14IB |  | Shopping | [13 empty] | MOOE | 5000 | 4999 | 1 | 5000 | 4999 | 1
| Office Supplies Expense | [19 empty] | CLSH |  | Shopping | [13 empty] | MOOE | 1659.6 | 1659 | 0.6 | 1659.6 | 1659 | 0.6
| Office Supplies Expense | [19 empty] | OG1 |  | Shopping | [13 empty] | MOOE | 30000 | 30000 | 0 | 30000 | 30000 | 0
| Office Supplies Expense | [19 empty] | MFO |  | Shopping | [13 empty] | MOOE | 19200 | 19197 | 3 | 19200 | 19197 | 3
| Office Supplies Expense | [19 empty] | DPAO |  | Shopping | [13 empty] | MOOE | 5200 | 5200 | 0 | 5200 | 5200 | 0
| Office Supplies Expense | [19 empty] | 93IB |  | Shopping | [13 empty] | MOOE | 2000 | 2000 | 0 | 2000 | 2000 | 0
| Office Supplies Expense | [19 empty] | SDO |  | Shopping | [13 empty] | MOOE | 20000 | 20000 | 0 | 20000 | 20000 | 0
| Office Supplies Expense | [19 empty] | CLSH |  | Shopping | [13 empty] | MOOE | 50000 | 49985 | 15 | 50000 | 49985 | 15
| Office Supplies Expense | [19 empty] | Chaplain |  | Shopping | [13 empty] | MOOE | 12000 | 11955 | 45 | 12000 | 11955 | 45
| Office Supplies Expense | [19 empty] | ODSM |  | Shopping | [13 empty] | MOOE | 3000 | 2987 | 13 | 3000 | 2987 | 13
| Office Supplies Expense | [19 empty] | ODA |  | Shopping | [13 empty] | MOOE | 8100 | 8080 | 20 | 8100 | 8080 | 20
| Office Supplies Expense | [19 empty] | OG3 |  | Shopping | [13 empty] | MOOE | 46100 | 46050 | 50 | 46100 | 46050 | 50
| Office Supplies Expense | [19 empty] | OG3 |  | Shopping | [13 empty] | MOOE | 20000 | 19984 | 16 | 20000 | 19984 | 16
| Office Supplies Expense | [19 empty] | OG6 |  | Shopping | [13 empty] | MOOE | 8000 | 7980 | 20 | 8000 | 7980 | 20
| Office Supplies Expense | [19 empty] | OG4 |  | Shopping | [13 empty] | MOOE | 80000 | 79886 | 114 | 80000 | 79886 | 114
| Office Supplies Expense | [19 empty] | OG2 |  | Shopping | [13 empty] | MOOE | 80205 | 205 | 0 | 80205 | 205 | 0
| Office Supplies Expense | [19 empty] | OG2 |  | Shopping | [13 empty] | MOOE | 65000 | 64900 | 100 | 65000 | 64900 | 100
| Office Supplies Expense | [19 empty] | 801BDE |  | Shopping | [13 empty] | MOOE | 60000 | 59812 | 188 | 60000 | 59812 | 188
| Office Supplies Expense | [19 empty] | OG8 |  | Shopping | [13 empty] | MOOE | 8500 | 8500 | 0 | 8500 | 8500 | 0
| Office Supplies Expense | [19 empty] | OESPA |  | Shopping | [13 empty] | MOOE | 9200 | 9200 | 0 | 9200 | 9200 | 0
| Office Supplies Expense | [19 empty] | DPM |  | Shopping | [13 empty] | MOOE | 6000 | 6000 | 0 | 6000 | 6000 | 0
| Office Supplies Expense | [19 empty] | 8DCAU |  | Shopping | [13 empty] | MOOE | 38280 | 38016 | 264 | 38280 | 38016 | 264
| Office Supplies Expense | [19 empty] | 8DCAU |  | Shopping | [13 empty] | MOOE | 10000 | 9982 | 18 | 10000 | 9982 | 18
| Office Supplies Expense | [19 empty] | 8DCAU |  | Shopping | [13 empty] | MOOE | 9150 | 9150 |  | 9150 | 9150
| Office Supplies Expense | [19 empty] | ODSJA |  | Shopping | [13 empty] | MOOE | 4900 | 4900 | 0 | 4900 | 4900 | 0
| Office Supplies Expense | [19 empty] | ODSJA |  | Shopping | [13 empty] | MOOE | 2210 | 2210 | 0 | 2210 | 2210 | 0
| Office Supplies Expense | [19 empty] | ODSJA |  | Shopping | [13 empty] | MOOE | 1050 | 1050 | 0 | 1050 | 1050 | 0
| Office Supplies Expense | [19 empty] | TOC |  | Shopping | [13 empty] | MOOE | 20000 | 20000 |  | 20000 | 20000
| Office Supplies Expense | [19 empty] | 46IB |  | Shopping | [13 empty] | MOOE | 8760 | 8760 |  | 8760 | 8760
| Office Supplies Expense | [19 empty] | OG3 |  | Shopping | [13 empty] | MOOE | 46100 | 46100 |  | 46100 | 46100
| Office Supplies Expense | [19 empty] | 19IB |  | Shopping | [13 empty] | MOOE | 2750 | 2750 |  | 2750 | 2750
| Office Supplies Expense | [19 empty] | ODIG |  | Shopping | [13 empty] | MOOE | 14660 | 14660 |  | 14660 | 14660
| Office Supplies Expense | [19 empty] | MFO |  | Shopping | [13 empty] | MOOE | 19200 | 19179 | 21 | 19200 | 19179 | 21
| Office Supplies Expense | [19 empty] | 20IB |  | Shopping | [13 empty] | MOOE | 4630 | 4630 |  | 4630 | 4630
| Office Supplies Expense | [19 empty] | 8DTS |  | Shopping | [13 empty] | MOOE | 25000 | 24926 | 74 | 25000 | 24926 | 74
| Office Supplies Expense | [19 empty] | 8DTS |  | Shopping | [13 empty] | MOOE | 17000 | 16904 | 96 | 17000 | 16904 | 96
| Office Supplies Expense | [19 empty] | OG6 |  | Shopping | [13 empty] | MOOE | 8000 | 8000 |  | 8000 | 8000
| Office Supplies Expense | [19 empty] | DRO |  | Shopping | [13 empty] | MOOE | 10000 | 10000 | 0 | 10000 | 10000 | 0
| Office Supplies Expense | [19 empty] | PDS |  | Shopping | [13 empty] | MOOE | 5000 | 5000 |  | 5000 | 5000
| Office Supplies Expense | [19 empty] | 14IB |  | Shopping | [13 empty] | MOOE | 2000 | 2000 |  | 2000 | 2000
| Office Supplies Expense | [19 empty] | 803BDE |  | Shopping | [13 empty] | MOOE | 30000 | 30000 |  | 30000 | 30000
| Office Supplies Expense | [19 empty] | GADO |  | Shopping | [13 empty] | MOOE | 10400 | 10400 |  | 10400 | 10400
| Office Supplies Expense | [19 empty] | SSBN |  | Shopping | [13 empty] | MOOE | 24500 | 24500 |  | 24500 | 24500
| Office Supplies Expense | [19 empty] | 63IB |  | Shopping | [13 empty] | MOOE | 4500 | 4402 | 98 | 4500 | 4402 | 98
| Office Supplies Expense | [19 empty] | OG4 |  | Shopping | [13 empty] | MOOE | 8500 | 8500 |  | 8500 | 8500
| Office Supplies Expense | [19 empty] | DPAO |  | Shopping | [13 empty] | MOOE | 5200 | 5200 |  | 5200 | 5200
| Office Supplies Expense | [19 empty] | SDO |  | Shopping | [13 empty] | MOOE | 20000 | 19998 | 2 | 20000 | 19998 | 2
| Office Supplies Expense | [19 empty] | OG7 |  | Shopping | [13 empty] | MOOE | 40800 | 40800 | 0 | 40800 | 40800 | 0
| Office Supplies Expense | [19 empty] | OG7 |  | Shopping | [13 empty] | MOOE | 12250 | 12250 | 0 | 12250 | 12250 | 0
| Office Supplies Expense | [19 empty] | OG7 |  | Shopping | [13 empty] | MOOE | 17850 | 17835 | 15 | 17850 | 17835 | 15
| Office Supplies Expense | [19 empty] | OG1 |  | Shopping | [13 empty] | MOOE | 30000 | 30000 | 0 | 30000 | 30000 | 0
| Office Supplies Expense | [19 empty] | OG1 |  | Shopping | [13 empty] | MOOE | 3206 | 3206 |  | 3206 | 3206
| Office Supplies Expense | [19 empty] | CPO |  | Shopping | [13 empty] | MOOE | 5000 | 5000 |  | 5000 | 5000
| Office Supplies Expense | [19 empty] | MWRC |  | Shopping | [13 empty] | MOOE | 5100 | 5100 | 0 | 5100 | 5100 | 0
| Office Supplies Expense | [19 empty] | ODA |  | Shopping | [13 empty] | MOOE | 8100 | 8100 | 0 | 8100 | 8100 | 0
| Office Supplies Expense | [19 empty] | TAP |  | Shopping | [13 empty] | MOOE | 21100 | 21100 | 0 | 21100 | 21100 | 0
| Office Supplies Expense | [19 empty] | CLSH |  | Shopping | [13 empty] | MOOE | 50000 | 49870 | 130 | 50000 | 49870 | 130
| Office Supplies Expense | [19 empty] | Dental |  | Shopping | [13 empty] | MOOE | 7512.5 | 7243 | 269.5 | 7512.5 | 7243 | 269.5
| Office Supplies Expense | [19 empty] | 8CMO |  | Shopping | [13 empty] | MOOE | 13060 | 13060 |  | 13060 | 13060
| Office Supplies Expense | [19 empty] | Chaplain |  | Shopping | [13 empty] | MOOE | 12000 | 12000 |  | 12000 | 12000
| Office Supplies Expense | [19 empty] | 93IB |  | Shopping | [13 empty] | MOOE | 2000 | 2000 | 0 | 2000 | 2000 | 0
| Representation Expense | [19 empty] | 19IB |  | Negotiated 53.9 | [13 empty] | MOOE | 52000 | 52000 | 0 | 52000 | 52000 | 0
| Training Expense | [19 empty] | 19IB |  | Negotiated 53.9 | [13 empty] | MOOE | 60000 | 59960 | 40 | 60000 | 59960 | 40
| RM Building | [19 empty] | 63IB |  | Negotiated 53.9 | [13 empty] | MOOE | 294650 | 294580 | 70 | 294650 | 294580 | 70
| RM Other Structures | [19 empty] | 63IB |  | Negotiated 53.9 | [13 empty] | MOOE | 75000 | 74990 | 10 | 75000 | 74990 | 10
| Semi-Expendable ICT Equipment | [19 empty] | 63IB |  | Negotiated 53.9 | [13 empty] | MOOE | 100000 | 99800 | 200 | 100000 | 99800 | 200
| RM Machinery - Military | [19 empty] | 803BDE |  | Negotiated 53.9 | [13 empty] | MOOE | 67000 | 66940 | 60 | 67000 | 66940 | 60
| RM Other Structures | [19 empty] | 803BDE |  | Negotiated 53.9 | [13 empty] | MOOE | 198500 | 198488 | 12 | 198500 | 198488 | 12
| RM Motor Vehicles | [19 empty] | 803BDE |  | Negotiated 53.9 | [13 empty] | MOOE | 216125 | 216085 | 40 | 216125 | 216085 | 40
| Training Expense | [19 empty] | 83DRC |  | Negotiated 53.9 | [13 empty] | MOOE | 85000 | 84992 | 8 | 85000 | 84992 | 8
| RM Building | [19 empty] | 52IB |  | Negotiated 53.9 | [13 empty] | MOOE | 65000 | 64995 | 5 | 65000 | 64995 | 5
| Training Expense | [19 empty] | 52IB |  | Negotiated 53.9 | [13 empty] | MOOE | 152000 | 151900 | 100 | 152000 | 151900 | 100
| Representation Expense | [19 empty] | 52IB |  | Negotiated 53.9 | [13 empty] | MOOE | 88500 | 88400 | 100 | 88500 | 88400 | 100
| RM Motor Vehicles | [19 empty] | 52IB |  | Negotiated 53.9 | [13 empty] | MOOE | 69000 | 68500 | 500 | 69000 | 68500 | 500
| RM Other Structures | [19 empty] | 52IB |  | Negotiated 53.9 | [13 empty] | MOOE | 80000 | 79992 | 8 | 80000 | 79992 | 8
| Med, Den and Lab Supplies | [19 empty] | Dental |  | Negotiated 53.9 | [13 empty] | MOOE | 86867.5 | 86862 | 5.5 | 86867.5 | 86862 | 5.5
| RM Other Structures | [19 empty] | SSBN |  | Negotiated 53.9 | [13 empty] | MOOE | 100000 | 99960 | 40 | 100000 | 99960 | 40
| RM Motor Vehicles | [19 empty] | SSBN |  | Negotiated 53.9 | [13 empty] | MOOE | 89615 | 89606 | 9 | 89615 | 89606 | 9
| Training Expense | [19 empty] | 78IB |  | Negotiated 53.9 | [13 empty] | MOOE | 71000 | 70869 | 131 | 71000 | 70869 | 131
| RM Building | [19 empty] | 78IB |  | Negotiated 53.9 | [13 empty] | MOOE | 256000 | 255800 | 200 | 256000 | 255800 | 200
| RM Other Structures | [19 empty] | 78IB |  | Negotiated 53.9 | [13 empty] | MOOE | 155000 | 154700 | 300 | 155000 | 154700 | 300
| RM Building | [19 empty] | 802BDE |  | Negotiated 53.9 | [13 empty] | MOOE | 130199 | 130029 | 170 | 130199 | 130029 | 170
| Training Expense | [19 empty] | 802BDE |  | Negotiated 53.9 | [13 empty] | MOOE | 115000 | 114800 | 200 | 115000 | 114800 | 200
| RM Motor Vehicles | [19 empty] | 802BDE |  | Negotiated 53.9 | [13 empty] | MOOE | 144000 | 143780 | 220 | 144000 | 143780 | 220
| RM Other Structures | [19 empty] | 802BDE |  | Negotiated 53.9 | [13 empty] | MOOE | 155000 | 154820 | 180 | 155000 | 154820 | 180
| Semi-Expendable - Military | [19 empty] | 43IB |  | Negotiated 53.9 | [13 empty] | MOOE | 280925 | 280550 | 375 | 280925 | 280550 | 375
| Semi-Expendable - ICT Equipment | [19 empty] | 43IB |  | Negotiated 53.9 | [13 empty] | MOOE | 100000 | 99000 | 1000 | 100000 | 99000 | 1000
| RM Building | [19 empty] | 8DTS |  | Negotiated 53.9 | [13 empty] | MOOE | 175000 | 174810 | 190 | 175000 | 174810 | 190
| RM Other Structures | [19 empty] | 8DTS |  | Negotiated 53.9 | [13 empty] | MOOE | 56000 | 55810 | 190 | 56000 | 55810 | 190
| Representation Expense | [19 empty] | OG7 |  | Negotiated 53.9 | [13 empty] | MOOE | 74000 | 73970 | 30 | 74000 | 73970 | 30
| Semi-Expendable - ICT Equipment | [19 empty] | 8MIB |  | Negotiated 53.9 | [13 empty] | MOOE | 70000 | 69950 | 50 | 70000 | 69950 | 50
| RM Machinery ICT Equipment | [19 empty] | 8MIB |  | Negotiated 53.9 | [13 empty] | MOOE | 110000 | 109900 | 100 | 110000 | 109900 | 100
| RM Other Structures | [19 empty] | 8MIB |  | Negotiated 53.9 | [13 empty] | MOOE | 100000 | 99950 | 50 | 100000 | 99950 | 50
| Med, Den and Lab Supplies | [19 empty] | 8MIB |  | Negotiated 53.9 | [13 empty] | MOOE | 100000 | 99900 | 100 | 100000 | 99900 | 100
| Training Expense | [19 empty] | 20IB |  | Negotiated 53.9 | [13 empty] | MOOE | 78840 | 78724 | 116 | 78840 | 78724 | 116
| Representation Expense | [19 empty] | 20IB |  | Negotiated 53.9 | [13 empty] | MOOE | 62000 | 62000 | 0 | 62000 | 62000 | 0
| Representation Expense | [19 empty] | 8CMO |  | Negotiated 53.9 | [13 empty] | MOOE | 59500 | 59500 | 0 | 59500 | 59500 | 0
| Semi-Expendable Military | [19 empty] | 14IB |  | Negotiated 53.9 | [13 empty] | MOOE | 68250 | 67000 | 1250 | 68250 | 67000 | 1250
| Other Supplies and Materials Expense | [19 empty] | 14IB |  | Negotiated 53.9 | [13 empty] | MOOE | 68500 | 68455 | 45 | 68500 | 68455 | 45
| RM Building | [19 empty] | 14IB |  | Negotiated 53.9 | [13 empty] | MOOE | 100000 | 99925 | 75 | 100000 | 99925 | 75
| RM Building | [19 empty] | 46IB |  | Negotiated 53.9 | [13 empty] | MOOE | 72200 | 71950 | 250 | 72200 | 71950 | 250
| Representation Expense | [19 empty] | 87IB |  | Negotiated 53.9 | [13 empty] | MOOE | 118575 | 118234 | 341 | 118575 | 118234 | 341
| RM Building | [19 empty] | 87IB |  | Negotiated 53.9 | [13 empty] | MOOE | 115000 | 114844 | 156 | 115000 | 114844 | 156
| Other Supplies and Materials Expense | [19 empty] | 93IB |  | Negotiated 53.9 | [13 empty] | MOOE | 89800 | 89685 | 115 | 89800 | 89685 | 115
| RM Building | [19 empty] | 93IB |  | Negotiated 53.9 | [13 empty] | MOOE | 66000 | 65907 | 93 | 66000 | 65907 | 93
| RM Building | [19 empty] | CLSH |  | Negotiated 53.9 | [13 empty] | MOOE | 247500 | 247477 | 23 | 247500 | 247477 | 23
| RM Motor Vehicles | [19 empty] | CLSH |  | Negotiated 53.9 | [13 empty] | MOOE | 70000 | 69990 | 10 | 70000 | 69990 | 10
| Semi-Expendable ICT Equipment | [19 empty] | 801BDE |  | Negotiated 53.9 | [13 empty] | MOOE | 100000 | 99850 | 150 | 100000 | 99850 | 150
| RM Motor Vehicles | [19 empty] | 801BDE |  | Negotiated 53.9 | [13 empty] | MOOE | 292000 | 291970 | 30 | 292000 | 291970 | 30
| Training Expense | [19 empty] | 801BDE |  | Negotiated 53.9 | [13 empty] | MOOE | 65000 | 65000 | 0 | 65000 | 65000 | 0
| Other Supplies and Materials Expense | [19 empty] | 19IB |  | Negotiated 53.9 | [13 empty] | MOOE | 27700 | 27690 | 10 | 27700 | 27690 | 10
| Representation Expense | [19 empty] | 19IB |  | Negotiated 53.9 | [13 empty] | MOOE | 14000 | 13978 | 22 | 14000 | 13978 | 22
| Subscription Expenses | [19 empty] | 19IB |  | Negotiated 53.9 | [13 empty] | MOOE | 5000 | 5000 | 0 | 5000 | 5000 | 0
| Mobile Expense | [19 empty] | 19IB |  | Negotiated 53.9 | [13 empty] | MOOE | 28200 | 28200 | 0 | 28200 | 28200 | 0
| RM Machinery | [19 empty] | 63IB |  | Negotiated 53.9 | [13 empty] | MOOE | 3000 | 2980 | 20 | 3000 | 2980 | 20
| Training Expense | [19 empty] | 63IB |  | Negotiated 53.9 | [13 empty] | MOOE | 50000 | 49610 | 390 | 50000 | 49610 | 390
| Representation Expense | [19 empty] | 63IB |  | Negotiated 53.9 | [13 empty] | MOOE | 12000 | 12000 | 0 | 12000 | 12000 | 0
| Cable, Sat, Tel and Radio Expense | [19 empty] | 63IB |  | Negotiated 53.9 | [13 empty] | MOOE | 6000 | 6000 | 0 | 6000 | 6000 | 0
| Training Expense | [19 empty] | 63IB |  | Negotiated 53.9 | [13 empty] | MOOE | 30000 | 29990 | 10 | 30000 | 29990 | 10
| Training Expense | [19 empty] | 63IB |  | Negotiated 53.9 | [13 empty] | MOOE | 40000 | 39805 | 195 | 40000 | 39805 | 195
| Other Supplies and Materials Expense | [19 empty] | 63IB |  | Negotiated 53.9 | [13 empty] | MOOE | 31500 | 31465 | 35 | 31500 | 31465 | 35
| RM Building | [19 empty] | 63IB |  | Negotiated 53.9 | [13 empty] | MOOE | 35000 | 34980 | 20 | 35000 | 34980 | 20
| RM Building | [19 empty] | 63IB |  | Negotiated 53.9 | [13 empty] | MOOE | 15000 | 15000 | 0 | 15000 | 15000 | 0
| RM Building | [19 empty] | 63IB |  | Negotiated 53.9 | [13 empty] | MOOE | 6000 | 5995 | 5 | 6000 | 5995 | 5
| RM Other Structures | [19 empty] | 63IB |  | Negotiated 53.9 | [13 empty] | MOOE | 29860 | 29840 | 20 | 29860 | 29840 | 20
| Telephone Expense | [19 empty] | TAP |  | Negotiated 53.9 | [13 empty] | MOOE | 8400 | 8400 | 0 | 8400 | 8400 | 0
| Cable, Sat, Tel and Radio Expense | [19 empty] | 803BDE |  | Negotiated 53.9 | [13 empty] | MOOE | 14000 | 14000 | 0 | 14000 | 14000 | 0
| Drugs and Medicines | [19 empty] | 803BDE |  | Negotiated 53.9 | [13 empty] | MOOE | 20000 | 19985 | 15 | 20000 | 19985 | 15
| Subscription Expenses | [19 empty] | 803BDE |  | Negotiated 53.9 | [13 empty] | MOOE | 12000 | 12000 | 0 | 12000 | 12000 | 0
| Med, Den and Lab Supplies | [19 empty] | 803BDE |  | Negotiated 53.9 | [13 empty] | MOOE | 10000 | 9965 | 35 | 10000 | 9965 | 35
| Cable, Sat, Tel and Radio Expense | [19 empty] | 803BDE |  | Negotiated 53.9 | [13 empty] | MOOE | 4000 | 4000 | 0 | 4000 | 4000 | 0
| RM Machinery | [19 empty] | 803BDE |  | Negotiated 53.9 | [13 empty] | MOOE | 7000 | 6998 | 2 | 7000 | 6998 | 2
| RM Communication Equipment | [19 empty] | 803BDE |  | Negotiated 53.9 | [13 empty] | MOOE | 5000 | 4994 | 6 | 5000 | 4994 | 6
| RM ICT Equipment | [19 empty] | 803BDE |  | Negotiated 53.9 | [13 empty] | MOOE | 45250 | 45250 | 0 | 45250 | 45250 | 0
| RM Other Machineries and Equipment | [19 empty] | 803BDE |  | Negotiated 53.9 | [13 empty] | MOOE | 11125 | 11115 | 10 | 11125 | 11115 | 10
| Cable, Sat, Tel and Radio Expense | [19 empty] | 83DRC |  | Negotiated 53.9 | [13 empty] | MOOE | 1500 | 1500 | 0 | 1500 | 1500 | 0
| Training Expense | [19 empty] | 83DRC |  | Negotiated 53.9 | [13 empty] | MOOE | 20000 | 19960 | 40 | 20000 | 19960 | 40
| Representation Expense | [19 empty] | 83DRC |  | Negotiated 53.9 | [13 empty] | MOOE | 25000 | 25000 | 0 | 25000 | 25000 | 0
| Other Supplies and Materials Expense | [19 empty] | 83DRC |  | Negotiated 53.9 | [13 empty] | MOOE | 5000 | 4988 | 12 | 5000 | 4988 | 12
| Training Expense | [19 empty] | 83DRC |  | Negotiated 53.9 | [13 empty] | MOOE | 10000 | 9988 | 12 | 10000 | 9988 | 12
| Training Expense | [19 empty] | 83DRC |  | Negotiated 53.9 | [13 empty] | MOOE | 15000 | 14998 | 2 | 15000 | 14998 | 2
| Training Expense | [19 empty] | 83DRC |  | Negotiated 53.9 | [13 empty] | MOOE | 2500 | 2488 | 12 | 2500 | 2488 | 12
| RM Other Machineries and Equipment | [19 empty] | 52IB |  | Negotiated 53.9 | [13 empty] | MOOE | 30000 | 29500 | 500 | 30000 | 29500 | 500
| RM ICT Equipment | [19 empty] | 52IB |  | Negotiated 53.9 | [13 empty] | MOOE | 20000 | 19900 | 100 | 20000 | 19900 | 100
| RM Building | [19 empty] | 52IB |  | Negotiated 53.9 | [13 empty] | MOOE | 50000 | 49955 | 45 | 50000 | 49955 | 45
| Other Supplies and Materials Expense | [19 empty] | 52IB |  | Negotiated 53.9 | [13 empty] | MOOE | 50500 | 50490 | 10 | 50500 | 50490 | 10
| RM Watercraft | [19 empty] | 52IB |  | Negotiated 53.9 | [13 empty] | MOOE | 20000 | 19900 | 100 | 20000 | 19900 | 100
| RM Building | [19 empty] | Dental |  | Negotiated 53.9 | [13 empty] | MOOE | 20000 | 19925 | 75 | 20000 | 19925 | 75
| RM ICT Equipment | [19 empty] | Dental |  | Negotiated 53.9 | [13 empty] | MOOE | 5824.75 | 5820 | 4.75 | 5824.75 | 5820 | 4.75
| RM Machinery Equipment | [19 empty] | 81DRC |  | Negotiated 53.9 | [13 empty] | MOOE | 10000 | 10000 | 0 | 10000 | 10000 | 0
| Representation Expense | [19 empty] | 81DRC |  | Negotiated 53.9 | [13 empty] | MOOE | 10000 | 10000 | 0 | 10000 | 10000 | 0
| Representation Expense | [19 empty] | 81DRC |  | Negotiated 53.9 | [13 empty] | MOOE | 5000 | 5000 | 0 | 5000 | 5000 | 0
| Training Expense | [19 empty] | 81DRC |  | Negotiated 53.9 | [13 empty] | MOOE | 19000 | 18983 | 17 | 19000 | 18983 | 17
| Representation Expense | [19 empty] | 81DRC |  | Negotiated 53.9 | [13 empty] | MOOE | 1000 | 994 | 6 | 1000 | 994 | 6
| Training Expense | [19 empty] | 81DRC |  | Negotiated 53.9 | [13 empty] | MOOE | 4500 | 4490 | 10 | 4500 | 4490 | 10
| RM Machinery | [19 empty] | 81DRC |  | Negotiated 53.9 | [13 empty] | MOOE | 7500 | 7500 | 0 | 7500 | 7500 | 0
| Representation Expense | [19 empty] | SSBN |  | Negotiated 53.9 | [13 empty] | MOOE | 45000 | 45000 | 0 | 45000 | 45000 | 0
| Representation Expense | [19 empty] | SSBN |  | Negotiated 53.9 | [13 empty] | MOOE | 50000 | 50000 | 0 | 50000 | 50000 | 0
| Other Supplies and Materials Expense | [19 empty] | SSBN |  | Negotiated 53.9 | [13 empty] | MOOE | 30000 | 29972 | 28 | 30000 | 29972 | 28
| Training Expense | [19 empty] | SSBN |  | Negotiated 53.9 | [13 empty] | MOOE | 30000 | 29990 | 10 | 30000 | 29990 | 10
| Representation Expense | [19 empty] | SSBN |  | Negotiated 53.9 | [13 empty] | MOOE | 12000 | 11986 | 14 | 12000 | 11986 | 14
| Med, Den and Lab Supplies | [19 empty] | SSBN |  | Negotiated 53.9 | [13 empty] | MOOE | 20000 | 19996 | 4 | 20000 | 19996 | 4
| Semi-Expendable - Medical Equipment | [19 empty] | SSBN |  | Negotiated 53.9 | [13 empty] | MOOE | 24000 | 23996 | 4 | 24000 | 23996 | 4
| Training Expense | [19 empty] | SSBN |  | Negotiated 53.9 | [13 empty] | MOOE | 26000 | 25994 | 6 | 26000 | 25994 | 6
| Semi-Expendable Communication | [19 empty] | SSBN |  | Negotiated 53.9 | [13 empty] | MOOE | 5000 | 5000 | 0 | 5000 | 5000 | 0
| Semi-Expendable Expense-Medical Equipment | [19 empty] | SSBN |  | Negotiated 53.9 | [13 empty] | MOOE | 400 | 400 | 0 | 400 | 400 | 0
| Subscription Expenses | [19 empty] | 78IB |  | Negotiated 53.9 | [13 empty] | MOOE | 10000 | 9950 | 50 | 10000 | 9950 | 50
| Other Supplies and Materials Expense | [19 empty] | 78IB |  | Negotiated 53.9 | [13 empty] | MOOE | 40720 | 40667 | 53 | 40720 | 40667 | 53
| Representation Expense | [19 empty] | 78IB |  | Negotiated 53.9 | [13 empty] | MOOE | 12720 | 12635 | 85 | 12720 | 12635 | 85
| Internet Expense | [19 empty] | 78IB |  | Negotiated 53.9 | [13 empty] | MOOE | 9000 | 9000 | 0 | 9000 | 9000 | 0
| Telephone Expense | [19 empty] | 78IB |  | Negotiated 53.9 | [13 empty] | MOOE | 9000 | 9000 | 0 | 9000 | 9000 | 0
| Training Expense | [19 empty] | 78IB |  | Negotiated 53.9 | [13 empty] | MOOE | 35000 | 34905 | 95 | 35000 | 34905 | 95
| Representation Expense | [19 empty] | 78IB |  | Negotiated 53.9 | [13 empty] | MOOE | 20000 | 19920 | 80 | 20000 | 19920 | 80
| Drugs and Medicines | [19 empty] | 802BDE |  | Negotiated 53.9 | [13 empty] | MOOE | 10000 | 9937 | 63 | 10000 | 9937 | 63
| RM Machinery | [19 empty] | 802BDE |  | Negotiated 53.9 | [13 empty] | MOOE | 30000 | 29960 | 40 | 30000 | 29960 | 40
| RM ICT Equipment | [19 empty] | 802BDE |  | Negotiated 53.9 | [13 empty] | MOOE | 28000 | 27960 | 40 | 28000 | 27960 | 40
| Representation Expense | [19 empty] | 802BDE |  | Negotiated 53.9 | [13 empty] | MOOE | 25500 | 25400 | 100 | 25500 | 25400 | 100
| Internet Expense | [19 empty] | 802BDE |  | Negotiated 53.9 | [13 empty] | MOOE | 33000 | 33000 | 0 | 33000 | 33000 | 0
| Mobile Expense | [19 empty] | 802BDE |  | Negotiated 53.9 | [13 empty] | MOOE | 49500 | 49500 | 0 | 49500 | 49500 | 0
| Med, Den and Lab Supplies | [19 empty] | 802BDE |  | Negotiated 53.9 | [13 empty] | MOOE | 25000 | 24920 | 80 | 25000 | 24920 | 80
| Semi-Expendable Machinery Equipment | [19 empty] | 802BDE |  | Negotiated 53.9 | [13 empty] | MOOE | 43960 | 43890 | 70 | 43960 | 43890 | 70
| Training Expense | [19 empty] | 43IB |  | Negotiated 53.9 | [13 empty] | MOOE | 40000 | 39902 | 98 | 40000 | 39902 | 98
| Subscription Expenses | [19 empty] | 43IB |  | Negotiated 53.9 | [13 empty] | MOOE | 22925 | 22850 | 75 | 22925 | 22850 | 75
| Representation Expense | [19 empty] | 43IB |  | Negotiated 53.9 | [13 empty] | MOOE | 20000 | 19900 | 100 | 20000 | 19900 | 100
| RM Motor Vehicles | [19 empty] | 8DTS |  | Negotiated 53.9 | [13 empty] | MOOE | 50000 | 49830 | 170 | 50000 | 49830 | 170
| Telephone Expense | [19 empty] | OG7 |  | Negotiated 53.9 | [13 empty] | MOOE | 3000 | 3000 | 0 | 3000 | 3000 | 0
| Internet Expense | [19 empty] | OG7 |  | Negotiated 53.9 | [13 empty] | MOOE | 15000 | 15000 | 0 | 15000 | 15000 | 0
| RM Other Structures | [19 empty] | OG7 |  | Negotiated 53.9 | [13 empty] | MOOE | 5200 | 5200 | 0 | 5200 | 5200 | 0
| RM Motor Vehicles | [19 empty] | OG7 |  | Negotiated 53.9 | [13 empty] | MOOE | 8000 | 8000 | 0 | 8000 | 8000 | 0
| ICT-Office Supplies Expense | [19 empty] | OG7 |  | Negotiated 53.9 | [13 empty] | MOOE | 14000 | 14000 | 0 | 14000 | 14000 | 0
| Mobile Expense | [19 empty] | ODIG |  | Negotiated 53.9 | [13 empty] | MOOE | 7700 | 7700 | 0 | 7700 | 7700 | 0
| Mobile Expense | [19 empty] | GADO |  | Negotiated 53.9 | [13 empty] | MOOE | 6600 | 6600 | 0 | 6600 | 6600 | 0
| Mobile Expense | [19 empty] | ODCS |  | Negotiated 53.9 | [13 empty] | MOOE | 1500 | 1500 | 0 | 1500 | 1500 | 0
| Mobile Expense | [19 empty] | ODSJA |  | Negotiated 53.9 | [13 empty] | MOOE | 4000 | 4000 | 0 | 4000 | 4000 | 0
| Other Supplies and Materials Expense | [19 empty] | 82DRC |  | Negotiated 53.9 | [13 empty] | MOOE | 4500 | 4471 | 29 | 4500 | 4471 | 29
| Representation Expense | [19 empty] | 82DRC |  | Negotiated 53.9 | [13 empty] | MOOE | 15000 | 14940 | 60 | 15000 | 14940 | 60
| Training Expense | [19 empty] | 82DRC |  | Negotiated 53.9 | [13 empty] | MOOE | 5000 | 4967 | 33 | 5000 | 4967 | 33
| Training Expense | [19 empty] | 82DRC |  | Negotiated 53.9 | [13 empty] | MOOE | 20700 | 20578 | 122 | 20700 | 20578 | 122
| Internet Expense | [19 empty] | OG2 |  | Negotiated 53.9 | [13 empty] | MOOE | 9000 | 9000 | 0 | 9000 | 9000 | 0
| Telephone Expense | [19 empty] | OG2 |  | Negotiated 53.9 | [13 empty] | MOOE | 3600 | 3600 | 0 | 3600 | 3600 | 0
| RM Machinery Equipment | [19 empty] | 20IB |  | Negotiated 53.9 | [13 empty] | MOOE | 10000 | 9994 | 6 | 10000 | 9994 | 6
| RM ICT Equipment | [19 empty] | 20IB |  | Negotiated 53.9 | [13 empty] | MOOE | 15000 | 14988 | 12 | 15000 | 14988 | 12
| RM Other Structures | [19 empty] | 20IB |  | Negotiated 53.9 | [13 empty] | MOOE | 40000 | 39984 | 16 | 40000 | 39984 | 16
| Other Supplies and Materials Expense | [19 empty] | 20IB |  | Negotiated 53.9 | [13 empty] | MOOE | 35370 | 35310 | 60 | 35370 | 35310 | 60
| Other Supplies and Materials Expense | [19 empty] | 20IB |  | Negotiated 53.9 | [13 empty] | MOOE | 15500 | 15455 | 45 | 15500 | 15455 | 45
| Semi-Expendable ICT Equipment | [19 empty] | 20IB |  | Negotiated 53.9 | [13 empty] | MOOE | 10000 | 9970 | 30 | 10000 | 9970 | 30
| Training Expense | [19 empty] | 20IB |  | Negotiated 53.9 | [13 empty] | MOOE | 8160 | 8160 | 0 | 8160 | 8160 | 0
| Other Supplies and Materials Expense | [19 empty] | 8CMO |  | Negotiated 53.9 | [13 empty] | MOOE | 10000 | 10000 | 0 | 10000 | 10000 | 0
| Subscription Expenses | [19 empty] | 8CMO |  | Negotiated 53.9 | [13 empty] | MOOE | 3000 | 3000 | 0 | 3000 | 3000 | 0
| RM ICT Equipment | [19 empty] | 8CMO |  | Negotiated 53.9 | [13 empty] | MOOE | 3000 | 3000 | 0 | 3000 | 3000 | 0
| RM Building | [19 empty] | 8CMO |  | Negotiated 53.9 | [13 empty] | MOOE | 50000 | 50000 | 0 | 50000 | 50000 | 0
| Telephone Expense | [19 empty] | OG4 |  | Negotiated 53.9 | [13 empty] | MOOE | 7000 | 7000 | 0 | 7000 | 7000 | 0
| Internet Expense | [19 empty] | OG4 |  | Negotiated 53.9 | [13 empty] | MOOE | 5400 | 5400 | 0 | 5400 | 5400 | 0
| Internet Expense | [19 empty] | OG8 |  | Negotiated 53.9 | [13 empty] | MOOE | 3000 | 3000 | 0 | 3000 | 3000 | 0
| Representation Expense | [19 empty] | OG8 |  | Negotiated 53.9 | [13 empty] | MOOE | 18500 | 18500 | 0 | 18500 | 18500 | 0
| RM Motor Vehicles | [19 empty] | OG8 |  | Negotiated 53.9 | [13 empty] | MOOE | 15000 | 15000 | 0 | 15000 | 15000 | 0
| Internet Expense | [19 empty] | ODPM |  | Negotiated 53.9 | [13 empty] | MOOE | 3600 | 3600 | 0 | 3600 | 3600 | 0
| RM Motor Vehicles | [19 empty] | Chaplain |  | Negotiated 53.9 | [13 empty] | MOOE | 3000 | 2960 | 40 | 3000 | 2960 | 40
| Cable, Sat, Tel and Radio Expense | [19 empty] | 14IB |  | Negotiated 53.9 | [13 empty] | MOOE | 4500 | 4500 | 0 | 4500 | 4500 | 0
| Internet Expense | [19 empty] | 14IB |  | Negotiated 53.9 | [13 empty] | MOOE | 9000 | 9000 | 0 | 9000 | 9000 | 0
| Representation Expense | [19 empty] | 14IB |  | Negotiated 53.9 | [13 empty] | MOOE | 20000 | 20000 | 0 | 20000 | 20000 | 0
| Mobile Expense | [19 empty] | 14IB |  | Negotiated 53.9 | [13 empty] | MOOE | 6000 | 6000 | 0 | 6000 | 6000 | 0
| Semi-Expendable-ICT Equipment | [19 empty] | 14IB |  | Negotiated 53.9 | [13 empty] | MOOE | 40000 | 40000 | 0 | 40000 | 40000 | 0
| Representation Expense | [19 empty] | 14IB |  | Negotiated 53.9 | [13 empty] | MOOE | 9000 | 9000 | 0 | 9000 | 9000 | 0
| Semi-Expendable - DRRE | [19 empty] | 14IB |  | Negotiated 53.9 | [13 empty] | MOOE | 30000 | 30000 | 0 | 30000 | 30000 | 0
| Training Expense | [19 empty] | 14IB |  | Negotiated 53.9 | [13 empty] | MOOE | 11679 | 11679 | 0 | 11679 | 11679 | 0
| RM Land Improvement | [19 empty] | 14IB |  | Negotiated 53.9 | [13 empty] | MOOE | 15000 | 15000 | 0 | 15000 | 15000 | 0
| Training Expense | [19 empty] | 14IB |  | Negotiated 53.9 | [13 empty] | MOOE | 10000 | 10000 | 0 | 10000 | 10000 | 0
| RM Other Structures | [19 empty] | 14IB |  | Negotiated 53.9 | [13 empty] | MOOE | 20000 | 20000 | 0 | 20000 | 20000 | 0
| Training Expense | [19 empty] | 14IB |  | Negotiated 53.9 | [13 empty] | MOOE | 8000 | 8000 | 0 | 8000 | 8000 | 0
| Training Expense | [19 empty] | 14IB |  | Negotiated 53.9 | [13 empty] | MOOE | 37821 | 37821 | 0 | 37821 | 37821 | 0
| Representation Expense | [19 empty] | 46IB |  | Negotiated 53.9 | [13 empty] | MOOE | 15560 | 15550 | 10 | 15560 | 15550 | 10
| Other Supplies and Materials Expense | [19 empty] | 46IB |  | Negotiated 53.9 | [13 empty] | MOOE | 14090 | 14016 | 74 | 14090 | 14016 | 74
| RM Machinery | [19 empty] | 46IB |  | Negotiated 53.9 | [13 empty] | MOOE | 5000 | 4970 | 30 | 5000 | 4970 | 30
| RM Other Structures | [19 empty] | 46IB |  | Negotiated 53.9 | [13 empty] | MOOE | 15000 | 14940 | 60 | 15000 | 14940 | 60
| RM Office Equipment | [19 empty] | 46IB |  | Negotiated 53.9 | [13 empty] | MOOE | 2000 | 1980 | 20 | 2000 | 1980 | 20
| RM ICT Equipment | [19 empty] | 46IB |  | Negotiated 53.9 | [13 empty] | MOOE | 11000 | 10980 | 20 | 11000 | 10980 | 20
| Representation Expense | [19 empty] | 46IB |  | Negotiated 53.9 | [13 empty] | MOOE | 15560 | 15440 | 120 | 15560 | 15440 | 120
| Representation Expense | [19 empty] | 46IB |  | Negotiated 53.9 | [13 empty] | MOOE | 10500 | 10430 | 70 | 10500 | 10430 | 70
| Training Expense | [19 empty] | 46IB |  | Negotiated 53.9 | [13 empty] | MOOE | 40340 | 40240 | 100 | 40340 | 40240 | 100
| Training Expense | [19 empty] | 46IB |  | Negotiated 53.9 | [13 empty] | MOOE | 19660 | 19580 | 80 | 19660 | 19580 | 80
| Training Expense | [19 empty] | 46IB |  | Negotiated 53.9 | [13 empty] | MOOE | 40340 | 40220 | 120 | 40340 | 40220 | 120
| RM Semi-Expendable | [19 empty] | 46IB |  | Negotiated 53.9 | [13 empty] | MOOE | 20000 | 19960 | 40 | 20000 | 19960 | 40
| Internet Expense | [19 empty] | ODIG |  | Negotiated 53.9 | [13 empty] | MOOE | 4600 | 4600 | 0 | 4600 | 4600 | 0
| Training Expense | [19 empty] | 87IB |  | Negotiated 53.9 | [13 empty] | MOOE | 15000 | 14982 | 18 | 15000 | 14982 | 18
| Training Expense | [19 empty] | 87IB |  | Negotiated 53.9 | [13 empty] | MOOE | 30000 | 29997 | 3 | 30000 | 29997 | 3
| Mobile Expense | [19 empty] | 87IB |  | Negotiated 53.9 | [13 empty] | MOOE | 1000 | 1000 | 0 | 1000 | 1000 | 0
| Cable Expense | [19 empty] | 87IB |  | Negotiated 53.9 | [13 empty] | MOOE | 1000 | 1000 | 0 | 1000 | 1000 | 0
| Internet Expense | [19 empty] | 87IB |  | Negotiated 53.9 | [13 empty] | MOOE | 2000 | 2000 | 0 | 2000 | 2000 | 0
| Representation Expense | [19 empty] | 87IB |  | Negotiated 53.9 | [13 empty] | MOOE | 10000 | 10000 | 0 | 10000 | 10000 | 0
| Printing and Publication | [19 empty] | 87IB |  | Negotiated 53.9 | [13 empty] | MOOE | 5000 | 5000 | 0 | 5000 | 5000 | 0
| Representation Expense | [19 empty] | 93IIB |  | Negotiated 53.9 | [13 empty] | MOOE | 5000 | 5000 | 0 | 5000 | 5000 | 0
| RM Machinery | [19 empty] | 93IB |  | Negotiated 53.9 | [13 empty] | MOOE | 10000 | 10000 | 0 | 10000 | 10000 | 0
| Mobile Expense | [19 empty] | 93IB |  | Negotiated 53.9 | [13 empty] | MOOE | 3200 | 3200 | 0 | 3200 | 3200 | 0
| Semi-Expendable ICT Equipment | [19 empty] | 93IB |  | Negotiated 53.9 | [13 empty] | MOOE | 7000 | 7000 | 0 | 7000 | 7000 | 0
| Training Expense | [19 empty] | 93IB |  | Negotiated 53.9 | [13 empty] | MOOE | 25000 | 24996 | 4 | 25000 | 24996 | 4
| Training Expense | [19 empty] | 93IB |  | Negotiated 53.9 | [13 empty] | MOOE | 25000 | 24990 | 10 | 25000 | 24990 | 10
| Training Expense | [19 empty] | 93IB |  | Negotiated 53.9 | [13 empty] | MOOE | 27500 | 27475 | 25 | 27500 | 27475 | 25
| RM ICT Equipment | [19 empty] | CLSH |  | Negotiated 53.9 | [13 empty] | MOOE | 20000 | 19960 | 40 | 20000 | 19960 | 40
| RM ICT Equipment | [19 empty] | CLSH |  | Negotiated 53.9 | [13 empty] | MOOE | 23750 | 23725 | 25 | 23750 | 23725 | 25
| Drugs and Medicines | [19 empty] | 801BDE |  | Negotiated 53.9 | [13 empty] | MOOE | 10000 | 10000 | 0 | 10000 | 10000 | 0
| Semi-Expendable Communication | [19 empty] | 801BDE |  | Negotiated 53.9 | [13 empty] | MOOE | 10000 | 10000 | 0 | 10000 | 10000 | 0
| Cable, Sat, Tel and Radio Expense | [19 empty] | 801BDE |  | Negotiated 53.9 | [13 empty] | MOOE | 10800 | 10800 | 0 | 10800 | 10800 | 0
| ICT Software Subscription Expense | [19 empty] | 801BDE |  | Negotiated 53.9 | [13 empty] | MOOE | 2250 | 2250 | 0 | 2250 | 2250 | 0
| Internet Expense | [19 empty] | 801BDE |  | Negotiated 53.9 | [13 empty] | MOOE | 15450 | 15450 | 0 | 15450 | 15450 | 0
| Semi-Expendable-Military | [19 empty] | 801BDE |  | Negotiated 53.9 | [13 empty] | MOOE | 39900 | 39880 | 20 | 39900 | 39880 | 20
| RM Machinery | [19 empty] | 801BDE |  | Negotiated 53.9 | [13 empty] | MOOE | 39500 | 39490 | 10 | 39500 | 39490 | 10
| RM Building | [19 empty] | 801BDE |  | Negotiated 53.9 | [13 empty] | MOOE | 50000 | 49980 | 20 | 50000 | 49980 | 20
| RM Machinery | [19 empty] | OG1 |  | Negotiated 53.9 | [13 empty] | MOOE | 15000 | 15000 | 0 | 15000 | 15000 | 0
| RM Motor Vehicles | [19 empty] | OG1 |  | Negotiated 53.9 | [13 empty] | MOOE | 10000 | 9900 | 100 | 10000 | 9900 | 100
| Telephone Expense | [19 empty] | OG1 |  | Negotiated 53.9 | [13 empty] | MOOE | 4800 | 4800 | 0 | 4800 | 4800 | 0
| Internet Expense | [19 empty] | OG1 |  | Negotiated 53.9 | [13 empty] | MOOE | 2500 | 2500 | 0 | 2500 | 2500 | 0
| Telephone Expense | [19 empty] | 8DCAU |  | Negotiated 53.9 | [13 empty] | MOOE | 4500 | 4500 | 0 | 4500 | 4500 | 0
| Training Expense | [19 empty] | 8DCAU |  | Negotiated 53.9 | [13 empty] | MOOE | 45708 | 45690 | 18 | 45708 | 45690 | 18
| RM ICT Equipment | [19 empty] | 8DCAU |  | Negotiated 53.9 | [13 empty] | MOOE | 11000 | 10980 | 20 | 11000 | 10980 | 20
| RM Communication Equipment | [19 empty] | 8DCAU |  | Negotiated 53.9 | [13 empty] | MOOE | 8000 | 7992 | 8 | 8000 | 7992 | 8
| RM Motor Vehicles | [19 empty] | 8DCAU |  | Negotiated 53.9 | [13 empty] | MOOE | 15000 | 14780 | 220 | 15000 | 14780 | 220
| Training Expense | [19 empty] | 8DCAU |  | Negotiated 53.9 | [13 empty] | MOOE | 13750 | 13750 | 0 | 13750 | 13750 | 0
| Training Expense | [19 empty] | 8DCAU |  | Negotiated 53.9 | [13 empty] | MOOE | 13750 | 13750 | 0 | 13750 | 13750 | 0
| Cable, Sat, Tel and Radio Expense | [19 empty] | 8DCAU |  | Negotiated 53.9 | [13 empty] | MOOE | 9000 | 9000 | 0 | 9000 | 9000 | 0
| RM Building | [19 empty] | 8DCAU |  | Negotiated 53.9 | [13 empty] | MOOE | 41900 | 41800 | 100 | 41900 | 41800 | 100
| Training Expense | [19 empty] | 8DCAU |  | Negotiated 53.9 | [13 empty] | MOOE | 10542 | 10500 | 42 | 10542 | 10500 | 42
| RM Building | [19 empty] | 8DCAU |  | Negotiated 53.9 | [13 empty] | MOOE | 15000 | 14985 | 15 | 15000 | 14985 | 15
| Mobile Expense | [19 empty] | DPAO |  | Negotiated 53.9 | [13 empty] | MOOE | 5500 | 5500 | 0 | 5500 | 5500 | 0
| Cable, Sat, Tel and Radio Expense | [19 empty] | DPAO |  | Negotiated 53.9 | [13 empty] | MOOE | 900 | 900 | 0 | 900 | 900 | 0
| Internet Expense | [19 empty] | DPAO |  | Negotiated 53.9 | [13 empty] | MOOE | 3900 | 3900 | 0 | 3900 | 3900 | 0
| RM ICT Equipment | [19 empty] | DPAO |  | Negotiated 53.9 | [13 empty] | MOOE | 6500 | 6500 | 0 | 6500 | 6500 | 0
| Telephone Expense | [19 empty] | ODSM |  | Negotiated 53.9 | [13 empty] | MOOE | 3500 | 3500 | 0 | 3500 | 3500 | 0
| Mobile Expense | [19 empty] | OG3 |  | Negotiated 53.9 | [13 empty] | MOOE | 15000 | 15000 | 0 | 15000 | 15000 | 0
| RM ICT Equipment | [19 empty] | OG3 |  | Negotiated 53.9 | [13 empty] | MOOE | 8500 | 8500 | 0 | 8500 | 8500 | 0
| Mobile Expense | [19 empty] | OG3 |  | Negotiated 53.9 | [13 empty] | MOOE | 9000 | 9000 | 0 | 9000 | 9000 | 0
| Cable, Sat, Tel and Radio Expense | [19 empty] | OG3 |  | Negotiated 53.9 | [13 empty] | MOOE | 900 | 900 | 0 | 900 | 900 | 0
| Internet Expense | [19 empty] | OG3 |  | Negotiated 53.9 | [13 empty] | MOOE | 6000 | 6000 | 0 | 6000 | 6000 | 0
| RM ICT Equipment | [19 empty] | OG6 |  | Negotiated 53.9 | [13 empty] | MOOE | 3200 | 3200 | 0 | 3200 | 3200 | 0
| Internet Expense | [19 empty] | GSMO |  | Negotiated 53.9 | [13 empty] | MOOE | 6000 | 6000 |  | 6000 | 6000
| Mobile Expense | [19 empty] | GSMO |  | Negotiated 53.9 | [13 empty] | MOOE | 1500 | 1500 | 0 | 1500 | 1500 | 0
| Representation Expense | [19 empty] | 52IB |  | Negotiated 53.9 | [13 empty] | MOOE | 129500 | 129250 | 250 | 129500 | 129250 | 250
| RM Building | [19 empty] | 52IB |  | Negotiated 53.9 | [13 empty] | MOOE | 120000 | 119951 | 49 | 120000 | 119951 | 49
| RM Motor Vehicles | [19 empty] | 52IB |  | Negotiated 53.9 | [13 empty] | MOOE | 54000 | 53880 | 120 | 54000 | 53880 | 120
| Representation Expense | [19 empty] | 8DCAU |  | Negotiated 53.9 | [13 empty] | MOOE | 100000 | 100000 | 0 | 100000 | 100000 | 0
| RM Building | [19 empty] | 8DCAU |  | Negotiated 53.9 | [13 empty] | MOOE | 105000 | 104950 | 50 | 105000 | 104950 | 50
| Med, Den & Lab and Lab Supplies | [19 empty] | 8DCAU |  | Negotiated 53.9 | [13 empty] | MOOE | 100034.5 | 99962 | 72.5 | 100034.5 | 99962 | 72.5
| RM Building | [19 empty] | 8DCAU |  | Negotiated 53.9 | [13 empty] | MOOE | 390850 | 390500 | 350 | 390850 | 390500 | 350
| Representation Expense | [19 empty] | 46IB |  | Negotiated 53.9 | [13 empty] | MOOE | 56000 | 55776 | 224 | 56000 | 55776 | 224
| RM Building | [19 empty] | 46IB |  | Negotiated 53.9 | [13 empty] | MOOE | 134360 | 134120 | 240 | 134360 | 134120 | 240
| Semi-Expendable-Military | [19 empty] | 43IB |  | Negotiated 53.9 | [13 empty] | MOOE | 280923 | 280410 | 513 | 280923 | 280410 | 513
| Representation Expense | [19 empty] | 43IB |  | Negotiated 53.9 | [13 empty] | MOOE | 90000 | 89640 | 360 | 90000 | 89640 | 360
| Training Expense | [19 empty] | 43IB |  | Negotiated 53.9 | [13 empty] | MOOE | 95800 | 95633 | 167 | 95800 | 95633 | 167
| Representation Expense | [19 empty] | 19IB |  | Negotiated 53.9 | [13 empty] | MOOE | 125000 | 125000 | 0 | 125000 | 125000 | 0
| Training Expense | [19 empty] | 19IB |  | Negotiated 53.9 | [13 empty] | MOOE | 60000 | 59980 | 20 | 60000 | 59980 | 20
| Training Expense | [19 empty] | 19IB |  | Negotiated 53.9 | [13 empty] | MOOE | 60000 | 59500 | 500 | 60000 | 59500 | 500
| Representation Expense | [19 empty] | SSBN |  | Negotiated 53.9 | [13 empty] | MOOE | 60000 | 60000 | 0 | 60000 | 60000 | 0
| RM Motor Vehicles | [19 empty] | SSBN |  | Negotiated 53.9 | [13 empty] | MOOE | 89615 | 89603 | 12 | 89615 | 89603 | 12
| Representation Expense | [19 empty] | 20ib |  | Negotiated 53.9 | [13 empty] | MOOE | 61500 | 61500 | 0 | 61500 | 61500 | 0
| Representation Expense | [19 empty] | 87IB |  | Negotiated 53.9 | [13 empty] | MOOE | 83675 | 83393 | 282 | 83675 | 83393 | 282
| RM Building | [19 empty] | 8DTS |  | Negotiated 53.9 | [13 empty] | MOOE | 70000 | 69720 | 80 | 70000 | 69720 | 80
| RM ICT Equipment | [19 empty] | OG6 |  | Negotiated 53.9 | [13 empty] | MOOE | 100000 | 100000 | 0 | 100000 | 100000 | 0
| Representation Expense | [19 empty] | 78IB |  | Negotiated 53.9 | [13 empty] | MOOE | 80000 | 79680 | 320 | 80000 | 79680 | 320
| Other Supplies and Materials Expense | [19 empty] | 78IB |  | Negotiated 53.9 | [13 empty] | MOOE | 58410 | 58258 | 152 | 58410 | 58258 | 152
| RM Building | [19 empty] | 78IB |  | Negotiated 53.9 | [13 empty] | MOOE | 153000 | 152850 | 150 | 153000 | 152850 | 150
| Representation Expense | [19 empty] | 14IB |  | Negotiated 53.9 | [13 empty] | MOOE | 55000 | 44750 | 250 | 55000 | 44750 | 250
| RM Hospital Building | [19 empty] | CLSH |  | Negotiated 53.9 | [13 empty] | MOOE | 97500 | 96200 | 300 | 97500 | 96200 | 300
| RM Motor Vehicles | [19 empty] | CLSH |  | Negotiated 53.9 | [13 empty] | MOOE | 70000 | 69990 | 10 | 70000 | 69990 | 10
| Med, Den & Lab and Lab Supplies | [19 empty] | CLSH |  | Negotiated 53.9 | [13 empty] | MOOE | 125000 | 124990 | 10 | 125000 | 124990 | 10
| Semi-Expendable-ICT Equipment | [19 empty] | CLSH |  | Negotiated 53.9 | [13 empty] | MOOE | 79000 | 78950 | 50 | 79000 | 78950 | 50
| Med, Den & Lab and Lab Supplies | [19 empty] | CLSH |  | Negotiated 53.9 | [13 empty] | MOOE | 335077 | 334862 | 215 | 335077 | 334862 | 215
| RM Motor Vehicles | [19 empty] | 801BDE |  | Negotiated 53.9 | [13 empty] | MOOE | 262000 | 261965 | 35 | 262000 | 261965 | 35
| RM Building | [19 empty] | 801BDE |  | Negotiated 53.9 | [13 empty] | MOOE | 70000 | 69920 | 80 | 70000 | 69920 | 80
| RM Building | [19 empty] | 801BDE |  | Negotiated 53.9 | [13 empty] | MOOE | 99000 | 98100 | 900 | 99000 | 98100 | 900
| RM Building | [19 empty] | 801BDE |  | Negotiated 53.9 | [13 empty] | MOOE | 99000 | 98950 | 50 | 99000 | 98950 | 50
| Training Expense | [19 empty] | 801BDE |  | Negotiated 53.9 | [13 empty] | MOOE | 55000 | 55000 | 0 | 55000 | 55000 | 0
| Med, Den & Lab and Lab Supplies | [19 empty] | 801BDE |  | Negotiated 53.9 | [13 empty] | MOOE | 80000 | 79960 | 40 | 80000 | 79960 | 40
| RM Other Structures | [19 empty] | 803BDE |  | Negotiated 53.9 | [13 empty] | MOOE | 186000 | 185935 | 65 | 186000 | 185935 | 65
| RM Motor Vehicles | [19 empty] | 803BDE |  | Negotiated 53.9 | [13 empty] | MOOE | 181125 | 181025 | 100 | 181125 | 181025 | 100
| RM Other Structures | [19 empty] | 802BDE |  | Negotiated 53.9 | [13 empty] | MOOE | 100000 | 99830 | 170 | 100000 | 99830 | 170
| RM Building | [19 empty] | 802BDE |  | Negotiated 53.9 | [13 empty] | MOOE | 100000 | 99865 | 135 | 100000 | 99865 | 135
| RM Motor Vehicles | [19 empty] | 802BDE |  | Negotiated 53.9 | [13 empty] | MOOE | 144000 | 143720 | 280 | 144000 | 143720 | 280
| RM Building | [19 empty] | 802BDE |  | Negotiated 53.9 | [13 empty] | MOOE | 100000 | 99865 | 135 | 100000 | 99865 | 135
| Training Expense | [19 empty] | 802BDE |  | Negotiated 53.9 | [13 empty] | MOOE | 75000 | 74840 | 160 | 75000 | 74840 | 160
| Semi-Expendables ICT Equipment | [19 empty] | 3IB |  | Negotiated 53.9 | [13 empty] | MOOE | 61040 | 60500 | 540 | 61040 | 60500 | 540
| Representation Expense | [19 empty] | 63IB |  | Negotiated 53.9 | [13 empty] | MOOE | 82000 | 82000 | 0 | 82000 | 82000 | 0
| RM Building | [19 empty] | 63IB |  | Negotiated 53.9 | [13 empty] | MOOE | 175000 | 174900 | 100 | 175000 | 174900 | 100
| Med, Den & Lab and Lab Supplies | [19 empty] | Dental |  | Negotiated 53.9 | [13 empty] | MOOE | 86867.5 | 86862 | 5.5 | 86867.5 | 86862 | 5.5
| Other Supplies and Materials Expense | [19 empty] | 93IB |  | Negotiated 53.9 | [13 empty] | MOOE | 83800 | 83776 | 24 | 83800 | 83776 | 24
| Internet Expense | [19 empty] | OG4 |  | Negotiated 53.9 | [13 empty] | MOOE | 5400 | 5400 | 0 | 5400 | 5400 | 0
| Telephone Mobile Expense | [19 empty] | OG4 |  | Negotiated 53.9 | [13 empty] | MOOE | 7000 | 7000 | 0 | 7000 | 7000 | 0
| RM Motor Vehicles | [19 empty] | OG8 |  | Negotiated 53.9 | [13 empty] | MOOE | 15000 | 15000 | 0 | 15000 | 15000 | 0
| Representation Expense | [19 empty] | OG8 |  | Negotiated 53.9 | [13 empty] | MOOE | 18500 | 18500 |  | 18500 | 18500
| Internet Expense | [19 empty] | OG8 |  | Negotiated 53.9 | [13 empty] | MOOE | 3000 | 3000 | 0 | 3000 | 3000 | 0
| Telephone Mobile Expense | [19 empty] | OESPA |  | Negotiated 53.9 | [13 empty] | MOOE | 4300 | 4300 |  | 4300 | 4300
| Internet Expense | [19 empty] | DPM |  | Negotiated 53.9 | [13 empty] | MOOE | 3600 | 3600 |  | 3600 | 3600
| Training Expense | [19 empty] | 52IB |  | Negotiated 53.9 | [13 empty] | MOOE | 23000 | 23000 |  | 23000 | 23000
| Other Supplies and Materials Expense | [19 empty] | 52IB |  | Negotiated 53.9 | [13 empty] | MOOE | 30500 | 30455 | 45 | 30500 | 30455 | 45
| RM Other Structures | [19 empty] | 52IB |  | Negotiated 53.9 | [13 empty] | MOOE | 20000 | 20000 |  | 20000 | 20000
| RM ICT Equipment | [19 empty] | 52IB |  | Negotiated 53.9 | [13 empty] | MOOE | 50000 | 50000 |  | 50000 | 50000
| RM Other Machinery | [19 empty] | 52IB |  | Negotiated 53.9 | [13 empty] | MOOE | 30000 | 29960 | 40 | 30000 | 29960 | 40
| Cable, Sat, Tel and Radio Expense | [19 empty] | 8DCAU |  | Negotiated 53.9 | [13 empty] | MOOE | 9000 | 9000 | 0 | 9000 | 9000 | 0
| Subscription Expense | [19 empty] | 8DCAU |  | Negotiated 53.9 | [13 empty] | MOOE | 4000 | 4000 | 0 | 4000 | 4000 | 0
| Telephone Mobile Expense | [19 empty] | 8DCAU |  | Negotiated 53.9 | [13 empty] | MOOE | 4500 | 4500 | 0 | 4500 | 4500 | 0
| RM ICT Equipment | [19 empty] | 8DCAU |  | Negotiated 53.9 | [13 empty] | MOOE | 11000 | 10980 | 20 | 11000 | 10980 | 20
| RM Communication | [19 empty] | 8DCAU |  | Negotiated 53.9 | [13 empty] | MOOE | 8000 | 7992 | 8 | 8000 | 7992 | 8
| RM Motor Vehicles | [19 empty] | 8DCAU |  | Negotiated 53.9 | [13 empty] | MOOE | 30000 | 29969 | 31 | 30000 | 29969 | 31
| RM Machinery | [19 empty] | 8DCAU |  | Negotiated 53.9 | [13 empty] | MOOE | 15000 | 14985 | 15 | 15000 | 14985 | 15
| Internet Expense | [19 empty] | 8DCAU |  | Negotiated 53.9 | [13 empty] | MOOE | 15000 | 15000 |  | 15000 | 15000
| RM Building | [19 empty] | 8DCAU |  | Negotiated 53.9 | [13 empty] | MOOE | 50000 | 50000 |  | 50000 | 50000
| Mobile Expense | [19 empty] | ODSJA |  | Negotiated 53.9 | [13 empty] | MOOE | 4000 | 4000 |  | 4000 | 4000
| ICT Office Supply | [19 empty] | ODSJA |  | Negotiated 53.9 | [13 empty] | MOOE | 1120 | 1120 |  | 1120 | 1120
| RM ICT Equipment | [19 empty] | 46IB |  | Negotiated 53.9 | [13 empty] | MOOE | 11000 | 10980 | 20 | 11000 | 10980 | 20
| RM Office Equipment | [19 empty] | 46IB |  | Negotiated 53.9 | [13 empty] | MOOE | 2000 | 1970 | 30 | 2000 | 1970 | 30
| RM Communication Equipment | [19 empty] | 46IB |  | Negotiated 53.9 | [13 empty] | MOOE | 20000 | 19950 | 50 | 20000 | 19950 | 50
| RM Machinery | [19 empty] | 46IB |  | Negotiated 53.9 | [13 empty] | MOOE | 5000 | 4970 | 30 | 5000 | 4970 | 30
| Other Supplies and Materials Expense | [19 empty] | 46IB |  | Negotiated 53.9 | [13 empty] | MOOE | 13790 | 13790 |  | 13790 | 13790
| Representation Expense | [19 empty] | 46IB |  | Negotiated 53.9 | [13 empty] | MOOE | 14560 | 14560 |  | 14560 | 14560
| Training Expense | [19 empty] | 46IB |  | Negotiated 53.9 | [13 empty] | MOOE | 26940 | 26889 | 51 | 26940 | 26889 | 51
| Other Supplies and Materials Expense | [19 empty] | 46IB |  | Negotiated 53.9 | [13 empty] | MOOE | 3000 | 2970 | 30 | 3000 | 2970 | 30
| Training Expense | [19 empty] | 46IB |  | Negotiated 53.9 | [13 empty] | MOOE | 40340 | 40220 | 120 | 40340 | 40220 | 120
| RM Building | [19 empty] | 46IB |  | Negotiated 53.9 | [13 empty] | MOOE | 41600 | 41525 | 75 | 41600 | 41525 | 75
| Other Supplies and Materials Expense | [19 empty] | 46IB |  | Negotiated 53.9 | [13 empty] | MOOE | 3000 | 2976 | 24 | 3000 | 2976 | 24
| RM Building | [19 empty] | 46IBq |  | Negotiated 53.9 | [13 empty] | MOOE | 41600 | 41525 | 75 | 41600 | 41525 | 75
| Subscription Expense | [19 empty] | 43IB |  | Negotiated 53.9 | [13 empty] | MOOE | 8075 | 8075 |  | 8075 | 8075
| Semi-Expendable Expense-Military | [19 empty] | 43IB |  | Negotiated 53.9 | [13 empty] | MOOE | 8075 | 8075 |  | 8075 | 8075
| Training Expense | [19 empty] | 43IB |  | Negotiated 53.9 | [13 empty] | MOOE | 10000 | 10000 |  | 10000 | 10000
| Subscription Expense | [19 empty] | 43IB |  | Negotiated 53.9 | [13 empty] | MOOE | 22925 | 22825 | 100 | 22925 | 22825 | 100
| Mobile Expense | [19 empty] | OG3 |  | Negotiated 53.9 | [13 empty] | MOOE | 15000 | 15000 | 0 | 15000 | 15000 | 0
| Mobile Expense | [19 empty] | OG3 |  | Negotiated 53.9 | [13 empty] | MOOE | 15000 | 15000 |  | 15000 | 15000
| RM ICT Equipment | [19 empty] | OG3 |  | Negotiated 53.9 | [13 empty] | MOOE | 8500 | 8500 |  | 8500 | 8500
| Cable, Sat, Tel and Radio Expense | [19 empty] | OG3 |  | Negotiated 53.9 | [13 empty] | MOOE | 900 | 900 |  | 900 | 900
| Internet Expense | [19 empty] | OG3 |  | Negotiated 53.9 | [13 empty] | MOOE | 6000 | 6000 |  | 6000 | 6000
| Mobile Expense | [19 empty] | TOC |  | Negotiated 53.9 | [13 empty] | MOOE | 9000 | 9000 |  | 9000 | 9000
| Other Supplies and Materials Expense | [19 empty] | 19IB |  | Negotiated 53.9 | [13 empty] | MOOE | 27700 | 27700 |  | 27700 | 27700
| Other Supplies and Materials Expense | [19 empty] | 19IB |  | Negotiated 53.9 | [13 empty] | MOOE | 19500 | 19500 |  | 19500 | 19500
| Representation Expense | [19 empty] | 19IB |  | Negotiated 53.9 | [13 empty] | MOOE | 15800 | 15800 |  | 15800 | 15800
| Mobile Expense | [19 empty] | 19IB |  | Negotiated 53.9 | [13 empty] | MOOE | 14600 | 14600 |  | 14600 | 14600
| Mobile Expense | [19 empty] | ODIG |  | Negotiated 53.9 | [13 empty] | MOOE | 7700 | 7700 |  | 7700 | 7700
| Internet Expense | [19 empty] | ODIG |  | Negotiated 53.9 | [13 empty] | MOOE | 4600 | 4600 |  | 4600 | 4600
| Internet Expense | [19 empty] | OG2 |  | Negotiated 53.9 | [13 empty] | MOOE | 9000 | 9000 |  | 9000 | 9000
| Internet Expense | [19 empty] | OG2 |  | Negotiated 53.9 | [13 empty] | MOOE | 9000 | 9000 |  | 9000 | 9000
| Telephone Mobile Expense | [19 empty] | OG2 |  | Negotiated 53.9 | [13 empty] | MOOE | 3600 | 3600 |  | 3600 | 3600
| Cable, Sat, Tel and Radio Expense | [19 empty] | OG2 |  | Negotiated 53.9 | [13 empty] | MOOE | 1811 | 1800 | 11 | 1811 | 1800 | 11
| Cable, Sat, Tel and Radio Expense | [19 empty] | OG2 |  | Negotiated 53.9 | [13 empty] | MOOE | 900 | 900 | 0 | 900 | 900 | 0
| Representation Expense | [19 empty] | SSBN |  | Negotiated 53.9 | [13 empty] | MOOE | 45000 | 45000 |  | 45000 | 45000
| Representation Expense | [19 empty] | SSBN |  | Negotiated 53.9 | [13 empty] | MOOE | 7000 | 7000 |  | 7000 | 7000
| Training Expense | [19 empty] | SSBN |  | Negotiated 53.9 | [13 empty] | MOOE | 15000 | 15000 |  | 15000 | 15000
| Other Supplies and Materials Expense | [19 empty] | SSBN |  | Negotiated 53.9 | [13 empty] | MOOE | 30000 | 30000 |  | 30000 | 30000
| Med, Den & Lab and Lab Supplies | [19 empty] | SSBN |  | Negotiated 53.9 | [13 empty] | MOOE | 20000 | 20000 |  | 20000 | 20000
| Training Expense | [19 empty] | SSBN |  | Negotiated 53.9 | [13 empty] | MOOE | 38000 | 38000 |  | 38000 | 38000
| Semi-Expendable Communication | [19 empty] | SSBN |  | Negotiated 53.9 | [13 empty] | MOOE | 5000 | 5000 |  | 5000 | 5000
| RM DRRE Expense | [19 empty] | 20IB |  | Negotiated 53.9 | [13 empty] | MOOE | 2500 | 2500 |  | 2500 | 2500
| Other Supplies and Materials Expense | [19 empty] | 20IB |  | Negotiated 53.9 | [13 empty] | MOOE | 5000 | 5000 |  | 5000 | 5000
| Training Expense | [19 empty] | 20IB |  | Negotiated 53.9 | [13 empty] | MOOE | 7560 | 7560 |  | 7560 | 7560
| Training Expense | [19 empty] | 20IB |  | Negotiated 53.9 | [13 empty] | MOOE | 9040 | 9040 |  | 9040 | 9040
| Other Supplies and Materials Expense | [19 empty] | 20IB |  | Negotiated 53.9 | [13 empty] | MOOE | 15500 | 15500 |  | 15500 | 15500
| Other Supplies and Materials Expense | [19 empty] | 20IB |  | Negotiated 53.9 | [13 empty] | MOOE | 38870 | 38796 | 74 | 38870 | 38796 | 74
| RM Other Structures | [19 empty] | 20IB |  | Negotiated 53.9 | [13 empty] | MOOE | 15000 | 15000 |  | 15000 | 15000
| RM Building | [19 empty] | 20IB |  | Negotiated 53.9 | [13 empty] | MOOE | 20000 | 20000 |  | 20000 | 20000
| RM ICT Equipment | [19 empty] | 20IB |  | Negotiated 53.9 | [13 empty] | MOOE | 15000 | 15000 |  | 15000 | 15000
| Semi-Expendable ICT Eequipment | [19 empty] | 20IB |  | Negotiated 53.9 | [13 empty] | MOOE | 10000 | 10000 |  | 10000 | 10000
| Training Expense | [19 empty] | 20ib |  | Negotiated 53.9 | [13 empty] | MOOE | 16510 | 16510 | 0 | 16510 | 16510 | 0
| Training Expense | [19 empty] | 20IB |  | Negotiated 53.9 | [13 empty] | MOOE | 49390 | 49238 | 152 | 49390 | 49238 | 152
| Representation Expense | [19 empty] | 20ib |  | Negotiated 53.9 | [13 empty] | MOOE | 61500 | 61500 | 0 | 61500 | 61500 | 0
| RM ICT Equipment | [19 empty] | 81DRC |  | Negotiated 53.9 | [13 empty] | MOOE | 7500 | 7500 |  | 7500 | 7500
| RM ICT Equipment | [19 empty] | 81DRC |  | Negotiated 53.9 | [13 empty] | MOOE | 10000 | 10000 | 0 | 10000 | 10000 | 0
| Representation Expense | [19 empty] | 81DRC |  | Negotiated 53.9 | [13 empty] | MOOE | 1000 | 1000 | 0 | 1000 | 1000 | 0
| Training Expense | [19 empty] | 81DRC |  | Negotiated 53.9 | [13 empty] | MOOE | 4390 | 4375 | 15 | 4390 | 4375 | 15
| Training Expense | [19 empty] | 81DRC |  | Negotiated 53.9 | [13 empty] | MOOE | 4610 | 4610 | 0 | 4610 | 4610 | 0
| Representation Expense | [19 empty] | 81DRC |  | Negotiated 53.9 | [13 empty] | MOOE | 50000 | 50000 | 0 | 50000 | 50000 | 0
| Training Expense | [19 empty] | 81DRC |  | Negotiated 53.9 | [13 empty] | MOOE | 1600 | 1518 | 82 | 1600 | 1518 | 82
| Other Supplies and Materials Expense | [19 empty] | 87IB |  | Negotiated 53.9 | [13 empty] | MOOE | 4000 | 4000 |  | 4000 | 4000
| RM Motor Vehicles | [19 empty] | 8DTS |  | Negotiated 53.9 | [13 empty] | MOOE | 20000 | 19910 | 90 | 20000 | 19910 | 90
| RM Other Structures | [19 empty] | 8DTS |  | Negotiated 53.9 | [13 empty] | MOOE | 40000 | 39900 | 100 | 40000 | 39900 | 100
| Telephone Mobile Expense | [19 empty] | ODA |  | Negotiated 53.9 | [13 empty] | MOOE | 3500 | 3500 | 0 | 3500 | 3500 | 0
| Telephone Mobile Expense | [19 empty] | ODA |  | Negotiated 53.9 | [13 empty] | MOOE | 3500 | 3500 | 0 | 3500 | 3500 | 0
| RM ICT Equipment | [19 empty] | OG6 |  | Negotiated 53.9 | [13 empty] | MOOE | 5000 | 5000 |  | 5000 | 5000
| RM ICT Equipment | [19 empty] | OG6 |  | Negotiated 53.9 | [13 empty] | MOOE | 50000 | 49980 | 20 | 50000 | 49980 | 20
| RM ICT Equipment | [19 empty] | OG6 |  | Negotiated 53.9 | [13 empty] | MOOE | 3200 | 3200 |  | 3200 | 3200
| RM Motor Vehicles | [19 empty] | 78IB |  | Negotiated 53.9 | [13 empty] | MOOE | 10000 | 9960 | 40 | 10000 | 9960 | 40
| Semi-Expendable - DRRE | [19 empty] | 78IB |  | Negotiated 53.9 | [13 empty] | MOOE | 10000 | 9950 | 50 | 10000 | 9950 | 50
| Training Expense | [19 empty] | 78IB |  | Negotiated 53.9 | [13 empty] | MOOE | 40000 | 39905 | 95 | 40000 | 39905 | 95
| RM Motor Vehicles | [19 empty] | 78IB |  | Negotiated 53.9 | [13 empty] | MOOE | 15000 | 14940 | 60 | 15000 | 14940 | 60
| RM Machinery-DRRE | [19 empty] | 78IB |  | Negotiated 53.9 | [13 empty] | MOOE | 10000 | 9960 | 40 | 10000 | 9960 | 40
| Internet Expense | [19 empty] | 78IB |  | Negotiated 53.9 | [13 empty] | MOOE | 9000 | 9000 | 0 | 9000 | 9000 | 0
| Representation Expense | [19 empty] | 78ib |  | Negotiated 53.9 | [13 empty] | MOOE | 21720 | 21600 | 120 | 21720 | 21600 | 120
| Representation Expense | [19 empty] | 14IB |  | Negotiated 53.9 | [13 empty] | MOOE | 9000 | 9000 |  | 9000 | 9000
| Training Expense | [19 empty] | 14IB |  | Negotiated 53.9 | [13 empty] | MOOE | 10000 | 10000 |  | 10000 | 10000
| Training Expense | [19 empty] | 14IB |  | Negotiated 53.9 | [13 empty] | MOOE | 20000 | 20000 |  | 20000 | 20000
| Training Expense | [19 empty] | 14IB |  | Negotiated 53.9 | [13 empty] | MOOE | 38000 | 38000 |  | 38000 | 38000
| Representation Expense | [19 empty] | 14IB |  | Negotiated 53.9 | [13 empty] | MOOE | 55000 | 55000 |  | 55000 | 55000
| RM Building | [19 empty] | 14IB |  | Negotiated 53.9 | [13 empty] | MOOE | 50000 | 50000 |  | 50000 | 50000
| Training Expense | [19 empty] | 14IB |  | Negotiated 53.9 | [13 empty] | MOOE | 5000 | 5000 |  | 5000 | 5000
| Representation Expense | [19 empty] | 14IB |  | Negotiated 53.9 | [13 empty] | MOOE | 5000 | 5000 |  | 5000 | 5000
| Other Supplies and Materials Expense | [19 empty] | 14IB |  | Negotiated 53.9 | [13 empty] | MOOE | 47500 | 47500 |  | 47500 | 47500
| Mobile Expense | [19 empty] | 14IB |  | Negotiated 53.9 | [13 empty] | MOOE | 6000 | 6000 |  | 6000 | 6000
| Semi-Expendable - ICT Equipment | [19 empty] | 14IB |  | Negotiated 53.9 | [13 empty] | MOOE | 40000 | 40000 |  | 40000 | 40000
| Semi-Expendable -DRRE | [19 empty] | 14IB |  | Negotiated 53.9 | [13 empty] | MOOE | 30000 | 29885 | 15 | 30000 | 29885 | 15
| Cable, Sat, Tel and Radio Expense | [19 empty] | 14IB |  | Negotiated 53.9 | [13 empty] | MOOE | 4500 | 4500 |  | 4500 | 4500
| Internet Expense | [19 empty] | 14IB |  | Negotiated 53.9 | [13 empty] | MOOE | 9000 | 9000 |  | 9000 | 9000
| RM ICT Equipment | [19 empty] | CLSH |  | Negotiated 53.9 | [13 empty] | MOOE | 23750 | 23725 | 25 | 23750 | 23725 | 25
| RM Motor Vehicles | [19 empty] | CLSH |  | Negotiated 53.9 | [13 empty] | MOOE | 70000 | 69990 | 10 | 70000 | 69990 | 10
| Training Expense | [19 empty] | CLSH |  | Negotiated 53.9 | [13 empty] | MOOE | 27500 | 27312 | 188 | 27500 | 27312 | 188
| Representation Expense | [19 empty] | CLSH |  | Negotiated 53.9 | [13 empty] | MOOE | 14500 | 14494 | 6 | 14500 | 14494 | 6
| Telephone Mobile Expense | [19 empty] | CLSH |  | Negotiated 53.9 | [13 empty] | MOOE | 12900 | 12900 | 0 | 12900 | 12900 | 0
| Subscription Expense | [19 empty] | CLSH |  | Negotiated 53.9 | [13 empty] | MOOE | 3800 | 3800 | 0 | 3800 | 3800 | 0
| ICT Office Supply | [19 empty] | CLSH |  | Negotiated 53.9 | [13 empty] | MOOE | 4300 | 4300 | 0 | 4300 | 4300 | 0
| Semi-Expebdable-Furnitures | [19 empty] | CLSH |  | Negotiated 53.9 | [13 empty] | MOOE | 6900 | 6900 | 0 | 6900 | 6900 | 0
| Mobile Expense | [19 empty] | 801BDE |  | Negotiated 53.9 | [13 empty] | MOOE | 9000 | 9000 | 0 | 9000 | 9000 | 0
| Internet Expense | [19 empty] | 801BDE |  | Negotiated 53.9 | [13 empty] | MOOE | 15450 | 15000 | 450 | 15450 | 15000 | 450
| Cable, Sat, Tel and Radio Expense | [19 empty] | 801BDE |  | Negotiated 53.9 | [13 empty] | MOOE | 10800 | 10800 | 0 | 10800 | 10800 | 0
| Med, Den & Lab and Lab Supplies | [19 empty] | 801BDE |  | Negotiated 53.9 | [13 empty] | MOOE | 10000 | 9990 | 10 | 10000 | 9990 | 10
| Semi-Expendable- Communication | [19 empty] | 801BDE |  | Negotiated 53.9 | [13 empty] | MOOE | 10000 | 10000 | 0 | 10000 | 10000 | 0
| Drug and Medicines Expense | [19 empty] | 801BDE |  | Negotiated 53.9 | [13 empty] | MOOE | 10000 | 10000 | 0 | 10000 | 10000 | 0
| ICT Expense | [19 empty] | 801BDE |  | Negotiated 53.9 | [13 empty] | MOOE | 23250 | 23250 | 0 | 23250 | 23250 | 0
| RM ICT Equipment | [19 empty] | 801BDE |  | Negotiated 53.9 | [13 empty] | MOOE | 39500 | 39475 | 25 | 39500 | 39475 | 25
| Representation Expense | [19 empty] | 801BDE |  | Negotiated 53.9 | [13 empty] | MOOE | 10000 | 10000 | 0 | 10000 | 10000 | 0
| Cable, Sat, Tel and Radio Expense | [19 empty] | 83DRC |  | Negotiated 53.9 | [13 empty] | MOOE | 1500 | 1500 |  | 1500 | 1500
| Other Supplies and Materials Expense | [19 empty] | 83DRC |  | Negotiated 53.9 | [13 empty] | MOOE | 5000 | 5000 |  | 5000 | 5000
| Training Expense | [19 empty] | 83DRC |  | Negotiated 53.9 | [13 empty] | MOOE | 22500 | 22500 |  | 22500 | 22500
| Representation Expense | [19 empty] | 83DRC |  | Negotiated 53.9 | [13 empty] | MOOE | 25000 | 25000 |  | 25000 | 25000
| Med, Den & Lab and Lab Supplies | [19 empty] | 803BDE |  | Negotiated 53.9 | [13 empty] | MOOE | 20000 | 20000 | 0 | 20000 | 20000 | 0
| Cable, Sat, Tel and Radio Expense | [19 empty] | 803BDE |  | Negotiated 53.9 | [13 empty] | MOOE | 4000 | 4000 | 0 | 4000 | 4000 | 0
| Semi-Expendable - ICT Equipment | [19 empty] | 803BDE |  | Negotiated 53.9 | [13 empty] | MOOE | 23500 | 23500 | 0 | 23500 | 23500 | 0
| Med, Den & Lab and Lab Supplies | [19 empty] | 803BDE |  | Negotiated 53.9 | [13 empty] | MOOE | 18000 | 17960 | 40 | 18000 | 17960 | 40
| Drug and Medicines Expense | [19 empty] | 803BDE |  | Negotiated 53.9 | [13 empty] | MOOE | 20000 | 19994 | 6 | 20000 | 19994 | 6
| Subscription Expense | [19 empty] | 803BDE |  | Negotiated 53.9 | [13 empty] | MOOE | 12000 | 12000 | 0 | 12000 | 12000 | 0
| RM Machinery Equipment | [19 empty] | 803BDE |  | Negotiated 53.9 | [13 empty] | MOOE | 11125 | 11125 | 0 | 11125 | 11125 | 0
| RM Communication Equipment | [19 empty] | 803BDE |  | Negotiated 53.9 | [13 empty] | MOOE | 8000 | 7960 | 40 | 8000 | 7960 | 40
| RM ICT Equipment | [19 empty] | 803BDE |  | Negotiated 53.9 | [13 empty] | MOOE | 45250 | 45240 | 10 | 45250 | 45240 | 10
| RM Office Equipment | [19 empty] | 803BDE |  | Negotiated 53.9 | [13 empty] | MOOE | 7000 | 7000 | 0 | 7000 | 7000 | 0
| RM Building | [19 empty] | 803BDE |  | Negotiated 53.9 | [13 empty] | MOOE | 37500 | 37460 | 40 | 37500 | 37460 | 40
| Other Supplies and Materials Expense | [19 empty] | 8CMO |  | Negotiated 53.9 | [13 empty] | MOOE | 20000 | 20000 |  | 20000 | 20000
| RM ICT Equipment | [19 empty] | 8CMO |  | Negotiated 53.9 | [13 empty] | MOOE | 6000 | 6000 |  | 6000 | 6000
| Training Expense | [19 empty] | 8CMO |  | Negotiated 53.9 | [13 empty] | MOOE | 6000 | 6000 |  | 6000 | 6000
| Representation Expense | [19 empty] | 8CMO |  | Negotiated 53.9 | [13 empty] | MOOE | 48500 | 48500 |  | 48500 | 48500
| RM Building | [19 empty] | 8CMO |  | Negotiated 53.9 | [13 empty] | MOOE | 35000 | 35000 |  | 35000 | 35000
| ICT Office Supply | [19 empty] | 8CMO |  | Negotiated 53.9 | [13 empty] | MOOE | 29850 | 29850 |  | 29850 | 29850
| Telephone Mobile Expense | [19 empty] | 8CMO |  | Negotiated 53.9 | [13 empty] | MOOE | 10000 | 10000 |  | 10000 | 10000
| Telephone Mobile Expense | [19 empty] | 8CMO |  | Negotiated 53.9 | [13 empty] | MOOE | 30000 | 30000 | 0 | 30000 | 30000 | 0
| Internet Expense | [19 empty] | DPAO |  | Negotiated 53.9 | [13 empty] | MOOE | 3900 | 3900 | 0 | 3900 | 3900 | 0
| Cable, Sat, Tel and Radio Expense | [19 empty] | DPAO |  | Negotiated 53.9 | [13 empty] | MOOE | 900 | 900 |  | 900 | 900
| RM ICT Equipment | [19 empty] | DPAO |  | Negotiated 53.9 | [13 empty] | MOOE | 6500 | 6500 |  | 6500 | 6500
| Mobile Expense | [19 empty] | DPAO |  | Negotiated 53.9 | [13 empty] | MOOE | 5500 | 5500 |  | 5500 | 5500
| Mobile Expense | [19 empty] | GADO |  | Negotiated 53.9 | [13 empty] | MOOE | 6600 | 6600 |  | 6600 | 6600
| Telephone Mobile Expense | [19 empty] | OG7 |  | Negotiated 53.9 | [13 empty] | MOOE | 9000 | 9000 | 0 | 9000 | 9000 | 0
| Internet Expense | [19 empty] | OG7 |  | Negotiated 53.9 | [13 empty] | MOOE | 15000 | 15000 |  | 15000 | 15000
| Telephone Mobile Expense | [19 empty] | OG7 |  | Negotiated 53.9 | [13 empty] | MOOE | 3000 | 3000 |  | 3000 | 3000
| Telephone Mobile Expense | [19 empty] | OG7 |  | Negotiated 53.9 | [13 empty] | MOOE | 9000 | 9000 |  | 9000 | 9000
| Semi-Expendable- ICT Equipment | [19 empty] | OG7 |  | Negotiated 53.9 | [13 empty] | MOOE | 28200 | 28200 | 0 | 28200 | 28200 | 0
| Telephone Mobile Expense | [19 empty] | OG7 |  | Negotiated 53.9 | [13 empty] | MOOE | 4000 | 4000 | 0 | 4000 | 4000 | 0
| RM Machinery | [19 empty] | OG7 |  | Negotiated 53.9 | [13 empty] | MOOE | 21400 | 21350 | 50 | 21400 | 21350 | 50
| RM Building | [19 empty] | OG7 |  | Negotiated 53.9 | [13 empty] | MOOE | 5200 | 5200 | 0 | 5200 | 5200 | 0
| RM Motor Vehicles | [19 empty] | OG7 |  | Negotiated 53.9 | [13 empty] | MOOE | 8000 | 8000 | 0 | 8000 | 8000 | 0
| Representation Expense | [19 empty] | 802BDE |  | Negotiated 53.9 | [13 empty] | MOOE | 19738 | 19550 | 188 | 19738 | 19550 | 188
| Mobile Expense | [19 empty] | 802BDE |  | Negotiated 53.9 | [13 empty] | MOOE | 49500 | 49500 | 0 | 49500 | 49500 | 0
| Internet Expense | [19 empty] | 802BDE |  | Negotiated 53.9 | [13 empty] | MOOE | 33000 | 33000 | 0 | 33000 | 33000 | 0
| Med, Den & Lab and Lab Supplies | [19 empty] | 802BDE |  | Negotiated 53.9 | [13 empty] | MOOE | 6000 | 5920 | 80 | 6000 | 5920 | 80
| Telephone Mobile Expense | [19 empty] | OG1 |  | Negotiated 53.9 | [13 empty] | MOOE | 4800 | 4800 |  | 4800 | 4800
| Internet Expense | [19 empty] | OG1 |  | Negotiated 53.9 | [13 empty] | MOOE | 2500 | 2500 |  | 2500 | 2500
| RM ICT Equipment | [19 empty] | OG1 |  | Negotiated 53.9 | [13 empty] | MOOE | 15000 | 15000 |  | 15000 | 15000
| RM Motor Vehicles | [19 empty] | OG1 |  | Negotiated 53.9 | [13 empty] | MOOE | 10000 | 9995 | 5 | 10000 | 9995 | 5
| Telephone Mobile Expense | [19 empty] | OG1 |  | Negotiated 53.9 | [13 empty] | MOOE | 11600 | 11600 |  | 11600 | 11600
| RM Machinery | [19 empty] | OG1 |  | Negotiated 53.9 | [13 empty] | MOOE | 15000 | 15000 |  | 15000 | 15000
| Semi-Expendable ICT Eequipment | [19 empty] | OG1 |  | Negotiated 53.9 | [13 empty] | MOOE | 30539 | 30539 |  | 30539 | 30539
| Semi-Expendable ICT Eequipment | [19 empty] | OG1 |  | Negotiated 53.9 | [13 empty] | MOOE | 18646.23 | 18646.23 |  | 18646.23 | 18646.23
| Cable, Sat, Tel and Radio Expense | [19 empty] | OG1 |  | Negotiated 53.9 | [13 empty] | MOOE | 900 | 900 | 0 | 900 | 900 | 0
| Cable, Sat, Tel and Radio Expense | [19 empty] | OG1 |  | Negotiated 53.9 | [13 empty] | MOOE | 900 | 900 |  | 900 | 900
| Semi-Expendable Office Equipment | [19 empty] | OG1 |  | Negotiated 53.9 | [13 empty] | MOOE | 15000 | 15000 |  | 15000 | 15000
| RM Motor Vehicles | [19 empty] | OG1 |  | Negotiated 53.9 | [13 empty] | MOOE | 10000 | 9998 | 2 | 10000 | 9998 | 2
| Internet Expense | [19 empty] | CPO |  | Negotiated 53.9 | [13 empty] | MOOE | 4000 | 4000 |  | 4000 | 4000
| Telephone Mobile Expense | [19 empty] | CPO |  | Negotiated 53.9 | [13 empty] | MOOE | 1500 | 1500 |  | 1500 | 1500
| Internet Expense | [19 empty] | MWRC |  | Negotiated 53.9 | [13 empty] | MOOE | 3900 | 3900 |  | 3900 | 3900
| Telephone Mobile Expense | [19 empty] | TAP |  | Negotiated 53.9 | [13 empty] | MOOE | 8400 | 8400 | 0 | 8400 | 8400 | 0
| Internet Expense | [19 empty] | GSMO |  | Negotiated 53.9 | [13 empty] | MOOE | 6000 | 6000 | 0 | 6000 | 6000 | 0
| Mobile Expense | [19 empty] | GSMO |  | Negotiated 53.9 | [13 empty] | MOOE | 1500 | 1500 |  | 1500 | 1500
| Training Expense | [19 empty] | 82DRC |  | Negotiated 53.9 | [13 empty] | MOOE | 6300 | 6270 | 30 | 6300 | 6270 | 30
| Representation Expense | [19 empty] | 82DRC |  | Negotiated 53.9 | [13 empty] | MOOE | 20000 | 19920 | 80 | 20000 | 19920 | 80
| Training Expense | [19 empty] | 82DRC |  | Negotiated 53.9 | [13 empty] | MOOE | 2000 | 1965 | 35 | 2000 | 1965 | 35
| Training Expense | [19 empty] | 82DRC |  | Negotiated 53.9 | [13 empty] | MOOE | 20000 | 19874 | 126 | 20000 | 19874 | 126
| Other Supplies and Materials Expense | [19 empty] | 82DRC |  | Negotiated 53.9 | [13 empty] | MOOE | 6500 | 6457 | 43 | 6500 | 6457 | 43
| Military, Police and Security Expense | [19 empty] | 82DRC |  | Negotiated 53.9 | [13 empty] | MOOE | 15000 | 14960 | 40 | 15000 | 14960 | 40
| Training Expense | [19 empty] | 82DRC |  | Negotiated 53.9 | [13 empty] | MOOE | 30000 | 29900 | 100 | 30000 | 29900 | 100
| Cable, Sat, Tel and Radio Expense | [19 empty] | 63IB |  | Negotiated 53.9 | [13 empty] | MOOE | 6000 | 6000 | 0 | 6000 | 6000 | 0
| Other Supplies and Materials Expense | [19 empty] | 63IB |  | Negotiated 53.9 | [13 empty] | MOOE | 29500 | 29370 | 130 | 29500 | 29370 | 130
| RM Machinery | [19 empty] | 63IB |  | Negotiated 53.9 | [13 empty] | MOOE | 3000 | 2980 | 20 | 3000 | 2980 | 20
| RM Machinery | [19 empty] | Dental |  | Negotiated 53.9 | [13 empty] | MOOE | 31400 | 31300 | 100 | 31400 | 31300 | 100
| RM ICT Equipment | [19 empty] | Dental |  | Negotiated 53.9 | [13 empty] | MOOE | 5824.75 | 5824 | 0.75 | 5824.75 | 5824 | 0.75
| Representation Expense | [19 empty] | 93IB |  | Negotiated 53.9 | [13 empty] | MOOE | 45000 | 45000 | 0 | 45000 | 45000 | 0
| Semi-Expendable - ICT Equipment | [19 empty] | 93IB |  | Negotiated 53.9 | [13 empty] | MOOE | 7000 | 7000 | 0 | 7000 | 7000 | 0
| Mobile Expense | [19 empty] | 93IB |  | Negotiated 53.9 | [13 empty] | MOOE | 3200 | 3200 | 0 | 3200 | 3200 | 0
| Training Expense | [19 empty] | 93IB |  | Negotiated 53.9 | [13 empty] | MOOE | 20000 | 19985 | 15 | 20000 | 19985 | 15
| Training Expense | [19 empty] | 93IB |  | Negotiated 53.9 | [13 empty] | MOOE | 15000 | 14990 | 10 | 15000 | 14990 | 10
| Training Expense | [19 empty] | 93IB |  | Negotiated 53.9 | [13 empty] | MOOE | 20000 | 19996 | 4 | 20000 | 19996 | 4
| RM Machinery | [19 empty] | 93IB |  | Negotiated 53.9 | [13 empty] | MOOE | 10000 | 10000 | 0 | 10000 | 10000 | 0
| RM Other Structures | [19 empty] | 93IB |  | Negotiated 53.9 | [13 empty] | MOOE | 40000 | 39976 | 24 | 40000 | 39976 | 24
| RM Building | [19 empty] | 93IB |  | Negotiated 53.9 | [13 empty] | MOOE | 45000 | 44997 | 3 | 45000 | 44997 | 3
| Training Expense | [19 empty] | 93IB |  | Negotiated 53.9 | [13 empty] | MOOE | 10000 | 10000 | 0 | 10000 | 10000 | 0
| RM Motor Vehicles | [19 empty] | Chaplain |  | Negotiated 53.9 | [13 empty] | MOOE | 3000 | 3000 |  | 3000 | 3000
| Cable Expense | [19 empty] | 87IB |  | Negotiated 53.9 | [13 empty] | MOOE | 1500 | 1500 | 0 | 1500 | 1500 | 0
| Telephone Mobile Expense | [19 empty] | 87IB |  | Negotiated 53.9 | [13 empty] | MOOE | 2000 | 2000 | 0 | 2000 | 2000 | 0
| Internet Expense | [19 empty] | 87IB |  | Negotiated 53.9 | [13 empty] | MOOE | 3000 | 3000 | 0 | 3000 | 3000 | 0
| Training Expense | [19 empty] | 87IB |  | Negotiated 53.9 | [13 empty] | MOOE | 40000 | 39997 | 3 | 40000 | 39997 | 3
| Representation Expense | [19 empty] | 87IB |  | Negotiated 53.9 | [13 empty] | MOOE | 50000 | 50000 | 0 | 50000 | 50000 | 0
| Training Expense | [19 empty] | 87IB |  | Negotiated 53.9 | [13 empty] | MOOE | 8000 | 7995 | 5 | 8000 | 7995 | 5
| Printing and Publication | [19 empty] | 87IB |  | Negotiated 53.9 | [13 empty] | MOOE | 2500 | 2500 | 0 | 2500 | 2500 | 0
| Other Supplies and Materials Expense | [19 empty] | 87IB |  | Negotiated 53.9 | [13 empty] | MOOE | 4000 | 4000 | 0 | 4000 | 4000 | 0
Total Alloted Budget of Procurement Activities | [40 empty] | 19333734.33
Total Contract Price of Procurement Actitvites Conducted | [40 empty] | 19216294.23
Total Savings (Total Alloted Budget - Total Contract Price) | [37 empty] | 26135.1
0N-GOING PROCUREMENT ACTIVITIES
0
0
0
Total Alloted Budget of On-going Procurement Activities | [37 empty] | 0
| Prepared By: |  |  |  |  | CERTIFIED CORRECT BY: |  |  |  | NOTED BY: | [20 empty] | CERTIFIED CORRECT BY: | [9 empty] | NOTED BY:
|  | Roberto B Lucaban |  |  |  |  | Sonny Boy P Nazareno |  |  |  | JESUS A REYES JR
|  | SSg (OS) PA |  |  |  |  | Msg (QMS) PA |  |  |  | CPT (FS) PA | [19 empty] | Sonny Boy P Nazareno | [9 empty] | JESUS A REYES JR
| Roberto B Lucaban | [5 empty] | Chief, Clerk |  |  |  | Chief/Commanding Officer | [19 empty] | Msg (QMS) PA | [9 empty] | CPT (FS) PA
| SSg (OS) PA | [29 empty] | Chief, Clerk | [9 empty] | Commanding Officer
Operations NCO