## pmr
HEADQUARTRERS
|  | ANNEX A | [29 empty] | HEADQUARTERS & HEADQUARTERS SUPPORT GROUP, PA
Fort Bonifacio, Metro Manila
|  | Department of Budget and Management Annual Procurement Plan for FY 2006 | [29 empty] | Procurement Monitoring Report as of December 31, 2022
Code (PAP) | Procurement Project | PMO/ End-User | Mode of Procurement | Schedule for Each Procurement Activity | [11 empty] | Source of Funds | ABC (PhP) |  |  | Remarks (brief description of Program/Project) | PMO/ End-User | Is this an Early Procurement Activity? | Mode of Procurement | Actual Procurement Activity | [12 empty] | Source of Funds | ABC (PhP) |  |  | Contract Cost (PhP) |  |  | List of Invited Observers | Date of Receipt of Invitation | [5 empty] | Remarks (Explaining changes from the APP)
|  |  |  | Pre-Proc Conference | Ads/Post of IAEB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Contract Award | Contract Signing | Notice to Proceed | Delivery/ Accept | Payment Process |  | Total | MOOE | CO |  |  |  |  | Pre-Proc Conference | Ads/Post of IB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Date of BAC Resolution Recommending Award | Notice of Award | Contract Signing | Notice to Proceed | Delivery/ Completion | Inspection & Acceptance |  | Total | MOOE | CO | Total | MOOE | CO |  | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Delivery/ Completion/ Acceptance (If applicable)
COMPLETED PROCUREMENT ACTIVITIES
| S/D of 15 pcs Hardiflex 1/4" x 4' x 8' & 19 others | [19 empty] | HHSG | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-07-01 | 2022-07-01 | 2022-07-29 | 2022-08-05 | 2022-08-05 | GoP | 45936.75 | 45936.75 | 0 | 45661.75 | 45661.75 | 0 | [7 empty] | N/A
| S/D of 10 sets of LED Flood Light 50w IP66 WHS Type warm white and 14 others | [19 empty] | HHSG | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-07-29 | 2022-07-29 | 2022-09-05 | 2022-09-12 | 2022-09-12 | GoP | 100818 | 100818 | 0 | 99218 | 99218 | 0 | [7 empty] | N/A
| S/D of 60 pcs 4MP Fixed Bullet Network Camera and 4 others | [19 empty] | HHSG | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-07-29 | 2022-07-29 | 2022-08-10 | 2022-08-17 | 2022-08-17 | GoP | 900000 | 900000 | 0 | 890500 | 890500 | 0 | [7 empty] | N/A
| S/D of Desktop All-In-One Touchscreen Core i3 and 2 others | [19 empty] | HHSG | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-07-29 | 2022-07-29 | 2022-09-05 | 2022-09-12 | 2022-09-12 | GoP | 200000 | 200000 | 0 | 195920 | 195920 | 0 | [7 empty] | N/A
| S/D of 50 pcs Metal Furring 1 x 2 x 16 & 68 others | [19 empty] | HHSG | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-07-29 | 2022-07-29 | 2022-09-09 | 2022-09-16 | 2022-09-16 | GoP | 200000 | 200000 | 0 | 199275 | 199275 | 0 | [7 empty] | N/A
| S/D of 10 pcs 1/2'' x 1'' x 8' Lumber (nosing) (Alpha-0421) and 501 others | [19 empty] | HHSG | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-07-29 | 2022-07-29 | 2022-09-14 | 2022-09-21 | 2022-09-21 | GoP | 499385 | 499385 | 0 | 494625 | 494625 | 0 | [7 empty] | N/A
| S/D of 13 bags Cement and 57 others | [19 empty] | HHSG | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-08-02 | 2022-08-02 | 2022-09-01 | 2022-09-08 | 2022-09-08 | GoP | 342500 | 342500 | 0 | 340921 | 340921 | 0 | [7 empty] | N/A
| S/D 100 boxes Bond Paper 80gsm Size:210mm x 297mm (A4) & 26 others | [19 empty] | HHSG | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-08-09 | 2022-08-09 | 2022-08-31 | 2022-09-07 | 2022-09-07 | GoP | 342092 | 342092 | 0 | 340192 | 340192 | 0 | [7 empty] | N/A
| S/D of 1 pc Oil Filter Toyota Hi-lux SHF-315 and 74 others | [19 empty] | HHSG | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-08-09 | 2022-08-09 | 2022-09-12 | 2022-09-19 | 2022-09-19 | GoP | 528500 | 528500 | 0 | 518500 | 518500 | 0 | [7 empty] | N/A
| S/D of 4 ea 2TB Sata 64MB NAS Hard Drive and 4 others | [19 empty] | HHSG | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-08-09 | 2022-08-09 | 2022-09-12 | 2022-09-19 | 2022-09-19 | GoP | 163940 | 163940 | 0 | 162940 | 162940 | 0 | [7 empty] | N/A
| SD of 21 pcs Globe1000 & 3 others | [19 empty] | HHSG | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-08-16 | 2022-08-16 | 2022-09-09 | 2022-09-16 | 2022-09-16 | GoP | 72000 | 72000 | 0 | 71790 | 71790 | 0 | [7 empty] | N/A
| S/D of 29 sets of Lamp Post 4mts Galvanized Steel Tempered Glass Top Frosted White and 23 others | [19 empty] | HHSG | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-08-24 | 2022-08-24 | 2022-10-06 | 2022-10-13 | 2022-10-13 | GoP | 997726 | 997726 | 0 | 993005 | 993005 | 0 | [7 empty] | N/A
| S/D of 600 bags Portland Cement and 28 others | [19 empty] | HHSG | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-08-24 | 2022-08-24 | 2022-10-07 | 2022-10-14 | 2022-10-14 | GoP | 721380 | 721380 | 0 | 713935 | 713935 | 0 | [7 empty] | N/A
| S/D of 125 sets Curtains with Rings (W:58 inch L: 97inch | [19 empty] | HHSG | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-08-31 | 2022-08-31 | 2022-10-03 | 2022-10-10 | 2022-10-10 | GoP | 237500 | 237500 | 0 | 236250 | 236250 | 0 | [7 empty] | N/A
| S/D of 1 pc Oil Filter & & 12 others | [19 empty] | HHSG | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-09-02 | 2022-09-02 | 2022-10-06 | 2022-10-13 | 2022-10-13 | GoP | 25870 | 25870 | 0 | 24370 | 24370 | 0 | [7 empty] | N/A
| S/D of one (1) unit Main Distribution Panel (MDP) with 225 Amps 2 pole 250 AF (main ) and the ff branches 1-125 amps 250 AF 2 pole 1-100 100 amps 250 AF 2 pole 1-60 amp 250 AF 2 pole 1 -spare and 37 others | [19 empty] | HHSG | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-09-09 | 2022-09-09 | 2022-10-06 | 2022-10-13 | 2022-10-13 | GoP | 571181 | 571181 | 0 | 565931 | 565931 | 0 | [7 empty] | N/A
| S/D of 5 pcs UHF/FM Base Radio and 1 other | [19 empty] | HHSG | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-09-13 | 2022-09-13 | 2022-10-28 | 2022-11-04 | 2022-11-04 | GoP | 567500 | 567500 | 0 | 558900 | 558900 | 0 | [7 empty] | N/A
| S/D of 1 set Front Brake Pad Kit & 6 others | [19 empty] | HHSG | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-09-13 | 2022-09-13 | 2022-10-28 | 2022-11-04 | 2022-11-04 | GoP | 57650 | 57650 | 0 | 56905 | 56905 | 0 | [7 empty] | N/A
| S/D of 10 pcs MS Plate 4mm x 4ft x 8ft & 17 others | [19 empty] | HHSG | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-09-13 | 2022-09-13 | 2022-10-12 | 2022-10-19 | 2022-10-19 | GoP | 256739 | 256739 | 0 | 254839 | 254839 | 0 | [7 empty] | N/A
| RENTAL SERVICES | [19 empty] | HHSG | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-09-20 | 2022-09-20 | 2022-11-16 | 2022-11-23 | 2022-11-23 | GoP | 72000 | 72000 | 0 | 71000 | 71000 | 0 | [7 empty] | N/A
| S/D of Microsoft Office - Home and Student & 8 others | [19 empty] | HHSG | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-09-20 | 2022-09-20 | 2022-10-06 | 2022-10-13 | 2022-10-13 | GoP | 106300 | 106300 | 0 | 105670 | 105670 | 0 | [7 empty] | N/A
| S/D of 50 boxes Pastries Mamon Twin Pack 44gx6x12 and 22 others | [19 empty] | HHSG | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-09-20 | 2022-09-20 | 2022-10-06 | 2022-10-13 | 2022-10-13 | GoP | 246125 | 246125 | 0 | 239900 | 239900 | 0 | [7 empty] | N/A
| S/D of Trashbag Plastic 10s per pack and 38 others | [19 empty] | HHSG | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-09-20 | 2022-09-20 | 2022-10-03 | 2022-10-10 | 2022-10-10 | GoP | 584950 | 584950 | 0 | 581175 | 581175 | 0 | [7 empty] | N/A
| S/D of Cell Card Globe 500 and 5 others | [19 empty] | HHSG | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-09-20 | 2022-09-20 | 2022-10-06 | 2022-10-13 | 2022-10-13 | GoP | 284200 | 284200 | 0 | 283179 | 283179 | 0 | [7 empty] | N/A
| S/D of 50 pcs Ficem Board 1/4" x 4' x 8' and 26 others | [19 empty] | HHSG | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-09-23 | 2022-09-23 | 2022-10-12 | 2022-10-19 | 2022-10-19 | GoP | 246434 | 246434 | 0 | 242434 | 242434 | 0 | [7 empty] | N/A
| S/D of 4 units 5TR Compressor Motor & 4 others | [19 empty] | HHSG | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-09-23 | 2022-09-23 | 2022-10-06 | 2022-10-13 | 2022-10-13 | GoP | 106000 | 106000 | 0 | 103200 | 103200 | 0 | [7 empty] | N/A
| S/D of 1 unit Aircon compressor assy Toyota Vios NQA 607 and 54 others | [19 empty] | HHSG | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-09-30 | 2022-09-30 | 2022-10-17 | 2022-10-24 | 2022-10-24 | GoP | 548600 | 548600 | 0 | 545000 | 545000 | 0 | [7 empty] | N/A
| S/D of 1200 ream Paper Multicopy/Multi-purpose 80GSM A4 210mmx297mm & 4 others | [19 empty] | HHSG | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-10-11 | 2022-10-11 | 2022-11-04 | 2022-11-11 | 2022-11-11 | GoP | 478365 | 478365 | 0 | 472698 | 472698 | 0 | [7 empty] | N/A
| S/D of 3 pcs 1TB Solid-state Drive (SSD) and 4 others | [19 empty] | HHSG | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-10-11 | 2022-10-11 | 2022-10-27 | 2022-11-03 | 2022-11-03 | GoP | 51960 | 51960 | 0 | 51510 | 51510 | 0 | [7 empty] | N/A
| S/D of 12 bags Portland cement and 19 others | [19 empty] | HHSG | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-10-21 | 2022-10-21 | 2022-11-14 | 2022-11-21 | 2022-11-21 | GoP | 348440 | 348440 | 0 | 343640 | 343640 | 0 | [7 empty] | N/A
| S/D of 200 boxes SARS-CoV-2 Antigen Assay Test (Colloidal Gold Method) 20s | [19 empty] | HHSG | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-10-21 | 2022-10-21 | 2022-11-18 | 2022-11-25 | 2022-11-25 | GoP | 1000000 | 1000000 | 0 | 980000 | 980000 | 0 | [7 empty] | N/A
| S/D of 90 sq mtrs Pre-Painted Rib-Type Roof no 24 and 47 others | [19 empty] | HHSG | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-10-28 | 2022-10-28 | 2022-11-29 | 2022-12-06 | 2022-12-06 | GoP | 986316 | 986316 | 0 | 985816 | 985816 | 0 | [7 empty] | N/A
| S/D of 6 pcs Tire 9.00x20 (EN: 6HK1-867995) and 3 others | [19 empty] | HHSG | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-11-09 | 2022-11-09 | 2022-11-25 | 2022-12-02 | 2022-12-02 | GoP | 410400 | 410400 | 0 | 403200 | 403200 | 0 | [7 empty] | N/A
| S/D of 4 pcs DM5 SE Loud Speaker & 5 others | [19 empty] | HHSG | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-11-09 | 2022-11-09 | 2022-11-29 | 2022-12-06 | 2022-12-06 | GoP | 793356 | 793356 | 0 | 789382 | 789382 | 0 | [7 empty] | N/A
| S/D of 1 ea Filter drier (EN 4D33-L23635) & 124 others | [19 empty] | HHSG | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-11-09 | 2022-11-09 | 2022-12-09 | 2022-12-16 | 2022-12-16 | GoP | 593048 | 593048 | 0 | 589288 | 589288 | 0 | [7 empty] | N/A
| S/D of 400 pcs Lawn Rake Plastic 24 Teeth | [19 empty] | HSBN, HHSG | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-08-12 | 2022-08-12 | 2022-09-09 | 2022-09-16 | 2022-09-16 | GoP | 190192 | 190192 | 0 | 188000 | 188000 | 0 | [7 empty] | N/A
| S/D of 30 reams Bond Paper (A4) 8 1/4" x 11 3/4" 5 reams & 31 others | [19 empty] | HSBN, HHSG | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-08-24 | 2022-08-24 | 2022-10-12 | 2022-10-19 | 2022-10-19 | GoP | 95773.25 | 95773.25 | 0 | 94273.25 | 94273.25 | 0 | [7 empty] | N/A
| SD of 45 pcs Hardiflex 1/4 inch x 4 mtrs x 8 mtrs and 25 OTHERS to support the Repair and Maintenance of Office Building | [19 empty] | HSBN, HHSG | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-09-13 | 2022-09-13 | 2022-10-12 | 2022-10-19 | 2022-10-19 | GoP | 91579.75 | 91579.75 | 0 | 88539.75 | 88539.75 | 0 | [7 empty] | N/A
| S/D of 2 pcs Hardiflex 1/4" x 4' x 8' & 13 others | [19 empty] | HSBN, HHSG | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-09-13 | 2022-09-13 | 2022-10-17 | 2022-10-24 | 2022-10-24 | GoP | 45770 | 45770 | 0 | 45070 | 45070 | 0 | [7 empty] | N/A
Total Alloted Budget of Procurement Activities | [37 empty] | 14110526.75
Total Contract Price of Procurement Actitvites Conducted | [40 empty] | 13966652.75
Total Savings (Total Alloted Budget - Total Contract Price) | [37 empty] | 143874
0N-GOING PROCUREMENT ACTIVITIES
| S/D of 1 pc Release Bearing & 11 others | [19 empty] | HHSG | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-18 | 2022-11-18 | N/A | N/A | N/A | GoP | 25870 | 25870 | 0 | 25670 | 25670 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of 16 pcs Corrugated Roof #24 x 8' & 18 others | [19 empty] | HHSG | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-18 | 2022-11-18 | N/A | N/A | N/A | GoP | 45936.75 | 45936.75 | 0 | 45536.75 | 45536.75 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of 2 pcs Skeletal Rack Mount & 14 others | [19 empty] | HHSG | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-24 | 2022-11-24 | 2022-12-15 | 2022-12-21 | N/A | GoP | 382988 | 382988 | 0 | 382140 | 382140 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of 399 ea Philippine Army Athletic Jacket | [19 empty] | HHSG | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-24 | 2022-11-24 | 2022-12-16 | 2022-12-21 | N/A | GoP | 997500 | 997500 | 0 | 993510 | 993510 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of 13 bags Cement & 11 others | [19 empty] | HHSG | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-24 | 2022-11-24 | 2022-12-16 | 2022-12-19 | N/A | GoP | 502280 | 502280 | 0 | 501590 | 501590 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of 60 boxes Bond Paper (A4) 8 1/4" x 11 3/4" & 29 others | [19 empty] | HHSG | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-24 | 2022-11-24 | N/A | N/A | N/A | GoP | 145164.25 | 145164.25 | 0 | 143644.25 | 143644.25 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of 15 packs Disposable Spoon & Fork & 20 others | [19 empty] | HHSG | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-24 | 2022-11-24 | N/A | N/A | N/A | GoP | 143415 | 143415 | 0 | 143190 | 143190 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of 2 unit Leather (10 chairs) | [19 empty] | HHSG | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-14 | 2022-12-14 | N/A | N/A | N/A | GoP | 20000 | 20000 | 0 | 19800 | 19800 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of 1 unit Starter Motor and 10 others | [19 empty] | HHSG | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-14 | 2022-12-14 | N/A | N/A | N/A | GoP | 115300 | 115300 | 0 | 113550 | 113550 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Total Alloted Budget of On-going Procurement Activities | [37 empty] | 2378454
| Prepared by: | [31 empty] | Certified Correct by: | [7 empty] | Noted by:
| Junelyn J Tornalejo | [31 empty] | ROLAND ROY P PLAZA | [7 empty] | DARWIN A MANALO
| Sgt (QMS) PA | [31 empty] | CPT (OS) PA | [7 empty] | MAJ (QMS) PA
| Procurement NCO | [31 empty] | Admin Officer | [7 empty] | AC of S for Logistics, G4

## Sheet1 (hidden)
Competitive Bidding | GoP | YES
Limited Source Bidding | Foreign | NO
Direct Contracting | Special Purpose Fund
Repeat Order | Corporate Budget
Shopping | Income
NP-53.1 Two Failed Biddings | Others
NP-53.2 Emergency Cases
NP-53.3 Take-Over of Contracts
NP-53.4 Adjacent or Contiguous
NP-53.5 Agency-to-Agency
NP-53.6 Scientific, Scholarly, Artistic Work, Exclusive Technology and Media Services
NP-53.7 Highly Technical Consultants
NP-53.8 Defense Cooperation Agreement
NP-53.9 - Small Value Procurement
NP-53.10 Lease of Real Property and Venue
NP-53.11 NGO Participation
NP-53.12 Community Participation
NP-53.13 UN Agencies, Int'l Organizations or International Financing Institutions
Others - Foreign-funded procurement