## PMR December
ANNEX B
(LRR, PA) Procurement Monitoring Report as of January to 30 December 2022
Code (PAP) | Procurement Project | PMO/ End-User | Is this an Early Procurement Activity? | Mode of Procurement | Actual Procurement Activity | [12 empty] | Source of Funds | ABC (PhP) |  |  | Contract Cost (PhP) |  |  | List of Invited Observers | Date of Receipt of Invitation | [5 empty] | Remarks (Explaining changes from the APP)
[5 empty] | Pre-Proc Conference | Ads/Post of IB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Date of BAC Resolution Recommending Award | Notice of Award | Contract Signing | Notice to Proceed | Delivery/ Completion | Inspection & Acceptance |  | Total | MOOE | CO | Total | MOOE | CO |  | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Delivery/ Completion/ Acceptance (If applicable)
COMPLETED PROCUREMENT ACTIVITIES
5-02-03-080-00 | Medical & Dental & Laboratory Supplies Expenses | LRR, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-02-21 | N/A | 2022-03-07 | 2022-03-11 | 2022-03-11 | GoP | 150000 | 150000 | N/A | 148914 | 148914 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-05-020-01 | Mobile Cellcard | LRR, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-02-21 | N/A | 2022-03-07 | 2022-03-11 | 2022-03-11 | GoP | 87800 | 87800 | N/A | 87751.25 | 87751.25 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-990-00 | Other Supplies | LRR, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-02-21 | N/A | 2022-03-07 | 2022-03-11 | 2022-03-11 | GoP | 165680 | 165680 | N/A | 164980 | 164980 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-010-00 | Office Supplies Ps-remaining | LRR, PA | NO | Shopping 52.1b | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-02-21 | N/A | 2022-03-07 | 2022-03-11 | 2022-03-11 | GoP | 213319.8 | 213319.8 | N/A | 212526 | 212526 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-13-060-01 | Repair & Maintenance of Vehicle | LRR, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-02-21 | N/A | 2022-03-07 | 2022-03-11 | 2022-03-11 | GoP | 255000 | 255000 | N/A | 254100 | 254100 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-13-040-01 | Repair & Maintenance of Building | LRR, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-02-21 | N/A | 2022-03-15 | 2022-03-23 | 2022-03-23 | GoP | 196130 | 196130 | N/A | 195280 | 195280 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-13-040-01 | Repair & Maintenance of Building | LRS,LRR, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-02-21 | N/A | 2022-03-15 | 2022-03-29 | 2022-03-29 | GoP | 150000 | 150000 | N/A | 149347 | 149347 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-010-00 | Office Supplies Ps-remaining | LRS,LRR, PA | NO | Shopping 52.1b | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-02-21 | N/A | 2022-03-15 | 2022-03-29 | 2022-03-29 | GoP | 95693.09 | 95693.09 | N/A | 94944 | 94944 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-210-09 | Semi-Expendable Military Equipment | LRR, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-02-21 | N/A | 2022-03-15 | 2022-03-23 | 2022-03-23 | GoP | 529800 | 529800 | N/A | 528950 | 528950 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-080-00 | Medical & Dental & Laboratory Supplies Expenses OSS | LRR, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-02-22 | N/A | 2022-03-21 | 2022-03-23 | 2022-03-23 | GoP | 531600 | 531600 | N/A | 530895 | 530895 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-13-060-01 | Repair & Maintenance of Vehicle | LRR, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-02-16 | N/A | 2022-03-21 | 2022-03-29 | 2022-03-29 | GoP | 40000 | 40000 | N/A | 39800 | 39800 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-210-03 | Repair & Maintenance of ICT Equipment | LRR, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-02-21 | N/A | 2022-03-21 | 2022-03-23 | 2022-03-23 | GoP | 88100 | 88100 | N/A | 87700 | 87700 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-13-040-01 | Repair & Maintenance of Building | LRS,LRR, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-04-05 | N/A | 25 Apr 22 | 10 May 22 | 11 May 22 | GoP | 150000 | 150000 | N/A | 149347 | 149347 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-210-03 | Repair & Maintenance of ICT Equipment | LRR, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-04-04 | N/A | 2022-05-17 | 2022-05-19 | 2022-05-19 | GoP | 78100 | 78100 | N/A | 77700 | 77700 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-13-060-01 | Repair & Maintenance of Vehicle | LRR, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-04-04 | N/A | 2022-05-17 | 2022-05-19 | 2022-05-19 | GoP | 275000 | 275000 | N/A | 274450 | 274450 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-13-210-09 | Semi-Expendable Military Equipment | LRR, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-04-04 | N/A | 2022-05-17 | 2022-05-19 | 2022-05-19 | GoP | 500000 | 500000 | N/A | 499470 | 499470 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-13-060-01 | Repair & Maintenance of Vehicle | LRS,LRR, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-04-04 | N/A | 2022-05-17 | 2022-05-19 | 2022-05-19 | GoP | 40000 | 40000 | N/A | 39840 | 39840 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-010-00 | Office Supplies Ps-remaining | LRS,LRR, PA | NO | Shopping 52.1b | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-04-04 | N/A | 2022-05-17 | 2022-05-19 | 2022-05-19 | GoP | 93266.32 | 93266.32 | N/A | 92824 | 92824 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-990-00 | Other Supplies | LRR, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-04-04 | N/A | 2022-05-17 | 2022-05-19 | 2022-05-19 | GoP | 292710 | 292710 | N/A | 292610 | 292610 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-010-00 | Office Supplies Ps-remaining | LRR, PA | NO | Shopping 52.1b | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-04-04 | N/A | 2022-05-17 | 2022-05-19 | 2022-05-19 | GoP | 151076.7 | 151076.7 | N/A | 150674.02 | 150674.02 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-080-00 | Medical & Dental & Laboratory Supplies Expenses | LRR, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-04-04 | N/A | 2022-05-17 | 2022-05-19 | 2022-05-19 | GoP | 180000 | 180000 | N/A | 179500 | 179500 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-13-040-01 | Repair & Maintenance of Building | LRR, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-04-04 | N/A | 2022-05-17 | 2022-05-19 | 2022-05-19 | GoP | 726213 | 726213 | N/A | 725613 | 725613 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-210-09 | Semi-Expendable Military Equipment | LRR, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-04-04 | N/A | 2022-05-17 | 2022-06-09 | 2022-06-09 | GoP | 529800 | 529800 | N/A | 529410 | 529410 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-990-00 | Other Supplies | LRR, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-04-04 | N/A | 2022-05-19 | 2022-06-09 | 2022-06-09 | GoP | 345000 | 345000 | N/A | 344586 | 344586 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-05-020-01 | Mobile Cellcard | LRR, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-04-04 | N/A | 2022-05-19 | 2022-05-21 | 2022-05-21 | GoP | 87800 | 87800 | N/A | 87770 | 87770 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-990-00 | Other Supplies | LRR, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-04-18 | N/A | 06 June 22 | 09 June 22 | 09 June 22 | GoP | 500000 | 500000 | N/A | 499600 | 499600 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-13-210-09 | Semi-Expendable Military Equipment | LRR, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-05-11 | N/A | 06 June 22 | 09 June 22 | 09 June 22 | GoP | 500000 | 500000 | N/A | 499342 | 499342 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-220-01 | Semi-Expendable Furniture & Fixture | LRR, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-05-02 | N/A | 06 June 22 | 09 June 22 | 09 June 22 | GoP | 634205 | 634205 | N/A | 632622 | 632622 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-13-210-09 | Semi-Expendable Military Equipment | LRR, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-05-02 | N/A | 06 June 22 | 09 June 22 | 09 June 22 | GoP | 797400 | 797400 | N/A | 796920 | 796920 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-220-01 | Semi-Expendable Furniture & Fixture | LRS,LRR, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-05-02 | N/A | 2022-06-06 | 2022-06-09 | 2022-06-09 | GoP | 105800 | 105500 | N/A | 105400 | 105400 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-210-09 | Semi-Expendable Military Equipment | LRR, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-05-23 | N/A | 2022-06-29 | 2022-07-07 | 2022-07-07 | GoP | 608997 | 608997 | N/A | 608497 | 608497 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-13-040-01 | Repair & Maintenance of Building | LRR, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-05-23 | N/A | 2022-06-29 | 2022-07-07 | 2022-07-07 | GoP | 455070 | 455070 | N/A | 454665 | 454665 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-05-020-01 | Mobile Cellcard | LRR, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-05-24 | N/A | 2022-06-29 | 2022-07-07 | 2022-07-07 | GoP | 87800 | 87800 | N/A | 87742 | 87742 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-210-99 | Semi-Expendable Machinery equipment | LRS,LRR, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-05-16 | N/A | 2022-06-29 | 2022-07-07 | 2022-07-07 | GoP | 61500 | 61500 | N/A | 61200 | 61200 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-13-040-01 | Repair & Maintenance of Building | LRS,LRR, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-05-17 | N/A | 2022-06-29 | 2022-07-07 | 2022-07-07 | GoP | 32700 | 32700 | N/A | 32309 | 32309 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-13-060-01 | Repair & Maintenance of Vehicle | LRR, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-05-23 | N/A | 2022-07-11 | 2022-07-22 | 2022-07-22 | GoP | 678488.84 | 678488.84 | N/A | 677914 | 677914 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-13-040-99 | Repair and Maintenance of Other Strutures | LRR, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-05-23 | N/A | 2022-07-11 | 2022-07-22 | 2022-07-22 | GoP | 997860 | 997860 | N/A | 997210 | 997210 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-080-00 | Medical & Dental & Laboratory Supplies Expenses | LRR, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-05-23 | N/A | 2022-07-11 | 2022-07-22 | 2022-07-22 | GoP | 120000 | 120000 | N/A | 119610 | 119610 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-990-00 | Other Supplies | LRR, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-05-31 | N/A | 2022-07-14 | 2022-07-22 | 2022-07-22 | GoP | 205930 | 205930 | N/A | 205517 | 205517 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-010-00 | Office Supplies Ps-remaining | LRR, PA | NO | Shopping 52.1b | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-05-31 | N/A | 2022-07-14 | 2022-07-22 | 2022-07-22 | GoP | 207876.15 | 207876.15 | N/A | 207450 | 207450 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-210-03 | Repair and Maintenance of ICT Equipment | LRR, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-05-23 | N/A | 2022-08-01 | 2022-08-05 | 2022-08-05 | GoP | 78100 | 78100 | N/A | 77760 | 77760 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-210-09 | Semi-Expendable Military Equipment | LRR, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-06-27 | N/A | 2022-08-01 | 2022-08-05 | 2022-08-05 | GoP | 700000 | 700000 | N/A | 699600 | 699600 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-13-060-01 | Repair & Maintenance of Vehicle | LRR, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-06-27 | N/A | 2022-08-01 | 2022-08-05 | 2022-08-05 | GoP | 230000 | 230000 | N/A | 229620 | 229620 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-210-09 | Semi-Expendable Military Equipment | LRR, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-08 | N/A | 2022-08-30 | 2022-09-06 | 2022-09-06 | GoP | 900000 | 900000 | N/A | 899350 | 899350 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-13-040-01 | Repair & Maintenance of Building | LRS,LRR, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-06-28 | N/A | 2022-08-08 | 2022-08-16 | 2022-08-16 | GoP | 150000 | 150000 | N/A | 149347 | 149347 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-13-060-01 | Repair & Maintenance of Vehicle | LRS,LRR, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-06-30 | N/A | 2022-08-08 | 2022-08-16 | 2022-08-16 | GoP | 40000 | 40000 | N/A | 39700 | 39700 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-210-03 | Semi-Expendable ICT Equipment | LRR, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-06-27 | N/A | 2022-08-08 | 2022-08-16 | 2022-08-16 | GoP | 120000 | 120000 | N/A | 119780 | 119780 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-210-07 | Semi-Expendable C4s Equipment | LRR, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-06-27 | N/A | 2022-08-08 | 2022-08-16 | 2022-08-16 | GoP | 60000 | 60000 | N/A | 59750 | 59750 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-220-01 | Semi-Expendable Furniture & Fixture | LRR, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-07-04 | N/A | 2022-08-08 | 2022-08-16 | 2022-08-16 | GoP | 74995 | 74995 | N/A | 74790 | 74790 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-210-02 | Semi-Expendable Office Equipment | LRR, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-07-04 | N/A | 2022-08-08 | 2022-08-16 | 2022-08-16 | GoP | 106994 | 106994 | N/A | 106700 | 106700 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-13-040-01 | Repair & Maintenance of Building | LRR, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-07-04 | N/A | 2022-08-08 | 2022-08-16 | 2022-08-16 | GoP | 252901 | 252901 | N/A | 252525 | 252525 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-130-00 | Chemical Filtering Supplies Expenses (295) | LRR, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-07-26 | N/A | 2022-08-08 | 2022-08-16 | 2022-08-16 | GoP | 69980 | 69980 | N/A | 69700 | 69700 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-080-00 | Medical & Dental & Laboratory Supplies Expenses | LRR, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-07-18 | N/A | 2022-08-08 | 2022-08-16 | 2022-08-16 | GoP | 327819.65 | 327819.65 | N/A | 327521 | 327521 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-010-02 | Office Supplies | LRR, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-07-26 | N/A | 2022-08-08 | 2022-08-16 | 2022-08-16 | GoP | 207278 | 207278 | N/A | 207008 | 207008 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-990-00 | Other Supplies | LRR, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-07-26 | N/A | 2022-08-08 | 2022-08-16 | 2022-08-16 | GoP | 109887 | 109887 | N/A | 109680 | 109680 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-210-09 | Semi-Expendable Military Equipment | LRR, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-06-06 | N/A | 2022-08-08 | 2022-08-16 | 2022-08-16 | GoP | 943020 | 943020 | N/A | 942500 | 942500 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-210-08 | Semi-Expendable Disaster Response and Rescue Equipment | LRR, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-07-26 | N/A | 2022-08-08 | 2022-08-16 | 2022-08-16 | GoP | 398253.5 | 398253.5 | N/A | 388905 | 388905 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-010-01 | Office Supplies Ps-remaining | LRS,LRR, PA | NO | Shopping 52.1b | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-07-04 | N/A | 2022-08-30 | 2022-09-07 | 2022-08-17 | GoP | 139145.91 | 139145.91 | N/A | 138860 | 138860 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-080-00 | Medical & Dental & Laboratory Supplies Expenses | LRR, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-15 | N/A | 2022-08-30 | 2022-06-06 | 2022-06-06 | GoP | 200000 | 200000 | N/A | 199660 | 199660 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-010-02 | Office Supplies | LRR, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-01 | N/A | 2022-08-30 | 2022-08-16 | 2022-08-16 | GoP | 207278 | 207278 | N/A | 207000 | 207000 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-210-08 | Semi-Expendable Disaster Response and Rescue Equipment | LRR, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-01 | N/A | 2022-08-30 | 2022-09-06 | 2022-09-06 | GoP | 396753 | 396753 | N/A | 396480 | 396480 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-210-03 | Repair and Maintenance of ICT Equipment | LRR, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-02 | N/A | 2022-08-30 | 2022-09-06 | 2022-09-06 | GoP | 424635 | 424635 | N/A | 424330 | 424330 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-990-00 | Other Supplies | LRR, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-01 | N/A | 2022-08-30 | 2022-09-06 | 2022-09-06 | GoP | 111387.5 | 111387.5 | N/A | 111072 | 111072 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-210-04 | Repair and Maintenance of ICT Equipment | LRR, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-07-29 | N/A | 2022-08-30 | 2022-09-06 | 2022-09-06 | GoP | 600000 | 600000 | N/A | 599660 | 599660 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-990-00 | Other Supplies | LRR, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-15 | N/A | 2022-08-30 | 2022-09-07 | 2022-09-07 | GoP | 260983 | 260983 | N/A | 260630 | 260630 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-130-00 | Chemical Filtering Supplies Expenses (313) | LRR, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-02 | N/A | 2022-08-30 | 2022-09-06 | 2022-09-06 | GoP | 69980 | 69980 | N/A | 69705 | 69705 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-210-03 | Semi-Expendable ICT Equipment | LRS,LRR, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-07-25 | N/A | 2022-09-07 | 2022-09-09 | 2022-09-09 | GoP | 100000 | 100000 | N/A | 99755 | 99755 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-13-060-01 | Repair & Maintenance of Vehicle | LRR, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-30 | N/A | 2022-10-03 | 2022-10-07 | 2022-10-07 | GoP | 235000 | 235000 | N/A | 234645 | 234645 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-990-00 | Other Supplies | LRR, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-30 | N/A | 2022-10-03 | 2022-10-07 | 2022-10-07 | GoP | 173410 | 173410 | N/A | 173130 | 173130 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-05-020-01 | Mobile Cellcard | LRR, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-30 | N/A | 2022-10-03 | 2022-10-07 | 2022-10-07 | GoP | 87800 | 87800 | N/A | 87653.75 | 87653.75 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-210-09 | Semi-Expendable Military Equipment | LRR, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-30 | N/A | 2022-10-03 | 2022-10-07 | 2022-10-07 | GoP | 529800 | 529800 | N/A | 529415 | 529415 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-080-00 | Medical & Dental & Laboratory Supplies Expenses | LRR, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-30 | N/A | 2022-10-03 | 2022-10-07 | 2022-10-07 | GoP | 180000 | 180000 | N/A | 179660 | 179660 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-210-03 | Repair and Maintenance of ICT Equipment | LRR, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-30 | N/A | 2022-10-03 | 2022-10-07 | 2022-10-07 | GoP | 78100 | 78100 | N/A | 77740 | 77740 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-210-03 | Semi-Expendable ICT Equipment | LRS,LRR, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-05 | N/A | 2022-10-14 | 2022-10-27 | 2022-10-27 | GoP | 200000 | 200000 | N/A | 199730 | 199730 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-210-03 | Semi-Expendable ICT Equipment | LRR, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-20 | N/A | 2022-10-27 | 2022-11-11 | 2022-11-11 | GoP | 124600 | 124600 | N/A | 124300 | 124300 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-13-040-01 | Repair & Maintenance of Building | LRS,LRR, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-26 | N/A | 2022-10-27 | 2022-11-08 | 2022-11-08 | GoP | 150000 | 150000 | N/A | 149670 | 149670 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-13-060-01 | Repair & Maintenance of Vehicle | LRS,LRR, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-20 | N/A | 2022-10-27 | 2022-11-08 | 2022-11-08 | GoP | 40000 | 40000 | N/A | 39690 | 39690 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-210-09 | Semi-Expendable Military Police and Security Equipment | LRR, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-18 | N/A | 2022-11-09 | 2022-11-16 | 2022-11-16 | GoP | 369435 | 369435 | N/A | 369055 | 369055 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-990-00 | Other Supplies | LRR, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-18 | N/A | 2022-11-09 | 2022-11-16 | 2022-11-16 | GoP | 500000 | 500000 | N/A | 499400 | 499400 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-080-00 | Medical & Dental & Laboratory Supplies Expenses | LRR, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-24 | N/A | 2022-11-10 | 2022-11-16 | 2022-11-16 | GoP | 180000 | 180000 | N/A | 179500 | 179500 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-210-03 | Semi-Expendable ICT Equipment | LRR, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-07 | N/A | 2022-11-24 | 2022-12-01 | 2022-12-01 | GoP | 100000 | 100000 | N/A | 99700 | 99700 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-990-00 | Other Supplies | LRR, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-07 | N/A | 2022-11-24 | 2022-12-01 | 2022-12-01 | GoP | 500000 | 500000 | N/A | 499400 | 499400 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-990-00 | Other Supplies | LRR, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-07 | N/A | 2022-11-24 | 2022-12-01 | 2022-12-01 | GoP | 500000 | 500000 | N/A | 499400 | 499400 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-13-040-01 | Repair & Maintenance of Building | LRR, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-21 | N/A | 2022-12-07 | 2022-12-13 | 2022-12-13 | GoP | 588136 | 588136 | N/A | 587526 | 587526 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-13-050-03 | Repair of ICT Equipment | LRR, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-21 | N/A | 2022-12-14 | 2022-12-15 | 2022-12-15 | GoP | 60020 | 60020 | N/A | 59680 | 59680 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
[19 empty] | 23821407.46 | 23821107.46 |  | 23775662.02 | 23775662.02
Total Alloted Budget of Procurement Activities | [18 empty] | 23821407.46
Total Contract Price of Procurement Activities Conducted | [21 empty] | 23775662.02
Total Savings (Total Alloted Budget - Total Contract Price) | [21 empty] | 45745.44
0N-GOING PROCUREMENT ACTIVITIES
5-02-13-040-01 | Repair & Maintenance of Building | LRS,LRR, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | _ | N/A | _ | _ | _ | GoP | 535027 | 535027 | N/A | 534322 | 534322 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Inspected
Total Alloted Budget of On-going Procurement Activities | [18 empty] | 534322 |  |  |  | 534322
|  | Prepared by: | [10 empty] | Recommended for Approval by: | [10 empty] | APPROVED BY:
|  | Signed | [10 empty] | Signed | [10 empty] | Signed
|  | PAUL BENEDICT R CRUZ | [10 empty] | MIGUEL KARLO E ALAMBRA | [10 empty] | MONICO E ABANG
|  | MAJ (OS) PA | [10 empty] | CPT (QMS) PA | [10 empty] | BGEN PA
|  | AC of S for Logistics, G4 | [10 empty] | Chief, MFO, LRR | [10 empty] | Regiment Commander

## Sheet1 (hidden)
Competitive Bidding | GoP | YES
Limited Source Bidding | Foreign | NO
Direct Contracting | Special Purpose Fund
Repeat Order | Corporate Budget
Shopping | Income
NP-53.1 Two Failed Biddings | Others
NP-53.2 Emergency Cases
NP-53.3 Take-Over of Contracts
NP-53.4 Adjacent or Contiguous
NP-53.5 Agency-to-Agency
NP-53.6 Scientific, Scholarly, Artistic Work, Exclusive Technology and Media Services
NP-53.7 Highly Technical Consultants
NP-53.8 Defense Cooperation Agreement
NP-53.9 - Small Value Procurement
NP-53.10 Lease of Real Property and Venue
NP-53.11 NGO Participation
NP-53.12 Community Participation
NP-53.13 UN Agencies, Int'l Organizations or International Financing Institutions
Others - Foreign-funded procurement