## 52EBDE
|  |  | ANNEX A | [24 empty] | ANNEX B
|  |  | Department of Budget and Management Annual Procurement Plan for FY 2022 | [24 empty] | 107TH CONTRACTING OFFICE - SFR(A), PA - PROJECT MONITORING REPORT - 2nd Semester CY 2022
| Code (PAP) | Procurement Project | PMO/ End-User | Mode of Procurement | Schedule for Each Procurement Activity | [11 empty] | Source of Funds | ABC (PhP) |  |  | Remarks (brief description of Program/Project) | PMO/ End-User | Is this an Early Procurement Activity? | Mode of Procurement | Actual Procurement Activity | [12 empty] | Source of Funds | ABC (PhP) |  |  | Contract Cost (PhP) |  |  | List of Invited Observers | Date of Receipt of Invitation | [5 empty] | Remarks (Explaining changes from the APP)
[5 empty] | Pre-Proc Conference | Ads/Post of IAEB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Contract Award | Contract Signing | Notice to Proceed | Delivery/ Accept | Payment Process |  | Total | MOOE | CO |  |  |  |  | Pre-Proc Conference | Ads/Post of IB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Date of BAC Resolution Recommending Award | Notice of Award | Contract Signing | Notice to Proceed | Delivery/ Completion | Inspection & Acceptance |  | Total | MOOE | CO / SPF | Total | MOOE | CO / SPF |  | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Delivery/ Completion/ Acceptance (If applicable)
COMPLETED PROCUREMENT ACTIVITIES
1 | 5-02-03-210-08 | DRRO | HSFRA | Neg 53.9 | [17 empty] | SFR(A) PA | no | [12 empty] | 2022-10-12 | 2022-10-12 | SPF | 808348 | 808348 |  | 807790 |  | 807790 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Completed
2 | 5-03-03-210-03 | Semi Expandable ICT | 33SFC | Neg 53.9 | [17 empty] | SFR(A) PA | no | [12 empty] | 2022-09-20 | 2022-09-20 | SPF | 50000 | 50000 |  | 49700 |  | 49700 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Completed
3 | 5-03-03-210-03 | Semi Expandable ICT | 18 SFC | Neg 53.9 | [17 empty] | SFR(A) PA | no | [12 empty] | 2022-09-20 | 2022-09-20 | SPF | 50000 | 50000 |  | 49690 |  | 49690 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Completed
4 | 5-03-03-210-04 | Semi Expandable ICT | 16SFC | Neg 53.9 | [17 empty] | SFR(A) PA | no | [12 empty] | 2022-10-12 | 2022-10-12 | SPF | 50000 | 50000 |  | 49700 |  | 49700 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Completed
5 | 5-02-03-080-00 | Medical Dental Supplies | HSFRA | Neg 53.9 | [17 empty] | SFR(A) PA | no | [12 empty] | 2022-10-26 | 2022-10-26 | SPF | 51730.25 | 51730.25 |  | 51480 |  | 51480 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Completed
6 | 5-02-03-080-00 | Medical Dental Supplies | HSFRA | Neg 53.9 | [17 empty] | SFR(A) PA | no | [12 empty] | 2022-10-26 | 2022-10-26 | SPF | 219489 | 219489 |  | 219150 |  | 219150 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Completed
7 | 5-02-03-080-00 | Medical Dental Supplies | HSFRA | Neg 53.9 | [17 empty] | SFR(A) PA | no | [12 empty] | 2022-10-26 | 2022-10-26 | SPF | 150900 | 150900 |  | 150528 |  | 150528 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Completed
8 | 5-02-03-220-01 | Furnitures & Fixtures | 33SFC | Neg 53.9 | [17 empty] | SFR(A) PA | no | [12 empty] | 2022-10-12 | 2022-10-12 | SPF | 135900 | 135900 |  | 135750 |  | 135750 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Completed
9 | 5-03-03-210-03 | Semi Expandable ICT | 33SFC | Neg 53.9 | [17 empty] | SFR(A) PA | no | [12 empty] | 2022-09-20 | 2022-09-20 | SPF | 64100 | 64100 |  | 63850 |  | 63850 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Completed
10 | 5-02-03-210-03 | Semi Expandable ICT | HSFRA | Neg 53.9 | [17 empty] | SFR(A) PA | no | [12 empty] | 2022-10-12 | 2022-10-12 | SPF | 58257 | 58257 |  | 58000 |  | 58000 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Completed
11 | 5-02-03-010-01 | RM ICT Equipment | HSFRA | Neg 53.9 | [17 empty] | SFR(A) PA | no | [12 empty] | 2022-10-13 | 2022-10-13 | SPF | 300584 | 300584 |  | 300260 |  | 300260 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Completed
12 | 5-02-13-060-01 | R&M of Vehicle | 18SFC | Neg 53.9 | [17 empty] | SFR(A) PA | no | [12 empty] | 2022-10-26 | 2022-10-26 | SPF | 5000 | 5000 |  | 4800 |  | 4800 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Completed
13 | 5-02-03-010-02 | Ofice Suplies | HSFRA | Neg 53.9 | [17 empty] | SFR(A) PA | no | [12 empty] | 2022-10-12 | 2022-10-12 | SPF | 101110 | 101110 |  | 100675 |  | 100675 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Completed
14 | 5-02-13-060-01 | R&M of Motor Vehicle | HSFRA | Neg 53.9 | [17 empty] | SFR(A) PA | no | [12 empty] | 2022-11-04 | 2022-11-04 | MOOE | 282660 | 282660 |  | 282210 |  | 282210 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Completed
15 | 5-02-13-050-07 | R&M of Communication Equip | HSFRA | Neg 53.9 | [17 empty] | SFR(A) PA | no | [12 empty] | 2022-11-04 | 2022-11-04 | MOOE | 100000 | 100000 |  | 99660 |  | 99660 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Completed
16 | 5-02-13-050-03 | ICT Equipment | HSFRA | Neg 53.9 | [17 empty] | SFR(A) PA | no | [12 empty] | 2022-11-18 | 2022-11-18 | MOOE | 58000 | 58000 |  | 57700 |  | 57700 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Completed
17 | 5-02-13-050-02 | Office Equipment | HSFRA | Neg 53.9 | [17 empty] | SFR(A) PA | no | [12 empty] | 2022-11-04 | 2022-11-04 | MOOE | 12000 | 12000 |  | 11800 |  | 11800 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Completed
18 | 5-02-13-040-99 | R&M of Other Structures | HSFRA | Neg 53.9 | [17 empty] | SFR(A) PA | no | [12 empty] | 2022-11-04 | 2022-11-04 | MOOE | 458835 | 458835 |  | 458350 |  | 458350 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Completed
19 | 5-02-13-040-01 | R&M of Famale Barracks | HSFRA | Neg 53.9 | [17 empty] | SFR(A) PA | no | [12 empty] | 2022-11-04 | 2022-11-04 | MOOE | 39185 | 39185 |  | 38880 |  | 38880 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Completed
20 | 5-02-03-210-02 | Semi Expandable Office Equip. | HSFRA | Neg 53.9 | [17 empty] | SFR(A) PA | no | [12 empty] | 2022-11-04 | 2022-11-04 | MOOE | 25000 | 25000 |  | 24800 |  | 24800 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Completed
21 | 5-02-03-080-00 | Medical Dental Supplies | HSFRA | Neg 53.9 | [17 empty] | SFR(A) PA | no | [12 empty] | 2022-11-18 | 2022-11-18 | MOOE | 89515 | 89515 |  | 89165 |  | 89165 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Completed
22 | 5-02-03-070-00 | Drugs & Medicine Supplies | HSFRA | Neg 53.9 | [17 empty] | SFR(A) PA | no | [12 empty] | 2022-11-18 | 2022-11-18 | MOOE | 10000 | 10000 |  | 9850 |  | 9850 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Completed
23 | 5-02-13-060-01 | R&M of Motor Vehicle | HSFRA | Neg 53.9 | [17 empty] | SFR(A) PA | no | [12 empty] | 2022-12-13 | 2022-12-13 | MOOE | 115000 | 115000 |  | 114610 |  | 114610 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Completed
24 | 5-02-13-050-03 | R&M of ICT Equipment | HSFRA | Neg 53.9 | [17 empty] | SFR(A) PA | no | [12 empty] | 2022-12-13 | 2022-12-13 | MOOE | 70000 | 70000 |  | 69680 |  | 69680 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Completed
25 | 5-02-13-050-01 | R&M of Other Machinery Equip | HSFRA | Neg 53.9 | [17 empty] | SFR(A) PA | no | [12 empty] | 2022-12-09 | 2022-12-09 | MOOE | 80000 | 80000 |  | 79700 |  | 79700 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Completed
26 | 5-02-03-010-00 | Office Supplies | HSFRA | Neg 53.9 | [17 empty] | SFR(A) PA | no | [12 empty] | 2022-11-18 | 2022-11-18 | MOOE | 211206.07 | 211206.07 |  | 210784 |  | 210784 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Completed
27 | 5-02-13-060-01 | R&M of Motor Vehicle | 18SFC | Neg 53.9 | [17 empty] | SFR(A) PA | no | [12 empty] | 2022-11-18 | 2022-11-18 | MOOE | 10000 | 10000 |  | 9800 |  | 9800 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Completed
28 | 5-02-13-040-01 | R&M of Belliting Facilities | 18SFC | Neg 53.9 | [17 empty] | SFR(A) PA | no | [12 empty] | 2022-11-18 | 2022-11-18 | MOOE | 30000 | 30000 |  | 29800 |  | 29800 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Completed
29 | 5-02-03-990-00 | Sustainment Support for PAPT | HSFRA | Neg 53.9 | [17 empty] | SFR(A) PA | no | [12 empty] | 2022-12-13 | 2022-12-13 | SPF | 737500 | 737500 |  | 737010 |  | 737010 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Completed
30 | 5-02-13-060-01 | Support for Operational Tempo | 18SFC | Neg 53.9 | [17 empty] | SFR(A) PA | no | [12 empty] | 2022-12-13 | 2022-12-13 | SPF | 10000 | 10000 |  | 9785 |  | 9785 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Completed
31 | 5-02-03-990-00 | Sustainment Support for Airborne | HSFRA | Neg 53.9 | [17 empty] | SFR(A) PA | no | [12 empty] | 2022-12-09 | 2022-12-09 | SPF | 737500 | 737500 |  | 737980 |  | 737980 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Completed
32 | 5-02-03-990-00 | Sustainment Support for Airborne | HSFRA | Neg 53.9 | [17 empty] | SFR(A) PA | no | [12 empty] | 2022-12-13 | 2022-12-13 | SPF | 737500 | 737500 |  | 736980 |  | 736980 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Completed
33 | 5-02-03-990-00 | Sustainment Support for PAPT | HSFRA | Neg 53.9 | [17 empty] | SFR(A) PA | no | [12 empty] | 2022-12-13 | 2022-12-13 | SPF | 737500 | 737500 |  | 737010 |  | 737010 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Completed
34 | 5-02-13-060-04 | R&M of Watercraft | HSFRA | Neg 53.9 | [17 empty] | SFR(A) PA | no | [12 empty] | 2022-12-13 | 2022-12-13 | SPF | 25000 | 25000 |  | 24360 |  | 24360 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Completed
35 | 5-02-13-040-99 | R&M of Other Structures | HSFRA | Neg 53.9 | [17 empty] | SFR(A) PA | no | [12 empty] | 2022-12-13 | 2022-12-13 | SPF | 40000 | 40000 |  | 39720 |  | 39720 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Completed
36 | 5-02-13-040-99 | R&M of Other Structures | HSFRA | Neg 53.9 | [17 empty] | SFR(A) PA | no | [12 empty] | 2022-12-13 | 2022-12-13 | MOOE | 400168 | 400168 |  | 399730 |  | 399730 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Completed
37 | 5-02-13-040-01 | R&M of Facilities | HSFRA | Neg 53.9 | [17 empty] | SFR(A) PA | no | [12 empty] | 2022-12-13 | 2022-12-13 | MOOE | 39185 | 39185 |  | 38975 |  | 38975 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Completed
38 | 5-02-03-080-00 | Medical Dental Supplies | HSFRA | Neg 53.9 | [17 empty] | SFR(A) PA | no | [12 empty] | 2022-12-12 | 2022-12-12 | MOOE | 89515 | 89515 |  | 89113 |  | 89113 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Completed
39 | 5-02-03-070-00 | Drugs & Medicine Supplies | HSFRA | Neg 53.9 | [17 empty] | SFR(A) PA | no | [12 empty] | 2022-12-29 | 2022-12-29 | MOOE | 10000 | 10000 |  | 9750 |  | 9750 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Completed
40 | 5-02-13-060-01 | R&M of Motor Vehicle | 18SFC | Neg 53.9 | [17 empty] | SFR(A) PA | no | [12 empty] | 2022-12-29 | 2022-12-29 | MOOE | 5000 | 5000 |  | 4850 |  | 4850 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Completed
41 | 5-02-03-050-07 | R&M of Communication Equip | 18SFC | Neg 53.9 | [17 empty] | SFR(A) PA | no | [12 empty] | 2022-12-13 | 2022-12-13 | MOOE | 1000 | 1000 |  | 910 |  | 910 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Completed
42 | 5-02-13-040-01 | R&M of Facilities | 18SFC | Neg 53.9 | [17 empty] | SFR(A) PA | no | [12 empty] | 2022-12-09 | 2022-12-09 | MOOE | 20000 | 20000 |  | 19725 |  | 19725 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Completed
43 | 5-02-13-060-01 | R&M of Motor Vehicle | 16SFC | Neg 53.9 | [17 empty] | SFR(A) PA | no | [12 empty] | 2022-12-29 | 2022-12-29 | MOOE | 40000 | 40000 |  | 39700 |  | 39700 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Completed
44 | 5-02-03-210-08 | DRRO | HSFRA | Neg 53.9 | [17 empty] | SFR(A) PA | no | [12 empty] | 2022-12-09 | 2022-12-09 | PAWAF | 439630 | 439630 |  | 439070 |  | 439070 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Completed
45 | 5-02-03-080-00 | Medical Dental Supplies | HSFRA | Neg 53.9 | [17 empty] | SFR(A) PA | no | [12 empty] | 2022-12-12 | 2022-12-12 | PAWAF | 16400 | 16400 |  | 16090 |  | 16090 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Completed
46 | 5-02-03-070-00 | Drugs & Medicine Supplies | HSFRA | Neg 53.9 | [17 empty] | SFR(A) PA | no | [12 empty] | 2022-12-12 | 2022-12-12 | PAWAF | 23825 | 23825 |  | 23620 |  | 23620 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Completed
47 | 5-03-03-210-03 | Semi Expandable ICT | HSFRA | Neg 53.9 | [17 empty] | SFR(A) PA | no | [12 empty] | 2022-12-13 | 2022-12-13 | SPF | 180000 | 180000 |  | 179490 |  | 179490 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Completed
48 | 5-02-03-210-03 | Semi-expendable ICT | HSFRA | Neg 53.9 | [17 empty] | SFR(A) PA | no | [12 empty] | 2022-12-13 | 2022-12-13 | PAWAF | 100000 | 100000 |  | 99570 |  | 99570 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Completed
50 | 5-02-03-010-00 | PS-DBM | HSFRA | 52.1b | [17 empty] | SFR(A) PA | no | [14 empty] | MOOE | 13793.93 | 13793.93 |  |  |  |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Completed
51 | 5-02-13-040-99 | Concreting of Pavement | HSFRA | Neg 53.9 | [17 empty] | SFR(A) PA | no | [12 empty] | 2022-12-29 | 2022-12-29 | PAWAF | 499760 | 499760 |  | 499100 |  | 499100 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Completed
52 | 5-02-03-210-09 | Semi Expendable Military, Police & Sec Equip | OG2, SFR(A) | Neg 53.9 | [17 empty] | SFR(A) PA | no | [12 empty] | 2022-12-29 | 2022-12-29 | SPF | 216864 | 216864 |  | 216440 |  | 216440 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Completed
53 | 5-02-03-220-03 | Semi-expendable ICT | OG3, SFR(A) | Neg 53.9 | [17 empty] | SFR(A) PA | no | [12 empty] | 2022-12-29 | 2022-12-29 | SPF | 135000 | 135000 |  | 134800 |  | 134800 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Completed
54 | 5-02-03-210-02 | Semi Expandable Office Equip. | OG2, SFR(A) | Neg 53.9 | [17 empty] | SFR(A) PA | no | [12 empty] | 2022-12-29 | 2022-12-29 | SPF | 17000 | 17000 |  | 16800 |  | 16800 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Completed
55 | 5-02-03-220-01 | Furnitures & Fixtures | OG2, SFR(A) | Neg 53.9 | [17 empty] | SFR(A) PA | no | [12 empty] | 2022-12-29 | 2022-12-29 | SPF | 47000 | 47000 |  | 46750 |  | 46750 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Completed
56 | 5-02-03-210-02 | Support for the Intelligence Capability Enhancement | OG2, SFR(A) | Neg 53.9 | [17 empty] | SFR(A) PA | no | [12 empty] | 2022-12-29 | 2022-12-29 | SPF | 87220 | 87220 |  | 86800 |  | 86800 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Completed
57 | 5-02-13-060-01 | R&M of Vehicle | 16SFC | Neg 53.9 | [17 empty] | SFR(A) PA | no | [12 empty] | 2022-12-29 | 2022-12-29 | SPF | 20000 | 20000 |  | 19800 |  | 19800 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Completed
58 | 5-02-13-060-04 | R&M of watercraft | HSFRA | Neg 53.9 | [17 empty] | SFR(A) PA | no | [12 empty] | 2022-12-29 | 2022-12-29 | SPF | 25000 | 25000 |  | 24750 |  | 24750 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Completed
59 | 5-02-03-010-01 | ICT Ofiice Supplies | OG7, SFR(A) | Neg 53.9 | [17 empty] | SFR(A) PA | no | [12 empty] | 2022-12-29 | 2022-12-29 | SPF | 8900 | 8900 |  | 8840 |  | 8840 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Completed
60 | 5-02-03-220-01 | Support for the Enhancement of Training Facility | HSFRA | Neg 53.9 | [17 empty] | SFR(A) PA | no | [12 empty] | 2022-12-29 | 2022-12-29 | SPF | 200000 | 200000 |  | 199375 |  | 199375 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Completed
61 | 5-02-03-210-03 | Support for Social Media Operations Equipment | OG7, SFR(A) | Neg 53.9 | [17 empty] | SFR(A) PA | no | [12 empty] | 2022-12-29 | 2022-12-29 | SPF | 491100 | 491100 |  | 490600 |  | 490600 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Completed
62 | 5-02-13-040-01 | R&M of Facilities | SFS | Neg 53.9 | [17 empty] | SFR(A) PA | no | [12 empty] | 2022-12-29 | 2022-12-29 | SPF | 997682 | 997682 |  | 996944 |  | 996944 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Completed
63 | 5-02-13-040-01 | R&M of Facilities | HSFRA | Neg 53.9 | [17 empty] | SFR(A) PA | no | [12 empty] | 2022-12-29 | 2022-12-29 | SPF | 998500 | 998500 |  | 997701 |  | 997701 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Completed
64 | 5-02-13-040-01 | R&M of Facilities | HSFRA | Neg 53.9 | [17 empty] | SFR(A) PA | no | [12 empty] | 2022-12-29 | 2022-12-29 | SPF | 996000 | 996000 |  | 995191 |  | 995191 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Completed
| Total Alloted Budget of Procurement Activities | [37 empty] | 12780362.25
| Total Contract Price of Procurement Actitvites Conducted | [40 empty] | 12745491
| Total Savings (Total Alloted Budget - Total Contract Price) | [37 empty] | 34871.25
ON-GOING PROCUREMENT ACTIVITIES
NONE
| Total Alloted Budget of Procurement Activities | [37 empty] | 0
| Total Contract Price of Procurement Actitvites Conducted | [40 empty] | 0
| Total Savings (Total Alloted Budget - Total Contract Price) | [37 empty] | 0
Prepared by:
FELECOR C JUMAGDAO
MAJ (INF) PA
AC of S for Logistics, G4
Certified Correct By:
BERNIE C CAMANCHO
MAJ (INF) PA
Chief, MFO
Certified Correct By:
FERDINAND B NAPULI
Colonel INF (MNSA) PA
Commander

## Sheet1
|  |  | ANNEX A | [18 empty] | ANNEX B
|  |  | Department of Budget and Management Annual Procurement Plan for FY 2022 | [18 empty] | 111TH CONTRACTING OFFICE - 52EBDE, PA - PROJECT MONITORING REPORT - 01 January - 31 December 2022
| Code (PAP) | Procurement Project | PMO/ End-User | Mode of Procurement | Schedule for Each Procurement Activity | [11 empty] | Source of Funds | ABC (PhP) |  |  | Remarks (brief description of Program/Project) | PMO/ End-User | Is this an Early Procurement Activity? | Mode of Procurement | Actual Procurement Activity | [12 empty] | Source of Funds | ABC (PhP) |  |  | Contract Cost (PhP) |  |  | List of Invited Observers | Date of Receipt of Invitation | [5 empty] | Remarks (Explaining changes from the APP)
[5 empty] | Pre-Proc Conference | Ads/Post of IAEB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Contract Award | Contract Signing | Notice to Proceed | Delivery/ Accept | Payment Process |  | Total | MOOE | CO |  |  |  |  | Pre-Proc Conference | Ads/Post of IB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Date of BAC Resolution Recommending Award | Notice of Award | Contract Signing | Notice to Proceed | Delivery/ Completion | Inspection & Acceptance |  | Total | MOOE | CO / SPF | Total | MOOE | CO / SPF |  | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Delivery/ Completion/ Acceptance (If applicable)
COMPLETED PROCUREMENT ACTIVITIES
1 |  | Office Supplies Expenses | 524ECB | Neg 53.9 | [17 empty] | 524ECB |  | MOOE | [8 empty] | 11 Mar 22 | 2022-03-14 | 2022-03-25 | 2022-03-28 | 2022-03-28 | MOOE | 72267.5 | 72267.5 |  | 71827 | 71827
2 |  | Office Supplies Expenses | 524ECB | Neg 53.9 | [17 empty] | 524ECB |  | MOOE | [8 empty] | 11 Mar 22 | 2022-03-14 | 2022-03-23 | 2022-03-25 | 2022-03-25 | MOOE | 14982.5 | 14982.5 |  | 14296 | 14296
3 |  | Repair & Maint - Building & Other Structures | 534ECB | Neg 53.9 | [17 empty] | 534ECB |  | MOOE | [8 empty] | 11 Mar 22 | 2022-03-14 | 2022-03-22 | 2022-03-28 | 2022-03-28 | MOOE | 74000 | 74000 |  | 72850 | 72850
4 |  | Semi-Expendable - Communication Equipment | 534ECB | Neg 53.9 | [17 empty] | 534ECB |  | MOOE | [8 empty] | 2022-03-14 | 2022-03-15 | 2022-03-25 | 2022-03-28 | 2022-03-28 | MOOE | 20000 | 20000 |  | 19600 | 19600
5 |  | Office Supplies Expenses | 534ECB | Neg 53.9 | [17 empty] | 534ECB |  | MOOE | [8 empty] | 2022-03-14 | 2022-03-15 | 2022-03-23 | 2022-03-28 | 2022-03-28 | MOOE | 5500 | 5500 |  | 5007 | 5007
6 |  | Repair & Maint - Construction and Heavy Equipment | 534ECB | Neg 53.9 | [17 empty] | 534ECB |  | MOOE | [8 empty] | 11 Mar 22 | 2022-03-14 | 2022-03-22 | 2022-03-28 | 2022-03-28 | MOOE | 28000 | 28000 |  | 27230 | 27230
7 |  | Repair & Maint - Construction and Heavy Equipment | 534ECB | Neg 53.9 | [17 empty] | 534ECB |  | MOOE | [8 empty] | 11 Mar 22 | 2022-03-14 | 2022-03-22 | 2022-03-28 | 2022-03-28 | MOOE | 85000 | 85000 |  | 83400 | 83400
8 |  | Repair & Maint - Motor Vehicles | 534ECB | Neg 53.9 | [17 empty] | 534ECB |  | MOOE | [8 empty] | 11 Mar 22 | 2022-03-14 | 2022-03-22 | 2022-03-28 | 2022-03-28 | MOOE | 55000 | 55000 |  | 53900 | 53900
9 |  | Repair & Maint - Buildings | 52E-G4 | Neg 53.9 | [17 empty] | 52E-G4 |  | MOOE | [8 empty] | 11 Mar 22 | 2022-03-14 | 2022-03-25 | 2022-03-31 | 2022-03-31 | MOOE | 134400 | 134400 |  | 132600 | 132600
10 |  | Repair & Maint - Motor Vehicles | 52E-G4 | Neg 53.9 | [17 empty] | 52E-G4 |  | MOOE | [8 empty] | 11 Mar 22 | 2022-03-14 | 2022-03-25 | 2022-03-31 | 2022-03-31 | MOOE | 152610 | 152610 |  | 151410 | 151410
11 |  | Representation Expenses | 534ECB | Neg 53.9 | [17 empty] | 534ECB |  | MOOE | [8 empty] | 2022-03-14 | 2022-03-15 | 2022-03-23 | 2022-03-25 | 2022-03-25 | MOOE | 14000 | 14000 |  | 13740 | 13740
12 |  | Repair & Maint - Construction and Heavy Equipment | 524ECB | Neg 53.9 | [17 empty] | 524ECB |  | MOOE | [8 empty] | 2022-03-14 | 2022-03-15 | 2022-03-29 | 2022-04-04 | 2022-04-04 | MOOE | 81220 | 81220 |  | 79600 | 79600
13 |  | Repair & Maint - Vehicle | 524ECB | Neg 53.9 | [17 empty] | 524ECB |  | MOOE | [8 empty] | 2022-03-14 | 2022-03-15 | 2022-03-29 | 2022-04-04 | 2022-04-04 | MOOE | 30890 | 30890 |  | 29970 | 29970
14 |  | Internet Subscription | ESC | Neg 53.9 | [17 empty] | ESC |  | MOOE | [8 empty] | 2022-03-14 | 2022-03-15 | 2022-03-25 | 2022-03-28 | 2022-03-28 | MOOE | 12600 | 12600 |  | 12420 | 12420
15 |  | Office Supplies Expenses | ESC | Neg 53.9 | [17 empty] | ESC |  | MOOE | [8 empty] | 2022-03-14 | 2022-03-15 | 2022-03-23 | 2022-03-25 | 2022-03-25 | MOOE | 29160 | 29160 |  | 28748 | 28748
16 |  | Representation Expenses | ESC | Neg 53.9 | [17 empty] | ESC |  | MOOE | [8 empty] | 2022-03-14 | 2022-03-15 | 2022-03-25 | 2022-03-28 | 2022-03-28 | MOOE | 8425 | 8425 |  | 8314 | 8314
17 |  | Repair & Maint - Construction and Heavy Equipment | ESC | Neg 53.9 | [17 empty] | ESC |  | MOOE | [8 empty] | 2022-03-14 | 2022-03-15 | 2022-03-25 | 2022-03-30 | 2022-03-30 | MOOE | 51000 | 51000 |  | 50350 | 50350
18 |  | ICT Software Subscription | 52E-HHCo | Neg 53.9 | [17 empty] | 52E-HHCo |  | MOOE | [8 empty] | 2022-03-15 | 2022-03-16 | 2022-03-29 | 2022-04-04 | 2022-04-04 | MOOE | 206400 | 206400 |  | 205020 | 205020
19 |  | Other Supplies and Materials Expenses | 52E-HHCo | Neg 53.9 | [17 empty] | 52E-HHCo |  | MOOE | [8 empty] | 2022-03-15 | 2022-03-16 | 2022-03-29 | 2022-04-04 | 2022-04-04 | MOOE | 22225 | 22225 |  | 21674 | 21674
20 |  | Semi-Expendable - ICT Equipment | 52E-HHCo | Neg 53.9 | [17 empty] | 52E-HHCo |  | MOOE | [8 empty] | 2022-03-15 | 2022-03-16 | 2022-03-29 | 2022-04-04 | 2022-04-04 | MOOE | 449497.8 | 449497.8 |  | 447800 | 447800
21 |  | Semi-Exp Office Equipment | 52E-HHCo | Neg 53.9 | [17 empty] | 52E-HHCo |  | MOOE | [8 empty] | 2022-03-15 | 2022-03-16 | 2022-03-29 | 2022-04-04 | 2022-04-04 | MOOE | 38000 | 38000 |  | 36500 | 36500
22 |  | Mobile Expenses | 52E-HHCo | Neg 53.9 | [17 empty] | 52E-HHCo |  | MOOE | [8 empty] | 2022-03-15 | 2022-03-16 | 2022-03-29 | 2022-04-04 | 2022-04-04 | MOOE | 5600 | 5600 |  | 5450 | 5450
23 |  | Semi-Expendable - ICT Equipment | 52E-HHCo | Neg 53.9 | [17 empty] | 52E-HHCo |  | MOOE | [8 empty] | 2022-03-15 | 2022-03-16 | 2022-03-29 | 2022-04-04 | 2022-04-04 | MOOE | 40000 | 40000 |  | 39150 | 39150
24 |  | RM Commo Equipment | 524ECB | Neg 53.9 | [17 empty] | 524ECB |  | MOOE | [8 empty] | 2022-03-15 | 2022-03-16 | 2022-03-29 | 2022-04-04 | 2022-04-04 | MOOE | 5220 | 5220 |  | 5100 | 5100
25 |  | Other Supplies and Materials Expenses | 512ECB | Neg 53.9 | [17 empty] | 512ECB |  | MOOE | [8 empty] | 2022-03-15 | 2022-03-16 | 2022-03-29 | 2022-04-04 | 2022-04-04 | MOOE | 31530 | 31530 |  | 31258 | 31258
26 |  | Medical, Dental & Lab Supplies | 52E-HHCo | Neg 53.9 | [17 empty] | 52E-HHCo |  | MOOE | [8 empty] | 2022-03-15 | 2022-03-16 | 2022-03-29 | 2022-04-04 | 2022-04-04 | MOOE | 25000 | 25000 |  | 23860 | 23860
27 |  | Semi Exp Medical Equipment | 52E-HHCo | Neg 53.9 | [17 empty] | 52E-HHCo |  | MOOE | [8 empty] | 2022-03-15 | 2022-03-16 | 2022-04-04 | 2022-04-08 | 2022-04-08 | MOOE | 10000 | 10000 |  | 9820 | 9820
28 |  | Chemical Filtering | 52E-HHCo | Neg 53.9 | [17 empty] | 52E-HHCo |  | MOOE | [8 empty] | 2022-03-15 | 2022-03-16 | 2022-03-29 | 2022-04-04 | 2022-04-04 | MOOE | 1200 | 1200 |  | 1150 | 1150
29 |  | Drugs and Medicines | 52E-HHCo | Neg 53.9 | [17 empty] | 52E-HHCo |  | MOOE | [8 empty] | 2022-03-15 | 2022-03-16 | 2022-03-29 | 2022-04-04 | 2022-04-04 | MOOE | 35000 | 35000 |  | 34766 | 34766
30 |  | RM ICT Equipment | 524ECB | Neg 53.9 | [17 empty] | 524ECB |  | MOOE | [8 empty] | 2022-03-23 | 2022-03-24 | 2022-04-04 | 2022-04-08 | 2022-04-08 | MOOE | 23500 | 23500 |  | 23200 | 23200
31 |  | Drugs and Medicines | 524ECB | Neg 53.9 | [17 empty] | 524ECB |  | MOOE | [8 empty] | 2022-03-23 | 2022-03-24 | 2022-04-04 | 2022-04-08 | 2022-04-08 | MOOE | 13000 | 13000 |  | 8700 | 8700
32 |  | Mobile Expenses | 524ECB | Neg 53.9 | [17 empty] | 524ECB |  | MOOE | [8 empty] | 2022-03-23 | 2022-03-24 | 2022-04-04 | 2022-04-08 | 2022-04-08 | MOOE | 2400 | 2400 |  | 2100 | 2100
33 |  | Representation Expenses | 524ECB | Neg 53.9 | [17 empty] | 524ECB |  | MOOE | [8 empty] | 2022-03-23 | 2022-03-24 | 2022-04-07 | 2022-04-12 | 2022-04-12 | MOOE | 8066 | 8066 |  | 7940 | 7940
34 |  | Representation Expenses | 524ECB | Neg 53.9 | [17 empty] | 524ECB |  | MOOE | [8 empty] | 2022-03-23 | 2022-03-24 | 2022-04-07 | 2022-04-12 | 2022-04-12 | MOOE | 10104 | 10104 |  | 9920 | 9920
35 |  | R&M - Communication Equipment | 52EBDE | Neg 53.9 | [17 empty] | 52EBDE |  | MOOE | [8 empty] | 2022-03-23 | 2022-03-24 | 2022-04-04 | 2022-04-08 | 2022-04-08 | MOOE | 74100 | 74100 |  | 72730 | 72730
36 |  | Printing and Publications | 52EBDE | Neg 53.9 | [17 empty] | 52EBDE |  | MOOE | [8 empty] | 2022-03-23 | 2022-03-24 | 2022-04-04 | 2022-04-08 | 2022-04-08 | MOOE | 9295 | 9295 |  | 8720 | 8720
37 |  | Office Supplies Expenses | 52EBDE | Neg 53.9 | [17 empty] | 52EBDE |  | MOOE | [8 empty] | 2022-03-23 | 2022-03-24 | 2022-04-07 | 2022-04-08 | 2022-04-08 | MOOE | 20000 | 20000 |  | 19281 | 19281
38 |  | Office Supplies Expenses | 52EBDE | Neg 53.9 | [17 empty] | 52EBDE |  | MOOE | [8 empty] | 2022-03-23 | 2022-03-24 | 2022-04-07 | 2022-04-13 | 2022-04-13 | MOOE | 280818 | 280818 |  | 275312 | 275312
39 |  | Other Supplies and Materials Expenses | 52EBDE | Neg 53.9 | [17 empty] | 52EBDE |  | MOOE | [8 empty] | 2022-03-23 | 2022-03-24 | 2022-04-04 | 2022-04-08 | 2022-04-08 | MOOE | 170069.25 | 170069.25 |  | 168210 | 168210
40 |  | RM of ICT Equipment | 534ECB | Neg 53.9 | [17 empty] | 534ECB |  | MOOE | [8 empty] | 2022-03-23 | 2022-03-24 | 2022-04-04 | 2022-04-08 | 2022-04-08 | MOOE | 10000 | 10000 |  | 9850 | 9850
41 |  | RM Construction Heavy Eqpt | 512ECB | Neg 53.9 | [17 empty] | 512ECB |  | MOOE | [8 empty] | 2022-03-15 | 2022-03-16 | 2022-03-29 | 2022-04-04 | 2022-04-04 | MOOE | 41210 | 41210 |  | 40310 | 40310
42 |  | Office Supplies Expenses | 544ECB | Neg 53.9 | [17 empty] | 544ECB |  | MOOE | [8 empty] | 2022-03-17 | 2022-03-18 | 2022-04-29 | 2022-05-06 | 2022-05-06 | MOOE | 13946 | 13946 |  | 13757 | 13757
43 |  | Office Supplies Expenses | 512ECB | Neg 53.9 | [17 empty] | 512ECB |  | MOOE | [8 empty] | 2022-03-23 | 2022-03-24 | 2022-04-07 | 2022-04-12 | 2022-04-12 | MOOE | 32095 | 32095 |  | 31882 | 31882
44 |  | Office Supplies Expenses | 512ECB | Neg 53.9 | [17 empty] | 512ECB |  | SPP | [8 empty] | 2022-03-23 | 2022-03-24 | 2022-04-07 | 2022-04-12 | 2022-04-12 | MOOE | 25535 | 25535 |  | 25365 | 25365
45 |  | Medical, Dental & Lab Supplies | 52EBDE | Neg 53.9 | [17 empty] | 52EBDE |  | MOOE | [8 empty] | 2022-03-23 | 2022-03-24 | 2022-04-13 | 18 Apr 22 | 18 Apr 22 | MOOE | 84200 | 84200 |  | 78441 | 78441
46 |  | Representation Expenses | 512ECB | Neg 53.9 | [17 empty] | 512ECB |  | MOOE | [8 empty] | 2022-03-23 | 2022-03-24 | 2022-04-07 | 2022-04-12 | 2022-04-12 | MOOE | 49095 | 49095 |  | 48750 | 48750
47 |  | Representation Expenses | 512ECB | Neg 53.9 | [17 empty] | 512ECB |  | MOOE | [8 empty] | 2022-03-23 | 2022-03-24 | 2022-04-07 | 2022-04-12 | 2022-04-12 | MOOE | 14630 | 14630 |  | 14430 | 14430
48 |  | RM ICT Equipment | 52EBDE | Neg 53.9 | [17 empty] | 52EBDE |  | MOOE | [8 empty] | 2022-04-04 | 2022-04-05 | 2022-04-29 | 2022-05-06 | 2022-05-06 | MOOE | 115146 | 115146 |  | 114450 | 114450
49 |  | RM Building | 52EBDE | Neg 53.9 | [17 empty] | 52EBDE |  | MOOE | [8 empty] | 2022-04-04 | 2022-04-05 | 2022-04-20 | 2022-04-27 | 2022-04-27 | MOOE | 68810 | 68810 |  | 68450 | 68450
50 |  | RM Vehicle | 52EBDE | Neg 53.9 | [17 empty] | 52EBDE |  | MOOE | [8 empty] | 2022-04-04 | 2022-04-05 | 2022-04-29 | 2022-05-06 | 2022-05-06 | MOOE | 208720 | 208720 |  | 207440 | 207440
51 |  | Medical, Dental & Lab Supplies | 52EBDE | Neg 53.9 | [17 empty] | 52EBDE |  | MOOE | [8 empty] | 2022-04-08 | 2022-04-11 | 2022-04-29 | 2022-05-06 | 2022-05-06 | MOOE | 150000 | 150000 |  | 149197 | 149197
52 |  | Other Supplies and Materials Expenses | 544ECB | Neg 53.9 | [17 empty] | 544ECB |  | MOOE | [8 empty] | 2022-04-12 | 2022-04-13 | 2022-04-29 | 2022-05-06 | 2022-05-06 | MOOE | 55780 | 55780 |  | 55768 | 55768
53 |  | RM Building | 544ECB | Neg 53.9 | [17 empty] | 544ECB |  | MOOE | [8 empty] | 2022-04-12 | 2022-04-13 | 2022-05-06 | 2022-05-11 | 2022-05-11 | MOOE | 160624 | 160624 |  | 159648 | 159648
54 |  | Representation Expenses | 544ECB | Neg 53.9 | [17 empty] | 544ECB |  | MOOE | [8 empty] | 2022-04-12 | 2022-04-13 | 2022-04-29 | 2022-05-06 | 2022-05-06 | MOOE | 15000 | 15000 |  | 12355 | 12355
55 |  | Medical, Dental & Lab Supplies | 52EBDE | Neg 53.9 | [17 empty] | 52EBDE |  | SPP | [8 empty] | 2022-04-22 | 2022-04-25 | 2022-05-13 | 2022-05-18 | 2022-05-18 | MOOE | 30000 | 30000 |  | 29895 | 29895
56 |  | Semi-Expendable - Medical Equipment | 52EBDE | Neg 53.9 | [17 empty] | 52EBDE |  | MOOE | [8 empty] | 2022-04-22 | 2022-04-25 | 17 May 22 | 2022-05-23 | 2022-05-23 | MOOE | 5000 | 5000 |  | 4800 | 4800
57 |  | Telephone - Mobile Expenses | 52EBDE | Neg 53.9 | [17 empty] | 52EBDE |  | MOOE | [8 empty] | 2022-04-22 | 2022-04-25 | 2022-05-13 | 2022-05-18 | 2022-05-18 | MOOE | 3000 | 3000 |  | 2860 | 2860
58 |  | Office Supplies Expenses | 52EBDE | Neg 53.9 | [17 empty] | 52EBDE |  | MOOE | [8 empty] | 2022-04-22 | 2022-04-25 | 2022-05-13 | 2022-05-18 | 2022-05-18 | MOOE | 47000 | 47000 |  | 45950 | 45950
59 |  | Semi-Expendable - Office Equipment | 52EBDE | Neg 53.9 | [17 empty] | 52EBDE |  | SPP | [8 empty] | 2022-04-22 | 2022-04-25 | 2022-05-13 | 2022-05-18 | 2022-05-18 | MOOE | 15000 | 15000 |  | 14600 | 14600
60 |  | Drugs and Medicines Expenses | 52EBDE | Neg 53.9 | [17 empty] | 52EBDE |  | MOOE | [8 empty] | 2022-04-25 | 2022-04-27 | 2022-05-13 | 2022-05-18 | 2022-05-18 | MOOE | 35000 | 35000 |  | 33865 | 33865
61 |  | Semi-Expendable - ICT Equipment | 52EBDE | Neg 53.9 | [17 empty] | 52EBDE |  | SPP | [8 empty] | 2022-04-25 | 2022-04-27 | 2022-05-13 | 2022-05-18 | 2022-05-18 | MOOE | 106211 | 106211 |  | 105900 | 105900
62 |  | Other Supplies and Materials Expenses | 52EBDE | Neg 53.9 | [17 empty] | 52EBDE |  | MOOE | [8 empty] | 2022-04-25 | 2022-04-27 | 2022-05-13 | 2022-05-18 | 2022-05-18 | MOOE | 2225 | 2225 |  | 2130 | 2130
63 |  | ICT Software Subscription | 52EBDE | Neg 53.9 | [17 empty] | 52EBDE |  | MOOE | [8 empty] | 2022-04-25 | 2022-04-27 | 17 May 22 | 2022-05-23 | 2022-05-23 | MOOE | 69100 | 69100 |  | 68140 | 68140
64 |  | Semi-Expendable - Machinery Equipment Expenses | 52EBDE | Neg 53.9 | [17 empty] | 52EBDE |  | MOOE | [8 empty] | 2022-04-25 | 2022-04-27 | 2022-05-13 | 2022-05-18 | 2022-05-18 | MOOE | 14990 | 14990 |  | 13000 | 13000
65 |  | Other Supplies and Materials Expenses | 52EBDE | Neg 53.9 | [17 empty] | 52EBDE |  | MOOE | [8 empty] | 2022-04-25 | 2022-04-27 | 2022-05-13 | 2022-05-18 | 2022-05-18 | MOOE | 98504.75 | 98504.75 |  | 95063 | 95063
66 |  | Printing and Publication Expenses | 52EBDE | Neg 53.9 | [17 empty] | 52EBDE |  | MOOE | [8 empty] | 2022-04-25 | 2022-04-27 | 2022-05-13 | 2022-05-18 | 2022-05-18 | MOOE | 4500 | 4500 |  | 4420 | 4420
67 |  | Representation Expenses | 534ECB | Neg 53.9 | [17 empty] | 534ECB |  | MOOE | [8 empty] | 2022-05-03 | 2022-05-05 | 17 May 22 | 2022-05-23 | 2022-05-23 | MOOE | 39500 | 39500 |  | 38040 | 38040
68 |  | R & M - ICT Equipment | 534ECB | Neg 53.9 | [17 empty] | 534ECB |  | MOOE | [8 empty] | 2022-05-03 | 2022-05-05 | 17 May 22 | 2022-05-23 | 2022-05-23 | MOOE | 10000 | 10000 |  | 9850 | 9850
69 |  | Other Supplies and Materials Expenses | 52EBDE | Neg 53.9 | [17 empty] | 52EBDE | [10 empty] | 2022-03-23 | 2022-03-24 | 2022-04-04 | 2022-04-08 | 2022-04-08 | SPF | 30000 |  | 30000 | 29165 |  | 29165
1 |  | Internet Expenses | 52EBDE | Direct Cont | [17 empty] | 52EBDE | [15 empty] | MOOE | 7840 | 7840 |  | 7840 | 7840
2 |  | Internet Expenses | 52EBDE | Direct Cont | [17 empty] | 52EBDE | [15 empty] | MOOE | 7840 | 7840 |  | 7840 | 7840
3 |  | Internet Expenses | 52EBDE | Direct Cont | [17 empty] | 52EBDE | [15 empty] | MOOE | 7840 | 7840 |  | 7840 | 7840
4 |  | Internet Expenses | 52EBDE | Direct Cont | [17 empty] | 52EBDE | [15 empty] | MOOE | 7840 | 7840 |  | 7840 | 7840
5 |  | Internet Expenses | 52EBDE | Direct Cont | [17 empty] | 52EBDE | [15 empty] | MOOE | 7840 | 7840 |  | 7840 | 7840
6 |  | Internet Expenses | 52EBDE | Direct Cont | [17 empty] | 52EBDE | [15 empty] | MOOE | 7840 | 7840 |  | 7840 | 7840
7 |  | Mobile Expenses | 52EBDE | Direct Cont | [17 empty] | 52EBDE | [15 empty] | MOOE | 1198 | 1198 |  | 1198 | 1198
8 |  | Mobile Expenses | 52EBDE | Direct Cont | [17 empty] | 52EBDE | [15 empty] | MOOE | 2998 | 2998 |  | 2998 | 2998
9 |  | Mobile Expenses | 52EBDE | Direct Cont | [17 empty] | 52EBDE | [15 empty] | MOOE | 599 | 599 |  | 599 | 599
10 |  | Mobile Expenses | 52EBDE | Direct Cont | [17 empty] | 52EBDE | [15 empty] | MOOE | 497.44 | 497.44 |  | 497.44 | 497.44
11 |  | Internet Expenses | 52EBDE | Direct Cont | [17 empty] | 52EBDE | [15 empty] | MOOE | 3999 | 3999 |  | 3999 | 3999
12 |  | Internet Expenses | 52EBDE | Direct Cont | [17 empty] | 52EBDE | [15 empty] | MOOE | 7840 | 7840 |  | 7840 | 7840
13 |  | Internet Expenses | 52EBDE | Direct Cont | [17 empty] | 52EBDE | [15 empty] | MOOE | 7840 | 7840 |  | 7840 | 7840
14 |  | Internet Expenses | 52EBDE | Direct Cont | [17 empty] | 52EBDE | [15 empty] | MOOE | 4407.19 | 4407.19 |  | 4407.19 | 4407.19
15 |  | Internet Expenses | 52EBDE | Direct Cont | [17 empty] | 52EBDE | [15 empty] | MOOE | 7840 | 7840 |  | 7840 | 7840
16 |  | Internet Expenses | 52EBDE | Direct Cont | [17 empty] | 52EBDE | [15 empty] | MOOE | 7840 | 7840 |  | 7840 | 7840
17 |  | Medical Retainer | 52EBDE | Direct Cont | [17 empty] | 52EBDE | [15 empty] | MOOE | 40000 | 40000 |  | 40000 | 40000
18 |  | Mobile Expenses | 52EBDE | Direct Cont | [17 empty] | 52EBDE | [15 empty] | MOOE | 1123.13 | 1123.13 |  | 1123.13 | 1123.13
19 |  | Mobile Expenses | 52EBDE | Direct Cont | [17 empty] | 52EBDE | [15 empty] | MOOE | 936.56 | 936.56 |  | 936.56 | 936.56
20 |  | Mobile Expenses | 52EBDE | Direct Cont | [17 empty] | 52EBDE | [15 empty] | MOOE | 2245.22 | 2245.22 |  | 2245.22 | 2245.22
21 |  | Mobile Expenses | 52EBDE | Direct Cont | [17 empty] | 52EBDE | [15 empty] | MOOE | 339.82 | 339.82 |  | 339.82 | 339.82
22 |  | Mobile Expenses | 52EBDE | Direct Cont | [17 empty] | 52EBDE | [15 empty] | MOOE | 4215.94 | 4215.94 |  | 4215.94 | 4215.94
23 |  | Mobile Expenses | 52EBDE | Direct Cont | [17 empty] | 52EBDE | [15 empty] | MOOE | 935.63 | 935.63 |  | 935.63 | 935.63
24 |  | Internet Expenses | 52EBDE | Direct Cont | [17 empty] | 52EBDE | [15 empty] | MOOE | 7840 | 7840 |  | 7840 | 7840
25 |  | Internet Expenses | 52EBDE | Direct Cont | [17 empty] | 52EBDE | [15 empty] | MOOE | 7840 | 7840 |  | 7840 | 7840
26 |  | Internet Expenses | 52EBDE | Direct Cont | [17 empty] | 52EBDE | [15 empty] | MOOE | 6048 | 6048 |  | 6048 | 6048
70 |  | Office Supplies Expenses | 544ECB | Neg 53.9 | [17 empty] | 544ECB | [10 empty] | 2022-03-23 | 2022-03-24 | 2022-04-08 | 13 Apr 22 | 13 Apr 22 | MOOE | 2160 | 2160 |  | 2034 | 2034
71 |  | RM Machinery Equipment | 544ECB | Neg 53.9 | [17 empty] | 544ECB | [10 empty] | 2022-04-12 | 2022-04-13 | 2022-05-12 | 17 May 22 | 17 May 22 | MOOE | 14120 | 14120 |  | 13955 | 13955
72 |  | RM Motor Vehicle | 544ECB | Neg 53.9 | [17 empty] | 544ECB | [10 empty] | 2022-04-12 | 2022-04-13 | 2022-04-29 | 06 May 22 | 06 May 22 | MOOE | 24936.5 | 24936.5 |  | 24485 | 24485
73 |  | RM Motor Vehicle | 544ECB | Neg 53.9 | [17 empty] | 544ECB | [10 empty] | 2022-04-12 | 2022-04-13 | 2022-04-29 | 06 May 22 | 06 May 22 | MOOE | 1175 | 1175 |  | 1150 | 1150
74 |  | RM Motor Vehicle | 512ECB | Neg 53.9 | [17 empty] | 512ECB | [10 empty] | 2022-04-22 | 2022-04-25 | 2022-05-24 | 30 May 22 | 30 May 22 | MOOE | 189509 | 189509 |  | 187409 | 187409
75 |  | Representation Expenses | 512ECB | Neg 53.9 | [17 empty] | 512ECB | [10 empty] | 2022-04-22 | 2022-04-25 | 2022-05-19 | 24 May 22 | 24 May 22 | MOOE | 55043 | 55043 |  | 53493 | 53493
76 |  | Representation Expenses | 512ECB | Neg 53.9 | [17 empty] | 512ECB | [10 empty] | 2022-04-22 | 2022-04-25 | 2022-05-19 | 24 May 22 | 24 May 22 | MOOE | 13930 | 13930 |  | 13574 | 13574
77 |  | Office Supplies Expenses | 52EBDE | Neg 53.9 | [17 empty] | 52EBDE | [10 empty] | 2022-04-22 | 2022-04-25 | 2022-06-10 | 16 Jun 22 | 16 Jun 22 | MOOE | 216521.5 | 216521.5 |  | 214395 | 214395
78 |  | R & M - Communication Equipment | 52EBDE | Neg 53.9 | [17 empty] | 52EBDE | [10 empty] | 2022-04-22 | 2022-04-25 | 2022-05-18 | 23 May 22 | 23 May 22 | MOOE | 27000 | 27000 |  | 26780 | 26780
79 |  | R & M - ICT Equipment | 52EBDE | Neg 53.9 | [17 empty] | 52EBDE | [10 empty] | 2022-04-22 | 2022-04-25 | 2022-05-24 | 30 May 22 | 30 May 22 | MOOE | 45000 | 45000 |  | 44480 | 44480
80 |  | Drugs and Medicines Expenses | 52EBDE | Neg 53.9 | [17 empty] | 52EBDE | [10 empty] | 2022-04-25 | 2022-04-27 | 2022-05-13 | 2022-05-18 | 2022-05-18 | MOOE | 35000 | 35000 |  | 33865 | 33865
81 |  | Chemical and Filtering Supplies Expenses | 52EBDE | Neg 53.9 | [17 empty] | 52EBDE | [10 empty] | 2022-04-25 | 2022-04-27 | 17 May 22 | 2022-05-23 | 2022-05-23 | MOOE | 1200 | 1200 |  | 1190 | 1190
82 |  | Other Supplies and Materials Expenses | 52EBDE | Neg 53.9 | [17 empty] | 52EBDE | [10 empty] | 2022-04-25 | 2022-04-27 | 2022-05-24 | 30 May 22 | 30 May 22 | MOOE | 70286.5 | 70286.5 |  | 69061 | 69061
83 |  | Semi-Expendable - Medical Equipment | 52EBDE | Neg 53.9 | [17 empty] | 52EBDE | [10 empty] | 2022-04-25 | 2022-04-27 | 2022-06-07 | 13 Jun 22 | 13 Jun 22 | MOOE | 15000 | 15000 |  | 14900 | 14900
84 |  | Medical, Dental & Lab Supplies | 52EBDE | Neg 53.9 | [17 empty] | 52EBDE | [10 empty] | 2022-04-25 | 2022-04-27 | 2022-05-13 | 2022-05-18 | 2022-05-18 | MOOE | 41350 | 41350 |  | 41150 | 41150
85 |  | Office Supplies Expenses | 524ECB | Neg 53.9 | [17 empty] | 524ECB | [10 empty] | 2022-05-03 | 2022-05-05 | 2022-05-19 | 25 May 22 | 25 May 22 | MOOE | 109750 | 109750 |  | 109632 | 109632
86 |  | Representation Expenses | 524ECB | Neg 53.9 | [17 empty] | 524ECB | [10 empty] | 2022-05-03 | 2022-05-05 | 2022-05-19 | 25 May 22 | 25 May 22 | MOOE | 40544 | 40544 |  | 40344 | 40344
87 |  | Telephone - Mobile Expenses | 524ECB | Neg 53.9 | [17 empty] | 524ECB | [10 empty] | 2022-05-03 | 2022-05-05 | 2022-05-23 | 27 May 22 | 27 May 22 | MOOE | 2400 | 2400 |  | 2100 | 2100
88 |  | R & M - Motor Vehicles | 534ECB | Neg 53.9 | [17 empty] | 534ECB | [10 empty] | 2022-05-03 | 2022-05-05 | 2022-05-27 | 01 Jun 22 | 01 Jun 22 | MOOE | 130000 | 130000 |  | 128060 | 128060
89 |  | R & M - Construction & Heavy Equipment | 534ECB | Neg 53.9 | [17 empty] | 534ECB | [10 empty] | 2022-05-03 | 2022-05-05 | 17 May 22 | 2022-05-23 | 2022-05-23 | MOOE | 89995 | 89995 |  | 88925 | 88925
90 |  | Office Supplies Expenses | 534ECB | Neg 53.9 | [17 empty] | 534ECB | [10 empty] | 2022-05-03 | 2022-05-05 | 2022-05-18 | 23 May 22 | 23 May 22 | MOOE | 16500 | 16500 |  | 15508 | 15508
91 |  | Semi-Expendable - Machinery Equipment Expenses | 512ECB | Neg 53.9 | [17 empty] | 512ECB | [10 empty] | 2022-05-03 | 2022-05-05 | 2022-05-19 | 24 May 22 | 24 May 22 | MOOE | 46189 | 46189 |  | 45100 | 45100
92 |  | Office Supplies Expenses | 512ECB | Neg 53.9 | [17 empty] | 512ECB | [10 empty] | 2022-05-03 | 2022-05-05 | 2022-06-10 | 16 Jun 22 | 16 Jun 22 | MOOE | 50959 | 50959 |  | 50389 | 50389
93 |  | R & M - ICT Equipment | 524ECB | Neg 53.9 | [17 empty] | 524ECB | [10 empty] | 2022-05-11 | 2022-05-12 | 2022-06-07 | 13 Jun 22 | 13 Jun 22 | MOOE | 19500 | 19500 |  | 19450 | 19450
94 |  | Representation Expenses | ESC | Neg 53.9 | [17 empty] | ESC | [10 empty] | 2022-05-11 | 2022-05-12 | 2022-05-27 | 30 May 22 | 30 May 22 | MOOE | 7040 | 7040 |  | 6666 | 6666
95 |  | R & M - Construction & Heavy Equipment | ESC | Neg 53.9 | [17 empty] | ESC | [10 empty] | 2022-05-11 | 2022-05-12 | 2022-05-27 | 02 Jun 22 | 02 Jun 22 | MOOE | 70000 | 70000 |  | 69000 | 69000
96 |  | R & M -Motor Vehicles | ESC | Neg 53.9 | [17 empty] | ESC | [10 empty] | 2022-05-11 | 2022-05-12 | 2022-05-27 | 02 Jun 22 | 02 Jun 22 | MOOE | 25000 | 25000 |  | 24500 | 24500
97 |  | Internet Expenses (Prepaid) | ESC | Neg 53.9 | [17 empty] | ESC | [10 empty] | 2022-05-11 | 2022-05-12 | 2022-05-27 | 01 Jun 22 | 01 Jun 22 | MOOE | 12600 | 12600 |  | 12250 | 12250
98 |  | Office Supplies Expenses | ESC | Neg 53.9 | [17 empty] | ESC | [10 empty] | 2022-05-11 | 2022-05-12 | 2022-05-27 | 01 Jun 22 | 01 Jun 22 | MOOE | 31545 | 31545 |  | 30015 | 30015
99 |  | R & M - Buildings and Other Structures | 544ECB | Neg 53.9 | [17 empty] | 544ECB | [10 empty] | 2022-05-17 | 2022-05-18 | 2022-05-27 | 03 Jun 22 | 03 Jun 22 | MOOE | 151821.25 | 151821.25 |  | 150950 | 150950
100 |  | Office Supplies Expenses | 544ECB | Neg 53.9 | [17 empty] | 544ECB | [10 empty] | 2022-05-17 | 2022-05-18 | 2022-05-27 | 01 Jun 22 | 01 Jun 22 | MOOE | 36054 | 36054 |  | 35291 | 35291
101 |  | R & M -Motor Vehicles | 544ECB | Neg 53.9 | [17 empty] | 544ECB | [10 empty] | 2022-05-17 | 2022-05-18 | 2022-05-27 | 02 Jun 22 | 02 Jun 22 | MOOE | 54536.5 | 54536.5 |  | 53495 | 53495
102 |  | Representation Expenses | 544ECB | Neg 53.9 | [17 empty] | 544ECB | [10 empty] | 2022-05-30 | 2022-06-01 | 2022-06-15 | 23 Jun 22 | 23 Jun 22 | MOOE | 52515 | 52515 |  | 52485 | 52485
103 |  | Other Supplies and Materials Expenses | 544ECB | Neg 53.9 | [17 empty] | 544ECB | [10 empty] | 30 May 22 | 01 June 2022 | 2022-06-15 | 23 Jun 22 | 23 Jun 22 | MOOE | 63055 | 63055 |  | 62517 | 62517
104 |  | R & M - Buildings | ESC | Neg 53.9 | [17 empty] | ESC | [10 empty] | 30 May 22 | 01 June 2022 | 2022-06-24 | 30 June 2022 | 30 June 2022 | MOOE | 73000 | 73000 |  | 71040 | 71040
105 |  | R & M - Motor Vehicles | 524ECB | Neg 53.9 | [17 empty] | 524ECB | [10 empty] | 30 May 22 | 01 June 2022 | 2022-06-23 | 30 June 2022 | 30 June 2022 | MOOE | 84150 | 84150 |  | 82600 | 82600
106 |  | Semi-Expendable - ICT Equipment | 524ECB | Neg 53.9 | [17 empty] | 524ECB | [10 empty] | 2022-06-09 | 2022-06-13 | 2022-06-23 | 29 Jun 22 | 29 Jun 22 | MOOE | 19050 | 19050 |  | 18400 | 18400
107 |  | Semi-Expendable - ICT Equipment | 524ECB | Neg 53.9 | [17 empty] | 524ECB | [10 empty] | 2022-06-09 | 2022-06-13 | 2022-06-23 | 29 Jun 22 | 29 Jun 22 | MOOE | 60180 | 60180 |  | 59800 | 59800
108 |  | Printing and Publication Expenses | 52EBDE | Neg 53.9 | [17 empty] | 52EBDE | [10 empty] | 10 June 2022 | 14 June 2022 | 29 June 2022 | 06 Jul 22 | 06 Jul 22 | MOOE | 4500 | 4500 |  | 4415 | 4415
109 |  | Other Supplies and Materials Expenses | 52EBDE | Neg 53.9 | [17 empty] | 52EBDE | [10 empty] | 10 June 2022 | 14 June 2022 | 29 June 2022 | 06 Jul 22 | 06 Jul 22 | MOOE | 198045.25 | 198045.25 |  | 194951 | 194951
110 |  | Semi-Expendable - ICT Equipment | 52EBDE | Neg 53.9 | [17 empty] | 52EBDE | [10 empty] | 2022-06-13 | 2022-06-14 | 2022-07-11 | 15 Jul 22 | 15 Jul 22 | MOOE | 87450 | 87450 |  | 86800 | 86800
111 |  | ICT - Software Subscription | 52EBDE | Neg 53.9 | [17 empty] | 52EBDE | [10 empty] | 2022-06-13 | 2022-06-14 | 29 June 2022 | 06 Jul 22 | 06 Jul 22 | MOOE | 6000 | 6000 |  | 4960 | 4960
112 |  | Medical, Dental & Lab Supplies | 52EBDE | Neg 53.9 | [17 empty] | 52EBDE | [10 empty] | 10 June 2022 | 14 June 2022 | 29 June 2022 | 06 Jul 22 | 06 Jul 22 | MOOE | 30000 | 30000 |  | 29915 | 29915
113 |  | Drugs and Medicines Expenses | 52EBDE | Neg 53.9 | [17 empty] | 52EBDE | [10 empty] | 10 June 2022 | 14 June 2022 | 29 June 2022 | 06 Jul 22 | 06 Jul 22 | MOOE | 35000 | 35000 |  | 33420 | 33420
114 |  | Office Supplies Expenses | 52EBDE | Neg 53.9 | [17 empty] | 52EBDE | [10 empty] | 15 June 2022 | 16 June 2022 | 29 June 2022 | 06 Jul 22 | 06 Jul 22 | MOOE | 136544.5 | 136544.5 |  | 135753 | 135753
115 |  | Enhancement of ICT Equipment | 512ECB | Neg 53.9 | [17 empty] | 512ECB | [10 empty] | 2022-06-20 | 2022-06-21 | 2022-07-05 | 11 Jul 22 | 11 Jul 22 | MOOE | 80000 | 80000 |  | 79880 | 79880
116 |  | R & M - Motor Vehicles | 512ECB | Neg 53.9 | [17 empty] | 512ECB | [10 empty] | 2022-06-29 | 2022-06-30 | 2022-07-15 | 21 Jul 22 | 21 Jul 22 | MOOE | 49858 | 49858 |  | 49450 | 49450
117 |  | R & M - Construction & Heavy Equipment | 512ECB | Neg 53.9 | [17 empty] | 512ECB | [10 empty] | 2022-05-30 | 2022-06-01 | 2022-06-15 | 22 Jun 22 | 22 Jun 22 | SPF | 530000 |  | 530000 | 524200 |  | 524200
118 |  | R & M - Buildings (Female Barracks) | 52EBDE | Neg 53.9 | [17 empty] | 52EBDE | [10 empty] | 2022-05-30 | 2022-06-01 | 2022-06-24 | 01 Jul 22 | 01 Jul 22 | SPF | 300000 |  | 300000 | 297960 |  | 297960
119 |  | ICT - Software Subscription | 52EBDE | Neg 53.9 | [17 empty] | 52EBDE | [10 empty] | 2022-06-09 | 2022-06-13 | 29 June 2022 | 06 Jul 22 | 06 Jul 22 | SPF | 8336 |  | 8336 | 8240 |  | 8240
120 |  | Semi-Expendable - ICT Equipment | 52EBDE | Neg 53.9 | [17 empty] | 52EBDE | [10 empty] | 2022-06-09 | 2022-06-13 | 29 June 2022 | 06 Jul 22 | 06 Jul 22 | SPF | 46690 |  | 46690 | 44900 |  | 44900
121 |  | ICT - Office Supplies Expenses | 52EBDE | Neg 53.9 | [17 empty] | 52EBDE | [10 empty] | 09 June 2022 | 13 June 2022 | 29 June 2022 | 06 Jul 22 | 06 Jul 22 | SPF | 18646.25 |  | 18646.25 | 18050 |  | 18050
122 |  | ICT - Office Supplies Expenses | 52EBDE | Neg 53.9 | [17 empty] | 52EBDE | [10 empty] | 09 June 2022 | 13 June 2022 | 29 June 2022 | 06 Jul 22 | 06 Jul 22 | SPF | 2500 |  | 2500 | 2375 |  | 2375
123 |  | Semi - Expendable - Office Equipment | 52EBDE | Neg 53.9 | [17 empty] | 52EBDE | [10 empty] | 09 June 2022 | 13 June 2022 | 29 June 2022 | 06 Jul 22 | 06 Jul 22 | SPF | 17490 |  | 17490 | 16750 |  | 16750
124 |  | Other Supplies and Materials Expenses | 52EBDE | Neg 53.9 | [17 empty] | 52EBDE | [10 empty] | 09 June 2022 | 13 June 2022 | 29 June 2022 | 06 Jul 22 | 06 Jul 22 | SPF | 7500 |  | 7500 | 7280 |  | 7280
125 |  | Semi-Expendable - Furniture and Fixtures | 52EBDE | Neg 53.9 | [17 empty] | 52EBDE | [10 empty] | 09 June 2022 | 13 June 2022 | 29 June 2022 | 06 Jul 22 | 06 Jul 22 | SPF | 22800 |  | 22800 | 22400 |  | 22400
126 |  | Semi-Expendable - ICT Equipment | 52EBDE | Neg 53.9 | [17 empty] | 52EBDE | [10 empty] | 2022-06-13 | 2022-06-14 | 2022-06-29 | 06 Jul 22 | 06 Jul 22 | SPF | 44522.05 |  | 44522.05 | 42540 |  | 42540
127 |  | ICT - Software Subscription | 52EBDE | Neg 53.9 | [17 empty] | 52EBDE | [10 empty] | 2022-06-13 | 2022-06-14 | 2022-06-29 | 06 Jul 22 | 06 Jul 22 | SPF | 4689.5 |  | 4689.5 | 3580 |  | 3580
128 |  | Internet Subsctiption Expenses (Prepaid) | 52EBDE | Neg 53.9 | [17 empty] | 52EBDE | [10 empty] | 2022-06-15 | 2022-06-16 | 2022-07-01 | 08 Jul 22 | 08 Jul 22 | SPF | 5500 |  | 5500 | 5340 |  | 5340
129 |  | R & M - ICT Equipment | 52EBDE | Neg 53.9 | [17 empty] | 52EBDE | [10 empty] | 2022-06-20 | 2022-06-21 | 2022-07-08 | 14 Jul 22 | 14 Jul 22 | SPF | 6250 |  | 6250 | 6230 |  | 6230
130 |  | Semi-Expendable - ICT Equipment | 52EBDE | Neg 53.9 | [17 empty] | 52EBDE | [10 empty] | 2022-06-22 | 2022-06-23 | 2022-08-15 | 26 Aug 22 | 26 Aug 22 | SPF | 30539.75 |  | 30539.75 | 30400 |  | 30400
131 |  | R & M - Apartment Building Nr 1 | 52EBDE | Neg 53.9 | [17 empty] | 52EBDE | [10 empty] | 2022-06-23 | 2022-06-24 | 2022-07-05 | 11 Jul 22 | 11 Jul 22 | SPF | 516740 |  | 516740 | 512840 |  | 512840
132 |  | R & M - Apartment Building Nr 4 | 52EBDE | Neg 53.9 | [17 empty] | 52EBDE | [10 empty] | 2022-06-23 | 2022-06-24 | 2022-07-11 | 18 Jul 22 | 18 Jul 22 | SPF | 504330 |  | 504330 | 500600 |  | 500600
133 |  | R & M - Apartment Building Nr 3 | 52EBDE | Neg 53.9 | [17 empty] | 52EBDE | [10 empty] | 2022-06-23 | 2022-06-24 | 2022-07-15 | 22 Jul 22 | 22 Jul 22 | SPF | 508500 |  | 508500 | 504770 |  | 504770
134 |  | R & M - Apartment Building Nr 2 | 52EBDE | Neg 53.9 | [17 empty] | 52EBDE | [10 empty] | 2022-06-23 | 2022-06-24 | 2022-07-26 | 02 Aug 22 | 02 Aug 22 | SPF | 537340 |  | 537340 | 533440 |  | 533440
135 |  | R & M - Construction & Heavy Equipment | 544ECB | Neg 53.9 | [17 empty] | 544ECB | [10 empty] | 2022-06-27 | 2022-06-28 | 2022-07-11 | 18 Jul 22 | 18 Jul 22 | SPF | 461000 |  | 461000 | 457100 |  | 457100
136 |  | R & M - Construction & Heavy Equipment | ESC | Neg 53.9 | [17 empty] | ESC | [10 empty] | 2022-06-29 | 2022-06-30 | 2022-07-15 | 21 Jul 22 | 21 Jul 22 | SPF | 337400 |  | 337400 | 334500 |  | 334500
137 |  | R & M - Motor Vehicles | 52EBDE | Neg 53.9 | [17 empty] | 52EBDE | [10 empty] | 2022-07-11 | 2022-07-12 | 2022-07-27 | 01 Aug 22 | 01 Aug 22 | MOOE | 155000 | 155000 |  | 153860 |  | 153860
138 |  | Mobile Expenses | 524ECB | Neg 53.9 | [17 empty] | 524ECB | [10 empty] | 2022-07-20 | 2022-07-21 | 2022-08-08 | 19 Aug 22 | 19 Aug 22 | MOOE | 2400 | 2400 |  | 2100 |  | 2100
139 |  | Representation Expenses | 524ECB | Neg 53.9 | [17 empty] | 524ECB | [10 empty] | 2022-07-20 | 2022-07-21 | 2022-08-08 | 19 Aug 22 | 19 Aug 22 | MOOE | 10104 | 10104 |  | 10086 |  | 10086
140 |  | Drugs and Medicines Expenses | 524ECB | Neg 53.9 | [17 empty] | 524ECB | [10 empty] | 2022-07-20 | 2022-07-21 | 2022-08-08 | 19 Aug 22 | 19 Aug 22 | MOOE | 13000 | 13000 |  | 12600 |  | 12600
141 |  | R & M - Building | 544ECB | Neg 53.9 | [17 empty] | 544ECB | [10 empty] | 2022-07-20 | 2022-07-21 | 2022-08-08 | 23 Aug22 | 23 Aug22 | SPL | 996700 |  | 996700 | 990349 |  | 990349
142 |  | R & M - Buildings | 52EBDE | Neg 53.9 | [17 empty] | 52EBDE | [10 empty] | 2022-07-15 | 2022-07-18 | 2022-08-08 | 15 Aug 22 | 15 Aug 22 | MOOE | 416481.45 | 416481.45 |  | 413822 |  | 413822
143 |  | R & M - Motor Vehicles | 524ECB | Neg 53.9 | [17 empty] | 524ECB | [10 empty] | 2022-07-25 | 2022-07-26 | 2022-08-11 | 24 Aug 22 | 24 Aug 22 | MOOE | 105355 | 105355 |  | 101905 |  | 101905
144 |  | Semi-Expendable - Communication Equipment | 524ECB | Neg 53.9 | [17 empty] | 524ECB | [10 empty] | 2022-07-25 | 2022-07-26 | 2022-08-08 | 19 Aug 22 | 19 Aug 22 | MOOE | 21300 | 21300 |  | 21000 |  | 21000
145 |  | Office Supplies Expenses | 512ECB | Neg 53.9 | [17 empty] | 512ECB | [10 empty] | 2022-07-25 | 2022-07-26 | 2022-08-11 | 19 Aug 22 | 19 Aug 22 | MOOE | 29781 | 29781 |  | 28688 |  | 28688
146 |  | R & M - Motor Vehicles | 512ECB | Neg 53.9 | [17 empty] | 512ECB | [10 empty] | 2022-07-25 | 2022-07-26 | 2022-08-11 | 24 Aug 22 | 24 Aug 22 | MOOE | 83170 | 83170 |  | 80150 |  | 80150
147 |  | Representation Expenses | 512ECB | Neg 53.9 | [17 empty] | 512ECB | [10 empty] | 2022-07-25 | 2022-07-26 | 2022-08-11 | 26 Aug 22 | 26 Aug 22 | MOOE | 26305 | 26305 |  | 25490 |  | 25490
148 |  | Semi-Expendable - ICT Equipment | 52EBDE | Neg 53.9 | [17 empty] | 52EBDE | [10 empty] | 2022-07-25 | 2022-07-26 | 2022-08-15 | 26 Aug 22 | 26 Aug 22 | SPF | 30539.75 |  | 30539.75 | 30400 |  | 30400
149 |  | Medical, Dental & Lab Supplies | 544ECB | Neg 53.9 | [17 empty] | 544ECB | [10 empty] | 2022-08-03 | 2022-08-04 | 2022-08-17 | 26 Aug 22 | 26 Aug 22 | MOOE | 8000 | 8000 |  | 7830 |  | 7830
150 |  | R & M - Buildings | 544ECB | Neg 53.9 | [17 empty] | 544ECB | [10 empty] | 2022-08-03 | 2022-08-04 | 2022-08-18 | 24 Aug 22 | 24 Aug 22 | MOOE | 195140.5 | 195140.5 |  | 192938 |  | 192938
151 |  | R & M - Construction & Heavy Equipment | 534ECB | Neg 53.9 | [17 empty] | 534ECB | [10 empty] | 2022-08-03 | 2022-08-04 | 2022-08-15 | 24 Aug 22 | 24 Aug 22 | MOOE | 95000 | 95000 |  | 93010 |  | 93010
152 |  | R & M - Motor Vehicles | 534ECB | Neg 53.9 | [17 empty] | 534ECB | [10 empty] | 2022-08-03 | 2022-08-04 | 2022-08-15 | 24 Aug 22 | 24 Aug 22 | MOOE | 35000 | 35000 |  | 33960 |  | 33960
153 |  | R & M - Motor Vehicles | 544ECB | Neg 53.9 | [17 empty] | 544ECB | [10 empty] | 2022-08-03 | 2022-08-04 | 2022-08-17 | 24 Aug 22 | 24 Aug 22 | MOOE | 24936.5 | 24936.5 |  | 24250 |  | 24250
154 |  | R & M - Buildings and Other Structures | 534ECB | Neg 53.9 | [17 empty] | 534ECB | [10 empty] | 2022-08-08 | 2022-08-09 | 2022-08-18 | 24 Aug 22 | 24 Aug 22 | MOOE | 100000 | 100000 |  | 99620 |  | 99620
155 |  | Office Supplies Expenses | 534ECB | Neg 53.9 | [17 empty] | 534ECB | [10 empty] | 2022-08-08 | 2022-08-09 | 2022-08-17 | 22 Aug 22 | 22 Aug 22 | MOOE | 13000 | 13000 |  | 12443 |  | 12443
156 |  | Representation Expenses | 534ECB | Neg 53.9 | [17 empty] | 534ECB | [10 empty] | 2022-08-08 | 2022-08-09 | 2022-08-24 | 30 Aug 22 | 30 Aug 22 | MOOE | 44500 | 44500 |  | 42915 |  | 42915
157 |  | R & M - ICT Equipment (Machinery and Equipment) | 534ECB | Neg 53.9 | [17 empty] | 534ECB | [10 empty] | 2022-08-08 | 2022-08-09 | 2022-08-17 | 24 Aug 22 | 24 Aug 22 | MOOE | 10000 | 10000 |  | 7700 |  | 7700
158 |  | Representation Expenses | 544ECB | Neg 53.9 | [17 empty] | 544ECB | [10 empty] | 2022-08-08 | 2022-08-09 | 2022-08-18 | 30 Aug 22 | 30 Aug 22 | MOOE | 32170 | 32170 |  | 32120 |  | 32120
159 |  | Other Supplies and Materials Expenses | 544ECB | Neg 53.9 | [17 empty] | 544ECB | [10 empty] | 2022-08-08 | 2022-08-09 | 2022-08-18 | 24 Aug 22 | 24 Aug 22 | MOOE | 73805 | 73805 |  | 73711 |  | 73711
160 |  | Office Supplies Expenses | 544ECB | Neg 53.9 | [17 empty] | 544ECB | [10 empty] | 2022-08-10 | 2022-08-11 | 2022-08-13 | 19 Aug 22 | 19 Aug 22 | MOOE | 33684.25 | 33684.25 |  | 32949 |  | 32949
161 |  | Office Supplies Expenses | 524ECB | Neg 53.9 | [17 empty] | 524ECB | [10 empty] | 2022-08-10 | 2022-08-11 | 2022-08-13 | 19 Aug 22 | 19 Aug 22 | MOOE | 100352.5 | 100352.5 |  | 99795 |  | 99795
162 |  | Semi-Expendable - Military Police and Security Equipment | 524ECB | Neg 53.9 | [17 empty] | 524ECB | [10 empty] | 2022-08-10 | 2022-08-11 | 2022-09-06 | 09 Aug 22 | 09 Aug 22 | MOOE | 7800 | 7800 |  | 7700 |  | 7700
163 |  | R & M - Buildings (Officer Apartment) | 52EBDE | Neg 53.9 | [17 empty] | 52EBDE | [10 empty] | 2022-08-10 | 2022-08-11 | 2022-09-13 | 20 Sep 22 | 20 Sep 22 | SPF | 500365 |  | 500365 | 496805 |  | 496805
164 |  | R & M - Buildings | ESC | Neg 53.9 | [17 empty] | ESC | [10 empty] | 2022-08-15 | 2022-08-16 | 2022-09-06 | 12 Sep 22 | 12 Sep 22 | MOOE | 25000 | 25000 |  | 24900 |  | 24900
165 |  | R & M - Motor Vehicles | ESC | Neg 53.9 | [17 empty] | ESC | [10 empty] | 2022-08-15 | 2022-08-16 | 2022-09-13 | 19 Sep 22 | 19 Sep 22 | MOOE | 65000 | 65000 |  | 63500 |  | 63500
166 |  | Semi-Exp ICT Equipment | 52EBDE | Neg 53.9 | [17 empty] | 52EBDE | [10 empty] | 2022-08-26 | 2022-08-27 | 2022-09-14 | 19 Sep 22 | 19 Sep 22 | MOOE | 50000 | 50000 |  | 49500 |  | 49500
167 |  | R & M - ICT Equipment | 544ECB | Neg 53.9 | [17 empty] | 544ECB | [10 empty] | 2022-08-26 | 2022-08-30 | 2022-09-13 | 19 Sep 22 | 19 Sep 22 | MOOE | 51500 | 51500 |  | 51200 |  | 51200
168 |  | Internet Subsctiption Expenses (Prepaid) | ESC | Neg 53.9 | [17 empty] | ESC | [10 empty] | 2022-09-05 | 2022-09-06 | 2022-09-19 | 23 Sep 22 | 23 Sep 22 | MOOE | 12600 | 12600 |  | 12250 |  | 12250
169 |  | Representation Expenses | ESC | Neg 53.9 | [17 empty] | ESC | [10 empty] | 2022-09-05 | 2022-09-06 | 2022-09-26 | 12 Oct 22 | 12 Oct 22 | MOOE | 10150 | 10150 |  | 9536 |  | 9536
170 |  | Office Supplies Expenses | ESC | Neg 53.9 | [17 empty] | ESC | [10 empty] | 2022-09-05 | 2022-09-06 | 2022-09-19 | 23 Sep 22 | 23 Sep 22 | MOOE | 32435 | 32435 |  | 31713 |  | 31713
171 |  | R & M - ICT Equipment | 544ECB | Neg 53.9 | [17 empty] | 544ECB | [10 empty] | 2022-09-09 | 2022-09-12 | 2022-09-20 | 23 Sep 22 | 23 Sep 22 | MOOE | 63000 | 63000 |  | 55200 |  | 55200
172 |  | Other Supplies and Materials Expenses | 111TH CO | Neg 53.9 | [17 empty] | 111TH CO | [10 empty] | 2022-09-20 | 2022-09-21 | 2022-10-03 | 06 Oct 22 | 06 Oct 22 | MOOE | 19500 | 19500 |  | 19170
173 |  | Mobile Expenses | 111TH CO | Neg 53.9 | [17 empty] | 111TH CO | [10 empty] | 2022-09-20 | 2022-09-21 | 2022-10-03 | 06 Oct 22 | 06 Oct 22 | MOOE | 5000 | 5000 |  | 4640
174 |  | Representation Expenses | 111TH CO | Neg 53.9 | [17 empty] | 111TH CO | [10 empty] | 2022-09-20 | 2022-09-21 | 2022-10-03 | 06 Oct 22 | 06 Oct 22 | MOOE | 5000 | 5000 |  | 4933
175 |  | Office Supplies Expenses | 111TH CO | Neg 53.9 | [17 empty] | 111TH CO | [10 empty] | 2022-09-20 | 2022-09-21 | 2022-10-03 | 06 Oct 22 | 06 Oct 22 | MOOE | 16250 | 16250 |  | 15500
176 |  | Office Supplies Expenses | 524ECB | Neg 53.9 | [17 empty] | 524ECB | [10 empty] | 2022-09-21 | 2022-09-22 | 2022-09-30 | 05 Oct 22 | 05 Oct 22 | MOOE | 15332 | 15332 |  | 15285
177 |  | Representation Expenses | 524ECB | Neg 53.9 | [17 empty] | 524ECB | [10 empty] | 2022-09-21 | 2022-09-22 | 2022-09-30 | 05 Oct 22 | 05 Oct 22 | MOOE | 8066 | 8066 |  | 8030
178 |  | RM of Motor Vehicle | 524ECB | Neg 53.9 | [17 empty] | 524ECB | [10 empty] | 2022-09-21 | 2022-09-22 | 2022-09-30 | 05 Oct 22 | 05 Oct 22 | MOOE | 8020 | 8020 |  | 8000
179 |  | Office Supplies Expenses | 512ECB | Neg 53.9 | [17 empty] | 512ECB | [10 empty] | 2022-09-28 | 2022-09-29 | 2022-10-03 | 07 Oct 22 | 07 Oct 22 | MOOE | 18475 | 18475 |  | 17840
180 |  | Office Supplies Expenses | 544ECB | Neg 53.9 | [17 empty] | 544ECB | [10 empty] | 2022-09-28 | 2022-09-29 | 2022-10-03 | 07 Oct 22 | 07 Oct 22 | MOOE | 9460 | 9460 |  | 9396
181 |  | RM of Building | 544ECB | Neg 53.9 | [17 empty] | 544ECB | [10 empty] | 2022-09-28 | 2022-09-29 | 2022-10-03 | 07 Oct 22 | 07 Oct 22 | MOOE | 4260 | 4260 |  | 4197
182 |  | Military Police Equipment | 524ECB | Neg 53.9 | [17 empty] | 524ECB | [10 empty] | 2022-09-28 | 2022-09-29 | 2022-10-03 | 07 Oct 22 | 07 Oct 22 | MOOE | 11200 | 11200 |  | 9000
183 |  | Representation Expenses | 512ECB | Neg 53.9 | [17 empty] | 512ECB | [10 empty] | 2022-09-29 | 2022-09-30 | 2022-10-10 | 17 Oct 22 | 17 Oct 22 | MOOE | 128970 | 128970 |  | 124255
184 |  | Office Supplies Expenses | 512ECB | Neg 53.9 | [17 empty] | 512ECB | [10 empty] | 2022-09-29 | 2022-09-30 | 2022-10-10 | 17 Oct 22 | 17 Oct 22 | MOOE | 24410 | 24410 |  | 23615
185 |  | Office Supplies Expenses | 524ECB | Neg 53.9 | [17 empty] | 524ECB | [10 empty] | 2022-09-29 | 2022-09-30 | 2022-10-10 | 17 Oct 22 | 17 Oct 22 | MOOE | 72267.5 | 72267.5 |  | 72246
186 |  | Mobile Expenses | 524ECB | Neg 53.9 | [17 empty] | 524ECB | [10 empty] | 2022-09-29 | 2022-09-30 | 2022-10-10 | 17 Oct 22 | 17 Oct 22 | MOOE | 2400 | 2400 |  | 2100
187 |  | Other Supplies and Materials Expenses | 524ECB | Neg 53.9 | [17 empty] | 524ECB | [10 empty] | 2022-09-29 | 2022-09-30 | 2022-10-10 | 17 Oct 22 | 17 Oct 22 | MOOE | 6228 | 6228 |  | 6060
188 |  | Representation Expenses | 524ECB | Neg 53.9 | [17 empty] | 524ECB | [10 empty] | 2022-09-29 | 2022-09-30 | 2022-10-10 | 17 Oct 22 | 17 Oct 22 | MOOE | 55935 | 55935 |  | 55924
189 |  | Representation Expenses | 534ECB | Neg 53.9 | [17 empty] | 534ECB | [10 empty] | 2022-09-29 | 2022-09-30 | 2022-10-10 | 17 Oct 22 | 17 Oct 22 | MOOE | 28500 | 28500 |  | 27487
190 |  | Office Supplies Expenses | 534ECB | Neg 53.9 | [17 empty] | 534ECB | [10 empty] | 2022-09-29 | 2022-09-30 | 2022-10-10 | 17 Oct 22 | 17 Oct 22 | MOOE | 14000 | 14000 |  | 13470
191 |  | R & M - ICT Equipment | 534ECB | Neg 53.9 | [17 empty] | 534ECB | [10 empty] | 2022-09-29 | 2022-09-30 | 2022-10-10 | 17 Oct 22 | 17 Oct 22 | MOOE | 10000 | 10000 |  | 7700
192 |  | Office Supplies Expenses | 544ECB | Neg 53.9 | [17 empty] | 544ECB | [10 empty] | 2022-09-29 | 2022-09-30 | 2022-10-10 | 17 Oct 22 | 17 Oct 22 | MOOE | 19674 | 19674 |  | 19123
193 |  | Other Supplies and Materials Expenses | 544ECB | Neg 53.9 | [17 empty] | 544ECB | [10 empty] | 2022-09-29 | 2022-09-30 | 2022-10-10 | 17 Oct 22 | 17 Oct 22 | MOOE | 24240 | 24240 |  | 24168
194 |  | RM Motor Vehicles | 544ECB | Neg 53.9 | [17 empty] | 544ECB | [10 empty] | 2022-09-29 | 2022-09-30 | 2022-10-10 | 17 Oct 22 | 17 Oct 22 | MOOE | 33911.5 | 33911.5 |  | 33445
195 |  |  |  | Neg 53.9 | [28 empty] | 2022-09-29 | 2022-09-30 | 2022-10-10 | 17 Oct 22 | 17 Oct 22 | MOOE |  | 0
196 |  | Representation Expenses | 544ECB | Neg 53.9 | [17 empty] | 544ECB | [10 empty] | 2022-09-30 | 2022-10-03 | 2022-10-14 | 20 Oct 22 | 20 Oct 22 | MOOE | 51039.25 | 51039.25 |  | 50429
197 |  | Semi-Expendable Furniture And Fixture Expense | 52EBDE | Neg 53.9 | [17 empty] | 52EBDE | [10 empty] | 2022-10-03 | 2022-10-04 | 2022-10-25 | 28 Oct 22 | 28 Oct 22 | MOOE | 11500 | 11500 |  | 11400
198 |  | Telephone-Mobile Expenses | 52EBDE | Neg 53.9 | [17 empty] | 52EBDE | [10 empty] | 2022-10-03 | 2022-10-04 | 2022-10-24 | 2022-10-28 | 28 Oct 22 | MOOE | 5600 | 5600 |  | 5580
199 |  | Other Supplies and Materials Expenses | 52EBDE | Neg 53.9 | [17 empty] | 52EBDE | [10 empty] | 2022-10-03 | 2022-10-04 | 2022-10-24 | 2022-10-28 | 2022-10-28 | MOOE | 163856 | 163856 |  | 160688
200 |  | Office Supplies Expenses | 52EBDE | Neg 53.9 | [17 empty] | 52EBDE | [10 empty] | 2022-10-03 | 2022-10-04 | 2022-10-26 | 2022-11-02 | 2022-11-02 | MOOE | 155400.5 | 155400.5 |  | 153452
201 |  | Medical, Dental & Laboratory Supplies | 52EBDE | Neg 53.9 | [17 empty] | 52EBDE | [10 empty] | 2022-10-03 | 2022-10-04 | 2022-11-07 | 11 Nov 22 | 11 Nov 22 | MOOE | 30000 | 30000 |  | 29810
202 |  | Drugs and Medicine | 52EBDE | Neg 53.9 | [17 empty] | 52EBDE | [10 empty] | 2022-10-03 | 2022-10-04 | 2022-11-07 | 11 Nov 22 | 11 Nov 22 | MOOE | 35000 | 35000 |  | 34425
203 |  | R & M of Building | 544ECB | Neg 53.9 | [17 empty] | 544ECB | [10 empty] | 2022-10-09 | 2022-10-10 | 2022-10-25 | 28 Oct 22 | 28 Oct 22 | MOOE | 108870 | 108870 |  | 108572
204 |  | Telephone-Mobile Expenses | 52EBDE | Neg 53.9 | [17 empty] | 52EBDE | [10 empty] | 2022-11-16 | 2022-11-17 | 2022-10-25 | 28 Oct 22 | 28 Oct 22 | SPF | 10000 |  | 10000 | 9980
205 |  | Semi - Expendables (Office- Equipment) | 52EBDE | Neg 53.9 | [17 empty] | 52EBDE | [10 empty] | 2022-11-16 | 2022-11-17 | 2022-10-25 | 28 Oct 22 | 28 Oct 22 | MOOE | 15000 | 15000 |  | 14700
206 |  | R & M of Building | ESC | Neg 53.9 | [17 empty] | ESC | [10 empty] | 2022-11-16 | 2022-11-17 | 2022-10-25 | 28 Oct 22 | 28 Oct 22 | MOOE | 23000 | 23000 |  | 21750
207 |  | R & M of Construction & Heavy Equipment | ESC | Neg 53.9 | [17 empty] | ESC | [10 empty] | 2022-11-16 | 2022-11-17 | 2022-10-25 | 28 Oct 22 | 28 Oct 22 | MOOE | 60000 | 60000 |  | 58900
208 |  | Office Supplies Expenses | ESC | Neg 53.9 | [17 empty] | ESC | [10 empty] | 2022-11-16 | 2022-11-17 | 2022-10-25 | 28 Oct 22 | 28 Oct 22 | MOOE | 31030 | 31030 |  | 30362
209 |  | Internet Expenses (Pre-paid) | ESC | Neg 53.9 | [17 empty] | ESC | [10 empty] | 2022-11-16 | 2022-11-17 | 2022-10-25 | 28 Oct 22 | 28 Oct 22 | MOOE | 12600 | 12600 |  | 12250
210 |  | Representation Expenses | ESC | Neg 53.9 | [17 empty] | ESC | [10 empty] | 2022-11-16 | 2022-11-17 | 2022-10-25 | 28 Oct 22 | 28 Oct 22 | MOOE | 7555 | 7555 |  | 7140
211 |  | R & M of Motor Vehicles | ESC | Neg 53.9 | [17 empty] | ESC | [10 empty] | 2022-10-16 | 2022-10-17 | 2022-11-07 | 11 Nov 22 | 11 Nov 22 | MOOE | 29000 | 29000 |  | 28500
212 |  | Semi - Expendables ICT Equipment) | ESC | Neg 53.9 | [17 empty] | ESC | [10 empty] | 2022-10-25 | 2022-10-26 | 2022-11-16 | 21 Nov 22 | 21 Nov 22 | MOOE | 24000 | 24000 |  | 22800
213 |  | Telephone-Mobile Expenses | 52EBDE | Neg 53.9 | [17 empty] | 52EBDE | [10 empty] | 2022-10-25 | 2022-10-26 | 2022-11-16 | 21 Nov 22 | 21 Nov 22 | MOOE | 5000 | 5000 |  | 4880
214 |  | RM Motor Vehicles | 52EBDE | Neg 53.9 | [17 empty] | 52EBDE | [10 empty] | 2022-11-03 | 2022-11-04 | 2022-11-16 | 21 Nov 22 | 21 Nov 22 | MOOE | 70000 | 70000 |  | 68920
215 |  | RM Motor Vehicles | 524ECB | Neg 53.9 | [17 empty] | 524ECB | [10 empty] | 2022-11-03 | 2022-11-04 | 2022-11-16 | 21 Nov 22 | 21 Nov 22 | MOOE | 36410 | 36410 |  | 35610
216 |  | Representation Expenses | 52EBDE | Neg 53.9 | [17 empty] | 52EBDE | [10 empty] | 2022-11-03 | 2022-11-04 | 2022-11-16 | 21 Nov 22 | 21 Nov 22 | MOOE | 33865 | 33865 |  | 32682
217 |  | Telephone-Mobile Expenses | 52EBDE | Neg 53.9 | [17 empty] | 52EBDE | [10 empty] | 2022-11-06 | 2022-11-07 | 2022-11-16 | 21 Nov 22 | 21 Nov 22 | MOOE | 8400 | 8400 |  | 8376
218 |  | Training Expenses | 52EBDE | Neg 53.9 | [17 empty] | 52EBDE | [10 empty] | 2022-11-06 | 2022-11-07 | 2022-11-16 | 21 Nov 22 | 21 Nov 22 | MOOE | 60000 | 60000 |  | 59534
219 |  | Office Supplies Expenses | 52EBDE | Neg 53.9 | [17 empty] | 52EBDE | [10 empty] | 2022-11-06 | 2022-11-07 | 2022-11-16 | 21 Nov 22 | 21 Nov 22 | MOOE | 10000 | 10000 |  | 9916
220 |  | Other Supplies & Materials Expense | 52EBDE | Neg 53.9 | [17 empty] | 52EBDE | [10 empty] | 2022-11-06 | 2022-11-07 | 2022-11-16 | 21 Nov 22 | 21 Nov 22 | MOOE | 10000 | 10000 |  | 9895
221 |  | Training Expenses | 52EBDE | Neg 53.9 | [17 empty] | 52EBDE | [10 empty] | 2022-11-06 | 2022-11-07 | 2022-11-16 | 21 Nov 22 | 21 Nov 22 | MOOE | 30000 | 30000 |  | 29970
222 |  | Representation Expenses | 52EBDE | Neg 53.9 | [17 empty] | 52EBDE | [10 empty] | 2022-11-06 | 2022-11-07 | 2022-11-16 | 21 Nov 22 | 21 Nov 22 | MOOE | 30000 | 30000 |  | 29762
223 |  | Office Supplies Expenses | 52EBDE | Neg 53.9 | [17 empty] | 52EBDE | [10 empty] | 2022-11-06 | 2022-11-07 | 2022-11-16 | 21 Nov 22 | 21 Nov 22 | MOOE | 47900 | 47900 |  | 40643
224 |  | Representation Expenses | 52EBDE | Neg 53.9 | [17 empty] | 52EBDE | [10 empty] | 2022-11-06 | 2022-11-07 | 2022-11-16 | 21 Nov 22 | 21 Nov 22 | MOOE | 16000 | 16000 |  | 15833
225 |  | Representation Expenses | 52EBDE | Neg 53.9 | [17 empty] | 52EBDE | [10 empty] | 2022-11-06 | 2022-11-07 | 2022-11-16 | 21 Nov 22 | 21 Nov 22 | MOOE | 50000 | 50000 |  | 49597
226 |  | Representation Expenses | 52EBDE | Neg 53.9 | [17 empty] | 52EBDE | [10 empty] | 2022-11-06 | 2022-11-07 | 2022-11-16 | 21 Nov 22 | 21 Nov 22 | MOOE | 3200 | 3200 |  | 3170
227 |  | Representation Expenses | 52EBDE | Neg 53.9 | [17 empty] | 52EBDE | [10 empty] | 2022-11-06 | 2022-11-07 | 2022-11-16 | 21 Nov 22 | 21 Nov 22 | MOOE | 16000 | 16000 |  | 15833
228 |  | Representation Expenses | 52EBDE | Neg 53.9 | [17 empty] | 52EBDE | [10 empty] | 2022-11-06 | 2022-11-07 | 2022-11-16 | 21 Nov 22 | 21 Nov 22 | MOOE | 20000 | 20000 |  | 19800
229 |  | ICT Software Subscription | 52EBDE | Neg 53.9 | [17 empty] | 52EBDE | [10 empty] | 2022-11-03 | 2022-11-04 | 2022-11-16 | 22 Nov 22 | 22 Nov 22 | MOOE | 1900 | 1900 |  | 1800
230 |  | Medical, Dental & Laboratory Supplies | 52EBDE | Neg 53.9 | [17 empty] | 52EBDE | [10 empty] | 2022-11-16 | 2022-11-17 | 2022-11-18 | 07 Dec 22 | 07 Dec 22 | MOOE | 41350 | 41350 |  | 39355
231 |  | Other Supplies & Materials Expense | 52EBDE | Neg 53.9 | [17 empty] | 52EBDE | [10 empty] | 2022-11-16 | 2022-11-17 | 2022-11-18 | 07 Dec 22 | 07 Dec 22 | MOOE | 7225 | 7225 |  | 7146
232 |  | Semi-Expendables (Media-Eqpt) | 52EBDE | Neg 53.9 | [17 empty] | 52EBDE | [10 empty] | 2022-11-16 | 2022-11-17 | 2022-11-18 | 07 Dec 22 | 07 Dec 22 | MOOE | 5000 | 5000 |  | 4975
233 |  | Representation Expenses | 52EBDE | Neg 53.9 | [17 empty] | 52EBDE | [10 empty] | 2022-11-16 | 2022-11-17 | 2022-11-18 | 07 Dec 22 | 07 Dec 22 | MOOE | 20000 | 20000 |  | 19560
234 |  | Office Supplies Expenses | 524ECB | Neg 53.9 | [17 empty] | 524ECB | [10 empty] | 2022-11-16 | 2022-11-17 | 2022-11-18 | 07 Dec 22 | 07 Dec 22 | MOOE | 14982 | 14982 |  | 14915
235 |  | Semi-Expendables (Furniture and Fixtures) | 544ECB | Neg 53.9 | [17 empty] | 544ECB | [10 empty] | 2022-11-17 | 2022-11-18 | 2022-12-15 | 21 Dec 22 | 21 Dec 22 | MOOE | 222270 | 222270 |  | 217150
236 |  | Admin & Supervision | 524ECB | Neg 53.9 | [17 empty] | 524ECB | [10 empty] | 2022-11-17 | 2022-11-18 | 2022-12-15 | 21 Dec 22 | 21 Dec 22 | SPF | 123594.68 |  | 123594.68 | 111679
237 |  | Admin & Supervision | 524ECB | Neg 53.9 | [17 empty] | 524ECB | [10 empty] | 2022-11-17 | 2022-11-18 | 2022-12-15 | 21 Dec 22 | 21 Dec 22 | SPF | 410687.67 |  | 410687.67 | 406768.5
238 |  | Other Supplies & Materials Expense | 52EBDE | Neg 53.9 | [17 empty] | 52EBDE | [10 empty] | 2022-11-24 | 2022-11-25 | 2022-12-12 | 16 Dec 22 | 16 Dec 22 | MOOE | 24833.2 | 24833.2 |  | 24524
239 |  | Representation Expenses | 512ECB | Neg 53.9 | [17 empty] | 512ECB | [10 empty] | 2022-11-24 | 2022-11-25 | 2022-12-12 | 16 Dec 22 | 16 Dec 22 | MOOE | 30925 | 30925 |  | 30894
240 |  | Office Supplies Expenses | 512ECB | Neg 53.9 | [17 empty] | 512ECB | [10 empty] | 2022-11-24 | 2022-11-25 | 2022-12-12 | 16 Dec 22 | 16 Dec 22 | MOOE | 18895 | 18895 |  | 18008
241 |  | RM of Building | 524ECB | Neg 53.9 | [17 empty] | 524ECB | [10 empty] | 2022-12-04 | 2022-12-05 | 2022-12-15 | 22 Dec 22 | 22 Dec 22 | MOOE | 32908 | 32908 |  | 32810
242 |  | RM of Building | 524ECB | Neg 53.9 | [17 empty] | 524ECB | [10 empty] | 2022-12-04 | 2022-12-05 | 2022-12-15 | 22 Dec 22 | 22 Dec 22 | MOOE | 59199 | 59199 |  | 59100
243 |  | Semi Expendable - Machinery Eqpt | 524ECB | Neg 53.9 | [17 empty] | 524ECB | [10 empty] | 2022-12-01 | 2022-12-05 | 2022-12-15 | 22 Dec 22 | 22 Dec 22 | MOOE | 22945.5 | 22945.5 |  | 22000
244 |  | Other Supplies & Materials Expense | 52EBDE | Neg 53.9 | [17 empty] | 52EBDE | [10 empty] | 2022-12-01 | 2022-12-05 | 2022-12-15 | 22 Dec 22 | 22 Dec 22 | SPF | 12000 |  | 12000 | 11800
245 |  | Other Supplies & Materials Expense | 52EBDE | Neg 53.9 | [17 empty] | 52EBDE | [10 empty] | 2022-12-01 | 2022-12-05 | 2022-12-15 | 22 Dec 22 | 22 Dec 22 | MOOE | 30000 | 30000 |  | 29684
246 |  | Other Supplies & Materials Expense | 544ECB | Neg 53.9 | [17 empty] | 544ECB | [10 empty] | 2022-12-01 | 2022-12-05 | 2022-12-15 | 22 Dec 22 | 22 Dec 22 | MOOE | 11755.81 | 11755.81 |  | 11630
247 |  | Medical, Dental & Laboratory Supplies | 534ECB | Neg 53.9 | [17 empty] | 534ECB | [10 empty] | 2022-12-01 | 2022-12-05 | 2022-12-15 | 22 Dec 22 | 22 Dec 22 | MOOE | 7852 | 7852 |  | 7200
248 |  | Other Supplies and Materials Expenses | 544ECB | Neg 53.9 | [17 empty] | 544ECB | [10 empty] | 2022-12-07 | 2022-12-07 | 2022-12-23 | 26 Dec 22 | 26 Dec 22 | SPF | 20000 |  | 20000 | 19465
| Total Alloted Budget of Procurement Activities | [37 empty] | 16958533.84
| Total Contract Price of Procurement Actitvites Conducted | [40 empty] | 16704995.43
| Total Savings (Total Alloted Budget - Total Contract Price) | [37 empty] | 253538.41
ON-GOING PROCUREMENT ACTIVITIES
NONE
| Total Alloted Budget of Procurement Activities | [37 empty] | 0
| Total Contract Price of Procurement Actitvites Conducted | [40 empty] | 0
| Total Savings (Total Alloted Budget - Total Contract Price) | [37 empty] | 0
Formulas:
Notice of Award = [Contract Signing]-1
Inspection & Acceptance = [Delivery/ Completion]
Prepared by:
Marvin M Tapulayan
SSg (Inf) PA
Operations NCO
Noted by:
MOISES L PECAYO
MAJ (QMS) PA
Commanding Officer